## Work List
Exported on: 2026-09-04 14:30:48
Filters applied:
Data source: MGNREGA + VBGRAMG
District: BHIND
Block: All
Panchayat: GHINONCHEE
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702001048/AV/22012034401209 — शांती धाम नरीपुरा | Physically Completed | 245000 | 250172 | 2019-02-27 | 2021-11-12
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702001048/AV/22012034401210 — शांती धाम घिनौची | Physically Completed | 245000 | 24984 | 2019-02-27 | 2021-11-12
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001048/AV/22012034466455 — Panchayat Bhawan - Ghinochee | Physically Completed | 579200 | 543152 | 2019-11-02 | 2021-11-12
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001048/AV/22012034514149 — Construction of civil work ( Nursery establishment) at repura GP Ginochee | Closed | 0 | 0 | 2020-05-05
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001048/AV/22012034537260 — गो शाला निर्माण खांद का पुरा | Physically Completed | 3804449.17 | 3375823.08 | 2021-01-29 | 2026-04-14
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702001048/AV/4258 — Anganwadi/Other Rural Infrastructure,ATER | Completed | 330000 | 320560 | 2015-12-28 | 2020-05-20
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702001048/AV/4259 — Anganwadi/Other Rural Infrastructure,ATER | Completed | 330000 | 323290 | 2015-12-28 | 2020-05-20
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Raising of Nursery for Groups / Raising of Nursery for Groups | Nursery Development | 1702001048/DP/22012034494553 — नर्सरी निर्माण कार्य रैपरा अटेर (उद्यानिकी विभाग) | Closed | 0 | 0 | 2020-04-14
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702001048/FP/22012034624415 — Nala nirman - gaushala ke ange khand ka pura | Closed | 0 | 0 | 2021-04-01
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001048/IF/22012034352711 — वृक्षारोपण सिद्ध बाबा का स्थान तालाब के किनारे आगनबाडी भवन स्कूल घिनोची | Deleted | 335000 | 0 | 2017-06-15
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1702001048/IF/22012034354432 — PLANTATION WORK at hanuman mandir ke , govt schoo , talab & shanti dham | Deleted | 335000 | 0 | 2017-06-20
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1702001048/IF/22012034354435 — PLANTATION WORK at mata ka mandir , pathshala , talab repura | Deleted | 335000 | 0 | 2017-06-03
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001048/IF/22012035476362 — Khet Talab Nirman chhotelal Jatav | Suspended | 147621.16 | 107470.38 | 2025-05-12
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001048/IF/22012035476375 — Khet Talab Nirman Janved Singh | Suspended | 147621.16 | 109680.53 | 2025-05-12
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001048/IF/22012035476402 — Khet Talab Nirman Amar Singh | Closed | 147621.16 | 0 | 2025-05-12
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001048/IF/22012035476412 — Khet Talab Nirman Murarilal | Closed | 147621.16 | 0 | 2025-05-19
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702001048/IF/22012035594376 — maa ke bagiya Rajesh devi | Ongoing | 263510.03 | 6264 | 2025-12-31
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001048/IF/22012035594378 — maa ke bagiya rachna devi | Deleted | 0 | 0 | 2025-08-14
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702001048/IF/22012035594380 — maa ke bagiya meena bai | Ongoing | 263510.03 | 4698 | 2025-12-16
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702001048/IF/22012035594381 — maa ke bagiya Seeta devi | Ongoing | 263510.03 | 0 | 2025-12-31
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001048/IF/22012035654051 — Ek Bagiya Ma ke naam Rachna Devi | Deleted | 0 | 0 | 2025-10-02
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702001048/IF/22012035654442 — Ek Bagiya maa ke naam rachana devi Ghinochi | Ongoing | 261748.57 | 0 | 2026-04-25
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001048/IF/9926717459 — Cattle shed shyam lal/ramdeen | Completed | 44200 | 44636 | 2014-03-13 | 2014-12-30
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001048/IF/9926719396 — Cattle shed Mukesh/ Hargovind | Completed | 44200 | 44636 | 2014-03-20 | 2014-06-30
ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1702001048/IF/9926722168 — Goat shelter Subhash / Baburam sharma | Completed | 50000 | 45362 | 2014-04-03 | 2014-10-30
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1702001048/IF/9926723443 — Goate Shelter Sanju/ Lekharam | Deleted | 50000 | 0 | 2014-01-26
ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1702001048/IF/9993656993 — Goat shelter Sanju | Deleted | 50000 | 0 | 2014-05-20
ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1702001048/IF/9993657236 — Goat shelter Sanju | Deleted | 50000 | 0 | 2014-03-01
ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702001048/IF/9993657237 — Land development Ramkumar | Completed | 8700 | 8635 | 2014-10-06 | 2014-12-30
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001048/IF/9993694933 — Farmbunding Jisram singh | Completed | 24407 | 13197 | 2015-12-10 | 2016-01-30
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001048/IF/IAY/134100 — Construction of IAY House -IAY REG. NO. MP-02-001-048-001/13 | Approved | 27000 | 0 | 2016-02-14
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001048/IF/IAY/3908810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132490725 | Physically Completed | 18360 | 8568 | 2022-12-03 | 2024-11-21
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001048/IF/IAY/4326090 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132490535 | Physically Completed | 18360 | 9792 | 2022-12-03 | 2024-11-21
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001048/IF/IAY/4335069 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125950103 | Physically Completed | 18360 | 11016 | 2022-12-03 | 2024-11-21
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001048/IF/IAY/4379510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132490515 | Physically Completed | 18360 | 11016 | 2022-12-03 | 2024-11-21
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001048/IF/IAY/4388172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125948746 | Closed | 18360 | 0 | 2022-12-12
ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001048/IF/IAY/4788226 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132490686 | Ongoing | 27000 | 18009 | 2026-05-03
ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001048/LD/1 — मेढ् बन्‍धान | Completed | 71000 | 5960 | 2009-04-20 | 2008-12-18
ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001048/LD/146 — मेढबन्‍धान रामगोपाल, प्रेमा, गोविन्‍द | Completed | 104005 | 64428 | 2009-09-01 | 2009-09-01
ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001048/LD/2 — मेढ बन्‍धान | Deleted | 13400 | 0 | 2008-12-18
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702001048/LD/22012034314956 — Shanti Dham- Ghinochi | Deleted | 245000 | 0 | 2017-06-12
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1702001048/LD/22012034521274 — Podh utpadhan Narsari Gram panchayat Ghinochee | Closed | 0 | 0 | 2020-05-05
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702001048/LD/22012034568888 — Chara gah - Gau shala ke piche khand ka pura ghinochee | Closed | 0 | 0 | 2021-04-14
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001048/LD/3 — मेढ बन्‍धान | Completed | 71000 | 13800 | 2010-05-15 | 2010-09-15
ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001048/LD/358 — मेढबन्‍धान रामनाथ/ठकुरी | Deleted | 0 | 0 | 2010-03-01
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001048/LD/359 — earth bunding syamlal/ramdin | Completed | 0 | 13800 | 2010-06-28 | 2010-09-15
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001048/LD/375 — Earth bunding kalicharn/chakkilal | Completed | 0 | 15800 | 2010-06-05 | 2010-06-05
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001048/LD/376 — Earth bunding | Completed | 0 | 16200 | 2010-05-28 | 2010-05-28
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001048/LD/377 — Earth bunding Battiram/chakki lal | Completed | 0 | 16800 | 2010-06-26 | 2010-06-26
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001048/LD/378 — Earth bunding Balram/sumeer | Completed | 0 | 14400 | 2010-05-01 | 2010-05-01
ATER | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001048/LD/3799435324 — Talab nirman Kodha | Deleted | 146400 | 0 | 2013-04-14
ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001048/LD/383 — Earth bunding lalaram/patiram | Deleted | 0 | 0 | 2010-03-01
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001048/LD/428 — earth bunding syamlal/ramdeen | Completed | 0 | 14400 | 2010-07-28 | 2010-09-15
ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001048/LD/429 — earth bunding Bhuri devi/panna lal | Completed | 0 | 14400 | 2010-07-15 | 2010-09-15
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034170660 — c.c. road shokeram ke darbaj se | Completed | 62500 | 59316 | 2013-06-22 | 2013-08-15
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034189817 — c.c. road Ramnaresh ke gate se munni lal tak | Completed | 165000 | 61100 | 2013-10-22 | 2014-03-30
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034207955 — C.C. road badan singh ke gate se | Completed | 104600 | 98808.7 | 2014-03-13 | 2014-12-20
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034212311 — C.C.road Ramnivish sharma ke gate se | Completed | 157000 | 62934 | 2014-08-18 | 2014-12-20
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001048/RC/22012034216644 — g s b road raipura village toword Old village Raip | Completed | 944000 | 307563 | 2014-06-23 | 2014-12-20
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034231110 — cc road Anand sharma house to Salim khan house | Completed | 205000 | 160249 | 2014-10-06 | 2016-04-18
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034266733 — CC Road Atibal houseto Sultan singh house | Completed | 136000 | 135887 | 2015-08-10 | 2017-09-01
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034285581 — CC Road from Hotam Singh Jurjar house to Sardar Singh house to Ganga Singh house | Completed | 89500 | 87684 | 2015-10-05 | 2017-09-01
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001048/RC/22012034298952 — Graval road from Puran house to Mata mandeer and Ganga singh house | Deleted | 923000 | 0 | 2016-02-17
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034310040 — CC ROAD | Deleted | 0 | 0 | 2016-04-01
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034329011 — C C ROAD ( RAMPRAKASH HOUSE TO PURANE DARWAJE ) | Completed | 243000 | 133302 | 2017-03-06 | 2019-06-30
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034365476 — CC Road Lakchiram ke makan se Mata Mandir hote huye Shantidham ki ore | Completed | 93000 | 61152 | 2017-10-30 | 2019-05-01
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034365478 — CC Road Bajrangii ke mandir se Lodhi Mohalla hote huye Shankar Ji ke Mandir ki ore Naripura | Completed | 93000 | 65076 | 2017-10-30 | 2019-05-01
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034365535 — CC Road ater road se salim khan ke makan ki ore Raipura | Completed | 102000 | 77016 | 2017-10-30 | 2019-07-01
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034373236 — cc road | Deleted | 0 | 0 | 2018-01-26
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034381922 — cc road | Deleted | 0 | 0 | 2017-10-02
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034382442 — cc road | Deleted | 0 | 0 | 2017-10-02
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034386569 — cc road pm road se ramotar ke darwaje tak Ghinochi | Completed | 35550 | 22968 | 2018-10-02 | 2020-06-30
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034442369 — cc road | Closed | 0 | 0 | 2019-01-26
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034446158 — सी सी रोड ( आशाराम से रामधनी के मकान की ओर ) | Completed | 32550 | 2088 | 2019-03-06 | 2020-06-30
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034446160 — सी सी रोड ( अजमेर के मकान से विशम्बर के मकान की ओर ) | Physically Completed | 69750 | 3132 | 2019-03-06 | 2021-11-12
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034446229 — सी सी रोड ( जगत सिंह के मकान से विशम्बर के मकान की ओर ) | Closed | 23250 | 0 | 2018-12-30
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034446248 — सी सी रोड ( रामभोग के मकान से श्याम लाल के मकान की ओर ) | Completed | 23250 | 14484 | 2020-01-08 | 2021-02-04
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034446254 — सी सी रोड ( गब्बर सिंह के मकान से कलियान सिंह के मकान की ओर ) | Completed | 37200 | 31484 | 2020-01-11 | 2021-09-07
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034514719 — cc road | Closed | 0 | 0 | 2019-10-02
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001048/RC/22012034539897 — sudoor road ( ghinochee se ramveer and kaliyan singh and ramdas singh ke makan to naresh singh ke or | Closed | 0 | 0 | 2020-05-05
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001048/RC/22012034539898 — sudoor road ( ghinocee se khinnipura hote huye mata mandir ke or ) | Closed | 0 | 0 | 2020-05-05
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001048/RC/22012034539899 — sudoor road ( ghinocee se bajrang bali sidd baba ka mandir purana gram tak ) | Closed | 0 | 0 | 2020-09-16
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034551850 — c c road ( PM sadak se nabab singh ke makan hote huye ram shanakr ke makan ke or ) | Closed | 83700 | 0 | 2020-08-15
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034551853 — c c road ( ater road se ramanand sharma ke makan ke or ) | Closed | 37200 | 0 | 2020-08-15
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034551858 — c c road ( ram kishan ke makan se shrilal rathor ke makan tak ) | Closed | 35700 | 0 | 2019-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/22012034586864 — c c road (PM Road se gandarv singh ke makan ke or ghinochee ) | Completed | 45900 | 30108 | 2021-11-25 | 2023-04-29
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001048/RC/22012034592501 — sudoor road (pm road se ramveer ke makan hote huye naresh singhke makan ke taraf ghinochee ) | Completed | 1569688.13 | 864372 | 2021-11-14 | 2026-06-02
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001048/RC/355 — c.c road shanker ji mandir se ramnaresh jatav ke darvaje tak | Completed | 0 | 82794 | 2012-06-05 | 2012-07-06
ATER | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001048/RC/68 — पहॅुच मार्ग | Deleted | 500000 | 0 | 2009-01-22
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702001048/RS/22012034506463 — सामुदायिक शौचालय ग्राम पंचायत घिनोची | Completed | 43000 | 18240 | 2021-01-24 | 2021-10-23
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1702001048/RS/22012034662371 — kachcha nala nirmankarya bindva ke pass repura | Closed | 0 | 0 | 2022-08-16
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1702001048/RS/22012034662372 — kachcha nala nirmankarya bindva ke pass repura | Closed | 0 | 0 | 2022-08-16
ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702001048/WC/22012034328524 — Talab Nirman- Raiya paar behad mi, Ghinochi | Completed | 385527 | 291852 | 2017-10-16 | 2020-06-30
ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001048/WC/22012034441123 — talab nirman - katarwali ghinochee | Physically Completed | 457000 | 263124 | 2019-03-06 | 2021-11-12
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001048/WC/22012034445138 — aardhan dam - purana gawn repura | Physically Completed | 195000 | 151860 | 2020-08-31 | 2026-04-16
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001048/WC/22012034445148 — Earthen dam - khariya | Completed | 195000 | 177330 | 2020-09-29 | 2021-09-07
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001048/WC/22012034445151 — Earthen dam - nai bari ka muhara | Completed | 199000 | 176700 | 2020-08-31 | 2021-03-02
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001048/WC/22012034584882 — Naveen talab - khand ke pura pura par | Closed | 0 | 0 | 2020-05-05
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001048/WC/22012034651196 — mitti bund nirman - ramotar ke khet ke pass | Completed | 239684.09 | 178332 | 2021-05-07 | 2025-05-06
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001048/WC/22012034651200 — mitti bund nirman - kand ka pura | Completed | 202237.06 | 190298 | 2021-05-07 | 2021-09-07
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001048/WC/22012034651219 — Naveen talab nirman - GauShala ke pass | Completed | 1497183.19 | 811758 | 2021-04-29 | 2025-05-06
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001048/WC/22012034881554 — Sok pit - raghunath sharma ke dwar ke pass naripura | Closed | 4600 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001048/WC/22012034881564 — sok pit -ramkeshav ojha naripura | Completed | 4600 | 4560 | 2021-12-04 | 2023-04-29
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001048/WC/22012034881585 — sok pit - buddh singh baghel naripura | Closed | 4600 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001048/WC/22012034881594 — sok pit - indresh sharma ke dwar ke pass | Completed | 4600 | 2316 | 2021-12-04 | 2023-04-29
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001048/WC/22012034881611 — sok pit - ram shankar ke dwar ke pass | Completed | 4600 | 2316 | 2021-12-04 | 2023-04-29
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001048/WC/22012034881614 — sok pit - govt midil school naripura | Completed | 4600 | 4560 | 2021-12-04 | 2023-04-29
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001048/WC/22012034992405 — naveen mitti band nirman ajeet sharma ke khet ke neeche repura | Closed | 0 | 0 | 2022-08-16
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001048/WC/22012034992406 — naveen mitti band nirman ajeet sharma ke khet ke neeche repura | Closed | 0 | 0 | 2022-08-16
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001048/WC/22012034992407 — naveen mitti band nirman karya lalaramke khet ke pass repura | Completed | 205844 | 173808 | 2022-09-13 | 2022-11-28
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001048/WC/22012034992408 — naveen talab nirman karya murarilal ke khet ke pass repura | Closed | 0 | 0 | 2022-08-16
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001048/WC/22012034992409 — naveen talab nirman karya murarilal ke khet ke pass repura | Closed | 0 | 0 | 2022-08-16
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001048/WC/22012034992410 — naveen talab nirman karya talab ke neeche bindva ke pass purana gaou repura | Closed | 0 | 0 | 2022-08-16
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001048/WC/22012034992411 — naveen talab nirman karya narsari ke pass repura | Closed | 0 | 0 | 2022-08-16
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001048/WC/22012034993497 — naveen talab nirman lalaram ke khet ke pass repura | Closed | 0 | 0 | 2022-08-16
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001048/WC/22012034993501 — naveen talab nirman karya ajeet sharma ke khet ke pass repura | Completed | 675077.57 | 553044 | 2022-09-14 | 2025-06-05
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001048/WC/22012035027830 — naveen talab nirman karya diviya vala repura | Closed | 0 | 0 | 2022-10-02
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001048/WC/22012035027831 — naveen talab nirman karya diviya vala repura | Closed | 0 | 0 | 2022-10-02
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001048/WC/22012035027832 — naveen talab nirman karya diviya vala repura | Completed | 1095201.49 | 952408 | 2023-04-18 | 2025-05-06
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001048/WC/22012035027836 — naveen mitti band nirman karya chotelal ke ghar ke samne repura | Completed | 684002.91 | 595255 | 2023-04-18 | 2025-05-06
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001048/WC/22012035052809 — naveen mitti band nirman murarilal ke ghar ke samne repura | Closed | 0 | 0 | 2023-01-25
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001048/WC/22012035052854 — naveen mitti band nirman karya lalaram ke khet ke pass repura | Closed | 0 | 0 | 2023-01-25
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702001048/WC/22012035058459 — naveen mitti band nirman karya mahesh ke khet ke pass repura | Completed | 593977.11 | 515593 | 2023-06-20 | 2025-05-06
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001048/WC/22012035058467 — naveen talab karya murari lal ke khet ke pass repura | Closed | 0 | 0 | 2023-04-14
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702001048/WC/22012035058477 — naveen mitti band nirman murarilal ke ghar ke samne repura | Completed | 569868.79 | 487305 | 2023-05-23 | 2025-05-06
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001048/WC/22012035089320 — naveen mitti band nirman karya muhare ke pass repura | Closed | 558085.8 | 0 | 2023-06-05
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001048/WC/22012035089323 — naveen mitti band nirman karya babloo ke khet ke pass repura | Suspended | 472798.1 | 321329 | 2023-09-05
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001048/WC/22012035089375 — naveen mitti band nirman karya maharaj singh ke khet ke neeche repura | Closed | 432460.16 | 0 | 2023-06-05
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001048/WC/22012035089376 — naveen mitti band nirman karya katela ke pass repura | Suspended | 272094.36 | 21216 | 2023-09-05
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001048/WC/22012035089377 — naveen mitti band nirman karya nai tor ke pass repura | Completed | 856652.54 | 717808 | 2023-07-18 | 2025-05-06
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001048/WC/22012035089378 — naveen mitti band nirman karya murarilal sharma ke khet ke pass repura | Suspended | 277952.96 | 2652 | 2023-09-05
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Raising of Nursery for Groups / Raising of Nursery for Groups | Nursery Development | 1702001048/WC/22012035097133 — vriksharopan amrit vatika karya murarilal ke band par repura | Suspended | 55847.4 | 3978 | 2023-09-05
ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001048/WC/22012035298405 — khet talab nirman karya chotelal ke khet par repura | Approved | 0 | 0 | 2025-04-14
ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001048/WC/22012035298410 — khet talab nirman karya janved ke khet par repura | Approved | 0 | 0 | 2025-04-14
ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001048/WC/22012035301292 — dag well reeharj pit brahman thok repura | Physically Completed | 25899.46 | 21564.53 | 2025-05-12 | 2026-04-14
ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001048/WC/22012035301320 — dug well recharge strucrure pit baghiya ke kua ke pass kadora | Approved | 0 | 0 | 2025-04-14
ATER | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001048/WC/9993651003 — Talab Nirman khonda Raipura | Deleted | 146400 | 0 | 2014-01-28
ATER | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001048/WH/19955480 — Desilting of talab | Deleted | 0 | 0 | 2016-01-26
ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001048/WH/19962653 — Renovation Of Pond- Purana Talab, Ghinochi | Completed | 98000 | 78948 | 2017-06-05 | 2020-08-09
ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001048/WH/19962936 — Renovation Of Pond- Mata Mandir ke Pass, Raipura, Ghinochi | Completed | 99000 | 46032 | 2017-06-13 | 2020-06-30
ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001048/WH/19962937 — Renovation Of Pond- Bajrangi Mandir Ke Pass, Naripura | Completed | 97000 | 91860 | 2017-06-15 | 2021-09-07
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001048/WH/22012034932891 — talab jirroddar - raiya ke khar | Closed | 0 | 0 | 2022-04-14
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001048/WH/22012034932893 — talab jirroddar - Nai bari ghinochee | Closed | 0 | 0 | 2022-04-14
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702/DP/22012034494555 — नर्सरी निर्माण कार्य रैपरा अटेर (उद्यानिकी विभाग) | Closed | 5221736 | 0 | 2020-08-15
ATER | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702/RC/22012034153088 — Gram Sampark Sadak Yojna | Completed | 812000 | 732 | 2011-02-14 | 2015-03-30