## Work List
Exported on: 2026-09-09 22:40:54
Filters applied:
Data source: MGNREGA
District: BHIND
Block: All
Panchayat: KHEREE
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702001049/AV/22012034390592 — Cattle Protection Wall-Govt. Primary Sachool, Ratnupura, Khipona | Closed | 36200 | 0 | 2018-08-15
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702001049/AV/22012034390597 — Cattle Protection Wall- Govt. Primary School, Kheeri, Khipona | Closed | 41545 | 0 | 2018-08-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702001049/AV/22012034563998 — Shantidham nirman karya khipona | Completed | 285409.48 | 284243.47 | 2021-04-08 | 2022-09-25
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001049/AV/22012034585249 — Boundary Ball Nirman Punchayat bhawan, khipona | Completed | 60000 | 59058 | 2021-08-28 | 2022-01-10
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001049/AV/22012034615700 — Maa Ki Bagiya Nirman Karya Govt. Primary School, Kheri | Closed | 9283 | 0 | 2021-10-02
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001049/AV/22012034615703 — Maa Ki Bagiya Nirman Karya Govt. Middle School, Khipona | Closed | 9283 | 0 | 2021-10-02
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702001049/AV/22012034616908 — Khel Maidhan Nirman Karya- Khipona | Deleted | 0 | 0 | 2022-01-26
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702001049/AV/22012034617369 — Khel Maidhan Nirman Karya- Khipona | Completed | 726812.4 | 420410 | 2022-05-13 | 2023-08-06
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001049/AV/22012034631193 — Shantidham kheri | Closed | 330733.3 | 0 | 2022-10-02
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702001049/AV/3896 — Aanganbadi/Other Rural Infrastructure,ATER | Completed | 330000 | 315725 | 2016-01-20 | 2017-05-01
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702001049/AV/4418 — Anganvadi bhavan Rantupura | Completed | 330000 | 315491 | 2016-02-17 | 2017-05-01
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1702001049/DP/22012034594094 — Plantation work -(Shankar ji ke Mandir ke pass yadavo ka pura khilona) | Suspended | 55847.4 | 15912 | 2023-08-23
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702001049/FP/22012034361811 — Nali Nirman- Ramkishan Ke Darwaje Se Talab Ki Or | Closed | 0 | 0 | 2018-10-02
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702001049/FP/22012034626138 — Nali Nirman Karya-Shiv Singh Ke Darwaje Se Talaiya Ki Or, Ratnupura | Closed | 26000 | 0 | 2021-07-02
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702001049/FP/22012034626139 — Nali Nirman Karya-Vinod Yadav Ke Darwaje Se Talab Ki Or, Kheri | Completed | 19000 | 18914 | 2022-03-16 | 2022-04-02
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702001049/FP/22012034626140 — नाली निर्माण कार्य उप स्वास्थ्य केंद्र खिपोना से तालाब की ओर, खिपोना | Completed | 25000 | 24897 | 2021-07-22 | 2022-03-20
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001049/IF/22012034298214 — Cattle Shed- Preetam Singh/ Hameer Singh | Deleted | 90000 | 0 | 2016-08-19
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001049/IF/22012034298215 — Cattle Shed- Rambabu/ Bhogi Singh | Deleted | 90000 | 0 | 2016-08-19
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034308294 — Cons. OF Compost Pit- Khalak Singh/ Ashrafilal | Completed | 12000 | 10303.88 | 2016-12-28 | 2017-05-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034308296 — Cons. Of Compost Pit- Bacchu / Mijaji Yadav | Completed | 12000 | 10303.88 | 2017-01-04 | 2017-05-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034313010 — Cons. OF Compost Pit- Goliram/ Tej Singh | Completed | 12000 | 10971.9 | 2017-02-04 | 2017-05-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034313012 — Cons. OF Compost Pit- Raj bahadur/ Dayaram | Completed | 12000 | 10971.9 | 2017-02-01 | 2017-05-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034313014 — Cons. OF Compost Pit- Sunil/ Kamal Singh | Completed | 12000 | 10971.9 | 2017-02-04 | 2017-05-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034313015 — Cons. OF Compost Pit- Rajveer/ Baburam | Completed | 12000 | 10971.88 | 2017-01-25 | 2017-05-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034313016 — Cons. OF Compost Pit- Foran Singh/ Tej Singh | Completed | 12000 | 10971.88 | 2017-01-18 | 2017-05-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034314120 — Cons. OF Compost Pit- Ramesh Singh/ Chakode Singh | Completed | 12000 | 10971.9 | 2017-02-10 | 2017-05-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034317357 — Cons. Of Compost Pit- Udal Singh/ Sughar Singh | Completed | 12000 | 10971.9 | 2017-02-10 | 2017-05-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034317358 — Cons. OF Compost Pit- Siyaram/ Ramsahay | Completed | 12000 | 10971.9 | 2017-02-10 | 2017-05-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034317374 — Cons. OF Compost Pit_ Radheshyam/ Dharam Singh | Completed | 12000 | 10971.9 | 2017-02-10 | 2017-05-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034317375 — Cons. OF Compost Pit- Sobha Singh/ Matare Singh | Completed | 12000 | 10971.9 | 2017-02-04 | 2017-05-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034317376 — Cons. OF Compost Pit- Soni Singh/ Ramesh Singh | Completed | 12000 | 10971.9 | 2017-02-02 | 2017-05-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034317377 — Cons. Of Compost Pit- Keshav Singh/ Mijaji Lal | Completed | 12000 | 10971.9 | 2017-02-02 | 2017-05-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034317378 — Cons. OF Compost Pit- Maya Devi / Dayaram | Completed | 12000 | 10971.9 | 2017-02-04 | 2017-05-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034317382 — Cons. OF Compost Pit- Chabiram/ Ramsahay | Completed | 12000 | 10971.9 | 2017-02-10 | 2017-05-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034322309 — Cons. Of Compost Pit- Nathuram Sharma/ Vishun narayan | Completed | 12000 | 10971.9 | 2017-02-26 | 2018-05-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034322311 — Cons. OF Compost Pit- Dinesh/ Ram sahay | Completed | 12000 | 10971.9 | 2017-03-01 | 2017-05-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034322316 — Cons. OF Compost Pit- Rajveer/ Gangadeen | Completed | 12000 | 10971.9 | 2017-03-08 | 2017-05-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034322319 — Cons. OF Compost Pit- Mahendra/ Ramsahay | Completed | 12000 | 10971.9 | 2017-02-26 | 2017-05-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034322324 — Cons. Of Compost Pit- Abhilakh/ Ramsahay | Completed | 12000 | 10971.9 | 2017-03-08 | 2017-05-30
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034322325 — Cons. OF Compost Pit- Santosh/ Mahendra | Completed | 12000 | 10971.9 | 2017-03-08 | 2017-05-30
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001049/IF/22012034352518 — Vrakhsharopan p.m. yojana sadak ke kinare | Physically Completed | 335000 | 12460 | 2017-08-12 | 2021-11-12
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001049/IF/22012034352521 — Vriksharopan PMGY SAdak kinare | Completed | 335000 | 12460 | 2017-07-15 | 2021-08-14
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001049/IF/22012034352522 — Vraksharopan PMGSY Sadak Ke Kinare | Completed | 335000 | 12460 | 2017-07-15 | 2021-08-14
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034375910 — Cons. of Nandep- Jaswant Singh / Dataram | Completed | 12000 | 11042 | 2017-09-23 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034375911 — Cons. of Nandep- Girraj/ Suresh | Completed | 12000 | 11042 | 2017-09-23 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034375912 — Cons. OF Nandep- Gabbar Singh/ Nathuram | Completed | 12000 | 11042 | 2017-09-23 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034375913 — Cons. OF Nandep- Pappu/ Harnaam | Completed | 12000 | 11042 | 2017-09-23 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034375914 — Cons. OF Nandep-Ram naresh/Gyadeen | Completed | 12000 | 11042 | 2017-09-23 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034375915 — Cons. OF Nandep- Laxman/ ramkishan | Completed | 12000 | 11042 | 2017-09-23 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034375916 — Cons. of nandep-Siyaram/ Mante Singh | Completed | 12000 | 11042 | 2017-09-23 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034375941 — Cons. OF Nandep- Shiv Singh/ Preetam | Completed | 12000 | 11042 | 2017-09-22 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034375942 — Cons. OF Nandep- Rajendra / Mante Singh | Completed | 12000 | 11042 | 2017-09-22 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034375943 — Cons. OF Nandep- Rajesh/ Mante Singh | Completed | 12000 | 11042 | 2017-09-22 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034375944 — Cons. OF Nandep- Naresh/ Man Singh | Completed | 12000 | 11042 | 2017-09-22 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034375945 — Cons. OF Nandep- Bhagwan / Preetam | Completed | 12000 | 11042 | 2017-09-22 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034375946 — Cons. OF Nandep- Sahdev/ Preetam | Completed | 12000 | 11042 | 2017-09-22 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034375947 — Cons. OF Nandep- Atar Singh/ Dataram | Completed | 12000 | 11042 | 2017-09-22 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034375948 — Cons. OF Nandep- Banti Singh/ Kalyan | Completed | 12000 | 11042 | 2017-09-22 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034375949 — Cons. OF Nandep- Ansul Singh/ Keshav | Completed | 12000 | 11042 | 2017-09-22 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034375950 — Cons. OF Nandep- Kriashnakant/ Suresh | Completed | 12000 | 11042 | 2017-09-22 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034376565 — Cons. Of Nandep- Subhash/Ram Singh | Completed | 12000 | 11042 | 2017-09-29 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034376566 — Cons. OF Nandep- Sanjay/ Moharman | Completed | 12000 | 11042 | 2017-09-29 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034376567 — Cons. OF Nandep- Narayan/ Bhajan Lal | Completed | 12000 | 11042 | 2017-09-29 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034376568 — Cons. OF Nandep- Shyam Singh/ Mohar | Completed | 12000 | 11042 | 2017-09-29 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034376569 — Cons. OF Nandep- Suresh/ Mewaram | Completed | 12000 | 11042 | 2017-09-29 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034376570 — Cons. OF Nandep- Sughar Singh/ Ram nath | Completed | 12000 | 11042 | 2017-09-29 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034376571 — Cons. of Nandep- Vimlesh/ Ramnath | Completed | 12000 | 11042 | 2017-09-29 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034376572 — Cons. OF Nandep- Ram Niwas/ Chakkilal | Completed | 12000 | 11042 | 2017-09-29 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034376573 — Cons. OF Nandep - Dhaniram/ Chatrapal | Completed | 12000 | 11042 | 2017-09-29 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034376574 — Cons. OF Nandep- Ram bhoj/ Khayaliram | Completed | 12000 | 11042 | 2017-09-29 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034376575 — Cons. OF Nandep- Krishna Murari/ Ramjilal | Completed | 12000 | 11042 | 2017-09-29 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034376576 — Cons. OF Nandep- Bharat Singh/ Dataram | Completed | 12000 | 11042 | 2017-09-29 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034376577 — Cons. OF Nandep- Om Prakash/ Ram sahay | Completed | 12000 | 11042 | 2017-09-29 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034376578 — Cons. Of Nandep- Ramveer/ Kalyan | Completed | 12000 | 11042 | 2017-09-29 | 2018-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034376579 — Cons. OF Nandep- Jawan Singh/ Ramratan | Completed | 12000 | 11042 | 2017-09-29 | 2018-09-25
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034437255 — Compost Of Nandep Taka- Sultan/Baturi Lal | Completed | 12000 | 11167 | 2019-03-09 | 2019-09-10
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034437256 — Compost Of Nandep- Gajadhar /Ramsahay | Deleted | 12000 | 0 | 2019-01-04
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034437257 — Compost Of Nandep- Surendra Singh/ Ramratan | Completed | 12000 | 11167 | 2019-03-09 | 2019-09-01
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034437258 — Compost Of Nandep- Nanthuram / Baturi | Deleted | 12000 | 0 | 2019-01-04
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034437259 — Compost Of Nandep- Rajveer/Rustam Singh | Completed | 12000 | 11167 | 2019-03-09 | 2019-03-27
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034438050 — Compost Of Nandep- Guddi Devi/Ram Naresh Baghel, khipona | Deleted | 12000 | 0 | 2019-01-04
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034438051 — Compost Of Nandep- Ram bahadur/Munni Lal | Deleted | 12000 | 0 | 2019-01-04
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034438052 — Compost Of Nandep- Rampreet/Hargovind | Deleted | 12000 | 0 | 2016-08-15
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034438053 — Compost Of Nandep- B.P.Singh/ Parimal | Completed | 12000 | 11167 | 2019-03-09 | 2019-04-02
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034438055 — Compost Of Nandep- Devidayal/ Gopi Singh | Completed | 12000 | 11167 | 2019-03-11 | 2019-03-27
ATER | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001049/IF/22012034469853 — खेत तालाब निर्माण- कोक सिंह/ नेकराम , खिपोना | Completed | 288000 | 167880 | 2019-03-09 | 2019-07-10
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034471073 — Cons. of Nandep- Kushma/ Gajadhar, Khipona | Deleted | 0 | 0 | 2018-10-02
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034471078 — Cons. of Nandep- Kushma/ Gajadhar | Completed | 12000 | 11167 | 2019-03-06 | 2019-09-10
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034471084 — Cons. of Nandep- munni bai/ Nathuram | Completed | 12000 | 11167 | 2019-03-06 | 2019-09-10
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034471090 — Nandep Of Conpost- Munnilal/ Girendra | Completed | 12000 | 11167 | 2019-03-09 | 2019-03-27
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001049/IF/22012034471094 — Cons. OF Nandep- Brajesh/ Ramnaresh | Completed | 12000 | 11167 | 2019-03-09 | 2019-09-05
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001049/IF/22012035035735 — Khet Talab nirman Mijaji/ajgar Ke Khet Par, Khipona | Closed | 0 | 0 | 2022-10-02
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001049/IF/22012035378348 — Khet Talab Suresh | Suspended | 147621.16 | 94942.62 | 2025-05-12
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001049/IF/22012035402485 — Khet talab Geetam singh | Suspended | 147621.16 | 96303.9 | 2025-05-12
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001049/IF/9993678482 — Farmbunding Sudher sing/ Badriprasad | Completed | 27100 | 26712 | 2015-10-21 | 2016-01-30
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001049/IF/9993678487 — Farmbunding Nathuram Kora/ Dayaram | Completed | 27100 | 24804 | 2015-10-28 | 2016-01-30
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001049/IF/9993678649 — Farmbunding Foran singh/ Tej singh | Completed | 10200 | 9540 | 2015-10-07 | 2016-01-30
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001049/IF/IAY/134101 — Construction of IAY House -IAY REG. NO. MP-02-001-049-003/81 | Completed | 14310 | 9018 | 2016-09-14 | 2016-10-15
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001049/IF/IAY/134102 — Construction of IAY House -IAY REG. NO. MP-02-001-049-003/88 | Completed | 14310 | 8016 | 2016-09-14 | 2016-10-15
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001049/IF/IAY/202953 — Construction of IAY House -IAY REG. NO. MP-02-001-049-003/80 | Approved | 23490 | 0 | 2016-02-14
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001049/IF/IAY/3691237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114697045 | Completed | 18360 | 17799 | 2022-09-09 | 2023-10-03
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001049/IF/IAY/3905522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148303817 | Completed | 18360 | 17799 | 2022-08-12 | 2023-10-03
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001049/IF/IAY/4285865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126044705 | Completed | 18360 | 17799 | 2022-09-09 | 2024-10-22
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001049/IF/IAY/4286313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122489309 | Completed | 18360 | 17901 | 2022-09-09 | 2023-10-03
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001049/IF/IAY/4325434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114713703 | Physically Completed | 18360 | 13668 | 2022-10-23 | 2024-11-21
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001049/IF/IAY/4336136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122490388 | Completed | 18360 | 17799 | 2022-11-13 | 2023-10-03
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001049/IF/IAY/4379696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126026211 | Completed | 18360 | 18276 | 2023-01-25 | 2024-10-21
ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001049/IF/IAY/4388173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126045378 | Physically Completed | 18360 | 16176 | 2023-05-29 | 2024-11-21
ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001049/IF/IAY/4774438 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126048298 | Ongoing | 23490 | 18954 | 2025-01-14
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001049/IF/IAY/79993 — Construction of IAY House -IAY REG. NO. MP-02-001-049-002/21 | Completed | 14310 | 14244 | 2016-08-03 | 2019-11-20
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001049/IF/IAY/79995 — Construction of IAY House -IAY REG. NO. MP-02-001-049-004/13 | Completed | 14310 | 14244 | 2016-08-03 | 2019-10-09
ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001049/LD/18 — मेढ बन्‍धान | Completed | 22000 | 3276 | 2009-02-27 | 2009-03-05
ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001049/LD/23 — मेढ बन्‍धान | Deleted | 15000 | 0 | 2008-08-18
ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001049/LD/24 — मेढ बन्‍धान | Deleted | 8500 | 0 | 2008-08-18
ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001049/LD/25 — मेढ बन्‍धान | Deleted | 7000 | 0 | 2008-08-18
ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001049/LD/26 — मेढ बन्‍धान रामौतार/छविराम | Deleted | 9000 | 0 | 2008-08-18
ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001049/LD/33 — मेढ बन्‍धान राजवीर/बाबूराम यादव | Completed | 4300 | 2730 | 2009-03-06 | 2009-03-14
ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001049/LD/34 — मेढ बन्‍धान मिजाजी/अजगर यादव | Deleted | 9000 | 0 | 2008-08-18
ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001049/LD/35 — मेढ बन्‍धान रामस्‍वरूप/तुलसीराम बघेल | Completed | 8500 | 3958.5 | 2009-03-07 | 2009-03-15
ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001049/LD/36 — मेढ बन्‍धान महावीर सिंह/हरविलास | Completed | 15000 | 7007 | 2009-03-07 | 2009-03-15
ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001049/LD/37 — मेढ बन्‍धान छविराम/खुशाल बघेल | Completed | 10600 | 6006 | 2009-03-06 | 2009-03-14
ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001049/LD/38 — मेढ बन्‍धान वदन सिंह | Deleted | 6100 | 0 | 2008-08-18
ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001049/LD/72 — मेंढ् बन्‍धान | Completed | 9400 | 0 | 2009-05-05 | 2009-05-05
ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001049/LD/73 — मेढ् बन्‍धान | Completed | 5400 | 0 | 2009-05-05 | 2009-05-05
ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001049/LD/74 — मेढ बन्‍धान | Completed | 9400 | 0 | 2009-05-05 | 2009-05-05
ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001049/LD/75 — मेंड बंधान निर्माण कार्य अनारसिहं / ज्ञान सिहं यादव | Completed | 95000 | 0 | 2009-04-14 | 2009-04-14
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702001049/OP/9425891415 — Ritraning Ball- Talab Tall Ka Pura | Deleted | 180000 | 0 | 2016-04-26
ATER | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001049/RC/116 — पहुंच मार्ग | Completed | 500000 | 155496 | 2009-06-20 | 2012-07-17
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034172826 — c.c. road main road se | Deleted | 160000 | 0 | 2012-04-14
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cross Drainage / Construction of Culvert / cross drainage structues for Community | Culvert | 1702001049/RC/22012034175373 — c.c. road main road harjan basti tak | Completed | 160000 | 149918 | 2013-09-25 | 2014-11-30
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034185443 — C.C.road S.P.V. khari se hnuman mander ke or | Completed | 167000 | 166840 | 2014-07-09 | 2014-12-20
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034190020 — c.c. road Amrit singh ke makan se | Completed | 74000 | 72564 | 2014-02-26 | 2014-05-20
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034190057 — c.c. road Amarnath se komal tak | Completed | 74000 | 65201 | 2013-12-18 | 2015-05-20
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034190059 — c.c. road Tulsiram jatab ke darbaj se | Completed | 126500 | 121534 | 2014-06-04 | 2015-12-25
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034219013 — cc road Rambabu bali Gali mai Ratnupura | Completed | 74000 | 67823 | 2014-06-18 | 2014-08-20
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034223287 — cc road Kachhi road to jasbant gurjar house Nirn | Completed | 168000 | 136154 | 2014-08-06 | 2014-12-20
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034223288 — ccroad s c basti p s khari to mata mander | Completed | 336000 | 212447 | 2014-10-22 | 2015-04-30
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034224253 — CC Road Ramdulara house to Kalicharn House | Completed | 168000 | 141811 | 2014-07-23 | 2014-12-30
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034266856 — CC ROAD Behind School Gurdayal Baretha house Via Rakshpal house to Ramesh prajapati house | Completed | 133000 | 90339 | 2015-07-01 | 2017-09-01
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001049/RC/22012034267148 — Gravel Road Main road to Bhaghelan ka pura Tal tak | Completed | 609000 | 542271 | 2015-07-15 | 2017-09-01
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001049/RC/22012034286195 — Graval road from Harijan Basti tal to Nahar puliya | Completed | 415000 | 336005.7 | 2015-11-04 | 2017-09-01
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034288316 — CC Road from Shankar lal Nai house to Talab | Completed | 131000 | 130588 | 2015-11-11 | 2016-04-20
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034288318 — CC Road from Rantnupura in mainroad to Hanuman mandeer | Completed | 92000 | 91058 | 2015-11-11 | 2017-09-01
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034307381 — C.C.road from Shiv singh house to Shiv narayan house | Completed | 41000 | 40749 | 2016-06-15 | 2017-09-01
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034309233 — cc road | Deleted | 0 | 0 | 2016-04-02
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034324837 — CC road Preetam Singh house to Rajesh house via Harnam house etc | Deleted | 0 | 0 | 2016-01-26
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034324954 — CC Road PREETAM HOUSE TO RAJESH HOUSE VIA HARNAM, JASMANT, BP SINGH , GIRRAJ HOUSE | Completed | 290000 | 289470 | 2017-03-08 | 2017-09-01
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001049/RC/22012034341656 — Sudur Samprak Sadak Bagiyapura se ratan singh pura hote hue niranjanpura tak | Completed | 3300000 | 1758213.65 | 2017-06-30 | 2021-05-15
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001049/RC/22012034341663 — Sudur Samprak Sadak Nahar ki puliya se ratanupura ki or | Physically Completed | 2200000 | 1454452.1 | 2017-06-30 | 2026-06-06
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034347790 — सी.सी.रोड मय नाली कच्चे मार्ग से हाकिम सिंह के द्वार होते हुए मिजाजी के दरवाजे की ओर रतन सिंह का पूर | Completed | 66375 | 54696 | 2017-10-30 | 2019-12-15
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034347791 — सी.सी.रोड मय नाली नाहर की पुलिया उदल जाटव के मकान की ओर हरिजन बस्ती ताल का पूरा | Completed | 119500 | 119112 | 2017-10-06 | 2019-04-15
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034368835 — C.C.Road Mohar Singh Ke Dwar Se Ramnath Baghel Ke Darwaje Ki Or, Khipona | Completed | 27900 | 15480 | 2018-02-28 | 2019-05-15
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034373266 — cc road | Deleted | 0 | 0 | 2018-01-26
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034381481 — C.C.Raod P.M. Sadak Se Ramdulare Sharma Ke Makan Ki Or, Taal Ka Pura, Khipona | Completed | 162750 | 161994 | 2018-04-26 | 2019-05-15
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034381943 — cc road | Closed | 0 | 0 | 2017-10-02
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034382464 — cc road | Closed | 0 | 0 | 2017-10-02
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034384696 — C C Road ( Main Road Se Dilasaram Nai Ke Makan & Rajendra Master Ke Makan Ke Or Kheri ) | Completed | 85500 | 89784 | 2018-02-28 | 2018-05-25
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034388581 — सी सी रोड ( कच्ची सडक से राम किशुन के मकान की ओर ताल का पुरा ) | Completed | 20925 | 20532 | 2018-08-17 | 2019-05-15
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034388588 — सी सी रोड ( प्रधानमंत्री सडक से संतोष यादव के मकान की ओर खिपौना ) | Completed | 30225 | 28710 | 2018-07-26 | 2019-05-15
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034394015 — सी सी रोड ( प्रधानमंत्री सडक से राधेश्याम के मकान की ओर यादवो क पुरा ) | Completed | 12900 | 12528 | 2018-10-05 | 2018-11-15
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034394016 — सी सी रोड ( प्रधानमंत्री सडक से फेरन सिंह के दरवाजे की ओर ) | Completed | 11475 | 10440 | 2018-10-05 | 2019-05-15
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034395685 — C.C.Road Mai Nali PM Sadak Se Primary Shala Bhawan Ki Or, Kheeri, Khipona | Completed | 37200 | 34800 | 2018-10-05 | 2019-05-15
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034397617 — C.C.Road Mai Nali Annai Ke Gonda Se Chabiram nai ke makan hote hue mata mandir ki or, khipona | Completed | 51150 | 48024 | 2019-01-04 | 2019-05-15
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034432894 — C.C.Raod Mai nali Annai Ke Darwaje Se Ram Niwas Ke Darwaje Ki Or, Khipona | Completed | 44175 | 40716 | 2019-01-25 | 2019-05-15
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034434769 — C.C.Road Satendra Jatav Ke Darwaje Se Shankar Ji mandir Ki or, Khree | Completed | 18999 | 18852 | 2019-02-15 | 2019-05-15
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034434770 — C.C.Raod Hanuman Mandir Se Dharam Singh Jatav Ke Darwaje Ki Or, Khree | Completed | 29096 | 28188 | 2019-02-22 | 2019-05-15
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034436854 — C.C.Raod Mai Nali Sarnam Baghel Ke Dar. Se Ramhari Ke Dar. Hote Hue Shiv singh Ke makan Ki or | Completed | 111600 | 111534 | 2019-02-08 | 2019-05-15
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034442388 — cc road | Closed | 0 | 0 | 2019-01-26
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034444748 — सी.सी.रोड मय नाली राम दिवाकर के दरवाजे से रामकुमार जोशी के दरवाजे की ओर खिपोना | Completed | 37200 | 35496 | 2019-02-22 | 2019-05-15
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034448810 — सी.सी.रोड मय नाली परिमाल सिंह के दरवाजे से तालाब की ओर , खिपोना | Completed | 44100 | 42240 | 2019-07-22 | 2019-08-20
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034482374 — सी.सी.रोड निर्माण गंगा सिंह के दरवाजे से हरिराम के दरवाजे की ओर , रतनुपुरा | Completed | 76500 | 74976 | 2019-11-13 | 2020-05-21
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034482376 — सी.सी.रोड मय नाली निर्माण प्रधान मंत्री सड़क से प्रेम सिंह के दरवाजे की ओर , रतनुपुरा | Completed | 18600 | 16896 | 2019-11-29 | 2020-05-21
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034482379 — सी.सी.रोड निर्माण सी.सी.सड़क से मान श्री जाटव के दरवाजे की ओर , रतनुपुरा | Completed | 22950 | 21472 | 2019-11-22 | 2020-05-21
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034514744 — cc road | Closed | 0 | 0 | 2019-10-02
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034514748 — cc road | Closed | 0 | 0 | 2019-10-02
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034529207 — C.C.Road PM Sadak Se Sobharam Ke Darwaje Ki Or,Yadavo Ki Thar Khipona | Completed | 22950 | 22800 | 2020-08-21 | 2020-09-15
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034529208 — C.C.Road nali Nirman Main Road Se Aaganwadi Bhawan Ki Or, Ratnupura | Completed | 34875 | 34200 | 2020-08-28 | 2020-09-15
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034553631 — C.C.Raod Nirman Niranjanpura Primary Shala Bhawan Se Preetam Ke Darwaje Ki Or, Khipona | Completed | 65625 | 65550 | 2021-01-09 | 2021-05-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001049/RC/22012034611142 — Sudur Road Nirman Niranjan Pura Se Hulapura Ki Or, Khipona | Closed | 0 | 0 | 2022-01-26
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001049/RC/22012034611143 — Sudur Road Nirman Niranjan Pura Se Hulapura Ki Or, Khipona | Closed | 0 | 0 | 2022-01-26
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001049/RC/22012034612169 — Sudur Road Niranjanpura se Hulapura Ki or, Khipona | Closed | 0 | 0 | 2022-04-01
ATER | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034832866 — c c road kachhi sadak se suresh sarhama ke darwaje ke or | Ongoing | 30000 | 27945 | 2025-02-20
ATER | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034832871 — c c road rajveer ke darwaje se hote huye foran singh ke darwaje ke or | Ongoing | 60000 | 59631.3 | 2025-02-20
ATER | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/22012034832873 — c c road - pradhan mantri sadak se harijan basti mahadev jatav ke darwaje ke or ratnupura | Completed | 15000 | 14580 | 2025-02-11 | 2026-04-21
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/332 — cc road deneda belinding se ps ke or | Completed | 0 | 95732 | 2012-05-25 | 2012-06-10
ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001049/RC/508 — 1702001049/RC/508 | Completed | 155400 | 145890.2 | 2013-03-01 | 2013-06-25
ATER | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001049/RC/58 — पहॅुच मार्ग | Completed | 500000 | 84812 | 2009-02-28 | 2009-01-14
ATER | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001049/RC/64 — पहॅुच मार्ग | Deleted | 500000 | 0 | 2009-05-18
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001049/RS/22012034253992 — toilet 1 Jasvant 2 Ramnivas 3 Patiram 4 Sultansing | Completed | 54000 | 53929 | 2014-08-06 | 2014-11-30
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001049/RS/22012034254092 — toilet 1Maniram 2 Folad 3 Mahesh 4 Gambeer 5 Rajve | Completed | 54000 | 53929 | 2014-08-20 | 2014-12-30
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001049/RS/22012034254096 — toilet 1 Surendkumar 2 Ramratan 3 Gangadhar 4 Vire | Completed | 27000 | 26886 | 2014-10-22 | 2014-11-30
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001049/RS/22012034254099 — toilet 1 Darshansingh 2 Rambabu 3 Raghuveer 4 Moha | Completed | 21600 | 21446 | 2014-10-29 | 2014-12-30
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001049/RS/22012034278435 — Toilet- | Completed | 54000 | 53929 | 2014-10-30 | 2014-11-30
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001049/RS/22012034278436 — Toilet- | Completed | 54000 | 53929 | 2014-10-29 | 2014-11-04
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001049/RS/22012034278437 — Toilet- | Completed | 27000 | 26886 | 2014-10-29 | 2014-11-05
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001049/RS/22012034278438 — Toilet- | Completed | 54000 | 53929 | 2014-10-29 | 2014-11-30
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034530919 — Soak Pit Nirman-Dhaniram Ke Darwaje Ke Pass, Ratan Singh ka Pura, Khipona | Completed | 4600 | 4439 | 2021-07-08 | 2021-08-14
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034530975 — Soak Pit Nirman-Mandir Bale Handpump Ke Pass, Yadavban ka Pura | Completed | 4600 | 4439 | 2021-07-08 | 2021-08-14
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034530981 — Soak Pit Nirman-Ramniwas Ke Darwaje Ke Pass, Khipona | Completed | 4600 | 4896 | 2022-05-27 | 2022-07-25
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034530985 — Soak Pit Nirman-Ramniwas Ke Darwaje Ke Pass, Khipona | Deleted | 0 | 0 | 2021-04-14
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034530986 — Soak Pit Nirman-Krishnamurari Sharma Ke Darwaje Ke Pass, Khipona | Completed | 4600 | 4439 | 2021-07-08 | 2021-08-14
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034530992 — Soak Pit Nirman-Krishnamurari Sharma Ke Darwaje Ke Pass, Khipona | Deleted | 0 | 0 | 2021-04-14
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034530996 — Soak Pit Nirman-Guddi Baghel Ke Darwaje Ke Pass, Khipona | Completed | 4600 | 4439 | 2021-07-08 | 2021-08-14
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034530999 — Soak Pit Nirman-Guddi Baghel Ke Darwaje Ke Pass, Khipona | Deleted | 0 | 0 | 2021-04-14
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034531003 — Soak Pit Nirman- Yashpal Singh Ke Darwaje Ke Pass, Khipona | Completed | 4600 | 4830 | 2021-11-15 | 2022-11-25
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034531022 — Soak Pit Nirman- Santosh singh Ke Darwaje Ke Pass, Khipona | Completed | 4600 | 4632 | 2021-11-15 | 2022-07-26
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034531026 — Soak Pit Nirman- Rammoj Singh Ke Darwaje Ke Pass, Khipona | Completed | 4600 | 4439 | 2021-07-08 | 2021-08-14
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034531031 — Soak Pit Nirman- Mahendra Balmik Ke Darwaje Ke Pass, Khipona | Completed | 4600 | 4439 | 2021-07-08 | 2021-08-14
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034531039 — Soak Pit Nirman-Gajadhar Singh Ke Darwaje Ke Pass, Khipona | Completed | 4600 | 4439 | 2021-11-15 | 2023-04-29
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034531047 — Soak Pit Nirman-Pipal Bale Handpump Ke Pass, Ratnupura | Completed | 4600 | 4439 | 2021-07-08 | 2021-08-14
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034531055 — Soak Pit Nirman-Ram prakash Jatav Ke Darwaje Ke Pass, Ratnupura | Completed | 4600 | 4439 | 2021-07-08 | 2021-08-14
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034531060 — Soak Pit Nirman-Lau Ke Darwaje Ke Pass, Khipona | Completed | 4600 | 4439 | 2021-11-15 | 2022-07-26
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034531061 — Soak Pit Nirman-Lau Ke Darwaje Ke Pass, Khipona | Deleted | 0 | 0 | 2021-04-14
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034531066 — Soak Pit Nirman-Ramnath Baghel Ke Darwaje Ke pass, Khipona | Completed | 4600 | 4439 | 2021-07-08 | 2021-08-14
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034531074 — Soak Pit Nirman-Surendra Baghel ke Darwaje Ke Pass, Khipona | Completed | 4600 | 4439 | 2021-07-08 | 2021-08-14
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702001049/RS/22012034560374 — सामुदायिक स्वछता परिसर -पंचायत भवन के पास ग्राम-खिपोना | Completed | 43000 | 43811 | 2021-09-18 | 2022-07-26
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Community / Construction of Berkeley Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702001049/RS/22012034562431 — सेग्रीगेशन शैड निर्माण-कोमल शर्मा के मकान के पीछे खिपोना | Completed | 30076 | 30108 | 2021-09-18 | 2021-11-30
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034565927 — Soak Pit Nirman Gya Prasad Jatav Ke Darwaje Ke Pass, Khipona | Completed | 4600 | 4896 | 2022-06-03 | 2022-07-24
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034565928 — Soak Pit Nirman Dinesh Singh Ke Darwaje Ke Pass, Khipona | Completed | 4600 | 4488 | 2022-11-27 | 2022-12-10
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034565929 — Soak Pit Nirman Siyaram Singh Ke Darwaje Ke Pass, Khipona | Completed | 4600 | 4488 | 2022-04-15 | 2022-07-26
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034565930 — Soak Pit Nirman Siyaram Baghel Ke Darwaje Ke Pass, Khipona | Closed | 4600 | 0 | 2021-09-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034565931 — Soak Pit Nirman Jaswant Gurjar Ke Darwaje Ke Pass, Niranjanpura,Khipona | Closed | 4600 | 0 | 2021-09-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034565932 — Soak Pit Nirman Ramesh Baghel Ke Darwaje Ke Pass, Khipona | Closed | 4600 | 0 | 2021-09-15
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034565933 — Soak Pit Nirman Suresh Sharma Ke Ghar Ke Pass, Khipona | Completed | 4600 | 4488 | 2022-11-27 | 2022-12-10
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034565935 — Soak Pit Nirman Foran Singh ke Darwaje Par, Khipona | Completed | 4600 | 4488 | 2022-11-27 | 2022-12-10
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034565937 — Soak Pit Nirman Raj Bahadur Ke Darwaje Ke Pass, Khipona | Closed | 4600 | 0 | 2021-09-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034565940 — SoakPit Nirman Jasram Singh Ke Darwaje Ke Pass, Khipona | Closed | 4600 | 0 | 2021-09-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034565942 — Soak Pit Nirman-Radheshyam Singh ke Darwaje Ke Pass, Khipona | Closed | 4600 | 0 | 2021-09-15
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034565944 — Soak Pit Nirman Surendra Sharma Ke Darwaje Ke Pass, Khipona | Closed | 4600 | 0 | 2021-09-15
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001049/RS/22012034565956 — Soak Pit Nirman Abhilakh Singh Ke Darwaje Ke Pass, Khipona | Completed | 4600 | 4488 | 2022-04-08 | 2022-07-26
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001049/RS/22012034670202 — Samudayak nandep Nirman Kailash/ Gangadeen Ke Ghar ke pass, Khipona | Completed | 2040 | 2040 | 2022-11-06 | 2022-11-21
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001049/RS/22012034670203 — Samudayak nandep Nirman Ramprakash/Patu KE Ghar Ke Pass, Khipona | Completed | 2040 | 1904 | 2023-04-24 | 2023-08-06
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001049/RS/22012034670204 — Samudayak nandep Nirman Mahaveer/Harvilas Ke Ghar Ke Pass, Khipona | Completed | 2040 | 2040 | 2023-02-01 | 2023-03-01
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001049/RS/22012034670206 — Samudayak nandep nirman Tehseeldar/Randhor Ke Ghar Ke Pass, Khipona | Completed | 2040 | 1836 | 2022-11-13 | 2022-11-28
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001049/RS/22012034670207 — Samudayak Nandep Nirman Ashok Singh/Shridayal Ke Ghar Ke Pass, Khipona | Completed | 2040 | 2040 | 2022-11-06 | 2022-11-20
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001049/RS/22012034670209 — Samudayk Nandep Nirman Rambabu Gurjar Ke Ghar Ke Pass,, Khipona | Completed | 2040 | 2040 | 2022-11-28 | 2023-03-01
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001049/RS/22012034670210 — Samudayak Nandep nirman Brajesh/ Pancham Singh ke Ghar Ke Pass, Khipona | Completed | 2040 | 2040 | 2022-11-06 | 2022-11-20
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001049/RS/22012034670212 — Samudayak Nandep Nirman Rajveer/Mahendra Ke Ghar Ke Pass, Khipona | Completed | 2040 | 2040 | 2023-02-01 | 2023-03-01
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Community / Construction of Berkeley Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702001049/RS/22012034670213 — Samudayak Leej Pit Nirman Ashok Singh/Shridayal Ke handpump Ke Pass, Khipona | Completed | 2670 | 2652 | 2022-11-28 | 2022-12-10
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Community / Construction of Berkeley Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702001049/RS/22012034670215 — Samudayak Leej Pit Nirman Bhupendra/ Laxman Ke Handpump Ke Pass, Khipona | Completed | 2670 | 2652 | 2022-11-28 | 2022-12-10
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Community / Construction of Berkeley Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702001049/RS/22012034670218 — Samudayak Leej Pit Nirman Brajesh/Puncham Ke Handpump Ke Pass, Khipona | Completed | 2670 | 2652 | 2022-11-28 | 2022-12-10
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Community / Construction of Berkeley Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702001049/RS/22012034670222 — Samudayak Leej pit nirman Rambabu Ke Handpump Ke Pass, Khipona | Completed | 2670 | 2652 | 2022-11-06 | 2022-11-20
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Community / Construction of Berkeley Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702001049/RS/22012034670225 — Samudayak Leej pit Nirman Deendayal/Chetram ke handpump Ke Pass, Khipona | Completed | 2670 | 2652 | 2022-11-06 | 2022-11-20
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Community / Construction of Berkeley Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702001049/RS/22012034670227 — Samudayak Leej pit Nirman Raghuveer Ke Handpump Ke Pass, Khipona | Completed | 2670 | 2652 | 2022-11-28 | 2022-12-10
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Community / Construction of Berkeley Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702001049/RS/22012034670229 — Samudayak Leej Pit Nirman Suresh/Chetram Ke handpump Ke Pass, Khipona | Completed | 2670 | 2652 | 2022-11-06 | 2022-11-20
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Community / Construction of Berkeley Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702001049/RS/22012034670230 — Samudayak Leej Pit Nirman Ganga Singh/Mahendra Ke Handpump Ke Pass, Khipona | Completed | 2670 | 2652 | 2022-11-06 | 2022-11-20
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Community / Construction of Berkeley Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702001049/RS/22012034670231 — Samudayak Leej Pit Nirman Sanjay/Shiv Singh Ke Handpump Ke Pass, Khipona | Completed | 2670 | 2652 | 2022-11-06 | 2022-11-20
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001049/SK/9993649353 — Bharat Nirman Rajeev Gandhi Sewa Kendra,KHEREE | Completed | 1285000 | 519552 | 2017-09-23 | 2019-01-10
ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001049/WC/21 — नवीन तालाब निर्माण | Completed | 182000 | 0 | 2009-09-17 | 2009-01-26
ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1702001049/WC/22012034326840 — Talab Nirman- Kodari Ke Pass, Khipona | Deleted | 426637 | 0 | 2017-05-17
ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702001049/WC/22012034326842 — Talab Nirman- Nai Tor Ke Neeche, Khipona | Completed | 426637 | 312524 | 2017-05-31 | 2018-08-01
ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001049/WC/22012034426109 — Earthan Bund- Hiddh Bale Ke Neeche, Khipona | Completed | 159200 | 80280 | 2019-03-06 | 2020-06-04
ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001049/WC/22012034426113 — Earthan Bund- Jagne Ki Tor, Khipona | Completed | 131000 | 84540 | 2019-03-09 | 2020-06-04
ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001049/WC/22012034444208 — नवीन मिट्टी डेम निर्माण-पीला डाडा के पास , खिपोना | Closed | 199000 | 0 | 2019-01-26
ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001049/WC/22012034444219 — नवीन मिट्टी डेम निर्माण-फीडर के नीचे , खिपोना | Closed | 195000 | 0 | 2019-01-26
ATER | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702001049/WC/22012034466422 — Retaining Wall nirman- talab par, khipona | Physically Completed | 180000 | 1056 | 2019-07-03 | 2022-01-25
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001049/WC/22012034472063 — Earthan Check Dem- Feedar Ke Neeche, Khipona | Completed | 168895.73 | 127680 | 2020-05-14 | 2020-12-20
ATER | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001049/WC/22012034472064 — Earthan Dem Nirman-Peela Danda Ke Pass, Khipona | Completed | 158386.66 | 132168 | 2019-08-23 | 2020-06-04
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702001049/WC/22012034556936 — Talab Nirman Dabel Ke Neeche, Khipona | Deleted | 0 | 0 | 2020-04-01
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001049/WC/22012034556937 — Check Dem- Pipara Bali Ke Pass, Khipona | Completed | 202589.75 | 140220 | 2020-07-10 | 2021-04-15
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001049/WC/22012034556938 — Naveen Mitti Bandh Nirman Paduya Ke Neeche, Khipona | Deleted | 0 | 0 | 2020-04-01
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001049/WC/22012034562134 — Dug Pond- Dabel ke Neeche, Khipona | Completed | 442014 | 355490 | 2020-07-03 | 2021-02-02
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702001049/WC/22012034567766 — Naveen Talab Nirman Chandan Singh Ki Tor Ke Neeche, Khipona | Completed | 552517.5 | 454860 | 2020-08-14 | 2021-03-07
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702001049/WC/22012034619964 — Naveen Talab Nirman Khipona Khrik Bale Ke Neeche | Completed | 1202211.73 | 906855 | 2021-03-06 | 2021-10-03
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702001049/WC/22012034713989 — Dug Point Kamal Singh Ki Tor Ke Neeche, Khipona | Deleted | 0 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001049/WC/22012034736038 — Dug Pond Kamal Singh Ki Tor Ke Neeche, Khipona | Completed | 589915.29 | 336978 | 2021-06-03 | 2021-08-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001049/WC/22012034773947 — Dug Pond Chuchari mata ke pass, Khipona | Completed | 850822.07 | 280236 | 2021-07-22 | 2021-12-15
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001049/WC/22012034773948 — Dug Pond Chak Bali Khandiya ke pass, Khipona | Completed | 777714.05 | 386291 | 2021-07-22 | 2023-08-06
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702001049/WC/22012034856030 — Talab Saudrikaran Panchayat Bhawan Ke Pass, Khipona | Completed | 785316.17 | 782686 | 2022-01-19 | 2022-08-15
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Upland Bench Terrace Terrace for Comm / Construction of Upland Bench Terrace for Community | Terracing | 1702001049/WC/22012034924189 — Naveen Talab Nirman Semar Thok Ke Pass, Khipona | Physically Completed | 1409932.26 | 1263716.24 | 2022-03-16 | 2026-04-17
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001049/WC/22012034994415 — Earthan Bund Nirman Kotari Ke Khadika Ke Neeche, Khipona | Completed | 109848.34 | 91800 | 2022-09-09 | 2022-11-03
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001049/WC/22012034994417 — Earthan Bund Nirman Kamal Singh Ke Banda Ke Neeche, Khipona | Completed | 148005.28 | 124644 | 2022-09-09 | 2022-11-03
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001049/WC/22012035014849 — Earthan Bund Nirman Gaudi Bali ke pass, Khipona | Completed | 250849.96 | 180999 | 2022-12-19 | 2024-10-22
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001049/WC/22012035033785 — Dug Pond Nirman Pilua Kola , Khipona | Physically Completed | 1080458.42 | 621044 | 2023-02-08 | 2026-04-17
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001049/WC/22012035053337 — Navin Talab Nirman Badan singh ki tor ke Niche Khipona | Deleted | 0 | 0 | 2023-01-24
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001049/WC/22012035056497 — Talab Nirman Badan singh ke tor ke nichhe khipona | Completed | 1496343.26 | 819468 | 2023-05-22 | 2025-05-13
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001049/WC/22012035089203 — Earthen check dam nirman Bhuda ke pass Khipona | Completed | 1496763.5 | 651066 | 2023-07-10 | 2024-10-22
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001049/WC/22012035094906 — chek dem nirman sakuli baba than ke pichhe khipona | Closed | 0 | 0 | 2023-04-14
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001049/WC/22012035094907 — chek dem nirman nahar kola ke pass khipona | Closed | 0 | 0 | 2023-04-14
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001049/WC/22012035094908 — chek dem nirman Gadara vali ke pass khipona | Physically Completed | 1343681.97 | 371501 | 2023-09-17 | 2026-04-17
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001049/WC/22012035176232 — Earthen Chek bund Nirman - Arusan vali thari ke pass khipona | Suspended | 1490847.17 | 746184.88 | 2024-03-03
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1702001049/WC/22012035176238 — Earthen Gully Plugs - ikavai ke muhare ke pass khipona | Completed | 396930.06 | 314700 | 2024-03-10 | 2025-05-13
ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001049/WC/22012035316424 — Parcolation tank Nirman Pilua kola Thari ke pass khiphona | Approved | 0 | 0 | 2025-04-14
ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Pebble contour Bund for Community / Construction of Pebble contour Bund for Community | Construction of Bund | 1702001049/WC/22012035316592 — pheriphal Earthan bund Nirman Pilua kola thari ke pass khiphona | Approved | 0 | 0 | 2025-04-14
ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001049/WC/4 — तालाब निर्माण | Completed | 58000 | 32669 | 2009-02-19 | 2008-12-02
ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001049/WC/8 — तालाब निर्माण | Completed | 164000 | 11466 | 2009-03-01 | 2008-12-02
ATER | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001049/WC/9993640312 — Const.of tank near kondri | Completed | 418000 | 400399.6 | 2013-12-18 | 2014-03-30
ATER | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001049/WC/9993662538 — Talab nirman Shankar ji mandir ke pass | Completed | 320000 | 186030 | 2016-01-20 | 2017-09-01
ATER | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001049/WC/9993666433 — Talab nirman Khipona | Completed | 341000 | 185876 | 2016-02-17 | 2017-09-01
ATER | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001049/WH/19956771 — Deepning of tank | Deleted | 100000 | 0 | 2016-05-25
ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001049/WH/19963889 — Renovation of Pond- Khipona | Completed | 100000 | 61920 | 2017-06-28 | 2019-08-18
ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001049/WH/22012034325352 — तालाब गहरीकरण स्कूल के पास रतनुपुरा | Completed | 97000 | 61576 | 2017-06-28 | 2017-08-15
ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001049/WH/22012034389221 — talab niraman - kodari ke paas khiphona | Completed | 426000 | 246384 | 2018-09-28 | 2019-01-05