## Work List
Exported on: 2026-09-10 02:50:14
Filters applied:
Data source: MGNREGA + VBGRAMG
District: BHIND
Block: All
Panchayat: KHADIT
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702001076/AV/22012034537788 — aganwadi bhawan khadit | Completed | 180000 | 178398 | 2020-09-29 | 2022-11-05
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702001076/AV/22012034548464 — khel maidan - gram panchayat khadit | Closed | 0 | 0 | 2020-12-01
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702001076/AV/22012034624577 — khel maidan - khadit | Completed | 428758.5 | 194344 | 2022-11-23 | 2025-06-07
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1702001076/DP/22012034548157 — maa ke bagiya - shashkiya madhiyamik vidhalaya khadit | Closed | 9283 | 0 | 2021-10-02
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1702001076/DP/22012034590174 — ब्रक्षारोपण कार्य - शा० मा० विद्यालय खडीत | Suspended | 55847.4 | 15912 | 2023-08-21
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702001076/FP/22012034624676 — nali nirman - panchayat bhawan se ramlaxin kushwah ke ghar ke or | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702001076/FP/22012034624677 — nali nirman - hospital se ramkaran singh ke dwar ke or | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702001076/FP/22012034626798 — Nali nirman - hospital se ramkaran singh kushwah ke dwar ke or | Closed | 121206 | 0 | 2021-09-29
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702001076/FP/22012034629609 — Nala nirman - rakesh ke darwaje se c c road ke or | Suspended | 94203.7 | 3672 | 2022-11-23
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702001076/FP/22012034629720 — kachha Nala nirman- kali mata mandir se behad ke or | Closed | 0 | 0 | 2022-08-16
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001076/FP/22012034633970 — nala nirman - savdeen sharma ke ghar se behad ke or | Closed | 0 | 0 | 2023-04-14
ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001076/FP/22012034637383 — kachha nala nirman - mata mandir se behad ke or | Closed | 0 | 0 | 2023-10-02
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001076/IF/22012034352482 — braksharopan karya gram panchayat khadit | Completed | 335000 | 3000 | 2017-09-15 | 2021-10-26
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001076/IF/22012034354418 — PLANTATION WORK at govt school & road side gram khadit | Deleted | 335000 | 0 | 2017-06-22
ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001076/IF/22012034742215 — maid bandan - raghuveer / ramnath bakeel | Closed | 13904.14 | 0 | 2021-04-14
ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001076/IF/22012034742216 — maid bandan - atiraj / ramdayal | Closed | 21416.32 | 0 | 2021-04-14
ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001076/IF/22012034742218 — maid bandan - Sonu / jagram | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001076/IF/22012034742222 — maid bandan - pooran singh / narayan singh | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001076/IF/22012034742229 — maid bandan -rajesh / mahendra singh | Completed | 24985.65 | 8106 | 2021-06-17 | 2021-10-26
ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001076/IF/22012034742233 — maid bandan - tahseeldar / latoori | Completed | 18356.82 | 11580 | 2021-06-17 | 2021-10-26
ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001076/IF/22012034742235 — maid bandan -bhure / jeevaram | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001076/IF/22012034742237 — maid bandan - sughar singh / paijram | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001076/IF/22012034742254 — maid bandan - ram singh / shankar singh | Completed | 26515.4 | 20844 | 2021-06-17 | 2021-10-26
ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001076/IF/22012034742258 — maid bandan - jagdeesh / tej singh | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001076/IF/22012034788956 — maid bandan -Ramkaran / baijanath | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001076/IF/22012034788960 — maid bandan - rambilash / lotan ke khet par | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001076/IF/22012034813854 — maid bandan - layak singh / narayan singh ke khet par | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001076/IF/22012034813860 — maid bandan - dhaniram / ramdeen ke khet par | Closed | 0 | 0 | 2021-04-14
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001076/IF/22012035322309 — khet talab amar singh ke khet par | Suspended | 147621.16 | 78748.2 | 2025-05-12
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001076/IF/22012035322317 — khet talab radhelal kushwah ke khet par | Suspended | 147621.16 | 68858.93 | 2025-05-12
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001076/IF/22012035322327 — khet talab veerbhan ke khet ke pass | Suspended | 147621.16 | 9302.94 | 2025-05-12
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702001076/IF/22012035600915 — maa ke bagiya Rambavati | Approved | 0 | 0 | 2025-08-14
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702001076/IF/22012035613681 — maa ke bagiya bahota devi | New | 0 | 0 | 2025-08-14
ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702001076/IF/22012035626327 — maa ke bagiya bahota | New | 0 | 0 | 2025-08-14
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001076/IF/IAY/125574 — Construction of IAY House -IAY REG. NO. MP-02-001-076-001/73 | Approved | 27000 | 0 | 2016-02-01
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001076/IF/IAY/209509 — Construction of IAY House -IAY REG. NO. MP1057607 | Completed | 17100 | 12463 | 2017-02-08 | 2021-10-26
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001076/IF/IAY/262436 — Construction of IAY House -IAY REG. NO. MP2672811 | Completed | 15030 | 15362 | 2017-02-27 | 2019-01-05
ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001076/IF/IAY/270495 — Construction of IAY House -IAY REG. NO. MP2663796 | Completed | 17100 | 14618 | 2017-03-02 | 2020-08-21
ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001076/IF/IAY/3282413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2687303 | Physically Completed | 17370 | 15912 | 2023-04-25 | 2024-11-21
ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001076/IF/IAY/3907824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148417653 | Ongoing | 27000 | 3978 | 2023-04-27
ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001076/IF/IAY/3978306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119531201 | Physically Completed | 18360 | 15912 | 2023-04-27 | 2024-11-21
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001076/IF/IAY/3985095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124807594 | Physically Completed | 18360 | 16218 | 2022-11-05 | 2024-11-21
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001076/IF/IAY/4030013 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148416929 | Physically Completed | 18360 | 16626 | 2022-11-13 | 2024-11-21
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001076/IF/IAY/4030015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148417249 | Physically Completed | 23490 | 10098 | 2022-11-05 | 2026-01-10
ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001076/IF/IAY/4109984 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148417573 | Physically Completed | 18360 | 8772 | 2022-11-05 | 2024-11-21
ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001076/IF/IAY/4109987 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148417682 | Ongoing | 27000 | 16872 | 2023-04-27
ATER | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001076/IF/IAY/684592 — Construction of IAY House -IAY REG. NO. MP1764447 | Completed | 15030 | 14616 | 2018-11-05 | 2019-09-25
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001076/IF/IAY/685279 — Construction of IAY House -IAY REG. NO. MP2057344 | Completed | 15030 | 14384 | 2017-09-14 | 2019-09-25
ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001076/IF/IAY/80164 — Construction of IAY House -IAY REG. NO. MP-02-001-076-001/64 | Approved | 27000 | 0 | 2016-01-08
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001076/IF/IAY/831508 — Construction of IAY House -IAY REG. NO. MP1055920 | Completed | 15480 | 15230 | 2017-09-14 | 2019-09-25
ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001076/IF/IAY/980920 — Construction of IAY House -IAY REG. NO. MP3918372 | Completed | 15480 | 15480 | 2017-09-27 | 2018-02-20
ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001076/LD/16 — मेढ बन्‍धान रामप्रकाश/फूल सिंह | Deleted | 34200 | 0 | 2009-01-14
ATER | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001076/LD/22012034293609 — Shantidham Work- Khadeet | Completed | 410000 | 369018.5 | 2016-11-21 | 2017-09-01
ATER | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001076/LD/22012034301837 — SHANTIDHAM KHADIT | Deleted | 410000 | 0 | 2016-11-25
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034188079 — cc road from house of omprakash towords hospital | Completed | 160500 | 160490 | 2014-01-20 | 2014-07-10
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001076/RC/22012034192748 — Pahuch margh nirman main road se panchayat bhawan | Completed | 500000 | 482433.87 | 2013-12-02 | 2014-02-20
ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034215287 — C.C.Road P.M. Road Se Primary shala bhawan ki or A | Completed | 179000 | 178020 | 2014-03-24 | 2014-12-20
ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034221633 — C.C.Road Leeladhar Ke Makan Se Rajoriya Ke Makan K | Completed | 343800 | 343341 | 2014-06-16 | 2014-08-30
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001076/RC/22012034267023 — G S B Road pmgsy road to kachiyan ka pura Nale tak | Completed | 667000 | 243906 | 2015-07-06 | 2017-09-01
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001076/RC/22012034283355 — Pahuch Margh Suklapura main Road se mata mandir tak | Deleted | 803000 | 0 | 2015-08-21
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034284832 — CC road Ramdhakeli house to Bacharam house | Completed | 149500 | 145182 | 2015-10-26 | 2017-09-01
ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034286684 — cc road atiraj house to hand pump | Completed | 149500 | 149316 | 2015-10-26 | 2017-09-01
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034310047 — CC ROAD | Deleted | 0 | 0 | 2016-04-01
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034312142 — cc road Dhaniram house to Badan singh house | Deleted | 50000 | 0 | 2016-05-27
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034312144 — c c road vishunath house to Kali mata mandir and Mohar singh house to Panchayet bhaban | Completed | 243000 | 241188 | 2016-10-03 | 2019-09-25
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034314743 — CC Road Ramprakash Thapak House to Shivdeen house | Completed | 144000 | 143759 | 2016-09-10 | 2017-09-01
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034314745 — CC Road Dhaniram kushawah house to Badan singh house | Completed | 50000 | 49446 | 2016-09-05 | 2017-09-01
ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034315034 — cc road Munnalal house to Sukharam jatav house | Completed | 120000 | 108463 | 2016-09-26 | 2019-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034360120 — c c road ( ramdas ke makan se kali mata mandir tak khait ) | Completed | 72075 | 76024 | 2017-09-15 | 2019-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034365404 — c c road ( vijayram ke makan se shaskiya prathimik school ke or laxman nagar khadit) | Completed | 110160 | 108360 | 2017-10-28 | 2019-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034365408 — c c road ( ramesh ke darwaje se gyan singh ke or khadit ) | Completed | 73575 | 70176 | 2017-10-28 | 2019-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034365409 — c c road ( ram lakhan ke dwar se school ke or khadit ) | Completed | 34335 | 33024 | 2017-10-28 | 2019-09-25
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034376923 — cc road | Deleted | 0 | 0 | 2018-04-01
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034378781 — सी सी रोड ( सत्यनरायण मेहतर से राजेन्द्र के मकान की ओर खडीत ) | Completed | 79050 | 65376 | 2018-02-21 | 2019-09-25
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034381942 — cc road | Closed | 0 | 0 | 2017-10-02
ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034382463 — cc road | Closed | 0 | 0 | 2017-10-02
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034392674 — सी सी रोड ( मोधना रोड से सुरेश पुरोहित के मकान की ओर खडीत ) | Completed | 122625 | 121974 | 2018-10-06 | 2019-10-25
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034396419 — सी सी रोड ( मैन रोड से पंचायत भवन की ओर ) | Completed | 127000 | 126348 | 2018-10-06 | 2020-08-21
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034396421 — सी सी रोड (मोधना रोड से रतीराम बघेल की ओर | Completed | 76000 | 69948 | 2018-10-06 | 2019-08-25
ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034442387 — cc road | Closed | 0 | 0 | 2019-01-26
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034474165 — c c road ( rambabu ke khet se siya ram ke ke ghar ke or ) | Completed | 25627 | 23736 | 2019-10-22 | 2020-08-21
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034505709 — सी सी रोड भगवान सिह के दरवाजे से रामसहाय के घर की ओर (पंचायत भवन के पास) | Completed | 102000 | 96312 | 2019-11-26 | 2021-10-26
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034505710 — सी सी रोड रामलछिन के द्वार से रामदुलारे के घर की ओर (काली माता मन्दिर के पास) | Completed | 79312 | 77016 | 2019-11-26 | 2021-10-26
ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034514743 — cc road | Closed | 0 | 0 | 2019-10-02
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034541476 — c c road ( ram mukesh ke ghar se kushwah mohalla ke or ) | Completed | 100406 | 99676 | 2021-01-10 | 2021-10-26
ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001076/RC/22012034556847 — sudoor road ( ramanath baghel ke ghar se mata mandir tak laxman nagar khadit ) | Closed | 0 | 0 | 2020-12-01
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001076/RC/22012034570528 — c c road ( rambaran ke ghar se rakesh ke ghar ke or ) | Completed | 93000 | 69480 | 2021-11-22 | 2022-07-26
ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001076/RC/22012034629859 — SUdoor road - ram nath baghel ke ghar se amar singh baghel ke ghar ke or laxman garh | Closed | 0 | 0 | 2023-01-24
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001076/RS/22012034562708 — segregation sad - Khadit | Closed | 30076 | 0 | 2021-04-14
ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Vermi Compost structure for Community / Construction of Vermi Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001076/RS/22012034562713 — segregation sad - khadit. | Completed | 30076 | 28950 | 2021-11-08 | 2022-07-26
ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001076/WC/22012034355489 — bori bandhan at kwari river in gram khadit | Completed | 167000 | 138377.4 | 2017-09-27 | 2019-09-25
ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001076/WC/22012034426424 — Earthan Bund-Bacharam Katare Ke Khet Ke Pass, Khadit | Completed | 159200 | 152772 | 2018-12-15 | 2019-12-11
ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001076/WC/22012034426428 — Earthan Bund- Mata mandir Ke Peeche, khadit | Completed | 318400 | 310068 | 2018-12-15 | 2019-12-11
ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001076/WC/22012034426440 — Earthan Bund- Suresh Jatav Ka Khet Mahadev Mandir Ke Pass, khadit | Completed | 159200 | 151380 | 2018-12-15 | 2019-12-11
ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001076/WC/22012034439358 — Earthan Bund- Satyaram Sweepar ka patta khet ke pass | Completed | 159000 | 157524 | 2019-02-26 | 2020-06-15
ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001076/WC/22012034439359 — Earthan Bund- Hotam Kushwah Ke Khet Ke Pass | Completed | 191000 | 163036 | 2019-02-26 | 2019-12-11
ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001076/WC/22012034439361 — Earthan Bund- Devendra Jyotishi ke khet ke pass | Completed | 159000 | 187848 | 2019-02-26 | 2020-02-26
ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001076/WC/22012034446800 — mitti dam radheshyam ke khet ke pass | Closed | 195000 | 0 | 2019-01-26
ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001076/WC/22012034446807 — mitti dam ram kumar ke khet ke pass | Closed | 199000 | 0 | 2019-01-26
ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001076/WC/22012034446813 — mitti dam ramesh ke ghar ke pass | Closed | 195000 | 0 | 2019-01-26
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone contour Bund for Community / Construction of Stone contour Bund for Community | Construction of Bund | 1702001076/WC/22012034528865 — talab nirman - khadit | Completed | 1100515.67 | 389690 | 2020-06-17 | 2021-10-26
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001076/WC/22012034556448 — Talab nirman - khadit | Closed | 0 | 0 | 2020-05-05
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001076/WC/22012034556449 — talab nirman - khadit | Closed | 0 | 0 | 2020-05-05
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702001076/WC/22012034572615 — Earth band ( krparam / shriram) | Closed | 0 | 0 | 2020-05-05
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001076/WC/22012034610585 — band nirman - gram khadit behad | Closed | 0 | 0 | 2020-12-01
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001076/WC/22012034614928 — band nirman - khadit behad | Closed | 0 | 0 | 2021-01-22
ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001076/WC/22012034614930 — band nirman - behad | Closed | 0 | 0 | 2021-01-22
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001076/WC/22012034672116 — talab nirman - sheetla tal | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001076/WC/22012034672125 — talab nirman - muhan ka tal | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001076/WC/22012034672130 — Earth band nirman - khadit behad | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001076/WC/22012034672133 — Earth band nirman - khadit behad 2 | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Mini Percolation Tank for Comm / Repair and maintenance of Mini Percolation Tank for Community | Repair & maint of Percolation Tank | 1702001076/WC/22012034687004 — talab nirman - khadit behad | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001076/WC/22012034687011 — talab nirman - kushwah har me khadit | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001076/WC/22012034687017 — talab nirman - ghat wale baba ke pass | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001076/WC/22012034763368 — roof water Harvesting work - panchayat bhawan khadit | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001076/WC/22012034763370 — roof water Harvesting work - govt midil school khadit | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001076/WC/22012034763372 — roof water Harvesting work - aganwadi bhawan kushwah mohalla khadit | Closed | 0 | 0 | 2021-04-14
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001076/WC/22012034763374 — roof water Harvesting work - swashtya kendra khadit | Closed | 0 | 0 | 2021-04-14
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001076/WC/22012035046158 — talab nirman - khadit behad me | Closed | 1498829.43 | 0 | 2023-01-24
ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001076/WC/22012035091215 — band nirman - behad khadet | Closed | 0 | 0 | 2023-04-14
ATER | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001076/WH/19955487 — Desilting of talab | Deleted | 0 | 0 | 2016-01-26
ATER | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001076/WH/19956641 — Deepning of tank | Completed | 100000 | 45424 | 2016-05-30 | 2016-06-30
ATER | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001076/WH/19956764 — Talab Gahrikaran- Khand bala talab | Deleted | 0 | 0 | 2016-04-25
ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001076/WH/19961498 — Renovation Of Pond- Khad Bala Talab, Khadeet | Completed | 99000 | 50912 | 2017-05-22 | 2019-08-25
ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001076/WH/22012034450241 — talab jiroddar - khadit ( sheetala ka tal kahdit ) | Completed | 804753.06 | 294015 | 2022-01-26 | 2026-04-12
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001076/WH/22012034455929 — Talab jeerodhar - khadeet behad | Completed | 48358.31 | 41769 | 2022-11-23 | 2024-11-04
ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001076/WH/22012034455931 — Talab jeerodhar - khadeet | Completed | 49737.08 | 36040 | 2022-11-23 | 2024-11-04
ATER | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702/RC/22012034153090 — Gram Sampark Sadak Yojna | Completed | 812000 | 227890 | 2011-01-29 | 2015-03-30