## Work List
Exported on: 2026-10-18 04:05:35
Filters applied:
Data source: MGNREGA
District: BHIND
Block: All
Panchayat: MANPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Building for Gram Panchayats / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702002011/AV/22012034370554 — PANCHAYAT BHAVAN REPAIR MANPURA | Deleted | 0 | 0 | 2017-06-03
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002011/AV/22012034371018 — SHANTIDHAM NIRMAN MANPURA | Completed | 245000 | 240046.28 | 2017-12-29 | 2018-02-25
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002011/AV/22012034567338 — MUKTIDHAM ME CHABUTRA NIRMAN AND TEEN SHED | Closed | 287491.74 | 0 | 2021-04-14
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/100 — निर्मल वाटिका कार्य अमित / रामचन्‍द्र | Completed | 0 | 3591 | 2011-09-24 | 2011-12-28
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/101 — निर्मल वाटिका कार्य मातादीन / मिजाजी | Completed | 0 | 3591 | 2011-09-24 | 2011-12-28
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/102 — निर्मल वाटिका कार्य मुनेन्‍द्र / मंगल | Completed | 0 | 3591 | 2011-09-24 | 2012-01-04
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/103 — निर्मल वाटिका कार्य नरेश / अजुद्वी | Completed | 0 | 3591 | 2011-09-24 | 2011-12-28
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/104 — निर्मल वाटिका कार्य छोटेलाल / दुजू | Completed | 0 | 3591 | 2011-09-24 | 2011-12-21
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1702002011/DP/22012034601888 — वसुधा वंदन - अमृत वाटिका कार्य शांतिधाम मानपुरा | Closed | 0 | 0 | 2023-08-01
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/85 — निर्मल वाटिका कार्य रामचरन / बच्‍छीलाल | Completed | 0 | 3686 | 2011-09-24 | 2012-01-04
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/86 — निर्मल वाटिका कार्य सूधरी / लाखन | Completed | 0 | 3591 | 2011-09-24 | 2012-01-04
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/87 — निर्मल वाटिका कार्य रामचरन / सुल्‍तान | Completed | 0 | 3591 | 2011-09-24 | 2011-12-28
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/88 — निर्मल वाटिका कार्य सुखराम / बुन्‍डन | Completed | 0 | 1398 | 2011-09-24 | 2011-12-21
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/89 — निर्मल वाटिका कार्य श्रीक्रष्‍ण / भजनलाल | Completed | 0 | 1398 | 2011-09-24 | 2011-12-21
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/90 — निर्मल वाटिका कार्य अमर सिंह / रतिभान | Completed | 0 | 3591 | 2011-09-24 | 2011-12-28
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/91 — निर्मल वाटिका कार्य रामचरन/ घमण्‍डी | Completed | 0 | 3591 | 2011-09-24 | 2011-12-28
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/92 — निर्मल वाटिका कार्य गिरेन्‍द्र / भजनलाल | Completed | 0 | 1398 | 2011-09-24 | 2011-12-21
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/93 — निर्मल वाटिका कार्य काशीप्रसाद / श्रीराम | Completed | 0 | 3591 | 2011-09-24 | 2012-01-04
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/94 — निर्मल वाटिका कार्य नाथू / जोहरी | Completed | 0 | 1398 | 2011-09-24 | 2011-12-28
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/95 — निर्मल वाटिका कार्य मोहनमन / सरमन | Completed | 0 | 1398 | 2011-09-24 | 2011-12-28
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/96 — निर्मल वाटिका कार्य कीरत / श्रीराम | Completed | 0 | 3591 | 2011-09-04 | 2011-12-21
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/97 — निर्मल वाटिका कार्य सतेन्‍द्र / तेहसीलदार | Completed | 0 | 3591 | 2011-09-24 | 2011-12-21
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/98 — निर्मल वाटिका कार्य जगदीश / झुण्‍डन | Completed | 0 | 3591 | 2011-09-24 | 2012-01-04
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/99 — निर्मल वाटिका कार्य अशोक / ग्‍याराम | Completed | 0 | 3591 | 2011-09-24 | 2011-12-21
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702002011/FP/22012034363601 — NALI NIRMAN SCHOOL WALW TALAB KE PASS SE PANCHAYAT BHAVAN KI OR | Completed | 172000 | 52800 | 2019-09-21 | 2020-07-23
BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002011/FP/22012034637623 — NALA NIRMAN NATHU SINGH NARWARIYA KE MAKAN SE KEDAR NARWARIYA KI OR | Ongoing | 90000 | 33662 | 2024-02-09
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002011/IF/22012034338528 — NADEP TANKA RAJENDRA SINGH NARWARIYA S/O JAGMOHAN | Completed | 118000 | 3096 | 2017-05-12 | 2017-06-15
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002011/IF/22012034352218 — BRAKSHAROPAN KARYA MUKTIDHAM MANPURA | Completed | 335000 | 41104 | 2017-06-23 | 2017-12-17
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002011/IF/22012034353572 — BRAKSHA ROPAN KARYA MAIN ROAD SE SHANTIDHAM KI OR SADAK KINARE | Closed | 0 | 0 | 2017-04-19
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002011/IF/22012034566084 — SOKHTA GADDA SHRISINGH KE GHAR KE PASS | Ongoing | 14283.77 | 3420 | 2020-10-29
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002011/IF/22012034566085 — SOKHTA GADDA ARVINDRA SINGH KE GHAR KE PASS | Ongoing | 14283.77 | 3420 | 2020-11-17
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002011/IF/22012034575122 — Med bandhan vishambhar singh/hom singh | Closed | 0 | 0 | 2020-06-14
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002011/IF/22012034576775 — soak pit nirman subhash singh / bacchu singh | Closed | 14467.3 | 0 | 2020-04-14
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002011/IF/22012034576776 — soak pit nirman brajendra singh / hameer singh | Closed | 0 | 0 | 2020-04-14
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002011/IF/22012034576777 — soak pit nirman shivnath singh /bachhu singh | Closed | 0 | 0 | 2020-04-14
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002011/IF/22012034576778 — soak pit nirman neelu devi | Closed | 0 | 0 | 2020-04-14
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002011/IF/22012034576779 — soak pit nirman rajveer singh / hom singh | Closed | 0 | 0 | 2020-04-14
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002011/IF/22012034576780 — soak pit nirman satendra singh / tehsidar singh | Closed | 0 | 0 | 2020-04-14
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002011/IF/22012034576781 — soak pit nirman rdha moahan sharma | Closed | 0 | 0 | 2020-04-14
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002011/IF/22012034576782 — soak pit nirman lalveer singh | Closed | 0 | 0 | 2020-04-14
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002011/IF/22012034576783 — soak pit nirman ummed singh | Closed | 0 | 0 | 2020-04-14
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002011/IF/22012034576784 — soak pit nirman hameer singh | Closed | 0 | 0 | 2020-04-14
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002011/IF/22012034576785 — soak pit nirman ram singh | Closed | 0 | 0 | 2020-04-14
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002011/IF/22012034595495 — सोकता गढ्डा तेज सिंह के घर पर | Closed | 0 | 0 | 2020-04-14
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002011/IF/22012034596640 — sokta gadda veeru singh ke ghar me | Closed | 0 | 0 | 2020-04-14
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002011/IF/22012034596642 — sokta gadda rakesh singh chouhan ke ghar me | Closed | 0 | 0 | 2020-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002011/IF/22012034783004 — MED BANDHAN NIRMAN SHYAMBIHARI SHARMA KHET PAR | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002011/IF/22012034783013 — MED BANDHAN NIRMAN RAJENDRA NARVARIYA KHET PAR | Closed | 0 | 0 | 2021-04-14
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002011/IF/22012034980635 — INDIVIDUAL SOAK PIT LAL SINGH / AMRAT SINGH | Completed | 1100 | 1020 | 2022-09-05 | 2022-11-22
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002011/IF/22012034980638 — INDIVIDUAL SOAK PIT DHARMENDRA / RANJEET SINGH | Completed | 1100 | 1020 | 2022-05-25 | 2024-11-07
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002011/IF/22012035594006 — EK BAGIYA MAA KE NAAM SAVITA DEVI / INDAL SINGH | Ongoing | 271705.51 | 0 | 2026-01-09
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002011/IF/22012035594012 — EK BAGIYA MAA KE NAAM SUNITA DEVI / JANVED SINGH | Ongoing | 271705.51 | 1566 | 2025-09-12
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation(Coast) - horti-trees (Individuals) / Along the coast Line Plantation of Horticulture Trees for Individuals | Plantation | 1702002011/IF/22012035594015 — EK BAGIYA MAA KE NAAM SAVITA DEVI / INDAL SINGH | Deleted | 0 | 0 | 2025-08-01
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Block Plantation of Biodrainage Trees in Fields for Individuals | Plantation | 1702002011/IF/22012035627044 — Ek bagiya ma ke naam Seema ke khet par | Deleted | 0 | 0 | 2025-09-11
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Block Plantation of Biodrainage Trees in Fields for Individuals | Plantation | 1702002011/IF/22012035627048 — Ek bagiya ma ke naam sivmati ke khet par | Deleted | 0 | 0 | 2025-09-11
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002011/IF/22012035627116 — EK BAGIYA MAA KE NAAM SHIVMATI/RAJU TOMARR | Ongoing | 187841.53 | 0 | 2026-01-09
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002011/IF/22012035627117 — EK BAGIYA MAA KE NAAM SEEMA DEVI / RAJENDRA SINGH | Ongoing | 187580.39 | 1566 | 2025-12-28
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002011/IF/22012035636608 — EK BAGIYA MAA KE NAAM MANISHA DEVI / CHHATRAPAL SINGH | Ongoing | 266578.64 | 3132 | 2025-12-17
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002011/IF/22012035636614 — EK BAGIYA MAA KE NAAM POONAM DEVI / MUNENDRA SINGH | Ongoing | 266578.64 | 3132 | 2025-12-17
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002011/IF/22012035643257 — EK BAGIYA MAA KE NAAM POOJA DEVI / SUNEEL | Approved | 266578.64 | 0 | 2025-10-02
BHIND | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9926744313 — CATTLE SHED KAMLESH SHARMA / SHYAM BIHARI SHARAMA | Deleted | 88302 | 0 | 2014-04-14
BHIND | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9926744314 — CATTLE SHED RADHAMOHAN SHARMA / SHYAM BIHARI SHARMA | Deleted | 88302 | 0 | 2014-04-14
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993673420 — pashu shed keshav singh s/o jaychandra singh | Completed | 115900 | 98251 | 2015-09-04 | 2016-02-15
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993674300 — pashu shed suresh singh s/o indal singh | Completed | 115900 | 90937 | 2015-09-11 | 2016-02-20
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993680545 — CATTLE SHED DHEER SINGH/ GYA SINGH | Completed | 115900 | 96161 | 2015-10-16 | 2016-02-15
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993680548 — CATTLE SHED LALVEER SINGH/ MALKHAN SINGH | Completed | 115900 | 97981 | 2015-10-16 | 2017-03-30
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993680549 — CATTLE SHED UMMED SINGH/ GYAN SINGH | Completed | 115900 | 99483.25 | 2015-10-16 | 2017-03-30
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993700555 — Pashu shed shyambihari s/o ramnath sharma | Closed | 115900 | 0 | 2015-04-14
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993700775 — Pashu shed Rakesh s/o Keshav singh | Closed | 116000 | 0 | 2015-12-28
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993700776 — Pashu Shed Rajveer singh S/o Homsingh | Completed | 116000 | 3816 | 2016-01-01 | 2016-04-20
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993700777 — Pashu Shed Sumendra Singh S/o Sughar Singh | Completed | 116000 | 3816 | 2016-01-01 | 2016-08-15
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993700778 — Pashu Shed Shivraj Singh S/o Jaymangal singh | Closed | 116000 | 0 | 2015-12-28
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993701123 — Pashu Shed Jaymangal singh S/o Kanchan Singh | Completed | 116000 | 6678 | 2016-01-01 | 2016-04-15
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993701160 — Pashu shed Bhageerath singh S/O Balwant Singh | Closed | 115900 | 0 | 2015-12-29
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993701166 — Pashu Shed Shivnath Singh S/O Bachchu Singh | Completed | 116000 | 3816 | 2016-01-08 | 2016-04-15
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993701168 — Pashu Shed Ratan singh S/o Mathura Singh | Closed | 115900 | 0 | 2015-04-14
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993701188 — Pashu Shed Radhamohan Sharma S/o Shyam Bihari Sharma | Completed | 116000 | 3816 | 2016-01-01 | 2016-08-20
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993701190 — Pashu Shed Harendra Singh S/o Dev Singh Narwariya | Completed | 115900 | 6678 | 2016-01-01 | 2016-04-15
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993701194 — Pashu Shed Udey Singh S/o Rambabu Singh | Closed | 115900 | 0 | 2015-12-29
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993701196 — Pashu Shed Sardar Singh S/o Sultan Singh | Completed | 116000 | 5724 | 2016-01-01 | 2016-04-15
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993701199 — Pashu Shed Nathu Singh S/o Ajab Singh | Closed | 115900 | 0 | 2015-04-14
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993729548 — pashu shed badan singh s/o ratan singh | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993729555 — PASHU SHED BADAN SINGH S/O RATAN SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993729556 — PASHU SHED ARJUN SINGH S/O RAMPRASAD SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993729557 — PASHU SHED RAMESH SINGH S/O HOM SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993729558 — PASHU SHED RAMGOPAL SHARMA S/O SHYAM BIHARI SHARMA | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993729559 — PASHU SHED DHARMENDRA SINGH S/O RANJEET SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993729560 — PASHU SHED BISHAMBHAR SINGH S/O HOME SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993729561 — PASHU SHED RAJARAM JATAV | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993729562 — PASHU SHED RAKESH JATAV | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993729564 — PASHU SHED KAMLESH SHARMA S/O SHYAM BIHARI SHARMA | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993729566 — PASHU SHED HARISHCHANDRA S/O RATIBHAN | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993729568 — PASHU SHED RAMCHANDRA SINGH S/O AMOL SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993729572 — PASHU SHED DASHRATH SINGH S/O KOMAL SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993729573 — PASHU SHED RATAN SINGH S/O MATHURA SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993729575 — PASHU SED NAHAR SINGH S/O SHANKAR SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993729583 — PASHU SHED PHERAN SINGH S/O MATHURA SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993729584 — PASHU SHED MUNNI SINGH KE GHAR PER | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993729586 — PASHU SHED RAMPRKASH S/O RAMCHARAN | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993730299 — PASHU SHED RAMBHAROSE D/O MULU SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993730302 — PASHU SHED HARPAL SINGH S/O KUNDAN SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993730304 — PASHU SHED ATAR SINGH S/O KUAR SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993730306 — PASHU SHED PUTTU SINGH S/O GENDA SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993730307 — PASHU SHED JALDAN SINGH S/O HUKUM SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993730308 — PASHU SHED BAHADUR SINGH S/O PANCHAM SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993730309 — PASHU SHED JAYSHRI RAM S/O HAJURI SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993730310 — PASHU SHED GAJENDRA SINGH S/O HOM SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993730311 — PASHU SHED HAMEER SINGH S/O GYA SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993730312 — PASHU SHED SHRIRAM S/O GENDALAL | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993730313 — PASHU SHED GIRENDRA SINGH S/O BHAJAN SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993730314 — PASHU SHED JANVED SINGH S/O SHANKAR SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993730315 — PASHU SHED SHANTOSH S/O NATHU RAM | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993730318 — PASHU SHED RAJENDRA SINGH S/O RAMPRASAD | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993730319 — PASHU SHED BRAJRAJ S/O JAYMANGAL SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993730320 — PASHU SHED ARUN KUMAR S/O RANVEER SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993730321 — PASHU SHED SHIVNATH S/O PATIRAM | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993730322 — PASHU SHED BETAL SINGH KE GHAR PER | Closed | 0 | 0 | 2016-01-26
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002011/IF/IAY/3794632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103127416 | Approved | 23490 | 0 | 2022-05-04
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002011/IF/IAY/4326052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121345976 | Completed | 18360 | 18343 | 2022-08-10 | 2023-06-17
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002011/IF/IAY/4371361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142076179 | Completed | 18360 | 17136 | 2022-11-24 | 2023-09-06
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002011/IF/IAY/4375933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105421540 | Physically Completed | 18360 | 16711 | 2023-02-11 | 2024-11-21
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002011/IF/IAY/4384321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117870938 | Completed | 18360 | 17340 | 2022-12-15 | 2023-09-06
BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002011/LD/104 — मेढबन्‍धान कीरत / श्रीराम | Completed | 0 | 10596 | 2010-05-07 | 2010-05-07
BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002011/LD/105 — मेढबन्‍धान अशोक / रामसहाय | Completed | 0 | 3500 | 2010-08-18 | 2010-08-18
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002011/LD/22012034268550 — Medbandhan pooran singh s/o sarnam singh | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002011/LD/22012034268551 — Medbandhan jaychandra singh s/o korelal | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002011/LD/22012034268552 — Medbandhan bishambhar s/o hom singh | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002011/LD/22012034268553 — Medbandhan amrat singh s/o ramchandra | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002011/LD/22012034268554 — Medbandhan gajendra singh s/o bhaver singh | Deleted | 0 | 0 | 2016-01-26
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002011/LD/22012034518339 — मेडवांधन राजवीर सिंह के खेत में | Closed | 27816.84 | 0 | 2020-06-23
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002011/LD/22012034518480 — MED BANDHAN UMMED SINGH BAGHEL KE KHET PAR | Closed | 31154.86 | 0 | 2020-04-14
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002011/LD/22012034518481 — MED BANDHAN RAJVEER SINGH KHET PAR | Closed | 0 | 0 | 2020-04-14
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002011/LD/22012034518482 — MED BANDHAN DEVENDRA SINGH KHET PAR | Closed | 22253.47 | 0 | 2020-04-14
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002011/LD/3799395453 — MADBANDHAN RAJARAM / RAMSAHAY KE KHET MEIN | Completed | 18900 | 9782 | 2013-06-14 | 2013-07-20
BHIND | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002011/LD/9926709949 — MAD BANDHAN SURESH SINGH BHADOURIYA KE KHET PAR | Completed | 43300 | 30144 | 2014-06-27 | 2016-01-20
BHIND | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002011/LD/9926709950 — MAD BANDHAN DHEER SINGH CHAUHAN KE KHET ME | Completed | 43300 | 28260 | 2014-06-20 | 2016-01-20
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002011/OP/9425890333 — SANTIDHAM MARMMAT | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002011/OP/9425890334 — PANCHAYAT BHAVAN KI MARAMMAT | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002011/OP/9425890335 — brachharopan karya santidham me | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Production of building material / Production of building material for Community | Construction of Other Community Building/Assets | 1702002011/OP/9425890336 — E - kakch panchayat bhavan | Deleted | 0 | 0 | 2016-01-26
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002011/PG/22012034365790 — PLAY GROUND | Deleted | 0 | 0 | 2017-10-02
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002011/PG/22012034366341 — play ground | Closed | 0 | 0 | 2017-10-02
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034194860 — C.C.ROAD PURAN SINGH KE MAKAN SE BHOJRAJ KE MAKAN | Completed | 71268 | 68164 | 2013-12-20 | 2014-04-05
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034196532 — C.C.ROAD RAMBIHARI KE MAKAN SE HARIVILAS KE MAKAN | Completed | 85522 | 80896 | 2014-01-10 | 2014-05-20
BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034219112 — C.C.RAOD BHOJRAJ KE MAKAN SE NAHAR SINGH KE MAKAN | Completed | 49545 | 49283 | 2014-05-30 | 2015-06-05
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002011/RC/22012034292430 — KHET SADAK YOJANA MAIN ROAD SE RAJENDRA KE GHAR TAK | Completed | 817867 | 59148 | 2016-01-08 | 2016-08-15
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034309620 — CC ROAD PETROL PUMP SE BHEEKAM SINGH KE MAKAN KI AUR | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034309621 — C C ROAD MAN SINGH KE MAKAN SE BALVEER KE MAKAN KI AUR | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034309622 — CC ROAD RAJARAM KE MAKAN SE BETAL SINGH KE MAKAN KI AUR | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034309623 — CC ROAD GANGARAM KUSHWAH KE MAKAN SE VETAL KE MAKAN KI AUR | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034309624 — CC ROAD DEEPCHANDRA DUBE KE MAKAN SE INDRAJEET DOHARE KE MAKAN KI AUR | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034309625 — CC ROAD MEN ROAD SE BALMEEK KE GHAR KI AUR | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002011/RC/22012034309626 — mitti bajri karan bhojraj singh ke makan se muktidham ki aur | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002011/RC/22012034309627 — mitti bajri karna chatthar wali road se gaon ki aur | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034309628 — cc road muktidham se main road ki aur | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034309939 — CC ROAD NARESH PRJAPATI KE MAKAN KI AUR | Deleted | 0 | 0 | 2016-01-26
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034365826 — CC ROADASHOK GHAR SE SATENDRA GHAR TAK | Completed | 5700000000 | 59856 | 2017-11-03 | 2018-01-13
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034382735 — CC ROD SAROJ JOSHI GHAR SE SURESH GHAR TAK | Completed | 93000 | 92988 | 2018-02-23 | 2019-04-19
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034389598 — CC ROAD MEN ROAD SE BALMIK GHAR KI AUR | Completed | 93000 | 90828 | 2018-05-25 | 2018-12-29
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034432546 — cc rod prathmik shala manpura | Completed | 59000 | 59856 | 2018-12-18 | 2019-04-08
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034442727 — cc road | Deleted | 0 | 0 | 2019-01-26
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034477438 — CC ROAD MAIN ROAD SE MUKTIDHAM KI OR | Ongoing | 142000 | 3168 | 2019-09-21
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002011/RC/22012034477445 — GRAVAL ROAD MANPURA SE JAMNA KI OR | Deleted | 0 | 0 | 2019-08-15
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002011/RC/22012034477446 — GRAVAL ROAD SHIVSINGH KE GHAR SE MARGHATI TAK | Deleted | 0 | 0 | 2019-08-15
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002011/RC/22012034477447 — GRAVAL ROAD CHARTHAR MODE SE MANPURA KI OR | Deleted | 0 | 0 | 2019-08-15
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002011/RC/22012034477448 — GRAVAL ROAD GAMBHEER KE GHAR SE ANTAR SINGH KE GHAR KI OR | Deleted | 0 | 0 | 2019-08-15
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034521488 — C C ROAD GOOLU RAJAWAT WALI GALI SAMEER NAAR MANPURA | Closed | 58000 | 0 | 2020-01-26
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034521949 — C C ROAD MANOJ SHARMA KE GHAR SE KULDEEP RAJAWAT KE GHAR KI AUR | Completed | 100000 | 88086 | 2020-05-25 | 2022-11-22
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002011/RC/22012034532897 — SUDOOR GRAM SAMPARK SADAK SAMEER NAGAR WALI SADAK SE RAGHUNATH PURA KI OR | Closed | 0 | 0 | 2020-01-26
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002011/RC/22012034533213 — sudor sampark sadak sameer nagar bali road se raghunath pura ki or | Closed | 0 | 0 | 2020-04-14
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002011/RC/22012034558697 — GRAVAL ROAD HET SINGH KE MAKAN SE LAVKUSH E MAKAN KI OR | Closed | 0 | 0 | 2021-01-26
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034566805 — c.c.road nirman rathor mohalla me manpura | Completed | 81900 | 63690 | 2021-04-29 | 2022-11-22
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034608988 — CC ROAD SANJU KE MAKAN SE SITAMBER KE GHAR TAK SAMEER NAGAR | Completed | 17000 | 12240 | 2022-04-22 | 2022-11-22
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034608989 — CC ROAD SHANTIDHAM ME MANPURA | Completed | 32000 | 33048 | 2022-06-03 | 2022-11-22
BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034672297 — CC ROAD NIRMAN JAL SINGH NARWARIYA KE MAKAN SE HARGOVIND BALMIK KE MAKAN TAK | Closed | 34000 | 0 | 2023-10-02
BHIND | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/45 — सी0सी0 रोड निर्माण बैजन्‍ती के मकान से रामबिहारी के मकान तक | Completed | 293308 | 72629 | 2012-03-22 | 2012-10-04
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002011/RS/22012034240109 — MARYADA ABHIYAN SHIVRAJ SINGH /JAIMANGAL SINGH | Deleted | 5400 | 0 | 2013-04-14
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002011/RS/22012034240113 — MARYADA ABIYAN BRIJRAJ SINGH / JAI MANGAL SINGH | Deleted | 5400 | 0 | 2013-04-14
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702002011/RS/22012034503067 — Samudayak Swachhta Toilatr Work Manpura | Completed | 43000 | 41184 | 2020-12-17 | 2022-11-22
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002011/RS/22012034525048 — SEGREGATION SHED NIRMAN MANPURA | Completed | 37000 | 27792 | 2021-06-17 | 2022-11-22
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002011/RS/22012034539845 — samudayik soak pit nirman manpura | Closed | 6600 | 0 | 2021-07-10
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002011/RS/22012034541062 — samudayak soak pit nirman panchayat bhavan ke pas | Closed | 6600 | 0 | 2021-07-15
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002011/RS/22012034541509 — Samudayak soak pit baba ke kuya ke men rod ke hedpamp ke pas | Closed | 6600 | 0 | 2021-07-16
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002011/RS/22012034541512 — Samudayak soak pit rambharoshe ke hedpamp ke pas | Closed | 6600 | 0 | 2021-07-16
BHIND | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002011/RS/22012035137622 — nadep gajendra singh s/o bhavar singh ke ghar ke pass | Approved | 2400 | 0 | 2025-04-14
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | Upgradation/extension of Panchayat Bhawan / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002011/SK/9993649491 — Bharat Nirman Rajeev Gandhi Sewa Kendra,MANPURA | Completed | 200000 | 60888 | 2018-01-05 | 2018-02-15
BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002011/WC/21 — सौकपिट निर्माण कार्य रामवरन नाई के हैण्‍डपम्‍प के पास | Completed | 14950 | 14565 | 2009-07-25 | 2009-07-25
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702002011/WC/22012034293660 — TALAB GAHRIKANARN MANPURA | Deleted | 72000 | 0 | 2016-05-20
BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002011/WC/22012034325349 — TALAB MARAMMAT KARYA HAR KA LAT | Completed | 51000 | 16512 | 2017-05-19 | 2017-07-06
BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Block Plantation-Horticulture-Community / Along the coast Block Plantation of Horticulture Trees for Community | Plantation | 1702002011/WC/22012034431601 — talab gahri karan manpura renovations | Closed | 0 | 0 | 2018-04-14
BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002011/WC/22012034431994 — talab gahri karan manpura renovations | Closed | 0 | 0 | 2018-04-14
BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002011/WC/22012034444215 — NAVEEN TALAB TARI KA PURA | Completed | 1068000 | 427680 | 2019-03-06 | 2019-12-23
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002011/WC/22012034701178 — Water harvesting tank samudayik shauchalay ke pas | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002011/WC/22012034701182 — Water harvesting tank tehasidar ke kuaa ke samne main road | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002011/WC/22012034701185 — Water harvesting tank rajveer ke pas | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002011/WC/22012034701188 — Water harvesting tank rambharose ke pas | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002011/WC/22012034701189 — Water harvesting tank hanuman ji mandir ke pas | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002011/WC/22012034701191 — Water harvesting tank rajaram ke pas | Closed | 0 | 0 | 2021-04-14
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702002011/WC/22012034965771 — TALAB JIRDODDHAR DHRUVGAD TALAB MANPURA | Closed | 0 | 0 | 2022-04-14
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002011/WC/22012034965777 — TALAB JIRDODDHAR MARGHATI TALAB MANPURA | Closed | 0 | 0 | 2022-04-14
BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002011/WH/22012034389752 — talab gahri karan manpura renovations | Closed | 0 | 0 | 2018-04-14
BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002011/WH/22012034389753 — talab gahri karan manpura renovations | Closed | 0 | 0 | 2018-04-14
BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002011/WH/22012034389754 — talab gahri karan manpura renovations | Closed | 0 | 0 | 2018-04-14
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002011/WH/22012034934661 — talav jinudhar dhongada bala talav manpura | Completed | 42500 | 34272 | 2022-05-26 | 2024-08-01
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002011/WH/22012034934669 — TALAB JIRDODDHAR MARGHATI KA TALAB MANPURA | Completed | 42500 | 27234 | 2022-05-26 | 2025-05-13