## Work List
Exported on: 2026-09-05 02:04:28
Filters applied:
Data source: MGNREGA + VBGRAMG
District: BHIND
Block: All
Panchayat: KHARDARGAUGHAT
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002014/AV/22012034369322 — SHANTIDHAM NIRMAN LAXMIPURA | Completed | 180000 | 178403.83 | 2017-10-31 | 2018-01-22
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702002014/AV/22012034563875 — BOUNDARY WALL NIRMAN PS SCHOOL REMJAKAPURA | Ongoing | 73000 | 13896 | 2021-05-14
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702002014/AV/22012034563876 — BOUNDARY WALL NIRMAN PS/MS SCHOOL KUMHARAUWA | Ongoing | 73000 | 5211 | 2021-11-29
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002014/AV/3959 — Anganwadi/Other Rural Infrastructure,KHARDARGAUGHAT | Completed | 330000 | 329184 | 2015-11-17 | 2018-01-15
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002014/AV/4276 — Anganwadi/Other Rural Infrastructure,KHARDARGAUGHAT | Completed | 330000 | 328748 | 2016-01-05 | 2017-12-30
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002014/AV/4283 — Anganwadi/Other Rural Infrastructure,KHARDARGAUGHAT | Completed | 330000 | 329664.4 | 2016-01-05 | 2020-09-09
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1702002014/DP/22012034548310 — MAA KI BAGIYA NIRMAN ANGANWADI KUMHARAUAA | Closed | 9000 | 0 | 2022-01-24
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1702002014/DP/22012034548311 — MAA KI BAGIYA NIRMAN PS REMJAPURA | Closed | 9000 | 0 | 2022-01-24
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1702002014/DP/22012034596021 — बृक्षारोपण कार्य बसुधा बंदन - अमृत वाटिका शासकीय प्राथ /माध्य. विद्यालय कुम्हरौआ | Closed | 55847.4 | 0 | 2023-08-10
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002014/FP/22012034624026 — NALA NIRMAN ROAD KE KINARE PAKKE NALE SE PURANI RAILWAY LAINE KI OR | Ongoing | 33000 | 22581 | 2021-11-12
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002014/FP/22012034629574 — KACHCHA NALA NIRMAN KAMAL SINGH KE GHAR SE KUSUMAR KI PULIYA TAK | Closed | 111291.23 | 0 | 2022-08-15
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002014/FP/22012034629636 — KACHCHA NALA NIRMAN KHADARGAUGHAT CHAURAH SE REMJAPURA KI OR KHADARGAUGHAT | Physically Completed | 108622.95 | 83776 | 2022-12-08 | 2026-04-17
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002014/IF/22012034352353 — BRAKSHA ROPAN KARYA SADAK KE KINARE KHDARGAUGHAT ROAD | Completed | 335000 | 4032 | 2017-06-20 | 2021-11-23
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002014/IF/22012034354222 — BRAKSHA ROPAN KARYA SHANTIDHAM KHADARGAUGHAT | Completed | 335000 | 6784 | 2017-07-04 | 2021-11-23
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002014/IF/22012034358092 — BRAKSHA ROPAN KARYA SADAK KINARE LAXMIPURA SE KHADARGAUGHAT TAK | Deleted | 335000 | 0 | 2017-07-04
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002014/IF/22012034358097 — BRAKSHA ROPAN KARYA SHANTIDHAM OR SCHOOL PARISHAR ME | Completed | 335000 | 3096 | 2017-08-29 | 2021-11-23
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002014/IF/22012034358099 — BRAKSHA ROPAN KARYA MATHIPURA SADAK SE KHADARGAUGHAT SADAK KINARE | Completed | 335000 | 6440 | 2017-07-25 | 2021-11-23
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002014/IF/22012034358100 — BRAKSHA ROPAN KARYA MATHIPURA MANDIR ME | Completed | 335000 | 33364 | 2017-07-25 | 2021-11-23
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002014/IF/22012034358101 — BRAKSHA ROPAN KARYA KUMHARAUA SCHOOL OR REMJAPURA SCHOOL ME | Completed | 335000 | 7472 | 2017-07-25 | 2021-11-23
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002014/IF/22012034358103 — BRAKSHA ROPAN KARYA KUMAHARAUA SE LAXMIPURA SADAK KINARE | Deleted | 0 | 0 | 2017-07-25
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002014/IF/22012034371533 — BRAKSHA ROPAN KARYA KUMHRAUA ROAD KINARE CALONI KHEL MEDAAN | Completed | 335000 | 2064 | 2017-08-29 | 2021-11-23
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702002014/IF/22012034606131 — श्री हरेंद्र सिंह पुत्र शिवलाल सिंह के निजी खेत मे फलो उद्यान रोपण कार्य | Ongoing | 141000 | 48642 | 2021-01-28
BHIND | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002014/IF/22012034606182 — श्री जडेल सिंह पुत्र बुद्ध सिंह के निजी खेत पर फलो उद्यान रोपण कार्य | Closed | 141000 | 0 | 2020-01-29
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002014/IF/22012034762644 — MED BANDHAN HARENDRA SINGH / SHIVLAL KE KHET PER | Closed | 30681.29 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002014/IF/22012034768758 — MED BANDHAN RAMVARAN SINGH / PHULAN SINGH KE KHET PER | Closed | 30681.29 | 0 | 2021-04-14
BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002014/IF/22012034787226 — MED BANDHAN SHIV SINGH / BHAVAR SINGH KE KHET PER | Closed | 30681.29 | 0 | 2021-04-14
BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002014/IF/22012034809447 — MED BANDHAN RAMPRAKASH SINGH PUTRA NIHAL SINGH KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002014/IF/22012034809453 — MED BANDHAN HARI SINGH / NIHAL SINGH KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002014/IF/22012034809455 — MED BANDHAN MAHESHWARI /NIHAL SINGH KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002014/IF/22012034809458 — MED BANDHAN KAMLESH / PREETAM KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002014/IF/22012034809460 — MED BANDHAN UPENDRA SINGH / PREETAM KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002014/IF/22012034809466 — MED BANDHAN ANIL SINGH / PREETAM KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002014/IF/22012034809469 — MED BANDHAN HARVEER SINGH /PYARELAL KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002014/IF/22012034809471 — MED BANDHAN VEENESH / BRAJENDRA SINGH KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002014/IF/22012034809479 — MED BANDHAN RAMVEER / PYARELAL KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702002014/IF/22012035611133 — EK BAGIYA MAA KE NAAM ANITA DEVI / PRAHLAD SINGH | Approved | 0 | 0 | 2025-08-01
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702002014/IF/22012035611145 — EK BAGIYA MAA KE NAAM SHILPI DEVI | Ongoing | 266577.25 | 0 | 2025-12-30
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702002014/IF/22012035615972 — EK BAGIYA MAA KE NAAM KALAVATI / MUKESH | Ongoing | 188138.86 | 0 | 2025-12-30
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702002014/IF/22012035627176 — EK BAGIYA MAA KE NAAM LAKKHO KUMARI / KAMLESH | Approved | 0 | 0 | 2025-08-15
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002014/IF/9993698813 — CATTLE SHED RAJARAM S/O BHADOLE KHADARGAUGHAT | Completed | 116000 | 87294.2 | 2015-12-22 | 2016-12-20
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002014/IF/9993698816 — CATTLE SHED RAM SANEHI S% PRABHUDAYAL | Deleted | 115900 | 0 | 2015-04-14
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002014/IF/9993700157 — CATTLE SHED SEBARAM S%RAMDYAL | Deleted | 115900 | 0 | 2015-09-14
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002014/IF/9993701040 — CATTLE SHED BABURAM/CHOTELAL | Deleted | 115900 | 0 | 2015-12-22
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002014/IF/9993701041 — CATTLE SHED KESHAV SINGH/JAIRAM | Deleted | 115900 | 0 | 2015-12-22
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002014/IF/9993701043 — CATTLE SHED MANOJ/PHOOLAN SINGH | Deleted | 115900 | 0 | 2015-04-15
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002014/IF/9993701044 — CATTLE SHED HOTAM SINGH/NATHURAM | Deleted | 115900 | 0 | 2015-12-22
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002014/IF/9993701045 — CATTLE SHED DILEEP/SARMAN SINGH | Deleted | 115900 | 0 | 2015-12-22
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002014/IF/9993701046 — CATTLE SHED HARNARAYAN/JHARGAD | Closed | 115900 | 0 | 2015-12-22
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002014/IF/9993701047 — CATTLE SHED MAHESWARI/ NIHAL SINGH | Deleted | 115900 | 0 | 2015-04-15
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002014/IF/9993701048 — CATTLE SHED SUBHASH SINGH/MOHVAT SINGH | Completed | 116000 | 90590.2 | 2016-07-19 | 2016-12-20
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002014/IF/9993701049 — CATTLE SHED LAXMINARAYAN/FOJDAR | Completed | 116000 | 86916.2 | 2016-07-19 | 2016-08-01
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002014/IF/9993701050 — CATTLE SHED RAMESH SINGH/ BAHGWAN SINGH | Completed | 116000 | 88920.2 | 2016-07-19 | 2016-12-20
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002014/IF/9993701051 — CATTLE SHED RAJESH SINGH/ KOK SINGH YADAV | Deleted | 115900 | 0 | 2015-04-15
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002014/IF/9993701052 — CATTLE SHED RAMVARAN/ PHOOLAN SINGH | Deleted | 115900 | 0 | 2015-04-15
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002014/IF/9993701053 — CATTLE SHED HARVILAS/GOPIRAM | Deleted | 115900 | 0 | 2015-12-22
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002014/IF/9993728502 — pashu shed amrish s/o dinesh singh | Deleted | 0 | 0 | 2016-01-26
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002014/IF/IAY/133922 — Construction of IAY House -IAY REG. NO. MP-02-002-014-001/04 | Completed | 14310 | 15246 | 2016-08-01 | 2019-09-05
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002014/IF/IAY/133924 — Construction of IAY House -IAY REG. NO. MP-02-002-014-001/16 | Approved | 27000 | 0 | 2016-02-14
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002014/IF/IAY/133927 — Construction of IAY House -IAY REG. NO. MP-02-002-014-001/23 | Completed | 14310 | 15300 | 2016-08-01 | 2019-09-05
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002014/IF/IAY/3846900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128126707 | Physically Completed | 18360 | 9894 | 2022-12-31 | 2024-11-21
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002014/IF/IAY/4780699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128126206 | Ongoing | 27000 | 18009 | 2025-06-28
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002014/IF/IAY/5621430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145486849 | Ongoing | 27000 | 16938 | 2025-12-08
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002014/IF/IAY/5621470 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106816679 | Ongoing | 27000 | 15633 | 2025-08-28
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002014/IF/IAY/5681875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105662105 | Ongoing | 27000 | 1305 | 2025-09-22
BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002014/LD/116 — मेड बन्‍धान कार्य श्री बाबूराम / डरू | Completed | 0 | 9800 | 2010-07-26 | 2010-07-26
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002014/LD/22012034518527 — MED BANDHAN RAMNARAYAN BARETHA KE KHET PER | Completed | 25673.34 | 20520 | 2020-07-18 | 2020-08-29
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002014/LD/22012034543295 — MED BANDHAN NIRMAN SHIV SINGH / BHAVAR SINGH | Closed | 0 | 0 | 2021-01-26
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002014/LD/263 — मेड बन्‍धान कार्य रामचन्‍द्र / खूवी | Completed | 0 | 1952 | 2011-05-01 | 2011-05-07
BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002014/OP/9425891284 — SHANTIDHAM NIRMAN KHDARGAUKHAT | Completed | 180000 | 179411.83 | 2016-12-20 | 2018-01-31
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002014/PG/22012034365788 — PLAY GROUND | Deleted | 0 | 0 | 2017-10-02
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002014/PG/22012034366340 — play ground | Closed | 0 | 0 | 2017-10-02
BHIND | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002014/RC/14 — पंहुचमार्ग मुन्‍शी के कुंआ से पीपल की ओर | Completed | 385436 | 42700 | 2011-06-23 | 2011-08-08
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034158234 — c.c. road rambabu ke gaunda se ravindra sharma ke | Completed | 144600 | 94597 | 2013-02-09 | 2014-02-20
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034165957 — C.C.ROAD VIMAL KE MAKAN SE GULAB KE MAKAN TAK | Completed | 92923 | 63812 | 2013-12-17 | 2014-08-30
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034165961 — C.C.RAOD PURANI RAILWAY PATARI SE BALMIKI MOHALLA TAK | Deleted | 0 | 0 | 2012-08-15
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034165965 — C.C.ROAD PURANI RAILWAY SE BALMIKI MOHALLA TAK | Completed | 103900 | 62112 | 2014-02-25 | 2015-08-20
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034166822 — C.C.ROAD RAGHUVEER KE MAKAN SE SHIVNATH KE MAKAN T | Completed | 103900 | 90754.9 | 2013-10-29 | 2014-05-01
BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034222772 — C.C.ROAD BEEJASEN KE MANDIR SE HEERA SINGH KE MAKA | Completed | 124045 | 39230 | 2014-07-08 | 2016-01-10
BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034228037 — C.C.ROAD HARIRAM KE MAKAN SE JAGDISH KE MAKAN TAK | Completed | 110047 | 51806 | 2014-09-02 | 2016-02-05
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034283413 — C.C.ROAD KUNWA SE KALI MATA KE MANDIR TAK HEWATPURA | Completed | 152198 | 132980 | 2015-08-24 | 2015-11-09
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034285508 — CC ROAD SHRI CHANDRA KE MAKAN SE MENROAD TAK | Completed | 126832 | 109188 | 2015-09-29 | 2015-11-23
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034295082 — C.C.ROAD KEDAR KE MAKAN SE RAMVEER KE MAKAN TAK | Completed | 153386 | 124138 | 2016-01-05 | 2016-03-28
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034352455 — CC ROAD HARADRAM KE MAKN SE JASMANT KE MAKAN HOTE HUYE SHIVHARE KE MAKAN TAK | Completed | 119500 | 119196 | 2017-09-12 | 2018-03-10
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034352456 — CC ROAD MATA MANDIR SE CHINOTI SHRIVAS KE MAKAN TAK | Completed | 66400 | 66220 | 2017-09-12 | 2018-03-10
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034352458 — CC ROAD BRAJBUSHAN KE MAKAN SE MUNNI LAL SHRIVASH KE MAKAN TAK | Completed | 44300 | 44204 | 2017-09-05 | 2018-03-10
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034352459 — CC ROAD RAHUL SHARMA KE MAKAN SE MONU SENGAR KE MAKAN TAK | Completed | 44300 | 44204 | 2017-09-26 | 2018-03-10
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034361234 — CC ROAD SHIVHARE KE MAKAN SE MANSARAM BALMIK KE MAKAN TAK | Completed | 66400 | 66048 | 2017-09-26 | 2018-03-09
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034365732 — CC ROAD PURANI RAILWAY LINE SE RAMNARESH JATAV KE MAKAN TAK | Completed | 46500 | 44172 | 2017-10-31 | 2018-05-17
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034365736 — CC ROAD PURANI RAILWAY LINE SE BAGWANDAS JATAV KE MAKAN TAK | Completed | 53500 | 50766 | 2017-10-31 | 2018-04-27
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034365737 — CC ROAD MUKHYA MARG SE HAR PRASAD JATAV KE MAKAN HOTE HUYE MATA MANDIR TAK MATHIPURA | Completed | 56000 | 88356 | 2017-10-31 | 2018-07-25
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034391273 — CC ROAD MUKHYA MARG SE KALI MATA MANDIR TAK HEWADPURA | Completed | 56000 | 54984 | 2018-07-24 | 2018-10-20
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034392263 — CC ROAD HARVEER KE MAKAN SE MAHARAJ SINGH KE MAKAN HOTE HUYE SCHOOL TAK | Completed | 116000 | 60660 | 2019-03-05 | 2021-11-23
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034397377 — CC ROAD MUKHYA MARG SE DILIP SHAKYA KE MAKAN TAK | Completed | 51000 | 50336 | 2019-07-24 | 2019-09-05
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034442720 — cc road | Closed | 0 | 0 | 2019-01-26
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034463144 — CC ROAD GUNDHARI LAL JATAV KE MAKAN SE PANCHAYAT BHAVAN HOTE HUYE SHANTIDHAM TAK KHADARGAUGHAT | Completed | 112000 | 93104 | 2019-12-02 | 2020-03-24
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034507710 — CC ROAD MUKHYA MARG SE VIDHARAM YADAV TAK | Closed | 29000 | 0 | 2019-09-29
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034507712 — CC ROAD MUKHYA MARG SE HEERA SINGH PATEL TAK | Closed | 44000 | 0 | 2019-09-29
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034507713 — CC ROAD MUKHYA MARG SE PRIMARI SCHOOL HOTE HUYE KOMAL SINGH TAK MATHIPURA | Closed | 63000 | 0 | 2019-09-29
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034507714 — CC ROAD MAHAVEER PRASAD YADAV KE MAKAN SE BHAGVATI YADAV KE MAKAN TAK | Ongoing | 55000 | 46987 | 2019-12-09
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034550361 — Cc Road Mukhya Marg Se Usha Devi Rajawat Ke Makan Ki Or | Completed | 76000 | 58900 | 2020-12-03 | 2021-02-10
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034556750 — CC ROAD PURANI RAILWAY LINE SE SHRINIWAS JATAV TAK | Completed | 191000 | 111915 | 2021-01-27 | 2021-06-12
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/22012034614670 — CC ROAD NIRMAN MUKHYA MARG SE ARVIND BHADAURIYA KE MAKAN KI OR | Ongoing | 177000 | 73440 | 2022-05-25
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002014/RC/67 — सी0सी0 रोड निर्माण रामप्रकाश के मकान से आनंद के मक | Completed | 166184 | 95233.7 | 2012-04-02 | 2012-09-07
BHIND | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002014/RC/9 — पहुंचमार्ग लक्ष्‍मीपुरा से मुन्‍शी के कुंआ तक | Completed | 0 | 25010 | 2011-06-03 | 2011-06-23
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002014/RS/22012034649971 — Construction Of Nadep Nirman Purane Railway Line Ke Kinare | Closed | 5000 | 0 | 2022-03-15
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002014/RS/22012034649972 — Construction Of Nadep Nirman Jabar Singh Ki Road Ke Bagal Me | Closed | 5000 | 0 | 2022-03-25
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002014/RS/22012034650067 — Construction Of Community Soak Pit Bhagwandas Jatav Ke Makan Ke Pass | Closed | 6500 | 0 | 2022-03-25
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002014/RS/22012034650072 — Construction Of Community Soak Pit Murarilal Jatav Ke Makan Ke Pass | Ongoing | 6500 | 6528 | 2022-04-13
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002014/RS/22012034650074 — Construction Of Community Soak Pit Jagdeesh Jatav Ke Makan Ke Pass | Ongoing | 6500 | 6528 | 2022-04-29
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002014/RS/22012034650076 — Construction Of Soak Pit Nirman Sewaram Jatav Ke Makan Ke Pass | Closed | 6500 | 0 | 2022-03-21
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002014/RS/22012034667784 — CONSTRUCTION OFSAMUDAYAK SOKHTA HARIJATAV KE MAKAN KE PASS | Completed | 10000 | 8568 | 2022-11-04 | 2025-05-25
BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002014/RS/22012034667785 — CONSTRUCTION OF SAMUDAYAK SOKHTA RAMNARAYAN JATAV KE MAKAN KE PASS | Closed | 10000 | 0 | 2023-07-17
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002014/RS/22012034667786 — CONSTRUCTION OF SAMUDAYAK SOKHTA SATENDRA SINGH JATAV KE MAKAN KE PASS | Completed | 10000 | 7344 | 2022-11-14 | 2025-05-25
BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002014/RS/22012034667787 — CONSTRUCTION OF SAMUDAYAK SOKHTA PRADEEP KUMAR JATAV KE GHAR KE PASS | Closed | 10000 | 0 | 2023-07-17
BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002014/RS/22012034667788 — CONSTRUCTION OF SAMUDAYAK NADEP RAMNARAYAN JATAV KE MAKAN KE PASS | Closed | 2000 | 0 | 2023-07-08
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002014/RS/22012034667791 — CONSTRUCTION OF SAMUDAYAK NADEP PRADEEP SHAKYA KE MAKAN KE PASS | Closed | 2000 | 0 | 2022-09-19
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702002014/RS/22012034685945 — SAMUDYAK SWACHHATA PARISAR KHADARGAUGHAT | Closed | 43000 | 0 | 2023-01-04
BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002014/WC/22012034329263 — TALAB MARAMMAT KARYA KUMHARAUA | Suspended | 97000 | 0 | 2017-06-13
BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002014/WC/22012034329264 — TALAB MARAMMAT KARYA LAXMIPURA KE PASS | Deleted | 97000 | 0 | 2017-06-05
BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002014/WC/22012034329265 — TALAB MARAMMAT KARYA HEWADPURA GAO ME | Deleted | 98000 | 0 | 2017-04-19
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002014/WC/22012034761570 — TALAB GAHRIKARAN TILLE KE GHAR KE PASS | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002014/WC/22012034761574 — TALAB GAHRIKARAN PS SCHOOL LAXMIPURA | Closed | 0 | 0 | 2021-04-14
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1702002014/WC/22012035029268 — मरम्मत एवं सौंदर्यकरण लक्ष्मीपुरा स्कूल के पास | Closed | 0 | 0 | 2022-10-02
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002014/WC/22012035029271 — डग टैंक निर्माण कार्य लक्ष्मीपुरा | Closed | 0 | 0 | 2022-10-02
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002014/WC/22012035029272 — तालाब मरम्मत एवं सौंदर्यकरण रेमजापुरा | Closed | 0 | 0 | 2022-10-02
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1702002014/WC/22012035104586 — DUG TANK NIRMAN KARYA LAXMIPURA | Closed | 0 | 0 | 2023-08-15
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702002014/WC/22012035125953 — DUG TANG NIRMAN KARYA LAXMIPURA | Closed | 389523.17 | 0 | 2023-08-14
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002014/WC/22012035144392 — नवीन तालाव निर्माण राय सिंह के खेत के पास लक्समीपुरा | Ongoing | 898623.19 | 59007 | 2023-10-30
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002014/WH/22012034938190 — TALAB MARAMMAT KARYA GOVT PS/MS LAXMIPURA KE PASS | Ongoing | 390000 | 1326 | 2023-09-17