## Work List
Exported on: 2026-10-18 14:02:49
Filters applied:
Data source: MGNREGA
District: BHIND
Block: All
Panchayat: PARSONA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002019/AV/22012034509406 — Naveen Shantidham Nirmaan Karya Parsona | Completed | 194312.08 | 172272.75 | 2020-05-28 | 2020-08-15
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002019/DP/22012034595785 — वृक्षारोपण कार्य वसुधैव बंधन अमृत वाटिका प्रायमरी स्कूल ग्राम पंचायत परसोना | Closed | 55847.4 | 0 | 2023-06-08
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702002019/FP/22012034627852 — नाला निर्माण कार्य माता मन्दिर से नदी की ओर परसोना | Completed | 299700.65 | 265200 | 2022-05-27 | 2022-12-12
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702002019/FP/22012034627853 — नाला निर्माण कार्य माता मन्दिर से नदी की ओर परसोना | Closed | 0 | 0 | 2022-01-01
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702002019/FP/22012034629969 — कच्चा नाला निर्माण कार्य करक ताल से परसोना गांव की ओर | Ongoing | 653672.17 | 262008 | 2022-12-29
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002019/IF/22012034353190 — BRAKSHAROPAN KARYA SHALA BHAVAN PARSONA | Closed | 335000 | 0 | 2017-04-24
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002019/IF/22012034360066 — BRAKSHA ROPAN KARYA SADAK KE KINARE | Closed | 335000 | 0 | 2017-04-24
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002019/IF/22012034752347 — med bandan guddu / ajabe | Completed | 13676.59 | 15054 | 2021-05-27 | 2021-07-06
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002019/IF/22012034752354 — med bamdan surendra / hom singh | Completed | 13676.59 | 13896 | 2021-05-27 | 2021-10-25
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002019/IF/22012034752358 — med bandan rajendra / munedra | Completed | 16411.89 | 6948 | 2021-06-10 | 2021-10-25
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002019/IF/22012034752361 — med bandan suresh / vishvnath | Completed | 16411.89 | 6948 | 2021-06-24 | 2022-02-26
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002019/IF/22012034752362 — med bandan sadhu singh / sultan singh | Completed | 15956.04 | 6948 | 2021-06-24 | 2021-10-25
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002019/IF/22012034752367 — med bandan dataram / ajabe | Completed | 18235.45 | 12738 | 2021-06-10 | 2021-10-25
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002019/IF/22012034752371 — med bandan vinod / narendra | Closed | 17323.68 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002019/IF/22012034752382 — med bandan vinay / satendra | Completed | 16411.89 | 6948 | 2021-06-24 | 2022-01-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002019/IF/22012034752385 — med bandan bhavar singh / judavan singh | Completed | 15500.12 | 11580 | 2021-05-27 | 2021-10-25
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002019/IF/22012034752387 — med bandan daroga singh / mehervan singh | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002019/IF/22012034752390 — med bandan ahivaran singh / kok singh | Completed | 15956.04 | 15054 | 2021-05-27 | 2021-10-25
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002019/IF/22012034752392 — med bandan chhote singh / himanchal singh | Completed | 18235.45 | 12738 | 2021-06-10 | 2022-01-03
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002019/IF/22012034752394 — med bandan jitendra / raja singh | Completed | 15827.34 | 12738 | 2021-06-10 | 2021-10-25
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002019/IF/22012034752395 — med bandan yadunath singh / kirat singh | Closed | 17636.14 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002019/IF/22012034752396 — med bandan surendra singh / randhor singh | Completed | 17779.6 | 6948 | 2021-06-24 | 2021-10-25
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002019/IF/22012035533011 — KHET TALAB NIRMAN SANTOSH SINGH / LALLURAM SINGH KE KHET PER | Ongoing | 450885.64 | 207756 | 2025-05-26
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002019/IF/22012035533043 — KHET TALAB NIRMAN NAGESHWAR / NARESH SINGH KE KHET PER | Physically Completed | 450885.64 | 207234 | 2025-05-26 | 2026-04-22
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002019/IF/22012035533118 — KHET TALAB NIRMAN KARYABALRAM SINGH / DHARAM SINGH KE KHET PER | Ongoing | 450885.64 | 219762 | 2025-05-26
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002019/IF/22012035533282 — KHET TALAB NIRMAN KARYA TEJ SINGH / KAPTAN SINGH KE KHET PER | Completed | 147621.16 | 90828 | 2025-05-26 | 2026-04-14
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002019/IF/IAY/322207 — Construction of IAY House -IAY REG. NO. MP1074272 | Completed | 15030 | 11516 | 2017-02-06 | 2017-12-01
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002019/IF/IAY/4336602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143911664 | Approved | 23490 | 0 | 2022-07-30
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002019/IF/IAY/4376157 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142099715 | Closed | 18360 | 0 | 2022-10-14
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002019/IF/IAY/4378315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143922235 | Closed | 18360 | 0 | 2022-10-14
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002019/IF/IAY/453939 — Construction of IAY House -IAY REG. NO. MP1617968 | Completed | 15030 | 13186 | 2017-02-06 | 2017-12-02
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002019/IF/IAY/474526 — Construction of IAY House -IAY REG. NO. MP1892646 | Completed | 15030 | 13176 | 2017-02-06 | 2017-12-05
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002019/IF/IAY/4881953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142099959 | Ongoing | 23490 | 12528 | 2025-08-11
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002019/IF/IAY/530910 — Construction of IAY House -IAY REG. NO. MP2820664 | Completed | 15030 | 14188 | 2017-02-13 | 2017-12-10
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002019/IF/IAY/533624 — Construction of IAY House -IAY REG. NO. MP2894727 | Completed | 15030 | 14178 | 2017-02-13 | 2017-12-08
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002019/IF/IAY/556992 — Construction of IAY House -IAY REG. NO. MP3560535 | Completed | 15030 | 11122 | 2017-02-13 | 2018-01-01
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002019/IF/IAY/686615 — Construction of IAY House -IAY REG. NO. MP2804028 | Completed | 15030 | 14964 | 2017-05-22 | 2018-01-05
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002019/IF/IAY/687785 — Construction of IAY House -IAY REG. NO. MP3534347 | Completed | 15030 | 12384 | 2017-05-22 | 2017-12-30
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002019/IF/IAY/687849 — Construction of IAY House -IAY REG. NO. MP3588357 | Completed | 15030 | 14964 | 2017-05-22 | 2017-12-25
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002019/IF/IAY/687914 — Construction of IAY House -IAY REG. NO. MP3642654 | Completed | 15030 | 13244 | 2017-05-22 | 2017-12-28
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002019/LD/3799395408 — MEDBANDHAN SOMVATI /SHRI GOVIND | Completed | 18900 | 14016 | 2013-06-24 | 2014-06-20
BHIND | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002019/LD/3799403623 — MAD BANDHAN VIRENDRA SINGH / MAHIPAT SINGH | Completed | 23600 | 11680 | 2013-09-16 | 2014-06-20
BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002019/OP/9425891266 — SHANTI DHAM NIRMAN PARSONA | Completed | 823000 | 33812 | 2016-12-26 | 2020-05-08
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002019/PG/22012034365794 — PLAY GROUND | Deleted | 0 | 0 | 2017-10-02
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002019/PG/22012034366338 — play ground | Closed | 0 | 0 | 2017-10-02
BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002019/RC/22012034221551 — C.C.ROAD MULAYAM SINGH KE DWAR SE PURANI HOLI TAK | Completed | 126007 | 9420 | 2014-06-16 | 2016-07-25
BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002019/RC/22012034221552 — C.C.ROAD DAROGA SINGH KE DWAR SE BALVEER SINGH KE DWAR KI AUR | Completed | 126007 | 17898 | 2014-06-23 | 2016-07-22
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002019/RC/22012034290681 — C.C.ROAD PRABHU KE MAKAN SE PRIMARY SCHOOL KI AUR | Completed | 84605 | 68635 | 2015-12-14 | 2019-01-01
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002019/RC/22012034290683 — C.C.ROAD INDAL KE MAKAN SE PRABHU KE MAKAN KI AUR | Completed | 143830 | 61692 | 2015-12-14 | 2019-01-01
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002019/RC/22012034308916 — C.C.ROD MEN ROD SE SHANKER JI KE MANDIR KI OR SHANKAR KA PURA | Deleted | 0 | 0 | 2016-01-26
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002019/RC/22012034348227 — cc road jagmohan pandit ke makan se ms parsona tak | Completed | 7965000000 | 44556 | 2017-08-14 | 2019-01-01
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002019/RC/22012034348228 — cc road jageshwar ke makan se kalicharan ke makan ta | Completed | 66375 | 24768 | 2017-08-10 | 2019-01-01
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002019/RC/22012034348229 — cc road main road se rajendra ke makan tak | Ongoing | 109740 | 97632 | 2019-02-04
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002019/RC/22012034348231 — cc road rajendra ke makan se mata ke mandir tak | Ongoing | 110125 | 87072 | 2019-01-28
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002019/RC/22012034348234 — cc road vishwanath ke ghoore se harijan basti tak | Physically Completed | 88500 | 81690 | 2018-12-31 | 2026-04-17
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002019/RC/22012034442735 — cc road | Closed | 0 | 0 | 2019-01-26
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002019/RC/22012034445165 — indal ke makan se sumer ke makan ki or | Ongoing | 56530 | 41592 | 2019-02-25
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002019/RC/22012034445169 — cc road mata ke mandr se shankar ji ke mandir ki or kaliyan ki thar | Ongoing | 46000 | 43692 | 2019-02-25
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002019/RC/22012034445256 — cc road dilliram ke makan se mata ke mandir ki or hubblal kapura | Ongoing | 60000 | 51504 | 2019-02-25
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002019/RC/22012034445259 — cc road munni ke makan se hakim ke makan ki or hubblala ka pura | Ongoing | 68000 | 53934 | 2019-02-25
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002019/RC/22012034445264 — cc road virendra ke makan se ps hubblalaa ka pura ki or | Ongoing | 65000 | 59544 | 2019-09-24
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002019/RC/22012034522012 — Approach Road work Mata ke Mandir se Shantidham ki or | Closed | 0 | 0 | 2020-01-26
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002019/RC/22012034542345 — cc rods ratiram ke makan se bhavani singh ke makan ki or | Deleted | 0 | 0 | 2020-08-15
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002019/RC/22012034542352 — cc rods ratiram ke makan se bhavani singh ke makan ki or | Deleted | 0 | 0 | 2020-08-15
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002019/RC/22012034542356 — cc rods ratiram ke makan se bhavani singh ke makan ki or | Completed | 127350 | 94890 | 2020-11-19 | 2021-10-25
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002019/RC/22012034542367 — CC RODS MEN ROD SE SHANKAR JI KA PURA | Completed | 120450 | 97128 | 2021-03-22 | 2021-10-25
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002019/RC/53 — सी0सी0 रोड निर्माण पदम सिंह के द्वार से माता के म | Completed | 179964 | 68448 | 2012-06-20 | 2014-06-20
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702002019/RS/22012034639470 — community toilet nirman parsona | Closed | 43000 | 0 | 2022-02-02
BHIND | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002019/RS/22012035133807 — SAMUDAYAK SOAK PIT NIRMAN KEDAR KE MAKAN KE PASS | Approved | 10000 | 0 | 2024-04-28
BHIND | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002019/RS/22012035133808 — SAMUDAYAK SOAK PIT NIRMAN PS SCHOOL BHAVAN PER | Approved | 10000 | 0 | 2024-04-01
BHIND | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002019/RS/22012035133811 — SAMUDAYAK SOAK PIT MUNNA SHARMA KE MAKAN KE PASS | Approved | 10000 | 0 | 2024-04-01
BHIND | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002019/RS/22012035133835 — SAMUDAYAK SOAK PIT MOHAR SINGH KE MAKAN KE PASS | Approved | 10000 | 0 | 2024-04-01
BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002019/WC/22012034324156 — TALAB NIRMAN MARAMMAT KARYA | Completed | 88000 | 41280 | 2017-05-15 | 2017-06-25
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002019/WC/22012034892844 — तालाव मरमति करण एंव गहरी करण | Closed | 0 | 0 | 2022-01-05
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Canal Line Plantation of Forestry-Community / Canal Line Plantation of Forestry Trees for Community | Plantation | 1702002019/WC/22012034952162 — kachha nala nirman mata k mandir k niche se shantidham ki or | Closed | 0 | 0 | 2022-01-24
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002019/WC/22012034961584 — अमृत सरोवर योजना अंतर्गत तालाब निर्माण कार्य छोटे के banda के पास रकबा नंबर 51 परसोना | Closed | 2430467.53 | 0 | 2022-04-18
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002019/WC/22012034970818 — अमृत सरोवर तालाब निर्माण कार्य छोटे के बंदा के पास रकवा नं 51 ग्राम परसोना ग्रा.पं. परसोना | Physically Completed | 1944000 | 865470 | 2022-05-27 | 2026-06-09
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1702002019/WC/22012035025826 — अमृत सरोवर अंतर्गत डग टैंक निर्माण कार्य मिडिल स्कूल के पीछे परसोना | Physically Completed | 1450750 | 731918 | 2022-12-21 | 2026-06-09
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1702002019/WC/22012035028667 — naveen talab nirman gokul k gonda k paas parsona | Physically Completed | 1471566.03 | 435591 | 2023-08-12 | 2026-06-10
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002019/WH/22012034455907 — तालाब मरम्मति करण एंव गहरी करण कार्य ताल का पुरा परसोना | Closed | 0 | 0 | 2021-01-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702002019/WH/22012034455912 — तालाब मरम्मति करण एंव गहरी करण कार्य परसोना | Closed | 0 | 0 | 2022-01-02
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702002019/WH/22012034455973 — तालाब मरम्मति करण एंव गहरी करण कार्य ताल का पुरा परसोना | Completed | 47059.2 | 33048 | 2022-05-26 | 2022-10-15
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702002019/WH/22012034455976 — तालाब मरम्मति करण एंव गहरी करण कार्य परसोना | Completed | 42353.28 | 28152 | 2022-05-26 | 2022-12-12