## Work List
Exported on: 2026-09-13 20:58:59
Filters applied:
Data source: MGNREGA
District: BHIND
Block: All
Panchayat: DINPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702002024/AV/22012034373745 — PANCHAYAT BHAVAN DEENPURA | Completed | 579200 | 578020 | 2018-06-11 | 2020-05-15
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002024/AV/22012034505414 — shanti dhaam nirmaan karya | Suspended | 192447.09 | 0 | 2020-01-20
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002024/AV/22012034552085 — उपार्जन केन्द्र पर चबूतरा निर्माण कार्य दीनपुरा | Completed | 802553.42 | 330427 | 2021-03-25 | 2022-11-02
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Construction of Road and Culvert | 1702002024/AV/22012034565547 — CONSTRUCTION WORK OF PAVOUR BLOCK IN CAMPAS OF GOVT SCHOOL DEENPURA | Completed | 126000 | 91800 | 2022-11-19 | 2024-01-23
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702002024/AV/22012034614869 — Shanti dham nirman middle school ke pass mircholi | Closed | 287491.74 | 0 | 2022-01-26
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1702002024/DP/22012034601897 — Amrat vatika nirman shamshan ghat deenpura | Closed | 55847.4 | 0 | 2023-08-06
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702002024/FP/22012034366672 — Nala nirman RTO balla se ramchandra kushwah evam chande ke makan ki or | Completed | 112000 | 37979 | 2021-02-18 | 2022-02-14
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002024/IF/22012034352300 — Braksharopan karya samudayik sthal per deenpura | Completed | 335000 | 1032 | 2017-06-17 | 2018-10-11
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002024/IF/22012034352315 — Braksharopan karya samudayik sthal per MIRCHOLI | Completed | 335000 | 5064 | 2017-06-17 | 2018-10-11
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1702002024/IF/22012034353249 — Braksharopan karya2 Samudayik sthal per deenpura | Deleted | 0 | 0 | 2017-04-14
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002024/IF/22012034353257 — Braksharopan karya2 Samudayik sthal per deenpura | Deleted | 335000 | 0 | 2017-06-24
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002024/IF/22012034353263 — Braksharopan karya 2 samudayik sthal per MIRCHOLI | Closed | 335000 | 0 | 2017-06-24
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002024/IF/22012034353266 — Braksharopan karya2 Samudayik sthal per MIRCHOLI | Deleted | 0 | 0 | 2017-04-14
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Nursery Raising / Raising of Nursery for Individuals | Nursery Development | 1702002024/IF/22012034353273 — Braksharopan karya 2 samudayik sthal per MIRCHOLI | Deleted | 0 | 0 | 2017-04-14
BHIND | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002024/IF/22012034602910 — श्री भगवान सिंह पुत्र श्री कृष्ण के निजी खेत मे फलो उद्यान रोपण कार्य | Closed | 141000 | 0 | 2020-03-09
BHIND | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002024/IF/22012034606098 — श्री कामता सिंह पुत्र वृन्दावन के निजी खेत मे फलो उद्यान रोपण कार्य | Closed | 141000 | 0 | 2020-03-09
BHIND | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002024/IF/22012034606105 — श्री रामसरन सिंह पुत्र रामरूप के निजी खेत मे फलो उद्यान रोपण कार्य | Closed | 141000 | 0 | 2020-03-09
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702002024/IF/22012034719254 — Nadep nirman narayan shri ke yaha dinpura | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702002024/IF/22012034719269 — Nadep nirman RAMMURTI ke yaha dinpura | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702002024/IF/22012034719289 — Nadep nirman VIPIN YADAV ke yaha dinpura | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034753921 — med bandhan kitab shree ke khet par mircholi | Completed | 18235.45 | 17563 | 2021-05-20 | 2021-12-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034753943 — med bandhan sughar shree ke khet par mircholi | Completed | 18235.45 | 19879 | 2021-05-20 | 2021-12-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034753954 — med bandhan bhagwan singh ke khet par mircholi | Completed | 16411.89 | 14861 | 2021-05-21 | 2021-12-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034753970 — med bandhan shree krishan ke khet par dinpura | Completed | 15956.04 | 11387 | 2021-05-20 | 2021-12-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002024/IF/22012034758582 — MED BANDHAN PREM SINGH KE MIRCHOLI | Completed | 25042.05 | 7334 | 2021-05-21 | 2022-01-03
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034758597 — MED BANDHAN KAMTA SINGH KE KHET PER MIRCHOLI | Completed | 23789.95 | 13317 | 2021-05-21 | 2021-12-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034758616 — MED BANDHAN PREM SINGH KE KHET PER MIRCHOLI | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034758631 — MED BANDHAN PREM SINGH KE KHET PER 3 MIRCHOLI | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034758660 — MED BANDHAN VIDHYARAM KE KHET PER MIRCHOLI | Completed | 24416 | 11387 | 2021-05-21 | 2021-12-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034758679 — MED BANDHAN SARLA DEVI KE KHET PER MIRCHOLI | Completed | 25042.05 | 9457 | 2021-05-20 | 2022-01-03
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034758991 — med bandhan suresh singh ke khet per dinpura | Completed | 22537.84 | 14282 | 2021-06-12 | 2021-10-28
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034759002 — med bandhan jiledar ke khet per dinpura | Completed | 23163.89 | 13703 | 2021-06-12 | 2021-12-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034759013 — med bandhan ramshankar ke khet per deenpura | Completed | 23789.95 | 11387 | 2021-06-12 | 2021-12-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034759026 — med bandhan banshi ke khet per deenpura | Completed | 23163.89 | 3281 | 2021-06-12 | 2022-02-07
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002024/IF/22012034759032 — med bandhan ramswaroop ke khet per deenpura | Completed | 23789.95 | 6760 | 2021-06-12 | 2022-11-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034760265 — med bandhan mula devi ke khet per dinpura | Completed | 16867.82 | 5790 | 2021-11-09 | 2022-01-05
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034760281 — med bandhan mahesh ke khet per deenpura | Completed | 17779.6 | 5790 | 2021-11-09 | 2022-01-05
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034760297 — med bandhan malikhan ke khet per deenpura | Completed | 16867.82 | 5790 | 2021-11-09 | 2022-01-05
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034760304 — med bandhan dhanvanti ke khet per deenpura | Completed | 15956.04 | 10422 | 2021-11-09 | 2022-01-28
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034797006 — Med bandhan Jagram ke khet per mircoli | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034798056 — Med bandhan Jagram ke khet per mircholi | Completed | 17647.21 | 965 | 2021-06-26 | 2022-01-28
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1702002024/IF/22012034798076 — med bandhan gyaram ke khet per mircholi | Deleted | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034798093 — med bandhan shyam singh ke khet per | Completed | 17141.32 | 965 | 2021-06-26 | 2022-01-28
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034798106 — med bandhan pawan ke khet per mircholi | Completed | 16764.85 | 965 | 2021-06-26 | 2022-01-28
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034798112 — med bandhan sonveer ke khet per mircholi | Completed | 16867.82 | 1158 | 2021-06-26 | 2022-01-28
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034798119 — med bandhan sawan shree ke khet per mircholi | Completed | 17506.02 | 1158 | 2021-06-26 | 2022-01-28
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034799186 — Med bandhan hukum singh ke khet per mircholi | Deleted | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034799193 — med bandhan govind singh ke khet per mircholi | Deleted | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034799203 — Med Bandhan Jantura ke khet per mircholi | Deleted | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034799207 — med bandhan ramprakash ke khet per mircholi | Deleted | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034799212 — med bandhan ramveer ke khet per mircholi | Deleted | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034799225 — med bandhan pradeep ke khet per mircholi | Deleted | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034799241 — Med Bandhan manoj ke khet per deenpura | Deleted | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034811472 — MED BANDHAN NEEKERAM SHARMA KE KHET PER DEENPURA | Deleted | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002024/IF/22012034811476 — MED BANDHAN JOHARI KE KHET PER MIRCHOLI | Deleted | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034816452 — MED BANDHAN KAILASH KE KHET PER MIRCHOLI | Deleted | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002024/IF/22012034816456 — MED BANHAN SAUKIRAM KE KHET PER MIRCHOLI | Deleted | 0 | 0 | 2021-04-14
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1702002024/IF/22012035513614 — khet talab nirman karyamircholi kamta singh /vidravan singh | New | 0 | 0 | 2025-05-13
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1702002024/IF/22012035517549 — khet talab nirma karya mircholi Prem singh/ Matadin singh | New | 0 | 0 | 2025-05-14
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002024/IF/22012035521335 — kamta singh /vindravan singh khet talab nirman mircholi | Ongoing | 147621.16 | 6264 | 2025-05-21
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002024/IF/22012035521594 — prem singh /matadin singh khet talab nirman mircholi | Ongoing | 147621.16 | 4959 | 2025-05-21
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002024/IF/9993686678 — CATTLE SHED VISHRAM/ RAMVARAN | Completed | 115900 | 47115.5 | 2015-11-05 | 2018-04-09
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002024/IF/9993686679 — CATTLE SHED DHEERAJ/ RAMRATAN | Completed | 115900 | 47115.5 | 2015-11-05 | 2018-04-07
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002024/IF/9993686682 — CATTLE SHED RAMESH/ BHEEKAM | Completed | 115900 | 54129.5 | 2015-11-05 | 2018-04-07
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002024/IF/9993686917 — CATTLE SHED RAM SHANKAR/ JANDEL | Completed | 115900 | 54129.5 | 2015-11-05 | 2018-04-07
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002024/IF/9993686918 — CATTLE SHED SARDEV/ KANHAIYALAL | Completed | 115900 | 55131.5 | 2015-11-05 | 2018-04-09
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002024/IF/9993686919 — CATTLE SHED RAM PRAKASH / BABU YADAV | Completed | 115900 | 61509.5 | 2015-11-05 | 2018-04-07
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002024/IF/9993747812 — CATTLE SHED FULJHARI/PANNALAL | Deleted | 7500039900 | 0 | 2015-11-24
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002024/IF/9993747816 — CATTLE SHED SANTOSH/KAPTAN | Deleted | 7500039900 | 0 | 2016-06-18
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002024/IF/9993747822 — CATTLE SHED RAMDATT/VIDHYARAM | Deleted | 7500039900 | 0 | 2015-11-24
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002024/IF/9993747825 — CATTLE SHED ANGAD/KASHIRAM | Deleted | 7500039900 | 0 | 2016-06-18
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002024/IF/9993747829 — CATTLE SHED HAKIM SINGH/NATHU SINGH | Deleted | 7500039900 | 0 | 2015-11-24
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002024/IF/9993747831 — CATTLE SHED AGYARAM SINGH/BRANDAVAN | Deleted | 7500039900 | 0 | 2015-11-24
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002024/IF/9993748771 — CATTLE SHED BRAMHANAND/HANUMANT | Deleted | 0 | 0 | 2016-06-22
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002024/IF/9993748806 — CATTLE SHED SHAILENDRA/BACHCHU SINGH | Deleted | 7500039900 | 0 | 2016-06-25
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002024/IF/9993749856 — CATTLE SHED SHIVNARAYAN SINGH/BINDRAVAN | Deleted | 7500039900 | 0 | 2015-11-24
BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002024/IF/IAY/1871620 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4732576 | Completed | 15660 | 15312 | 2018-08-03 | 2018-11-18
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002024/IF/IAY/4325716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150761948 | Physically Completed | 18360 | 17731 | 2022-12-15 | 2024-11-21
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002024/IF/IAY/4335918 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150217079 | Physically Completed | 18360 | 15543 | 2022-12-15 | 2024-11-21
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002024/IF/IAY/4371526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141721320 | Physically Completed | 18360 | 16404 | 2022-12-15 | 2024-11-21
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002024/IF/IAY/4384451 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150207123 | Physically Completed | 18360 | 15150 | 2023-01-20 | 2024-11-21
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002024/IF/IAY/506674 — Construction of IAY House -IAY REG. NO. MP2343015 | Completed | 15030 | 15060 | 2017-02-04 | 2018-04-07
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002024/IF/IAY/82254 — Construction of IAY House -IAY REG. NO. MP-02-002-024-002/06 | Completed | 14310 | 13360 | 2016-06-18 | 2018-04-07
BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002024/LD/101 — मेड बन्‍धान कार्य ठाकुरदीन / बेदरी बघेल | Completed | 11400 | 7100 | 2010-07-26 | 2010-07-26
BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002024/LD/102 — मेड बन्‍धान कार्य ठाकुरदीन / बेदरी बघेली | Completed | 47710 | 21300 | 2010-08-02 | 2010-08-02
BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002024/LD/22012034277338 — MEDBANDHAN JAISIRAM/BINDRAVAN KE KHET ME | Completed | 7410000000 | 37909 | 2016-07-09 | 2018-02-17
BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002024/LD/22012034277339 — MED BANDHAN BHARAT SINGH/GIRDAWAL KE KHET ME | Completed | 4332000000 | 22044 | 2016-07-16 | 2018-02-17
BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002024/LD/22012034277340 — MED BANDHAN HETRAM/KARAN SINGH KE KHET ME | Completed | 5500000000 | 25050 | 2016-07-23 | 2018-02-17
BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002024/LD/22012034277341 — MED BANDHAN KAMTA SINGH/BINDRAWAN KE KHET PAR | Completed | 7743400000 | 16032 | 2016-07-23 | 2018-02-17
BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002024/LD/22012034277342 — MED BANDHAN PREM SINGH/MATADENN KE KHET ME | Completed | 5122600000 | 14028 | 2016-07-23 | 2018-02-17
BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002024/LD/22012034277343 — MED BANDHAN RAMLAKHAN SINGH/ MALKHAN KE KHET ME | Completed | 5956500000 | 20040 | 2016-07-23 | 2018-02-17
BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002024/LD/22012034277344 — MED BANDHAN DEENANATH BAGHEL/UMRAV SINGH KE KHET ME | Completed | 5956500000 | 23046 | 2016-07-23 | 2018-02-17
BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002024/LD/22012034291421 — MED BANDHAN SURESH SINGH/BHEEKAM SINGH KE KHET PAR | Completed | 3931300000 | 29058 | 2016-07-23 | 2018-02-17
BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002024/LD/22012034291610 — MED BANDHAN JILEDAR/MALKHAN SINGH KE KHET ME | Completed | 5480000000 | 17034 | 2016-07-30 | 2018-02-17
BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002024/LD/22012034291611 — MED BANDHAN VIDHYARAM SINGH/ASHARAM SINGH | Completed | 5956500000 | 15030 | 2016-07-30 | 2018-02-17
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002024/LD/22012034550443 — med bandhan suresh singh ke khet par dinpura | Closed | 16823.66 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002024/LD/22012034550458 — med bandhan jiledar singh ke khet par dinpura | Closed | 17333.47 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002024/LD/22012034550470 — med bandhan ramshankar ke khet par dinpura | Closed | 18353.08 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002024/LD/22012034550475 — med bandhan banshi ke khet par dinpura | Closed | 17333.47 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002024/LD/22012034550477 — med bandhan Tej singh ke khet par dinpura | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002024/LD/22012034550479 — med bandhan Ramswaroop singh ke khet par dinpura | Closed | 16823.66 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002024/LD/22012034550480 — med bandhan mula devi ke khet par dinpura | Closed | 11215.78 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002024/LD/22012034550483 — med bandhan mahesh ke khet par dinpura | Closed | 23451.17 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002024/LD/22012034550484 — med bandhan malikhan ke khet par dinpura | Closed | 15811.9 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002024/LD/22012034550486 — med bandhan dhanvanti ke khet par dinpura | Closed | 14823.65 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1702002024/LD/22012034567394 — Braksharopan karya deenpura se etawah road tak sadak ke dono or deenpura | Closed | 814831.51 | 0 | 2021-04-14
BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002024/OP/9425892799 — Shanti Dham mirchauli | Completed | 180000 | 1002 | 2017-03-25 | 2019-07-01
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002024/OP/9425892801 — Shanti Dham Deenpura | Completed | 245000 | 243788.15 | 2017-09-30 | 2019-09-01
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002024/PG/22012034365782 — PLAY GROUND | Deleted | 0 | 0 | 2017-10-02
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002024/PG/22012034366334 — play ground | Closed | 0 | 0 | 2017-10-02
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002024/PG/9425896292 — Play Ground Mircholi | Completed | 353000 | 310794 | 2017-08-12 | 2019-09-01
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034172164 — C.C.ROAD SADAR KE BHAVAN SE CHINTAMAN KE MAKAN KI TARAF | Deleted | 91800 | 0 | 2012-08-15
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034172166 — C.C.ROAD SARDAR KE MAKAN SE AMRAT LAL KE BHAVAN TA | Completed | 91800 | 66736.8 | 2013-12-28 | 2014-09-29
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034287820 — C.C.ROAD HARIBHAJAN KE MAKAN SE RAM LAKHAN KE MAKAN KI AUR MIRCHOLI | Completed | 143000 | 130358 | 2015-10-31 | 2018-12-18
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034287821 — C.C.ROAD CHURAMAN KE MAKAN SE GOVT. PRIMARY SCHOOL MIRCHOLI KI AUR | Completed | 126000 | 119083 | 2015-10-31 | 2018-12-18
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034310608 — CC ROAD | Deleted | 0 | 0 | 2016-01-26
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034341752 — SUDUR SAMPARK SADAK MIRCHAULI SE GURJA KA PURA MUKHYAMANTRI SADAK TAK | Completed | 2499000 | 199344 | 2017-06-17 | 2019-03-31
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034343679 — C.C ROAD Shivnarayan ke makan se rustam singh ke makan tak | Completed | 133000 | 120360 | 2017-11-04 | 2018-12-18
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034343790 — CC ROAD RAMAUTAR KE MAKAN SE PARWAT BABA TAK | Completed | 155000 | 189888 | 2017-07-08 | 2018-10-11
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034351596 — CC Road Sarnam ke makan se sumer ke gaunda tak | Completed | 131000 | 89248 | 2017-11-04 | 2021-11-29
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034364569 — CC Road Vipin Bharadwaj ke makan se master ke makan tak | Completed | 64000 | 62580 | 2017-11-04 | 2018-10-11
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034364572 — CC Road Ramautar ke makan se jagdees ke makan tak | Completed | 145000 | 5160 | 2017-11-04 | 2019-07-01
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034364574 — Angad ke makan se shaskiye madhyamik vidhyalay mirchauli | Completed | 531000 | 83128 | 2017-11-04 | 2020-02-01
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034365760 — C.C.ROAD Uday ke makan se jagdeesh bhadauriya ke makan tak | Completed | 354000 | 49020 | 2017-11-04 | 2018-10-11
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034365762 — c.c.road Dashrath ke makan se Tankilal ke makan tak | Completed | 424800 | 53022 | 2017-11-04 | 2018-10-11
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034365767 — C.C ROAD Vijay ke makan se Bajariya tak | Completed | 719800 | 126936 | 2017-11-04 | 2019-07-01
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034442705 — cc road | Closed | 0 | 0 | 2019-01-26
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034504399 — C.C Road Mata Ke Mandir Se Radhe Ke Makan Ki Aur Khaud | Completed | 14000 | 36960 | 2019-11-09 | 2020-02-02
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034504402 — C.C Road Atar Singh Bhagel Ke Makan Se Abhilakh Ke Makan Ki Aur | Completed | 23000 | 23056 | 2019-12-04 | 2020-02-02
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034504404 — C.C Road Kailka Ke Makan Se Phodal Ke Makan Ki Aur | Completed | 23000 | 22528 | 2019-11-16 | 2020-02-20
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034504405 — C.C Road Ramashre Ke Makan Se Ajay Ke Makan Ke Aur | Completed | 70000 | 70048 | 2019-11-16 | 2020-02-02
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034504407 — C.C Road Maan Singh Ke Makan Se Sudhari Ke Makan Ki Aur | Completed | 23000 | 10348 | 2019-11-09 | 2022-01-02
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034504416 — C C ROAD MASTER KE KAMAN SE GUMTHI KI AUR | Ongoing | 153000 | 23202 | 2019-11-09
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002024/RC/22012034522020 — approch road mukhay sadak se shantidham tak deenpura | Closed | 0 | 0 | 2020-04-14
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002024/RC/22012034525654 — सुदूर सम्पर्क सडक दीनपुरा खोड मे गयाराम बघेल के घर से पंचायत भवन की ओर | Closed | 1489084.09 | 0 | 2020-07-23
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002024/RC/22012034531543 — सुदूर सडक निर्माण कार्य ग्याराम बघेल के घर से पंचायत भवन की ओर | Completed | 1476321.22 | 890392.02 | 2020-08-15 | 2023-04-29
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034569120 — C C ROAD DEENPURA KHOD MARG SE SHANTIDHAM KI AUR DEENPURA | Completed | 100000 | 72216 | 2022-06-10 | 2023-04-29
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034611733 — cc road ramveer baghel ke makan se bel wale baba ki or deenpura khod | Closed | 124000 | 0 | 2021-04-14
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034611886 — C C ROAD NIRMAN PANCHAYAT BHAWAN SE KARAN KE MAKAN KI AUR | Closed | 126000 | 0 | 2021-04-14
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034611889 — C C ROAD NIRMAN SHANKAR JI MANDIR SE HOMSINGH BAGHEL KE DUAR KI AUR | Closed | 99000 | 0 | 2021-04-14
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/22012034612028 — C C ROAD RAMVEER BAGHEL KE MAKAN BAIL WALE BABA KI AUR | Closed | 124000 | 0 | 2021-04-14
BHIND | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002024/RC/42 — सी0सी0रोड निर्माण कार्य केवल सिंह के मकान से ग्‍याराम के मकान की ओर | Completed | 299231 | 102723 | 2012-03-23 | 2013-06-10
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002024/RS/22012034191315 — MARYADA ABHIYAN SHER SINGH / BHULAN SINGH | Deleted | 4500 | 0 | 2013-04-14
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002024/RS/22012034191316 — MARYADA ABHIYAN HARIRAM SHARMA / BENIRAM | Deleted | 4500 | 0 | 2013-04-14
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702002024/RS/22012034501693 — naveen community toilet gp deenpura | Closed | 43000 | 0 | 2020-11-25
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1702002024/RS/22012034515433 — CONSTRUCTION WORK OF RCC NAALI NIRMAAN DEENPURA KHOD MARG SE SHANTIDHAM KI AUR | Closed | 86000 | 0 | 2021-04-18
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002024/RS/22012034515899 — sokhta gadda govt middle school dinpura | Closed | 20015.48 | 0 | 2021-04-14
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Community / Construction of Berkeley Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702002024/RS/22012034515900 — sokhta gadda govt primary school dinpura | Closed | 20015.48 | 0 | 2021-04-14
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Community / Construction of Berkeley Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702002024/RS/22012034515902 — sokhta gadda shantidham dinpura | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002024/RS/22012034515903 — sokhta gadda panchayat bhavan par dinpura | Closed | 10081.47 | 0 | 2021-04-14
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002024/RS/22012034650642 — COMMUNITY SOAKPIT NIRMAN GOVT MIDIL SCHOOL DEENPURA | Closed | 6600 | 0 | 2022-04-05
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002024/RS/22012034650647 — COMMUNITY SOAKPIT NIRMAN UPARJAN KAINDRA DEENPURA | Closed | 6600 | 0 | 2022-04-05
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002024/RS/22012034650688 — COMMUNITY SOAKPIT NIRMAN GOVT MIDIL SCHOOL HANDPUMP KE PASS | Closed | 6600 | 0 | 2022-04-06
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002024/RS/22012034650690 — COMMUNITY SOAKPIT RAMSHANKAR YADAV KE GHAR KE PASS | Closed | 6600 | 0 | 2022-04-06
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002024/RS/22012034650694 — COMMUNITY SOAKPIT NIRMAN PANCHAYAT BHAWAN KI PICHHE | Closed | 6600 | 0 | 2021-04-14
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002024/RS/22012034650699 — COMMUNITY NADEP NIRMAN SHIVNARAYAN SINGH YADAV | Closed | 5000 | 0 | 2022-04-06
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002024/RS/22012034650703 — COMMUNITY NADEP NIRMAN AAGYARAM SINGH YADAV | Closed | 5000 | 0 | 2022-04-06
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002024/RS/22012034664771 — ankit ke ghar ke pass sokhta gadda nirman | Closed | 0 | 0 | 2022-08-15
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002024/RS/22012034664772 — ankit ke ghar ke pass sokhta gadda nirman | Completed | 10000 | 7140 | 2022-09-12 | 2025-06-01
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002024/RS/22012034664774 — ASHOK KE GHAR KE PASS SOKHTA GADDA NIRMAN | Completed | 10000 | 9792 | 2023-02-11 | 2023-05-07
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002024/RS/22012034664776 — ANGAD KE GHAR KE PASS SOKHTA GADDA NIRMAN | Completed | 18000 | 9792 | 2022-10-04 | 2023-05-07
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002024/RS/22012034664778 — AGHYARAM KE GHAR KE PASS SOKHTA GADDA NIRMAN | Closed | 18000 | 0 | 2022-09-10
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002024/RS/22012034664779 — SHIVNARAYAN KE GHAR KE PASS SOKHTA GADDA NIRMAN | Completed | 10000 | 9792 | 2022-09-27 | 2023-05-07
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002024/RS/22012034664780 — BRAJMOHAN KE GHAR KE PASS SOKHTA GADDA NIRMAN | Completed | 10000 | 7140 | 2022-09-12 | 2023-05-06
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002024/RS/22012034664781 — SANTOSH KE GHAR KE PASS SOKHTA GADDA NIRMAN | Completed | 10000 | 9792 | 2022-10-04 | 2023-05-07
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002024/RS/22012034664783 — SHAILENDRA SINGH KE GHAR KE PASS SOKHTA GADDA NIRMAN | Completed | 10000 | 6120 | 2022-09-12 | 2023-05-06
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002024/RS/22012034664784 — RAKESH KE GHAR KE PASS SOKHTA GADDA NIRMAN | Completed | 10000 | 9792 | 2022-10-04 | 2023-05-06
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002024/RS/22012034664786 — AJAY KE GHAR KE PASS SOKHTA GADDA NIRMAN | Completed | 10000 | 9792 | 2022-09-27 | 2023-05-06
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002024/RS/22012034664787 — NARAYAN SINGH KE GHAR KE PASS SOKHTA GADDA NIRMAN | Closed | 10000 | 0 | 2022-09-10
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002024/RS/22012034664788 — RAMMOHAN KE GHAR KE PASS SOKTA NIRMAN | Completed | 10000 | 9792 | 2023-02-11 | 2023-05-07
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002024/RS/31777 — MARYADA ABHIYAN RAMPAL/PATIRAM | Completed | 4500 | 438 | 2013-06-15 | 2016-08-11
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002024/RS/31781 — MARYADA ABHIYAN BALRAM / RAGHUBAR | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002024/WC/16 — सोख्‍ता गडडा भूलन सिह के हैण्‍डपम्‍प के पास | Completed | 5305 | 14545 | 2009-07-10 | 2009-07-10
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702002024/WC/22012034324184 — Gaon ke pass talab MIRCHOLI | Completed | 467000 | 2064 | 2017-05-13 | 2019-02-21
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702002024/WC/22012034325872 — DINPURA_KHOD NAVIN TALAB NIRMAN | Completed | 508000 | 41796 | 2017-05-20 | 2019-02-19
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702002024/WC/22012034547975 — naveen khet talab deenpura khudan | Closed | 0 | 0 | 2020-04-14
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002024/WC/22012034547978 — earthan dam mirchuli | Closed | 0 | 0 | 2020-04-14
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002024/WC/22012034547980 — naveen talab mircholi | Closed | 0 | 0 | 2020-04-14
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Earthen Spur for Community / Construction of Earthen Spur for Community | Construction of Spur | 1702002024/WC/22012034994914 — NAVEEN TALAB NIRMAN KARYA MIRCHAULI | Ongoing | 1013076.04 | 363834 | 2023-01-12
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002024/WC/22012035070688 — GRAM DEENPURA KHOD NAVEEN TALAB NIRMAN | Closed | 0 | 0 | 2023-04-14
BHIND | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1702/RC/22012034153103 — Gram Sampark Sadak Yojna | Completed | 1218000 | 232220 | 2011-01-29 | 2016-12-18