## Work List
Exported on: 2026-08-30 11:50:16
Filters applied:
Data source: VBGRAMG
District: BHIND
Block: All
Panchayat: MOTIPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002042/FP/22012034366251 — NALA NIRMAN MOTIPURA SE TALAB TAK | Ongoing | 243824.4 | 0 | 2020-09-28
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002042/IF/22012034590456 — PASHU SHED ALOK / MAHAVEER SINGH | Ongoing | 101804.91 | 0 | 2020-12-17
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002042/IF/22012034590461 — PASHU SHED MEENA BEVA / MUNENDRA SINGH | Ongoing | 101804.91 | 0 | 2020-12-17
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002042/IF/22012034590463 — PASHU SHED PRAMOD / PARTH SINGH | Ongoing | 101804.91 | 0 | 2020-12-17
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002042/IF/22012034591422 — PASHU SHED NIRMAN LOKENDRA SINGH / RAM SINGH | Ongoing | 101804.91 | 0 | 2020-12-09
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002042/IF/22012035489927 — khet talab nirman santosh ke khet par gram bisalpura gp motipura | New | 0 | 0 | 2025-04-14
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002042/IF/22012035491014 — khet talab nirman santosh ke khet par gram bisalpura gp motipura | Ongoing | 147621.16 | 0 | 2025-05-15
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702002042/IF/22012035626382 — EK BAGIYA MAA KE NAAM KUNTI DEVI KE KHET PAR GRAM GARHISITA GP MOTIPURA | Ongoing | 189141.35 | 0 | 2025-12-27
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002042/RS/22012034679082 — SAMUDAYIK SOKHTA GOVT MIDIL SCHOOL BISALPURA GP MOTIPURA | Ongoing | 10000 | 0 | 2022-12-20
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002042/RS/22012034679087 — SAMUDAYIK SOKHTA GOVT AAGANWARI BHAWAN GRAM BISALPURA | Ongoing | 10000 | 0 | 2022-12-20
BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702002042/RS/22012034687640 — SAMUDAYIK SWACHCHHTA PARISAR GRAM BISALPURA GP MOTIPURA | Ongoing | 43000 | 0 | 2023-05-13
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002042/WC/22012034619870 — TALAB GAHRIKARAN POKHAR WALA GADISITA | Ongoing | 1132303.05 | 0 | 2021-03-09