## Work List
Exported on: 2026-09-11 14:08:29
Filters applied:
Data source: MGNREGA
District: BHIND
Block: All
Panchayat: GUSING
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND | 2019-2020 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1702002045/AV/22012034470944 — GAUSHALA NIRMAN GUSEENG | Completed | 2771628.29 | 2645608 | 2019-12-25 | 2023-04-20
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002045/AV/22012034621113 — SHANTI DHAM GUSING | Closed | 0 | 0 | 2022-08-16
BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002045/AV/22012034632444 — SHANTIDHAM NIRMAN KARYA GUSING | Physically Completed | 344468.23 | 288148.03 | 2023-07-26 | 2026-04-17
BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002045/AV/22012034638653 — SHANTIDHAM NIRMAN KARYA GUSEENG | Closed | 0 | 0 | 2023-04-14
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002045/AV/3790 — Aanganbadi/Other Rural Infrastructure,BHIND | Completed | 330000 | 317275 | 2015-11-04 | 2019-05-10
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002045/DP/22012034595238 — वसुधा वंदन अमृत वाटिका वृक्षारोपण कार्य माता का मंदिर गुसीग | Ongoing | 55847.4 | 1768 | 2023-09-20
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702002045/FP/22012034361868 — puliya nirman shivji ke ghar ke pas tal par | Completed | 35300 | 34560 | 2019-02-06 | 2021-10-09
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1702002045/FP/22012034361918 — NALA NIRMAN RAMLAKHAN BHAGEL KE GHAR SE RAMCHARAN KE GHAR KI OR GUSING | Closed | 62498 | 0 | 2019-01-09
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702002045/FP/22012034362763 — puliya nirman moolpal ke adda par | Ongoing | 35300 | 35280 | 2019-03-06
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702002045/FP/22012034362766 — रिटर्निंग बॉल सी.सी.मूलपाल के अड्डा पर | Closed | 36000 | 0 | 2019-03-03
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702002045/FP/22012034623973 — nala nirman balveer baghel ke makan se puliya tak | Deleted | 0 | 0 | 2021-01-21
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702002045/FP/22012034623975 — nala nirman balveer baghel ke makan se puliya tak | Ongoing | 210000 | 17370 | 2021-04-01
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1702002045/FP/22012034624880 — kachha nala nirman damar road gusing se puliya tak | Completed | 215783.4 | 134580 | 2021-06-02 | 2023-09-18
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002045/FP/22012034630277 — CONSTRUCTION WORK OF NALA NIRMAN VIKRAM KE GHAR SE MANI ROAD PULIYA TAK | Completed | 26000 | 24480 | 2022-11-24 | 2023-04-20
BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1702002045/FP/22012034632687 — Kachha nala nirman kary damp se pevali ki or | Completed | 559589.35 | 473824 | 2023-05-31 | 2024-07-23
BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002045/FP/22012034639019 — RCC NALA NIRMAN PANDIT KE GHAR SE SAMUDAYAK BHAVAN KI OR | Closed | 51000 | 0 | 2024-03-15
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Renovation of Feeder Canal for Community / Renovation of Feeder Canal for Community | Renovation of Canal | 1702002045/IC/22012034882981 — NAHAR MARAMMAT KHUDAI KARYA BEESALPURA KI PULIYA SE MUHAND KI OR | Ongoing | 433564.25 | 96135 | 2023-09-20
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002045/IF/22012034352275 — वृक्षारोपड़ कार्य सामुदायिक जगह पर गुसींग | Completed | 335000 | 3096 | 2017-06-21 | 2021-11-23
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002045/IF/22012034357759 — PAUDH ROPAD AGANWADI KE AS PAS GUSING | Completed | 335000 | 2064 | 2017-08-02 | 2021-11-23
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002045/IF/22012034357765 — PAUDHAROPAD ROD KE KINARE GADI SULTAN | Closed | 335000 | 0 | 2017-06-27
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002045/IF/22012034357771 — PAODHROPAD SAMSAN GHAT GADISULTAN | Closed | 335000 | 0 | 2017-06-27
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034601890 — pashu shed nirman mukesh / sukhlal | Completed | 101804.91 | 78110 | 2021-01-13 | 2023-05-08
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034601891 — pashu shed nirman mohar singh / gangaram | Closed | 101804.91 | 0 | 2020-08-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034601918 — PASHU SHED NIRMAN BEERBAL/BHARAT | Completed | 101804.91 | 93380 | 2020-12-30 | 2022-01-18
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034601920 — PASHU SHED NIRMAN SURENDRA/SUVALAL | Closed | 0 | 0 | 2020-08-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034601921 — PASHU SHED NIRMAN bhagawansingh /dunnuprasad | Completed | 101804.91 | 93380 | 2021-01-13 | 2022-01-18
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034601922 — PASHU SHED NIRMAN munneelal/shankar | Completed | 101804.91 | 75696 | 2021-03-05 | 2022-10-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034601923 — PASHU SHED NIRMAN bajrang/ramsiya | Completed | 101804.91 | 93380 | 2020-12-30 | 2022-01-18
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034601924 — PASHU SHED NIRMAN lalsingh / bhuresingh | Completed | 101804.91 | 71010 | 2021-03-10 | 2022-10-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034601925 — PASHU SHED NIRMAN ramvati / leeladhar | Closed | 101804.91 | 0 | 2020-08-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034601926 — PASHU SHED NIRMAN gyaprasad /bheekari | Closed | 0 | 0 | 2020-08-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034601927 — PASHU SHED NIRMAN anil /ravindra | Closed | 101804.91 | 0 | 2020-08-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034601928 — PASHU SHED NIRMAN ramsevak /kasheeram | Closed | 0 | 0 | 2020-08-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034601929 — PASHU SHED NIRMAN prembabu /lalaram | Completed | 101804.91 | 78420 | 2020-12-30 | 2022-10-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034601930 — PASHU SHED NIRMAN PRABHASH / FOJADAR | Completed | 101804.91 | 74538 | 2021-03-10 | 2022-10-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034601931 — PASHU SHED NIRMAN SURESH /MANSHARAM | Completed | 101804.91 | 93380 | 2021-02-10 | 2022-01-18
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034601932 — PASHU SHED NIRMAN KULDEEP / NATHURAM | Closed | 0 | 0 | 2020-08-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034602163 — PASHU SHED NIRMAN ramshankar / jordar | Closed | 0 | 0 | 2020-08-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034602165 — PASHU SHED NIRMAN bhogiram / kunji | Closed | 0 | 0 | 2020-08-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034602167 — PASHU SHED NIRMAN RAMLAKHAN /KASHEERAM | Completed | 101804.91 | 92810 | 2020-12-30 | 2022-01-18
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034602168 — PASHU SHED NIRMAN SURESH/ CHHOTELAL | Completed | 101804.91 | 93380 | 2020-12-30 | 2022-01-18
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034602170 — PASHU SHED NIRMAN ULFAT SINGH /AGYARAM | Completed | 101804.91 | 75160 | 2021-03-10 | 2022-10-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034602171 — PASHU SHED NIRMAN PRADEEP / NATHURAM | Completed | 101804.91 | 74056 | 2021-03-04 | 2022-10-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034602172 — PASHU SHED NIRMAN KAMLESH /SHRIRAM | Completed | 101804.91 | 85970 | 2021-01-13 | 2022-01-18
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034602173 — PASHU SHED NIRMAN | Closed | 0 | 0 | 2020-08-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034602174 — PASHU SHED NIRMAN JITENDRA SINGH /SUBALAL | Closed | 0 | 0 | 2020-08-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034602175 — PASHU SHED NIRMAN BALIRAM /CHHAVIRAM | Closed | 0 | 0 | 2020-08-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034602176 — PASHU SHED NIRMAN BALRAM /GANGARAM | Closed | 0 | 0 | 2020-08-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034602177 — PASHU SHED NIRMAN KAMLESH /BENIRAM | Closed | 0 | 0 | 2020-08-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034602178 — PASHU SHED NIRMAN RAJU / CHATURI | Closed | 0 | 0 | 2020-08-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034602179 — PASHU SHED NIRMAN PRAHALAD / PUTTEELAL | Closed | 101804.91 | 0 | 2020-08-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034607078 — PASHU SHED NIRMAN sudheer / veerendra | Completed | 101804.91 | 75142 | 2021-03-10 | 2022-10-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034607080 — PASHU SHED NIRMAN shyama devi /ramgovind | Completed | 101804.91 | 93570 | 2021-01-27 | 2022-01-18
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034672514 — pashu shed nieman deependra singh / ranveer singh | Closed | 0 | 0 | 2021-01-22
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034672518 — pashu shed nirman jagatsingh / matadeen | Closed | 0 | 0 | 2021-01-22
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034673161 — PASHU SHED NIRMAN RAMVARAN / VRANDAVAN | Closed | 0 | 0 | 2020-08-15
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034675407 — pashu shed nirman suresh/dhatu prashad | Closed | 0 | 0 | 2021-01-22
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034675410 — Pashu shed nirman ramdash/ramveer | Closed | 0 | 0 | 2021-01-22
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034675414 — Pashu shed nirman Aparbal/Ramkumar | Closed | 0 | 0 | 2021-01-22
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034675420 — Pashu shed nirman balram /fundi | Closed | 0 | 0 | 2021-01-22
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034675422 — Pashu shed nirman aasheesh/vidhyaram | Closed | 0 | 0 | 2021-01-22
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034677301 — Pashu shed nirman ramsiya / mahendra singh | Closed | 0 | 0 | 2021-01-22
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034677302 — Pashu shed nirman Munnibai /Ashok | Closed | 0 | 0 | 2021-01-22
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/22012034677344 — Pashu shed nirman Arvind / gangaram | Closed | 0 | 0 | 2021-01-22
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002045/IF/22012034768730 — med bandhan nirman baijnath / ramsahay | Closed | 24545.03 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002045/IF/22012034768738 — med bandhan nirman punuram / gundhari | Completed | 24851.85 | 4825 | 2021-06-20 | 2021-11-18
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002045/IF/22012034768748 — med bandhan nirman ram singh / dhaniram | Completed | 25158.65 | 6948 | 2021-07-01 | 2021-11-18
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002045/IF/22012034768754 — med bandhan nirman vitoli / jagnnath | Completed | 25465.47 | 12738 | 2021-06-20 | 2021-11-18
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002045/IF/22012034768767 — med bandhan nirman bajrang / ramsiya | Closed | 25772.28 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002045/IF/22012034768772 — med bandhan nirman ramlakhan / kashiram | Completed | 24545.03 | 12931 | 2021-06-20 | 2021-11-18
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002045/IF/22012034768775 — med bandhan nirman budhuram / ramjuprasad | Closed | 24851.85 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002045/IF/22012034768782 — med bandhan nirman beerbal / bharat | Completed | 25312.06 | 5790 | 2021-06-20 | 2021-11-18
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002045/IF/22012034768789 — med bandhan nirman surendra singh / subalal | Closed | 25772.28 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002045/IF/22012034768791 — med bandhan nirman raghuraj / kamal singh | Completed | 24137.31 | 10615 | 2021-06-20 | 2021-11-18
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002045/IF/22012034768795 — med bandhan nirman ramsevak / shankardayal | Completed | 25158.65 | 6948 | 2021-07-01 | 2021-11-18
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002045/IF/22012034768797 — med bandhan nirman rajendra / baburam | Completed | 25312.06 | 6948 | 2021-07-01 | 2021-11-18
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002045/IF/22012034768802 — med bandhan nirman ramji / chandrabhan | Completed | 25618.88 | 17370 | 2021-07-01 | 2021-11-18
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002045/IF/22012034768804 — med bandhan nirman atar singh / jodha singh | Completed | 25772.28 | 5790 | 2021-06-20 | 2021-11-18
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002045/IF/22012034770642 — med bandhan nirman dulare / bhure singh | Completed | 26079.09 | 13896 | 2021-06-20 | 2021-11-18
BHIND | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002045/IF/22012035163022 — KHET TALAB NIRMAN DHAN SINGH / MEWALAL KE KHET PER | Closed | 346836.59 | 0 | 2023-08-15
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002045/IF/22012035627475 — EK BAGIYA MAA KE NAAM RAMBETI / RAGHUVEER | Ongoing | 182130.43 | 0 | 2026-01-11
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002045/IF/22012035637429 — EK BAGIYA MAA KE NAAM POONAM / SHRIRAM | Deleted | 0 | 0 | 2025-10-02
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002045/IF/22012035637995 — EK BAGIYA MAA KE NAAM POONAM / SHRIRAM | Ongoing | 266578.64 | 0 | 2026-01-03
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993673908 — CATTLE SHED SARVESH / VAEJURAM | Completed | 115900 | 107026.33 | 2015-09-16 | 2015-10-20
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993673956 — CATTLE SHED VISHVNATH/JAYSHRERAM | Completed | 115900 | 107382.89 | 2015-09-16 | 2015-10-20
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993673959 — CATTEL SHED HOREELAL/BHOORE SINGH | Completed | 115900 | 108018.89 | 2015-09-16 | 2015-10-20
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993674165 — CATTLE SHED SHRIGOVIND / NETRAM | Completed | 115900 | 104679.89 | 2015-09-16 | 2016-08-20
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993674180 — CATTLE SHED ASHARAM / SHRIRAM | Completed | 115900 | 107821.33 | 2015-09-16 | 2016-01-20
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993676158 — CATTLE SHED SUKHVEER/MATADEEN | Completed | 115900 | 104750.15 | 2015-10-07 | 2015-11-30
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993676305 — CATTLE SHED MANSINGH/TULSEERAM | Completed | 115900 | 105227.15 | 2015-10-07 | 2015-12-05
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993676308 — CATTLE SHED RAMVATEE/RAMESHAVAR | Completed | 115900 | 104268.55 | 2015-10-07 | 2015-11-28
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993676311 — CATTLE SHED JITENDRA SINGH/JANDELSINGH | Completed | 115900 | 102842.15 | 2015-10-07 | 2015-12-05
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993679395 — CATTLE SHED RAMPRASAD/JAYSINGH | Completed | 115900 | 100935.59 | 2015-11-25 | 2016-09-25
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993688976 — CATTLE SHED RAMHANSH/JAGAT SINGH | Completed | 115900 | 101524.59 | 2015-11-25 | 2016-09-25
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993689173 — CATTLE SHED LAL BAHADUR/ HEERALAL | Completed | 115900 | 102796.59 | 2015-11-25 | 2016-09-20
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993689174 — CATTLE SHED KAMLESH/LAKHAN | Completed | 115900 | 103941.59 | 2015-11-25 | 2016-11-01
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993689175 — CATTLE SHED JITENDRA/ GANGA SINGH | Completed | 115900 | 100984.59 | 2015-11-25 | 2016-09-25
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993689176 — CATTLE SHED DULARE/BHURE SINGH | Completed | 115900 | 106072.59 | 2015-11-25 | 2016-09-25
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993689177 — CATTLE SHED RAKESH/GYAPRASAD | Completed | 115900 | 102160.59 | 2015-11-25 | 2016-11-01
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993689178 — CATTLE SHED VINOD/SIRNAM | Completed | 115900 | 99186.59 | 2015-11-25 | 2016-11-01
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993689179 — CATTLE SHED KASTURI DEVI/ RAMESH BALMIKI | Completed | 115900 | 103161.59 | 2015-11-25 | 2016-10-01
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993689180 — CATTLE SHED SUMER/ HARI SINGH | Completed | 115900 | 102001.59 | 2015-11-25 | 2016-09-25
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993689182 — CATTLE SHED RAM MOHARMAN/ PRABHU DAYAL | Completed | 115900 | 104545.59 | 2015-11-25 | 2016-09-25
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993689184 — CATTLE SHED RAMBABU/ MANOHAR LAL | Completed | 115900 | 103750.59 | 2015-11-25 | 2016-10-01
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993689186 — CATTLE SHED BAL KRISHNA/AJUDDHI | Completed | 115900 | 104386.59 | 2015-11-25 | 2016-10-01
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993689366 — CATTLE SHED RAMHET/ LALARAM | Completed | 115900 | 100729.59 | 2015-11-25 | 2016-09-25
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993728411 — CATTLE SHED RAMKISHOR/NATHURAM | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993728413 — cattle shed pooran/fhojdar | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993731635 — CATTLE SHED LALARAM/SUNDAR | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993731641 — CATTLE SHED BHOLASINGH/LAKHAN | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993731644 — CATTLE SHED DEEPENDR/RANVEER | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993731648 — CATTLE SHED ARJUN/MULAYAMSINGH | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993731650 — CATTLE SHED RAMDDT/MUGARAM | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993731654 — CATTLE SHED RANDHOR/RAMCHARAN | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993731658 — CATTLE SHED HAREE SINGH /SHIVJEE | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002045/IF/9993731662 — CATTLE SHED RAVINDRA/GANGASINGH | Deleted | 0 | 0 | 2016-01-27
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/134017 — Construction of IAY House -IAY REG. NO. MP-02-002-045-001/36 | Completed | 14310 | 13861 | 2016-07-20 | 2017-11-10
BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/1899226 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4541802 | Completed | 15660 | 15660 | 2018-09-19 | 2019-01-28
BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/1899473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4904136 | Completed | 15660 | 15660 | 2018-08-15 | 2019-01-28
BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/1907568 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4578123 | Completed | 15660 | 15660 | 2018-09-19 | 2019-01-28
BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/1916799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4904214 | Completed | 15660 | 14616 | 2018-08-15 | 2019-02-05
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/2146870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5187203 | Completed | 17100 | 13680 | 2020-05-27 | 2021-10-09
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/278375 — Construction of IAY House -IAY REG. NO. MP3763137 | Completed | 15030 | 15060 | 2017-01-25 | 2018-03-30
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/279094 — Construction of IAY House -IAY REG. NO. MP3925694 | Completed | 15030 | 15060 | 2017-02-01 | 2018-03-30
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/3653307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145553169 | Physically Completed | 18360 | 16758 | 2022-11-03 | 2024-11-21
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/3703091 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106188841 | Completed | 18360 | 16014 | 2022-09-09 | 2023-07-11
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/3844256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124179039 | Completed | 18360 | 16014 | 2022-09-09 | 2023-07-24
BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/3875408 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145549515 | Physically Completed | 18360 | 1458 | 2024-10-18 | 2024-11-21
BHIND | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/3876195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145553229 | Physically Completed | 18360 | 16044 | 2023-07-26 | 2024-11-21
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/4176320 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117536623 | Completed | 18360 | 16014 | 2022-09-09 | 2023-07-24
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/4177179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120399076 | Completed | 18360 | 15300 | 2023-01-22 | 2023-08-17
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/4524684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123888897 | Ongoing | 23490 | 23490 | 2025-04-18
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/4527236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128171995 | Ongoing | 23490 | 23490 | 2025-04-18
BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/4528924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142664662 | Ongoing | 23490 | 21384 | 2025-01-28
BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/4755209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117536179 | Ongoing | 23490 | 22842 | 2025-01-28
BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/4880841 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121367367 | Ongoing | 23490 | 21384 | 2025-01-28
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/5578083 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142664582 | Physically Completed | 23490 | 23490 | 2025-06-05 | 2026-03-29
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/5578084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142664609 | Ongoing | 23490 | 23490 | 2025-06-05
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/5578085 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142664637 | Ongoing | 23490 | 4698 | 2025-06-12
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/5578094 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147038542 | Physically Completed | 23490 | 23490 | 2025-06-05 | 2026-02-28
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/5578103 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147486686 | Physically Completed | 23490 | 23490 | 2025-07-31 | 2026-05-17
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/5578107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121390264 | Physically Completed | 23490 | 23490 | 2025-06-05 | 2026-01-10
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/5578116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117536461 | Physically Completed | 23490 | 23490 | 2025-06-05 | 2026-03-15
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/5578117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117536615 | Ongoing | 23490 | 23490 | 2025-06-05
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/5578126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128073714 | Approved | 23490 | 0 | 2025-04-13
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/5578137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144397621 | Physically Completed | 23490 | 23229 | 2025-06-12 | 2026-01-10
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/5578138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144397745 | Physically Completed | 23490 | 23490 | 2025-06-05 | 2026-02-28
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/5578139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144397875 | Ongoing | 23490 | 23229 | 2025-07-31
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/5578154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106188753 | Ongoing | 23490 | 23490 | 2025-06-05
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/5681927 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144391881 | Ongoing | 23490 | 23490 | 2025-08-13
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/5838682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142664690 | Ongoing | 23490 | 23229 | 2025-12-10
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/5838845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128171283 | Ongoing | 23490 | 21924 | 2025-12-10
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/5839385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123891907 | Ongoing | 23490 | 20358 | 2025-12-10
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002045/IF/IAY/619144 — Construction of IAY House -IAY REG. NO. MP3717459 | Completed | 15030 | 15240 | 2017-03-01 | 2018-03-30
BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/118 — मेढबन्‍धान छुन्‍ना / श्रीराम | Completed | 0 | 5300 | 2010-08-05 | 2010-08-05
BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/120 — मेड बन्‍धान कार्य बजरंग / रामसिया प्रजापति | Completed | 22720 | 9400 | 2010-08-05 | 2010-08-05
BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/121 — मेड बन्‍धान कार्य कुल्‍ले / लज्‍जू प्रजापति | Completed | 22423 | 3000 | 2010-08-05 | 2010-08-05
BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/127 — मेढबन्‍धान नेतराम / गुन्‍धारी | Completed | 0 | 1001 | 2009-07-15 | 2009-07-15
BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/128 — मेढबन्‍धान पुनूराम / गुन्‍धारी | Completed | 0 | 1365 | 2009-08-11 | 2009-08-11
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002045/LD/22012034228341 — MAD BANDHAN GANGA SINGH /NARAYAN SINGH | Completed | 52400 | 51198 | 2015-08-26 | 2015-09-16
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002045/LD/22012034228342 — MAD BANDHAN RAKESH/ GYAPRASAD | Completed | 36600 | 36411 | 2015-08-26 | 2015-09-16
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002045/LD/22012034228344 — MAD BANDHAN KAMAL SINGH/ GAJRAJ SINGH | Completed | 17000 | 16854 | 2015-08-26 | 2015-09-16
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002045/LD/22012034228345 — MAD BANDHAN PUTTILAL/BHAGWAN | Completed | 47200 | 46269 | 2015-08-26 | 2015-09-16
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002045/LD/22012034228346 — MAD BANDHAN SARUPE/ MATOLE | Completed | 33400 | 32913 | 2015-08-26 | 2015-09-16
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002045/LD/22012034228347 — MAD BANDHAN RAJESH/ LAKHAN SINGH | Completed | 31200 | 27984 | 2015-08-26 | 2015-09-25
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002045/LD/22012034228348 — MAD BANDHAN PUSHPENDRA SINGH / BALMANT SINGH | Completed | 47200 | 45792 | 2015-08-26 | 2015-09-16
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/22012034238869 — MAD BANDHAN KAMLESH/BENIRAM | Completed | 47200 | 42771 | 2015-12-09 | 2016-01-25
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/22012034238871 — MAD BANDHAN UDAY SINGH/ RATIRAM | Completed | 47200 | 43884 | 2015-12-09 | 2016-01-20
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/22012034238874 — MAD BANDHAN SHIV KUMAR/ RAM SANEHI | Completed | 47200 | 47064 | 2015-12-09 | 2016-01-20
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/22012034239010 — MAD BANDHAN PURAN/NATHURAM | Completed | 47200 | 45951 | 2015-12-09 | 2016-01-20
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/22012034239012 — MAD BANDHAN SHYAMSUNDAR/HARI SINGH | Completed | 47200 | 42771 | 2015-12-09 | 2016-01-20
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/22012034239014 — MAD BANDHAN MAYA DEVI/ MOHANLAL | Completed | 47200 | 45792 | 2015-12-23 | 2016-01-25
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/22012034239016 — MAD BANDHAN MANGLA/ GYAPRASAD | Completed | 47200 | 46269 | 2015-12-09 | 2016-01-20
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/22012034239018 — MAD BANDHAN RAM MOHAN/PRBHU DAYAL | Completed | 47200 | 42930 | 2015-12-09 | 2016-01-20
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/22012034239019 — MAD BANDHAN ULFAT/ RAMAGYA | Completed | 47200 | 46746 | 2015-12-09 | 2016-01-20
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/22012034239022 — MAD BANDHAN GOPINATH/ RAMJU PRASAD | Completed | 47200 | 45792 | 2015-12-09 | 2016-01-20
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/22012034239032 — MAD BANDHAN BEBA VIDHYAVATI/ NATHURAM | Completed | 47200 | 47064 | 2015-12-09 | 2016-01-20
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/22012034243142 — MAD BANDHAN ASHARAM/ SHRI RAM | Completed | 47200 | 46428 | 2015-12-23 | 2016-01-20
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Pebble Bunding / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1702002045/LD/22012034267327 — MED BANDHAN SHIVKUMAR/RADHESHYAM | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Pebble Bunding / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1702002045/LD/22012034268002 — med bandhan sirnam/UJAGAR | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Pebble Bunding / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1702002045/LD/22012034268003 — MED BANDHAN AKHLESH/CHATUREE | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/22012034268004 — MED BANDHANJANAK DULAREE/HAREESINGH | Deleted | 47200 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/22012034268005 — MED BANDHAN MOHAR SINGH/GANGARAM | Deleted | 47200 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Pebble Bunding / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1702002045/LD/22012034269034 — MED BANDHAN GEETA DEVI /LAKHAN | Deleted | 0 | 0 | 2016-01-26
BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/22012034269035 — MED BANDHAN VITOLEE/JAGNNATH | Deleted | 47200 | 0 | 2016-09-07
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Pebble Bunding / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1702002045/LD/22012034269036 — MED BANDHN YOGENDRASINGH/HAREESINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002045/LD/22012034269037 — MED BANDHAN TATEE/MEVARAM | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002045/LD/22012034269038 — med bandh SUDAMA/SUKHVASEE | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002045/LD/22012034269039 — shrikisan/gyadeen | Deleted | 0 | 0 | 2016-01-26
BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002045/LD/22012034292046 — MED BANDHAN JEASIRAM / DOLATRAM | Deleted | 47200 | 0 | 2016-09-07
BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/22012034292047 — MED BANDHAN OMPRAKASH/BABURAM | Deleted | 0 | 0 | 2016-06-01
BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002045/LD/22012034292048 — MED BANDHAN OMPRAKASH/BABURAM | Deleted | 47200 | 0 | 2016-09-07
BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/22012034292049 — MED BANDHAN BALVEER/JASMAND | Deleted | 47200 | 0 | 2016-09-07
BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/22012034292050 — MED BANDHAN JAYKARAN/BHOLASINGH | Deleted | 47200 | 0 | 2016-09-07
BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/22012034292054 — MED BANDHAN TEKRAM/CHATUREE | Deleted | 47200 | 0 | 2016-06-01
BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/22012034292069 — MED BANDHAN RAMSINGH/DHANEERAM | Deleted | 47200 | 0 | 2016-06-01
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1702002045/LD/22012034534890 — naveen charagah nirman gusing | Ongoing | 792213.45 | 32262 | 2021-03-03
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002045/LD/22012034553022 — med bandhan nirman dunnuprasad / bhulai | Closed | 23777.99 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002045/LD/22012034553024 — med bandhan nirman phoolan devi / pannalal | Completed | 24545.03 | 20844 | 2021-05-12 | 2021-10-09
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002045/LD/22012034553025 — med bandhan nirman shyama devi / ramgovind | Closed | 24238.22 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002045/LD/22012034553027 — med bandhan nirman munni / shankar | Completed | 23624.59 | 22002 | 2021-05-12 | 2021-10-09
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002045/LD/22012034553028 — med bandhan nirman lakan / bhulai | Completed | 23777.99 | 17370 | 2021-06-02 | 2021-11-18
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002045/LD/22012034553029 — med bandhan nirman suresh / chhote lal | Completed | 24084.81 | 20844 | 2021-05-12 | 2021-11-18
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002045/LD/22012034553030 — med bandhan nirman prembabu / lalaram | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002045/LD/22012034553031 — med bandhan nirman kamlesh / shriram | Completed | 23931.41 | 20844 | 2021-05-12 | 2021-11-18
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002045/LD/22012034553032 — med bandhan nirman baliram /chhaviram | Completed | 23471.19 | 8106 | 2021-06-02 | 2022-01-09
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002045/LD/22012034553033 — med bandhan nirman yogi / kunji | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002045/LD/22012034553034 — med bandhan nirman tej singh / shankar | Completed | 24545.03 | 20844 | 2021-05-12 | 2021-10-09
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002045/LD/22012034553035 — med bandhan nirman prabhash / phojdar | Completed | 24238.22 | 20844 | 2021-05-12 | 2021-10-09
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002045/LD/22012034553037 — med bandhan nirman pradeep / nathuram | Completed | 23624.59 | 18528 | 2021-05-12 | 2021-11-18
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002045/LD/22012034553038 — med bandhan nirman asharam / ajjudhi | Completed | 23624.59 | 23160 | 2021-05-12 | 2021-10-09
BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/328 — शमशान घाट एवं पहुंचमार्ग मिटटी कार्य गुंसीग | Completed | 393000 | 380475 | 2012-02-06 | 2014-04-30
BHIND | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/3799417694 — MAD BANDHAN GUDDI BAI / NATHURAM | Completed | 25000 | 20148 | 2014-01-01 | 2014-01-09
BHIND | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/3799417696 — MAD BANDHAN DASHRATH / RAGHUVEER | Completed | 25000 | 22338 | 2014-01-01 | 2014-01-09
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002045/LD/3799417697 — MAD BANDHAN RAMVATI / RAJ BAHADUR | Completed | 25000 | 22046 | 2014-01-01 | 2014-02-11
BHIND | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/3799419019 — MAD BHANDHAN SHEE RAM JI / CHANDRABHAN | Completed | 25000 | 18396 | 2014-01-08 | 2014-01-29
BHIND | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002045/LD/3799419021 — MAD BANDHAN KASHIRAM / KUNJILAL | Completed | 25000 | 20148 | 2014-01-08 | 2014-01-29
BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002045/LD/9926714019 — MAD BANDHAN BUDDH SINGH / PURAN SINGH | Completed | 43320 | 38308 | 2014-09-03 | 2015-04-28
BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002045/LD/9926714020 — MED BANDHAN RAM AVTAR / RAM SHANKAR | Completed | 43300 | 35482 | 2014-09-03 | 2015-04-28
BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002045/LD/9926714021 — MED BANDHAN RANVEER SINGH / CHTUR SINGH | Completed | 43300 | 36110 | 2014-09-03 | 2015-04-28
BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002045/LD/9926714033 — MED BANDHAN RAJBAHADUR / NARAYAN | Completed | 43300 | 33284 | 2014-09-03 | 2015-04-28
BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002045/LD/9926714034 — MED BANDHAN RAMSINGH / DHANIRAM | Completed | 43300 | 40663 | 2014-09-03 | 2015-04-28
BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002045/LD/9926714035 — MED BANDHAN KIRAT PRASAD / BHAGWAN | Completed | 43300 | 36738 | 2014-09-03 | 2015-04-28
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002045/OP/9425888836 — CATTLE PROTECTION WALL GUSEENG | Completed | 645800 | 562373 | 2016-01-27 | 2018-08-11
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002045/OP/9425888837 — PULIA NIRMAN BAGIA KE PASS GUSEENG | Completed | 349900 | 264152 | 2016-01-27 | 2018-12-28
BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002045/OP/9425892175 — SHANTIDHAM NIRMAN GRAM GADI SULTAN | Completed | 245000 | 242394.2 | 2017-02-08 | 2022-10-04
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002045/PG/22012034365784 — PLAY GROUND | Deleted | 0 | 0 | 2017-10-02
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002045/PG/22012034366324 — play ground | Closed | 0 | 0 | 2017-10-02
BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002045/PG/9425893506 — PLAY GROUND GOVT. HIGH SCHOOL KE SAMNE GUSING | Completed | 353000 | 286889 | 2017-02-08 | 2018-12-25
BHIND | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002045/RC/22 — सी0सी0 रोड रामसेवक जाटव के मकान से पेवली शहर के मोड तक | Completed | 233501 | 59512.21 | 2012-03-21 | 2013-03-27
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002045/RC/22012034160800 — C.C.ROAD CHUNNA PRAJAPATI KE MAKAN SE MEGHSINGH KE | Completed | 132200 | 124450.5 | 2013-03-14 | 2013-06-18
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002045/RC/22012034168188 — C.C.ROAD BHURE JATAV KE MAKAN SE VISHWNATH KE MAKA | Completed | 66409 | 61141 | 2013-06-12 | 2013-07-10
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002045/RC/22012034183680 — ANTRIK ROAD GUSING SE BAGIA TAK | Completed | 493800 | 411156 | 2013-09-25 | 2015-06-15
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002045/RC/22012034204115 — C.C.ROAD TEKRAM KE MAKAN SE BALVEER BAGHEL KE MAKA | Completed | 152963 | 145753.8 | 2014-02-12 | 2014-06-04
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002045/RC/22012034204117 — C.C.ROAD SHA.PRI. SCHOOL SE BRHAM PRAKASH KE MAKAN | Completed | 152963 | 145282.8 | 2014-02-12 | 2014-07-20
BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002045/RC/22012034227690 — C.C.ROAD RAJ BAHADUR KE MAKAN SE SURENDRA SINGH CHAUHAN KE MAKAN TAK | Deleted | 164465 | 0 | 2014-08-20
BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002045/RC/22012034321654 — C.C.ROAD RAJU JATAV KE DWAR SE BHARAT JATAV KE MAKAN KI AUR | Completed | 131000 | 85764 | 2017-02-01 | 2017-11-15
BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002045/RC/22012034330005 — SUDUR SADAK KARYA MAJRA PADWARI SE PULEH TAK | Completed | 1500000 | 1168954.73 | 2017-03-08 | 2019-01-17
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002045/RC/22012034350562 — CC ROAD AND NALI NIRMAN PRAHLAD KE MAKAN SE RAMBARAN BAGHEL KE MAKAN KI OR GUSING | Completed | 88500 | 80744 | 2017-08-30 | 2019-01-25
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002045/RC/22012034351372 — CC ROAD HANUMAN JI KE MANDIR SE H S SCHOOL KI OR | Deleted | 88500 | 0 | 2017-09-06
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002045/RC/22012034365398 — CC ROAD DEVENDRA RAJAWAT KE MAKAN SE RAMLAKHAN BAGHEL KE DWAR KI OR THAKUR MUHALLA BAGIYA | Completed | 177000 | 166008 | 2017-11-01 | 2018-12-25
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002045/RC/22012034442712 — cc road | Closed | 0 | 0 | 2019-01-26
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002045/RC/22012034449016 — C.C.Road Nirman mohar singh chauhan ke ghar se pevali ki or | Completed | 60000 | 59846 | 2019-03-06 | 2019-08-20
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002045/RC/22012034479459 — C.C.Road Nirman Ghanshyam ke dwar se panchayat bhavan ki or Gusing | Completed | 124000 | 122496 | 2019-11-06 | 2020-02-05
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002045/RC/22012034526756 — c.c.road nirman mahendrapal ke makan se himmat singh ke makan ki or | Completed | 31500 | 29640 | 2020-09-23 | 2021-10-09
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1702002045/RC/22012034526786 — c.c.road marmmat kary ashok pandit ke makan se basanti baghel ke makan ki or | Completed | 43200 | 42180 | 2020-07-22 | 2021-10-09
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002045/RC/22012034531954 — sudor sadak nirman gusing se pevali ki or | Completed | 1255081.9 | 774688 | 2020-08-20 | 2023-09-18
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002045/RC/22012034531956 — sudor sadak nirman damar road se gau shala ki or | Closed | 0 | 0 | 2020-04-14
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002045/RC/22012034554216 — c.c.road nirman mohar singh chauhan ghar se pradeep ke ghar ki or gusing | Completed | 76800 | 61560 | 2021-01-06 | 2022-02-09
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1702002045/RC/22012034561329 — c.c.road marmmat kary kraparam ke ghar se damar road ki or gadi sultan | Completed | 43000 | 40704 | 2021-03-03 | 2022-07-04
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002045/RC/22012034618669 — CC ROAD MOOLPAL KE ADDA SE HOM SINGH KE KHET KI OR | Closed | 191000 | 0 | 2022-08-16
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002045/RC/22012034621690 — CC ROAD RAMAVTAR KE GHAR SE RAMKISHOR KE GHAR HOTE HUYE TIRAHE TAK | Completed | 144000 | 128928 | 2022-11-30 | 2023-08-17
BHIND | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002045/RC/7 — मिटटी बजरीकरण पंहुचमार्ग राजेश चौहान के खेत से डिल्‍लीराम के खेत की ओर | Completed | 457000 | 93020 | 2010-09-06 | 2010-09-06
BHIND | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002045/RC/8 — Not Known1 | Completed | 0 | 130038 | 2010-11-08 | 2011-08-06
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702002045/RS/22012034640196 — Saamudaayik Svachchhata Parisar gusing | Completed | 43000 | 41688 | 2022-02-09 | 2022-08-05
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002045/RS/22012034670765 — SAMUDAYIK SOKHTA NEAR GOV.HIGH SCHOOL GUSING | Completed | 10000 | 9792 | 2022-12-15 | 2023-03-02
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002045/RS/22012034670782 — SAMUDAYIK SOKHTA NEAR Anganwadi BHAVAN KE PASH GUSING | Completed | 10000 | 9792 | 2022-12-22 | 2023-03-02
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002045/RS/22012034670784 — SAMUDAYIK SOKHTA NEAR gau shala parisar GUSING | Completed | 10000 | 9792 | 2022-12-22 | 2023-03-02
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002045/RS/22012034670789 — SAMUDAYIK SOKHTA NEAR Gov.Middle School GUSING | Completed | 10000 | 9792 | 2022-12-30 | 2023-03-02
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002045/RS/22012034670792 — SAMUDAYIK SOKHTA NEAR panchayat bhawan KE PASH GUSING | Closed | 10000 | 0 | 2022-10-06
BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002045/WC/22012034293715 — POKHARA TALAB KA GAHRIKARAN GUSING | Deleted | 86000 | 0 | 2016-05-25
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702002045/WC/22012034325287 — talab gaharikaran pokhara talab | Completed | 91200 | 84280 | 2017-05-17 | 2017-12-25
BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002045/WC/22012034355710 — BORI BANDHAN KARYA NALE PER | Completed | 22000 | 12556 | 2017-09-27 | 2018-08-11
BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002045/WC/22012034440648 — naveen talab nirman bagiya ke pas gusing | Ongoing | 1068000 | 669708 | 2019-03-06
BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002045/WC/22012034502958 — TALAB GAHRIKARAN PADWARI KE PASS | Closed | 0 | 0 | 2019-08-15
BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002045/WC/22012034502959 — TALAB GAHRIKARAN SHIVJI KE GHAR KE PASS | Closed | 0 | 0 | 2019-08-15
BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002045/WC/22012034502960 — TALAB GAHRIKARAN ROAD KINARE GADISULTAN | Closed | 0 | 0 | 2019-08-15
BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002045/WC/22012034502961 — TALAB GAHRIKARAN GUPHA KE PASS | Closed | 0 | 0 | 2019-08-15
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002045/WC/22012034548065 — TALAB MARMMAT KARY GAU SHALA KE PAS PADVARI | Completed | 1182414.79 | 705912 | 2020-05-20 | 2021-11-18
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002045/WC/22012034551712 — TALAB MARMMAT KARY GUFA KE PAS GADI SULTAN | Completed | 684678.66 | 279300 | 2020-06-03 | 2022-10-11
BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002045/WC/22012034551714 — TALAB MARMMAT KARY GAW KE PAS GADI SULTAN | Closed | 0 | 0 | 2019-08-16
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002045/WC/22012035025837 — amrat sarovar renovetion dung tank nirman shantidham ke pas | Closed | 0 | 0 | 2022-10-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002045/WH/22012034449032 — talav marmmat kary ramkishor ke ghar ke pas bhag me gusingh | Closed | 0 | 0 | 2021-04-14
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002060/IF/IAY/201465 — Construction of IAY House -IAY REG. NO. MP-02-002-060-003/39 | Approved | 23490 | 0 | 2016-02-14
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002060/IF/IAY/264701 — Construction of IAY House -IAY REG. NO. MP3839296 | Completed | 15030 | 15318 | 2017-03-01 | 2018-08-11