## Work List
Exported on: 2026-09-07 16:54:25
Filters applied:
Data source: MGNREGA
District: BHIND
Block: All
Panchayat: SAGARA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002051/AV/22012034354590 — AGANWADI BHANVAN NIRMAN KARYA GULAL PURA SAGARA | Completed | 330000 | 294390 | 2017-08-02 | 2020-05-10
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002051/AV/22012034392105 — SHANTI DHAM NIRMAN KARYA GULALPURA | Completed | 180000 | 176732 | 2018-12-26 | 2019-09-22
BHIND | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1702002051/AV/22012034469399 — GAUSHALA NIRAMAN KARYA SAGARA | Completed | 2771628.29 | 2751092.82 | 2019-11-20 | 2020-11-18
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002051/AV/22012034511406 — shantidham nirman karya sagara chodari | Closed | 0 | 0 | 2020-04-01
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002051/AV/22012034512846 — shantidham chaudhari thok sagara | Completed | 283566.25 | 274086 | 2020-09-06 | 2022-11-02
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1702002051/AV/22012034543690 — EXTRA PASHU SHED NIRMAN KARYA GAUSHALA | Completed | 942306.59 | 937316 | 2021-03-03 | 2022-11-02
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Stabilization Pond for Community / Construction of Stabilization Pond for Community | Construction of Tank | 1702002051/AV/22012034568344 — SEGREGATION SHED NIRMAN SAGARA | Closed | 37000 | 0 | 2021-04-14
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002051/AV/4108 — Aanganbadi/Other Rural Infrastructure,SAGARA | Completed | 330000 | 290610 | 2015-12-09 | 2018-07-30
BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002051/AV/5865 — SHAMSHANGHAT NIRMAN WORK SAGARA | Deleted | 288823 | 0 | 2016-10-12
BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002051/AV/7793 — SAMSHAN GHAT NIRMAN KARYA SAGARA | Completed | 180000 | 177684 | 2017-03-08 | 2018-02-14
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002051/IF/22012034352326 — PODHAROPAN KARYA MANDIR EVAM SHALABHAVAN SAGARA | Completed | 335000 | 16064 | 2017-06-27 | 2019-01-15
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002051/IF/22012034354093 — PODHAROPAN KARYA MANDIR SHAMSHANGHAT SAGAR | Suspended | 335000 | 0 | 2017-06-27
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1702002051/IF/22012034758595 — MED BANDHAN KARYA SHISHUPAL SINGH | Completed | 21000.23 | 18528 | 2021-06-03 | 2021-12-15
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1702002051/IF/22012034758614 — MED BANDHAN KARYA JAGATPAL KE KHET PAR | Closed | 22400.3 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002051/IF/22012034807880 — med bandhan karya bhanupratap | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1702002051/IF/22012034807884 — med bandhan karya kailash singh | Closed | 0 | 0 | 2021-04-14
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002051/IF/22012035017502 — KHET TALAB BHANUPRAT KE KHET PAR SAGARA | Closed | 0 | 0 | 2022-08-15
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1702002051/IF/22012035043774 — KHET TALAB NIRMAN KARYA ASHOK S/O DHAVAL SINGH | Closed | 0 | 0 | 2022-10-02
BHIND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1702002051/IF/22012035460314 — kheat talab nirman ravindra singh ramkumar singh ke kheat par gp sagara | Ongoing | 147621.16 | 1566 | 2025-05-12
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002051/IF/22012035530436 — kheat talab nirman ganesh singh kheat par gp sagara | Approved | 147621.16 | 0 | 2025-04-14
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993693273 — CATTLE SHED NIRMAN USHA DEVI SAGARA | Deleted | 115900 | 0 | 2015-12-09
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993693735 — CATTLE SHED NIRMAN BRAJMOHAN SAGARA | Deleted | 115900 | 0 | 2015-12-09
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993695937 — PASHU SHED NIRMAN GEETA DEVI SAGARA | Deleted | 115900 | 0 | 2015-12-16
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728550 — PASHU SHED NIRMAN KEDAR SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728554 — PASHU SHED NIRMAN INDAL | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728556 — PASHU SHED NIRMAN JAGPAL | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728557 — PASHU SHED NIRMAN MUNNA SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728558 — PASHU SHED NIRMAN DEVENDRA SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728559 — PASHU SHED NIRMAN SHRINATH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728560 — PASHU SHED NIRMAN MUNNI LAL | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728561 — PASHU SHED NIRMAN AVADESH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728562 — PASHU SHED NIRMAN MUNNA SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728563 — PASHU SHED NIRMAN VITOLI | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728564 — PASHU SHED NIRMAN DEVENDRA SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728565 — PASHU SHED NIRMAN RAMKUMAR | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728566 — PASHU SHED NIRMAN DHURAV SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728567 — PASHU SHED NIRMAN BRAJENDRA SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728568 — PASHU SHED NIRMAN TEJBAHADUR SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728569 — PASHU SHED NIRMAN MAKARAND SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728570 — PASHU SHED NIRMAN RAMBAHADUR SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728571 — PASHU SHED NIRMAN RAMBARAN | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728572 — PASHU SHED NIRMAN CHHOTU | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728573 — PASHU SHED NIRMAN KISHUN SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728574 — PASHU SHED NIRMAN PRABHUDAYAL | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728575 — PASHU SHED NIRMAN KARAN SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728576 — PASHU SHED NIRMAN RAMU | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728577 — PASHU SHED NIRMAN MOORAT | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728578 — PASHU SHED NIRMAN SANDHYA | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728579 — PASHU SHED NIRMAN RAMBABU | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728580 — PASHU SHED NIRMAN JAYENDRA | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728581 — PASHU SHED NIRMAN KEDAR | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002051/IF/9993728582 — PASHU SHED NIRMAN RAJOO | Deleted | 0 | 0 | 2016-01-26
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/133941 — Construction of IAY House -IAY REG. NO. MP-02-002-051-001/223 | Completed | 14310 | 13176 | 2016-06-08 | 2017-12-10
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/133942 — Construction of IAY House -IAY REG. NO. MP-02-002-051-001/224 | Completed | 14310 | 15180 | 2016-06-08 | 2017-12-10
BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/1871277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4177294 | Completed | 15660 | 15660 | 2018-09-12 | 2019-01-09
BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/1872825 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5318276 | Completed | 15660 | 15660 | 2018-08-09 | 2019-01-09
BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/1872949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5574030 | Completed | 15660 | 15486 | 2018-08-09 | 2019-02-01
BHIND | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/2126634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4688227 | Approved | 23490 | 0 | 2019-06-12
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/274549 — Construction of IAY House -IAY REG. NO. MP3198675 | Completed | 15030 | 15360 | 2017-02-01 | 2018-02-28
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/309892 — Construction of IAY House -IAY REG. NO. MP1047904 | Completed | 15030 | 13084 | 2017-09-06 | 2018-05-01
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/3815107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118617105 | Physically Completed | 18360 | 11964 | 2022-12-12 | 2024-11-21
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/3848864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127452157 | Physically Completed | 18360 | 9792 | 2022-08-25 | 2024-11-21
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/4232585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126461070 | Physically Completed | 18360 | 17982 | 2022-12-16 | 2024-11-21
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/4377337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127648930 | Physically Completed | 18360 | 17982 | 2022-12-12 | 2024-11-21
BHIND | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/4379156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118598792 | Physically Completed | 18360 | 6630 | 2023-09-11 | 2024-11-21
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/4379756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118590985 | Ongoing | 23490 | 15300 | 2022-12-16
BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/4389492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127776333 | Physically Completed | 18360 | 2916 | 2024-07-06 | 2024-11-21
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/465608 — Construction of IAY House -IAY REG. NO. MP1766893 | Completed | 15030 | 15360 | 2017-02-01 | 2017-12-10
BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/4758201 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118593090 | Ongoing | 23490 | 14661 | 2024-11-08
BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/4780144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127647616 | Ongoing | 23490 | 11988 | 2024-12-07
BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/4780147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127648409 | Ongoing | 23490 | 21168 | 2025-01-28
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/755845 — Construction of IAY House -IAY REG. NO. MP2769856 | Completed | 15030 | 2064 | 2017-08-09 | 2018-05-01
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/766066 — Construction of IAY House -IAY REG. NO. MP3238055 | Completed | 15030 | 15480 | 2017-05-03 | 2017-12-10
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/771609 — Construction of IAY House -IAY REG. NO. MP3507719 | Completed | 15030 | 15480 | 2017-05-03 | 2018-02-08
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/778893 — Construction of IAY House -IAY REG. NO. MP3929433 | Completed | 15030 | 15480 | 2017-06-10 | 2018-03-30
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/779429 — Construction of IAY House -IAY REG. NO. MP3961760 | Completed | 15030 | 14964 | 2017-08-30 | 2018-03-30
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002051/IF/IAY/82323 — Construction of IAY House -IAY REG. NO. MP-02-002-051-001/71 | Completed | 14310 | 11204 | 2016-08-02 | 2018-07-30
BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/180 — मेढबंधान तहसीलदार /रामलखन | Completed | 14000 | 8564 | 2010-08-06 | 2011-05-09
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034247252 — MED BANDHAN NIRMAN RAJENDRA SINGH | Deleted | 41400 | 0 | 2015-12-30
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034247257 — MED BANDHAN NIRMAN DEVENDRA SINGH | Deleted | 24600 | 0 | 2015-12-30
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034247260 — MED BANDHAN NIRMAN NARESH SINGH | Deleted | 34700 | 0 | 2015-12-30
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034247262 — MED BANDHAN NIRMAN RAMBABU SINGH | Deleted | 27900 | 0 | 2015-12-30
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263373 — MED BANDHAN NIRMAN OMKAR SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263374 — MED BANDHAN NIRMAN MUNNI | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263375 — MED BANDHAN NIRMAN KALLU SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263376 — MED BANDHAN NIRMAN PUSHPENDRA SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263377 — MED BANDHAN NIRMAN HIMMAT SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263378 — MED BANDHAN NIRMAN MOHAR SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263379 — MED BANDHAN NIRMAN RAMKISHOR SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263380 — MED BANDHAN NIRMAN PRATHIVI SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263381 — MED BANDHAN NIRMAN KISHUN SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263382 — MED BANDHAN NIRMAN MADHO SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263383 — MED BANDHAN NIRMAN NATHOO SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263384 — MED BANDHAN NIRMAN RAMNARAYAN | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263385 — MED BANDHAN NIRMAN SANJAY | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263386 — MED BANDHAN NIRMAN RAJARAM | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263387 — MED BANDHAN NIRMAN TULARAM | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263388 — MED BANDHAN NIRMAN BABU | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263389 — MED BANDHAN NIRMAN MAHENDDRA | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263390 — MED BANDHAN NIRMAN CHINTI | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263391 — MED BANDHAN NIRMAN RAMESHWAR | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263392 — MED BANDHAN NIRMAN JAGADISH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263393 — MED BANDHAN NIRMAN RAMKUMAR | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263394 — MED BANDHAN NIRMAN SHER SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263395 — MED BANDHAN NIRMAN KEDAR | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263396 — MED BANDHAN NIRMAN AMAR SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263397 — MED BANDHAN NIRMAN PRAHALAD | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263398 — MED BANDHAN NIRMAN RAMBABU | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263399 — MED BANDHAN NIRMAN SHIV SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263400 — MED BANDHAN NIRMAN NARHARI | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263401 — MED BANDHAN NIRMAN RAJENDRA SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263402 — MED BANDHAN NIRMAN NARESH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263403 — MED BANDHAN NIRMAN DEVENDRA | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263404 — MED BANDHAN NIRMAN MUNNA | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263405 — MED BANDHAN NIRMAN SANJAY | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263406 — MED BANDHAN NIRMAN BHANUPRATAP | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263407 — MED BANDHAN NIRMAN RAVINDRA | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263408 — MED BANDHAN NIRMAN BALVEER | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263409 — MED BANDHAN NIRMAN CHHOTE SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263410 — MED BANDHAN NIRMAN HAVALDAR | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263411 — MED BANDHAN NIRMAN RAJENDRA | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263412 — MED BANDHAN NIRMAN SIROMAN | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263413 — MED BANDHAN NIRMAN MUNNI | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263414 — MED BANDHAN NIRMAN MUNNA SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263415 — MED BANDHAN NIRMAN NARENDRA SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263416 — MED BANDHAN NIRMAN RAJU SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263417 — MED BANDHAN NIRMAN BHAN SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263418 — MED BANDHAN NIRMAN NIRAJAN SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263419 — MED BANDHAN NIRMAN MAKARAND | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263420 — MED BANDHAN NIRMAN JAGESHWAR | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263421 — MED BANDHAN NIRMAN LALLU | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263422 — MED BANDHAN NIRMAN CHANDRABHAN | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263423 — MED BANDHAN NIRMAN RAMBABU | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263424 — MED BANDHAN NIRMAN MOTI | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263425 — MED BANDHAN NIRMAN GUNDI | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263426 — MED BANDHAN NIRMAN BHAGWAN | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263427 — MED BANDHAN NIRMAN RAMDHAN | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263428 — MED BANDHAN NIRMAN JAGDISH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263429 — MED BANDHAN NIRMAN OMKAR | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263430 — MED BANDHAN NIRMAN RAMLAKHAN | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263431 — MED BANDHAN NIRMAN JAGRAM | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263432 — MED BANDHAN ANNATRAM | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263433 — MED BANDHAN NIRMAN CHANDAN | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263434 — MED BANDHAN NIRMAN BACHCHU | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263435 — MED BANDHAN NIRMAN KAILASHI | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263436 — MED BANDHAN JASMANT | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263437 — MED BANDHAN NIRMAN MANSHARAM | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263438 — MED BANDHAN NIRMAN SHRIRAM | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263439 — MED BANDHAN NIRMAN RAMBHAROSE PATWA | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263440 — MED BANDHAN NIRMAN MUNNI PATWA | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263441 — MED BANDHAN NIRMAN RAMAUTAR | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263442 — MED BANDHAN NIRMAN PRABHUDAYAL | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263443 — MED BANDHAN NIRMAN SAHAB SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263444 — MED BANDHAN NIRMAN MUNNILAL | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263445 — MED BANDHAN NIRMAN LAJJARAM | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263446 — MED BANDHAN NIRMAN MATADEEN | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263447 — MED BANDHAN NIRMAN MUNSHI | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263448 — MED BANDHAN NIRMAN HARGYAN | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034263449 — MED BANDHAN NIRMAN NADARI | Deleted | 0 | 0 | 2016-01-26
BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1702002051/LD/22012034474489 — CHARAGAHA NIRMAN KARYA GAUSHALA SAGARA | Closed | 0 | 0 | 2019-10-02
BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1702002051/LD/22012034474490 — CHARAGAHA NIRMAN KARYA GAUSHALA SAGARA | Closed | 0 | 0 | 2019-10-02
BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702002051/LD/22012034474687 — CHARAGAHA NIRMAN KARYA GAUSHALA SAGARA | Closed | 0 | 0 | 2019-10-02
BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1702002051/LD/22012034476313 — CHARAGAHA NIRMAN KARYA GAUSHALA SAGARA | Closed | 0 | 0 | 2019-10-02
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1702002051/LD/22012034478007 — charagaha nirman karya gaushala sagara | Ongoing | 750924.49 | 218398 | 2020-05-28
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002051/LD/22012034478555 — CHARAGAH GAUSHALA SAGRA | Deleted | 0 | 0 | 2020-04-14
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034521608 — med bandhan karya ranjendra singh s/o dalganjan singh sagara | Completed | 30754.54 | 26690 | 2020-09-24 | 2021-07-18
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034521609 — med bandhan karya ranjsukhpal singh s/o raghuveer singh sagara | Closed | 0 | 0 | 2020-04-01
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/22012034521610 — med bandhan karya bhanupratap singh s/o jhamman singh sagara | Closed | 0 | 0 | 2020-04-01
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Dev of Silvipasture Grassslands for Community / Development of Silvipasture Grassslands for Community | Grass Land Development | 1702002051/LD/22012034551246 — CHARAGHA GAUSHALA SAGARA | Deleted | 0 | 0 | 2021-04-01
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Dev of Silvipasture Grassslands for Community / Development of Silvipasture Grassslands for Community | Grass Land Development | 1702002051/LD/22012034553648 — CHARAGHA GAUSHAL SAGARA | Closed | 0 | 0 | 2021-04-01
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1702002051/LD/22012034557300 — VERMI COMPOSPIT GAUSHLA KE PASS | Closed | 0 | 0 | 2021-04-14
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1702002051/LD/22012034593737 — BRAKSHAROPAN KARAY SHAHID KARAN SINGH PARK SAGARA | Closed | 56725.4 | 0 | 2023-04-14
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1702002051/LD/22012034938780 — samodayak posarn vitaka nirman gousalla ke pichhe | Closed | 478005.61 | 0 | 2024-01-26
BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/257 — मेड बन्‍धान कार्य दलगंजन / लल्‍लू सिह | Deleted | 26000 | 0 | 2010-07-30
BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/258 — मेडबन्‍धान कार्य स्‍वयंवर सिंह / सूवेदार सिंह | Deleted | 15600 | 0 | 2010-12-04
BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002051/LD/262 — मेड बन्‍धान कार्य कन्‍हाई / तेजपाल हरिजन | Deleted | 21100 | 0 | 2011-01-18
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002051/OP/9425889572 — NALA NIRMAN MUNNI KE DWAR SE PRATHIMIK SHALA TAK | Deleted | 0 | 0 | 2016-01-26
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002051/PG/9425888454 — KHEL MAIDAN SAGARA | Completed | 186600 | 73272 | 2017-06-06 | 2019-12-01
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034161490 — C.C.ROAD RAMHET AND RAJU KE DWAR SE KHAD KI TARAF | Completed | 119300 | 118361 | 2014-03-05 | 2016-01-21
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034161492 — C.C.ROAD JARJODHAN KE DWAR SE MANSUKH MEHTAR KE DW | Completed | 125900 | 128686 | 2014-03-05 | 2016-01-20
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034161497 — C.C.ROAD JAGMOHAN KE DWAR SE ATARSINGH KE DWAR KI TARAF | Deleted | 0 | 0 | 2012-10-02
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034161498 — C.C.ROAD JAGMOHAN KE DWAR SE ATARSINGH KE DWAR KI | Completed | 136500 | 110843 | 2014-03-05 | 2016-01-20
BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034223567 — C.C.ROAD SHIVNARAYAN KE DWAR SE JAGDISH SURTAN KE | Deleted | 160106 | 0 | 2014-04-14
BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034223568 — C.C.ROAD KUNWA SE RAJOLE KE DWAR SE HOKAR MATA MAN | Deleted | 133421 | 0 | 2014-04-14
BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034223569 — C.C.ROAD KEWAL KE DWAR SE PANI KI TANKI KI AUR | Deleted | 160106 | 0 | 2014-04-14
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034284032 — CC ROAD NATHU KE DWAR SE PRABHU SE HOKAR RAJU KE DWAR TAK | Completed | 110667 | 98951 | 2015-09-09 | 2017-07-06
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034294830 — CC ROAD RAJENDRA KE DARBAJE SE BHAIRO KE DARBAJE HOKAR SODIN KE DARBAJE TAK GULALPURA | Completed | 80546 | 74783 | 2016-01-06 | 2016-05-17
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034303875 — CC ROAD PUSHPENDRA KE DARVAJE SE BIRBAL KE DARWAJE TAK | Completed | 40115 | 35955 | 2016-03-23 | 2017-07-06
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034306424 — CC ROAD NIRMAN SHRILAL KE DWAR SE JAMADAR MEHATAR KE DWAR TAK | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034306426 — CC ROAD NIRMAN AGANWADI SE NARESH KE DWAR TAK | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034306427 — CC ROAD NIRMAN MAIN ROAD SE JAIHIND KE DWAR TAK | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034306428 — CC ROAD NIRMAN MAIN ROAD SE JANDEL KE DWAR TAK | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034306429 — CC ROAD NIRMAN RAMVEER KE DARWAJE SE NADARI KE DARWAJE TAK | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034306430 — CC ROAD NIRMAN MANSHUKH MEHATAR KE DWAR SE MUKTI DHAM TAK | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034306431 — CC ROAD NIRMAN PANCHYAT BHAVAN SE AGANWADI TAK | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034306433 — CC ROAD NIRMAN RAMBIHARI KE DWAR SE BABU SINGH KE DWAR TAK NADRI KE DWAR HOKAR | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034306434 — CC ROAD NIRMAN MANSHUKH JAMADAR KE DWAR SE NARESH SINGH KE DWAR HOKAR PRATHMI BALAK SHALA TAK | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034306436 — CC ROAD NIRMAN MAIN ROAD KARAN SINGH SHAHID PARK KE SAMANE SE BABBLU KE GODA TAK | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034306437 — CC ROAD NIRMAN SIYALAL KE DWAR SE RAMBHAROSE KE DWAR TAK | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034306438 — CC ROAD NIRMAN MAIN ROAD SE OJHA COLLONY HOKAR RAJVEER KE DWAR TAK | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034306439 — CC ROAD NIRMAN TILLU URF RAGHVENDRA SINGH KE DWAR SE TIKET COLLONY TAK | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034306440 — CC ROAD NIRMAN VED SINGH KE DWAR SE RAJOLE KE DWAR TAK GULALPURA | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034306442 — CC ROAD NIRMAN JAIVEER KE DWAR SE DALVEER KE GODA KE DWAR HOKAR NADARI KE DWAR TAK | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034306444 — CC ROAD NIRMAN SHANKARJI KE MANDIR HOKAR HARVILAS FOJI KE DWAR HOKAR MATADEEN KE HEDPAMPU TAK | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034306445 — CC ROAD NIRMAN DR. ABHILAKH KE DWAR SE POORV SARPANCH RAMRATAN KE DWAR TAK | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034306447 — CC ROAD NIRMAN MAIN ROAD SE POORV SARPANCH RAVINDRA KE DWAR TAK | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034306449 — CC ROAD NIRMAN BALVEER KE DWAR SE RAMCHARAN KE DWAR KHHARAIYA TAK | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002051/RC/22012034306460 — MITTI SADAK NIRMAN PANCHYAT BHAVAN SE AGE MAIN ROAD KI AUR HARIJAN THOK | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002051/RC/22012034306463 — MITTI SADAK NIRMAN PANCHYAT BHAVAN SE AGE MAIN ROAD SE LEKAR TAL KI AUR SAGARA BOODI MATA TAK | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002051/RC/22012034306465 — MITTI SADAK NIRMAN GULALPURA SE LEKAAR HAR KI AUR | Deleted | 0 | 0 | 2016-01-26
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034348101 — CC ROAD NIRMAN AGANWADI SE PRIMARY SCHOOL SE HOTE HUE NARESH KE GHAR KI AUR | Completed | 80000 | 78432 | 2017-08-02 | 2018-02-14
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034349081 — CC ROAD NIRMAN BALVEER KE DWAR SE MANSUKH MEHATAR KE DWAR TAK SAGARA | Completed | 19470 | 18576 | 2017-09-06 | 2018-02-14
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034349535 — CC ROAD NIRMAN SHAHID KARAN SINGH PARK SE KEVAL BALMIK KE DWAR TAK SAGARA | Completed | 57968 | 52632 | 2017-10-25 | 2018-03-30
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034350172 — CC ROAD NIRMAN KARYA RAMBARAN KE DARWAJE SE NADARI HOKAR BABU KE DARWAJE TAK GULALPURA | Completed | 66375 | 42312 | 2017-08-23 | 2019-06-21
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034362729 — CC ROAD NIRMAN NARESH KE DWAR SE BHAGIRATH KE DWAR HOTE HUYE RAMNIK KE DWAR TAK | Completed | 39832 | 39216 | 2017-10-04 | 2018-02-14
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034364680 — CC ROAD NIRMAN VED SINGH KE DARWAJE SE KARAN SINGH KE DWAR TAK | Completed | 34957 | 34056 | 2017-10-25 | 2018-02-14
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034365518 — CC ROAD NIRMAN KARYA JAGESHWAR KE DWAR SE JAGPAL KE DWAR KI AUR | Completed | 29205 | 31992 | 2017-11-01 | 2018-03-30
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034374424 — CC ROAD | Deleted | 0 | 0 | 2017-10-02
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034378314 — C.C.ROAD NIRMAN PREETAM KE DWAR SE MAEN ROAD RAVINDRA | Completed | 34410 | 28896 | 2018-01-24 | 2019-02-01
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034379029 — CC ROAD NIRMAN PANCHYAT BHAVAN SE MAIN ROAD TAK SAGARA | Completed | 27435 | 26100 | 2018-11-07 | 2019-02-01
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034379034 — CC ROAD NIRMAN CHHOTE OJHA KE DWAR SE AGANWADI HOTE HYE POORAN KE DWAR TAK SAGARA | Completed | 21390 | 24012 | 2018-04-18 | 2019-02-01
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034379038 — CC ROAD NIRMAN KEVAL KE DWAR SE BHADORIYA KE DWAR TAK SAGARA | Completed | 30566 | 24012 | 2018-06-06 | 2019-02-01
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034390055 — CC ROAD NIRMAN LOKENDRA KE PECHHE SE MAIN ROAD JANDEL KE DWAR TAK | Completed | 77190 | 63684 | 2018-09-26 | 2019-02-01
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034390109 — CC ROAD EVAM NALI NIRMAN MAIN ROAD RAJJAN KE DWAR SE JAGDISH KE GHAR KI AUR KHAR GULALPURA | Completed | 30225 | 22968 | 2018-10-17 | 2018-12-30
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034395132 — CC ROAD EVAM NALI NIRMAN HARNARAYAN KE JAGAH SE RAMBARAN KE GHAR KE AGE TAK GULALPURA | Completed | 66030 | 69948 | 2018-10-10 | 2018-12-30
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034396347 — CC ROAD EVAM NALI NIRMAN KARYA JAISHRIRAM KE DWAR SE JAGMOHAN EVAM PANDIT WALI GALI GULALPURA | Completed | 79050 | 82536 | 2019-01-02 | 2019-07-13
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034396348 — CC ROAD EVAM NALIN NIRMAN KARYA BABU KE DWAR SE DR. KE DWAR TAK GULALPURA | Completed | 79050 | 79200 | 2019-10-30 | 2020-05-10
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034396349 — CC ROAD EVAM NALI NIRMAN KARYA RAJU KE GODA HOTE HUYE RAMKUMAR KE DWAR TAK NICHE MUSALMAN KI AUR SAG | Completed | 34875 | 28188 | 2019-01-02 | 2019-06-21
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034433282 — CC ROAD NIRAMAN EVAM NALI NIRAMAN MATA KE MANDIR SE JAGMOHAN KE GHAR KI AUR GULALPURA | Completed | 65100 | 64824 | 2019-02-06 | 2019-07-13
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034442740 — cc road | Deleted | 0 | 0 | 2019-01-26
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034446130 — CC ROAD EVAM NALI NIRMAN MAIN ROAD SE SCHOOL HOTE HUYE MAHESH KE DWAR TAK GUALALPURA | Suspended | 32550 | 0 | 2019-11-01
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034446414 — CC ROAD EVAM NALI NIRMAN KUNWAR SINGH KE GHAR SE KHAR TAK | Completed | 58125 | 69102 | 2019-03-06 | 2019-08-30
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034446415 — CC ROAD EVAM NALI NIRMAN SCHOOL KE PECHHE SE RAMJILAL KE DARWAJE RAJENDRA KE GODA TAK | Completed | 60450 | 56652 | 2019-02-26 | 2019-12-08
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034446417 — CC ROAD EVAM NALI NIRMAN SHANKAR JI SE HARVILAS FAUJI KE AUR | Completed | 30225 | 30624 | 2019-08-28 | 2019-11-07
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034446418 — CC ROAD EVAM NALI NIRMAN POORAN SINGH SE PINKI KE DARWAJE TAK | Completed | 25575 | 24288 | 2019-08-28 | 2019-10-10
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034446419 — CC ROAD EVAM NALI NIRMAN RAJU SINGH KE MAKAN SE NAVAL SINGH KI AUR SAGRA | Suspended | 37200 | 0 | 2019-11-01
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034446420 — CC ROAD EVAM NALI NIRMAN MAIN ROAD SE KHAR TAK | Completed | 77025 | 74476 | 2019-02-27 | 2019-09-22
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034483080 — CC ROAD NIRMAN RAJU SINGH KE GHAR KE AAGE SE RAJBAHADUR KE GHAR TAK | Completed | 59850 | 64416 | 2019-12-01 | 2020-05-10
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034483082 — CC ROAD AVADHESH KE GHAR KE NECHE SE TANKI TAK | Completed | 48750 | 47676 | 2019-12-01 | 2020-05-23
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002051/RC/22012034509284 — suduar sadak nirman aganwadi se shantidham se masukh gaushala tak sagara | Closed | 0 | 0 | 2019-11-02
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034510847 — CC ROAD NIRMAN PRAHALAD KE DWAR SE BHAGWAN SINGH KE GHAR KI AUR SAGARA | Completed | 48750 | 47460 | 2020-01-29 | 2020-05-23
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002051/RC/22012034518876 — SUDUR SADAK YOJNA AAGANVADI BHAVAN SE SHANTIDHAM EMV MANSUKH SE GAUSHALA TAK | Completed | 1021162.52 | 969141.96 | 2020-04-30 | 2021-12-15
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002051/RC/22012034526357 — sudur sadak tanki se mata mandir ki aur gulalpura | Closed | 0 | 0 | 2020-04-01
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002051/RC/22012034526358 — sudur sadak pancyat bhavan se main road se harijan basti | Closed | 0 | 0 | 2020-04-01
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Bitumen Top Roads for Comm / Repair and maintenance of Bitumen Top Roads for Community | Repair & maint of Road | 1702002051/RC/22012034528116 — nala nirman karya sagara | Ongoing | 457827 | 93888 | 2020-09-06
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034528117 — nala nirman karya gulalpura | Ongoing | 731951.5 | 198887 | 2020-09-24
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002051/RC/22012034529306 — sudur sadak nirman main rod panchyat bhavan se harijan thok puliya sagara | Closed | 0 | 0 | 2020-04-01
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1702002051/RC/22012034529307 — nala nirman main road khar se marghat ki aur sagara | Closed | 0 | 0 | 2020-04-01
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034531578 — CC ROAD NIRMAN KARYA MAIN ROAD SE SCHOOL AGANWADI KI AUR GULALPURA | Completed | 45300 | 45600 | 2020-09-24 | 2021-05-11
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034540100 — MAIN ROAD KE KINARE NALA NIRMAN GULALPURA KHAR TAK | Completed | 96900 | 50126 | 2020-09-24 | 2023-09-18
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034540108 — CC ROAD RAMJILAL KE GODA SE KHAR TAK GULALPURA | Completed | 30450 | 35520 | 2020-09-24 | 2021-05-11
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034540125 — CC ROAD MAIN ROAD KALLU KE DARBAJE SE HABIB MUSALMAN THOK SAGARA | Completed | 47850 | 46830 | 2020-09-24 | 2022-02-03
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034540128 — CC ROAD MAIN ROAD HANUMAN MANDIR SE PARMAL KE DARBAJE TAK GULALPURA | Completed | 52200 | 58140 | 2020-09-24 | 2021-05-11
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002051/RC/22012034569796 — SUDUR SADAK PANCHYAT BHAVAN SE HRIJAN BASTI MAIN ROAD | Deleted | 0 | 0 | 2021-04-01
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002051/RC/22012034570378 — SUDUR SADAK PANCHYAT BHAVAN SE HRIJAN BASTI MAIN ROAD | Closed | 0 | 0 | 2021-04-01
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034590817 — cc road nirman sukhveer ke makan se jarjodhan ke makan ki aur | Closed | 52200 | 0 | 2021-04-01
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/22012034590821 — boundary wall nirman midille school gulalpura | Completed | 54000 | 27406 | 2022-01-05 | 2022-04-05
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002051/RC/25 — सी0सी0 रोड गंगासिंह के द्वार से कमलेश के द्वार तक | Completed | 166491 | 134139.9 | 2012-04-01 | 2016-01-20
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Multi Unit Toilets for School / Construction of Multi Unit Toilets for School | Construction of Toilets | 1702002051/RS/22012034501836 — SAMUDAYIK TOILET NIRMAN KARYA GULALPURA | Completed | 43000 | 42180 | 2020-12-13 | 2021-12-02
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002051/RS/22012034526541 — construction of community sokpit gulalpura swachhata prishar | Closed | 6600 | 0 | 2021-06-20
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002051/RS/22012034526544 — construction of community NADEP NEAR GAUSHALA SAGARA | Closed | 5000 | 0 | 2021-06-20
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002051/RS/22012034543609 — COMMUNITY SOKPIT HANUMAN MANDIR GULALPURA | Closed | 6600 | 0 | 2021-04-14
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002051/RS/22012034543611 — COMMUNITY SOKPIT AGANWADI BHAVAN GULALPURA | Closed | 6600 | 0 | 2021-04-14
BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1702002051/WC/22012034293901 — TALAB GAHARIKARN KARAYA HANUMAN MANDIR KE PASS GULALPURA | Deleted | 98200 | 0 | 2016-05-24
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702002051/WC/22012034324921 — TALAB NIRMAN KARYA HANUMAN MANDIR KE SAMANE GULALPURA | Completed | 98000 | 83592 | 2017-06-06 | 2017-10-10
BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002051/WC/22012034441432 — NAVIN TALAB NIRMAN KARYA DID SINGH KE KUA KE PASS SAGARA | Completed | 611000 | 371616 | 2019-02-27 | 2021-02-03
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002051/WC/22012034567264 — naveen talab nirman karay khar ke pass sagara | Closed | 0 | 0 | 2020-04-01
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002051/WC/22012034676761 — SOKPIT NIRMAN KARYA GULALPURA MIDDIL | Deleted | 0 | 0 | 2021-04-01
BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1702002051/WC/22012034676775 — NAVEEN TALAB NIRMAN BHADORIYA | Deleted | 0 | 0 | 2021-04-01
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002051/WC/22012034676780 — SOKPIT NIRMAN KARYA PRIMARY SCHOOL SAGARA | Closed | 14467.3 | 0 | 2021-04-01
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002051/WC/22012034692894 — SOKPIT NIRMAN KARYA GULALPURA MIDDIL | Completed | 14467.3 | 6948 | 2021-05-13 | 2022-01-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1702002051/WC/22012034692902 — NAVEEN TALAB NIRMAN BHADORIYA | Ongoing | 1392677.11 | 13896 | 2021-05-13
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Fisheries Ponds for Comm / Repair and maintenance of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702002051/WC/22012034714022 — TALAB NIRMAN KARYA GAUSHALA KE PASS SAGARA | Completed | 785718.88 | 333504 | 2021-06-03 | 2022-04-05
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002051/WC/22012034770765 — ROOF WATER HARVESTING AGANWADI BHAVAN GULALPURA | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002051/WC/22012034770772 — WATER HARVESTING SAGANWADI BHAVAN SAGARA | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002051/WC/22012034770774 — WATER HARVESTING SCHOOL GUALALPURA | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002051/WC/22012034896609 — TALAB GAHARIKARAN HANUMAN MANDIR SAGARA | Closed | 22572.3 | 0 | 2021-10-02
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002051/WC/22012034994725 — NAVEEN TALAB NIRMAN TANKI KE PASS SAGARA | Closed | 1374000.21 | 0 | 2022-08-15
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002051/WC/22012035025097 — NAVEEN TALAB NIRMAN KUDAR SAGARA | Closed | 0 | 0 | 2022-10-02
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002051/WC/22012035025661 — AMRAT SAROVER DANG POND SAGARA | Ongoing | 1485141.99 | 8840 | 2023-10-28
BHIND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702002051/WC/22012035301184 — community recharge dug well nirman karya hanuman mandir ke pass gp sagara | Physically Completed | 25899.46 | 13893 | 2025-06-08 | 2026-06-04