## Work List
Exported on: 2026-10-12 19:11:34
Filters applied:
Data source: VBGRAMG
District: BHIND
Block: All
Panchayat: ATARSOOMA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702002052/IF/22012035486433 — KHET TALAB NIRMAN KARYA MUNNA S/O SHRIRAM | Approved | 450885.64 | 0 | 2025-04-14
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702002052/IF/22012035486562 — khet talab nirman karya badlesh s/o devicharan | Ongoing | 450885.64 | 0 | 2025-05-15
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702002052/IF/22012035560586 — khet talab nirman karya hakim singh s/o prem singh | Approved | 147621.16 | 0 | 2025-04-14
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702002052/IF/22012035599295 — MAA KI BAGIYA SEETA DEVI GRAM PURADUMANA | Approved | 273463.88 | 0 | 2025-08-15
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702002052/IF/22012035599301 — MAA KI BAGIYA SUVINA GRAM PURADUMANA | Approved | 271103.57 | 0 | 2025-08-15
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702002052/IF/22012035599307 — MAA KI BAGIYA SITA DEVI GRAM PURADUMANA | New | 0 | 0 | 2025-08-15
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702002052/IF/22012035611970 — EK BAGIYA MAA KE NAAM SUVEENA KE KHET PAR GRAM PURADUMNA GP ATARSUMA | Ongoing | 266577.25 | 0 | 2025-12-29
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702002052/IF/22012035611975 — EK BAGIYA MAA KE NAAM GEETA DEVI KE KHET PAR GRAM PURADUMNA GP ATARSUMA | Ongoing | 266577.25 | 0 | 2025-12-29
BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002052/IF/IAY/4778545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126865240 | Ongoing | 27000 | 0 | 2025-02-12
BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002052/IF/IAY/4872556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127334842 | Physically Completed | 27000 | 0 | 2025-02-19 | 2026-08-30
BHIND | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002052/IF/IAY/5614370 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127330039 | Ongoing | 27000 | 0 | 2026-10-05
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002052/IF/IAY/5614475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106539872 | Ongoing | 27000 | 0 | 2025-10-03
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002052/IF/IAY/5615032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126863602 | Ongoing | 27000 | 0 | 2025-12-15
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002052/IF/IAY/5615131 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107021558 | Ongoing | 27000 | 0 | 2026-02-14
BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002052/IF/IAY/5616112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127998766 | Approved | 27000 | 0 | 2025-03-29
BHIND | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002052/IF/IAY/5616139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127329706 | Ongoing | 27000 | 0 | 2026-04-04
BHIND | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002052/IF/IAY/5616161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113484150 | Ongoing | 27000 | 0 | 2026-05-20
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002052/IF/IAY/5616293 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107021376 | Ongoing | 27000 | 0 | 2025-06-16
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002052/IF/IAY/5616731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126862632 | Ongoing | 27000 | 0 | 2025-10-03
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002052/IF/IAY/5620913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106541417 | Approved | 27000 | 0 | 2025-04-29
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002052/IF/IAY/5621252 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106504309 | Ongoing | 27000 | 0 | 2026-02-14
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002052/IF/IAY/5622039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127337665 | Ongoing | 27000 | 0 | 2026-02-22
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002052/IF/IAY/5669726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106540518 | Ongoing | 27000 | 0 | 2025-10-03
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002052/IF/IAY/82327 — Construction of IAY House -IAY REG. NO. MP-02-002-052-003/41 | Approved | 27000 | 0 | 2016-01-07
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702002052/RC/22012034592289 — cc road baghel mohalla rajendra ke dwar ki aur | Ongoing | 52200 | 0 | 2021-12-13
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702002052/RC/22012034592403 — cc road aganwadi se rabude ke dwar ki aur atarsooma | Ongoing | 65250 | 0 | 2021-12-13
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soakage Channel for Community / Construction of Soakage Channel for Community | Solid and Liquid Waste Management | 1702002052/RS/22012034609772 — NALA NIRMAN MAIN ROAD SE BAGHEL MOHALA KI AUR | Ongoing | 43500 | 0 | 2021-12-13
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002052/WC/22012034812214 — CC CHECK DAM NIRMAN IKBAI KE PASS | Ongoing | 1476934.54 | 0 | 2021-11-14
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1702002052/WC/22012034995633 — NAVEEN TALAB NIRMAN KARYA MAHUANPURA KHERE KE PASS | Ongoing | 1449524.39 | 0 | 2023-02-05
BHIND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1702002052/WC/22012035289591 — neaven talab nirman levada bala khar atarsooma | Approved | 0 | 0 | 2025-04-14
BHIND | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1702002052/WC/22012035310734 — अमृत सरोवर निर्माण कार्य लवेड़ा वाले खार के पास ग्राम पंचायत अतरसूमा | Ongoing | 2365000 | 0 | 2026-05-11