## Work List
Exported on: 2026-09-11 06:52:15
Filters applied:
Data source: MGNREGA
District: BHIND
Block: All
Panchayat: TEHANGUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002056/AV/22012034304589 — SHANTIDHAM NIRMAN KARYA TEHANGUR | Completed | 180000 | 175049 | 2017-06-25 | 2018-02-02
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002056/AV/22012034505212 — SHANTI DHAM NIRMAN KARYA KHODAN | Deleted | 0 | 0 | 2019-10-02
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002056/AV/22012034508223 — shantidham nirman khodan | Deleted | 0 | 0 | 2019-10-02
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002056/AV/22012034565898 — SHANTIDHAM NIRMAN KARYA KHODAN | Completed | 285945.37 | 241742 | 2022-04-08 | 2023-02-04
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Stabilization Pond for Community / Construction of Stabilization Pond for Community | Construction of Tank | 1702002056/AV/22012034568798 — SEGREGATION SHED NIRMAN PEPAL KE PASS BANDHA TEHANGUR | Closed | 37000 | 0 | 2021-04-14
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002056/AV/4815 — AGANWADI BHAVAN NIRMAN HAVELI THOK TEHANGUR | Completed | 330000 | 345369 | 2016-03-22 | 2019-02-01
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002056/AV/4854 — AGANBADI BHAVAN NIRMAN TEHANGUR | Deleted | 0 | 0 | 2016-01-27
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002056/IF/22012034357291 — PODHAROPAN KARYA MAGAL PURI | Completed | 335000 | 6192 | 2017-08-22 | 2021-11-23
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002056/IF/22012034357294 — PODHAROPAN KARYA SCHOOL TEHANGUR | Completed | 335000 | 4128 | 2017-09-05 | 2021-11-23
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702002056/IF/22012034388475 — nadep tanka | Deleted | 0 | 0 | 2017-10-02
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002056/IF/22012034678529 — Pashu shed nirman vinod/silochan | Deleted | 0 | 0 | 2021-01-21
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002056/IF/22012034678531 — Pashu shed nirman omvasdev/mahaveer | Deleted | 0 | 0 | 2021-01-21
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1702002056/IF/22012034760458 — MED BANDHAN KARYA SHANTI DEVI | Completed | 22400.3 | 17370 | 2021-06-17 | 2023-09-13
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1702002056/IF/22012034778441 — MED BANDHAN KARYA RAJU SINGH | Closed | 21000.23 | 0 | 2021-04-14
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002056/IF/22012034994906 — KHET TALAB NIRMAN VIPLAV KE KHET PAR TEHANGUR | Closed | 356340.1 | 0 | 2022-04-01
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002056/IF/22012034994917 — KHET TALAB NIRMAN KARYA RAJENDRA SINGH TEHANGUR | Completed | 356340.1 | 243542 | 2023-09-18 | 2024-03-17
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002056/IF/22012034994932 — KHET TALAB NIRMAN KARYA PRASHANT SINGH TEHANGUR | Completed | 356340.1 | 233070 | 2022-12-16 | 2024-03-17
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002056/IF/22012034994946 — KHET TALAB NIRMAN KARYA KRISHANMURATI TEHANGUR | Deleted | 0 | 0 | 2022-04-01
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002056/IF/22012034994963 — KHET TALAB NIRMAN KARYA PAAN SINGH TEHANGUR | Completed | 356340.1 | 253266 | 2023-09-18 | 2024-01-09
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1702002056/IF/22012035138372 — KHET TALAB RAMVEER SINGH KE KHET PAR | Completed | 383083.54 | 210834 | 2023-08-19 | 2026-04-13
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1702002056/IF/22012035138380 — KHET TALAB AVAD BIHARI SINGH KE KHET PAR | Completed | 383083.54 | 265200 | 2023-10-04 | 2024-01-09
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Brushwood Check Dam for Individuals / Construction of Brushwood Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1702002056/IF/22012035138381 — KHET TALAB ANGAD SINGH KE KHET PAR | Completed | 383083.54 | 250614 | 2023-10-04 | 2024-01-09
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1702002056/IF/22012035138386 — KHET TALAB MUNENDRA SINGH KE KHET PAR | Completed | 383083.54 | 255918 | 2023-10-04 | 2024-03-30
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1702002056/IF/22012035138388 — KHET TALAB SAHUDRA KE KHET PAR | Completed | 383083.54 | 253266 | 2023-10-04 | 2024-01-09
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1702002056/IF/22012035138389 — KHET TALAB RAJENDRA SINGH KE KHET PAR | Completed | 383083.54 | 253266 | 2023-10-04 | 2024-01-09
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Brushwood Check Dam for Individuals / Construction of Brushwood Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1702002056/IF/22012035138390 — KHET TALAB VIPUL SINGH KE KHET PAR | Completed | 383083.54 | 246636 | 2023-08-19 | 2025-05-08
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1702002056/IF/22012035138392 — KHET TALAB KISAN PAL SINGH KE KHET PAR | Closed | 383083.54 | 0 | 2023-04-14
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1702002056/IF/22012035138393 — KHET TALAB RAM KISHAN SINGH KE KHET PAR | Closed | 383083.54 | 0 | 2023-04-14
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1702002056/IF/22012035138395 — KHET TALAB SATENDRA SINGH KE KHET PAR | Completed | 383083.54 | 188292 | 2023-08-19 | 2026-04-13
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002056/IF/22012035531406 — NAVEEN KHET TALAB NIRMAN PRASHANT SINGH KE KHET PAR | Physically Completed | 147621.16 | 86913 | 2025-05-22 | 2026-04-15
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002056/IF/22012035531428 — NAVEEN KHET TALAB NIRMAN RAJENDRA SINGH KE KHET PAR | Physically Completed | 147621.16 | 106488 | 2025-05-22 | 2026-04-23
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002056/IF/22012035531437 — NAVEEN KHET TALAB NIRMAN RAJANI DEVI KE KHET PAR | Ongoing | 147621.16 | 11745 | 2025-05-22
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002056/IF/22012035531442 — NAVEEN KHET TALAB NIRMAN SHRI BHAGWAN SINGH KE KHET PAR | Ongoing | 147621.16 | 10440 | 2025-06-18
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002056/IF/22012035543115 — khet talab nirman satrughan singh ke khet par gp tehangur | Approved | 0 | 0 | 2025-04-14
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002056/IF/22012035543125 — khet talab nirman suresh singh ke khet par gp tehangur | Approved | 0 | 0 | 2025-04-14
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002056/IF/22012035543140 — khet talab nirman radha devi ke khet par gp tehangur | Physically Completed | 147621.16 | 103356 | 2025-06-18 | 2026-04-15
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002056/IF/22012035543153 — khet talab nirman bijendra singh ke khet par gp tehangur | Completed | 147621.16 | 88218 | 2025-06-18 | 2026-04-15
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002056/IF/22012035628107 — EK BAGIYA MAA KE NAAM GUDDI DEVI KE KHET PAR GP TEHANGUR | Ongoing | 187841.53 | 261 | 2026-01-12
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002056/IF/22012035633327 — EK BAGIYA MAA KE NAAM SHIKHA DEVI KE KHET PAR GP TEHANGUR | Ongoing | 266578.64 | 0 | 2026-01-12
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002056/IF/22012035633332 — EK BAGIYA MAA KE NAAM NEMA KE KHET PAR GP TEHANGUR | Ongoing | 266578.64 | 522 | 2026-01-12
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002056/IF/22012035633337 — EK BAGIYA MAA KE NAAM VINEETA DEVI KE KHET PAR GP TEHANGUR | Ongoing | 266578.64 | 783 | 2025-12-31
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002056/IF/9993727952 — PASHU SHED NIRMAN RAMNIVAS | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002056/IF/9993727953 — PASHU SHED NIRMAN MANU | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002056/IF/9993727954 — PASHU SHED NIRMAN RAMGANESH | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002056/IF/9993727955 — PASHU SHED NIRMAN SHIVNARAYAN | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002056/IF/9993727956 — PASHU SHED NIRMAN BHAGWAN SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002056/IF/9993727957 — PASHU SHED NIRMAN MAHARAJ SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002056/IF/9993727958 — PASHU SHED NIRMAN RAMDEV | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002056/IF/9993727959 — PASHU SHED NIRMAN RAJROOP | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002056/IF/9993727960 — PASHU SHED NIRMAN KRISHANVIHARI | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002056/IF/9993727961 — PASHU SHED NIRMAN PAAN SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002056/IF/9993727963 — PASHU SHED NIRMAN UDAL SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002056/IF/9993727964 — PASHU SHED NIRMAN GAJENDRA SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002056/IF/9993727965 — PASHU SHED NIRMAN RAKESH SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002056/IF/9993727966 — PASHU SHED NIRMAN KARAMVEER | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002056/IF/9993727968 — PASHU SHED NIRMAN KAPTAN | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002056/IF/9993727969 — PASHU SHED NIRMAN SHIVCHARAN SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002056/IF/9993727970 — PASHU SHED NIRMAN HOM SIGNH | Deleted | 0 | 0 | 2016-01-27
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002056/IF/IAY/133949 — Construction of IAY House -IAY REG. NO. MP-02-002-056-001/08 | Completed | 14310 | 7014 | 2016-06-07 | 2018-03-25
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002056/IF/IAY/133950 — Construction of IAY House -IAY REG. NO. MP-02-002-056-001/106 | Completed | 14310 | 13012 | 2016-08-02 | 2018-03-25
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002056/IF/IAY/133951 — Construction of IAY House -IAY REG. NO. MP-02-002-056-001/120 | Completed | 14310 | 14836 | 2016-05-10 | 2018-03-25
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002056/IF/IAY/133952 — Construction of IAY House -IAY REG. NO. MP-02-002-056-001/78 | Completed | 14310 | 6012 | 2016-08-02 | 2018-03-25
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002056/IF/IAY/317737 — Construction of IAY House -IAY REG. NO. MP1064542 | Completed | 15030 | 14014 | 2017-03-07 | 2018-03-25
BHIND | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002056/IF/IAY/3825189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115136734 | Physically Completed | 18360 | 11934 | 2023-09-18 | 2024-11-21
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002056/IF/IAY/4745492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115147766 | Ongoing | 23490 | 17226 | 2025-05-17
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002056/IF/IAY/4908150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115156714 | Ongoing | 23490 | 20358 | 2025-09-04
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002056/IF/IAY/563675 — Construction of IAY House -IAY REG. NO. MP3795459 | Completed | 15030 | 14328 | 2017-03-07 | 2018-03-25
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002056/IF/IAY/591550 — Construction of IAY House -IAY REG. NO. MP1060235 | Completed | 15030 | 14844 | 2017-03-07 | 2018-03-25
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002056/IF/IAY/82329 — Construction of IAY House -IAY REG. NO. MP-02-002-056-001/21 | Completed | 14310 | 9018 | 2016-05-10 | 2018-03-25
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/22012034243814 — MED BANDHAN NIRAMAN RAMVEER SINGH | Deleted | 34700 | 0 | 2015-12-15
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/22012034243830 — MED BHANDHAN NIRMAN SANTOSH SINGH | Deleted | 27900 | 0 | 2015-12-15
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/22012034244146 — MED BANDHAN NIRMAN RAMJI SINGH | Deleted | 27900 | 0 | 2015-12-15
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/22012034262664 — MED BANDHAN NIRMAN SHILPI | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/22012034262666 — MED BANDHAN NIRMAN SURESH DHANUK | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/22012034262667 — MED BANDHAN NIRMAN SHRIKRISHAN SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/22012034262668 — MED BANDHAN NIRMAN RAMVEER SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/22012034262669 — MED BANDHAN NIRMAN VIDHYARAM | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/22012034262670 — MED BANDHAN NIRMAN PAAN SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/22012034262671 — MED BANDHAN NIRMAN KALANDAR | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/22012034262672 — MED BANDHAN NIRMAN RAM SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/22012034262673 — MED BANDHAN NIRAMAN JHAGADU | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/22012034262674 — MED BANDHAN NIRAMAN CHHOTELAL | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/22012034262675 — MED BANDHAN NIRMAN RAMKISHUN | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/22012034262676 — MED BANDHAN NIRMAN MAGAN | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/22012034262677 — MED BANDHAN NIRAMAN SHIVNARAYAN | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/22012034262678 — MED BANDHAN NIRAMAN RAMJI | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/22012034262679 — MED BANDHAN NIRMAN SANTOSH SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/22012034262680 — MED BANDHAN NIRMAN DILIP SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/22012034262683 — MED BANDHAN NIRAMAN BABU SINGH | Deleted | 30000 | 0 | 2016-01-27
BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/22012034262685 — MED BANDHAN NIRAMN SHIVCHARAN | Deleted | 0 | 0 | 2016-01-27
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002056/LD/22012034551216 — MED BANDHAN SHRI KISHAN SINGH RAJAWAT | Completed | 29147.22 | 20844 | 2021-05-13 | 2022-11-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002056/LD/22012034551217 — MED BANDHAN KARYA KIRAN DEVI | Completed | 27613.16 | 22002 | 2021-05-13 | 2023-09-13
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002056/LD/22012034551218 — MED BANDHAN KARYA SAMBAR SINGH | Completed | 29147.22 | 19686 | 2021-05-12 | 2025-05-08
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002056/LD/22012034551219 — MED BANDHAN KARYA SHANTI DEVI | Deleted | 0 | 0 | 2021-04-01
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Land Development | Drainage of Waterlogged Land for Community / Drainage of Community Waterlogged Land | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702002056/LD/22012034551536 — KACHHA NALA NIRMAN KARYA HARIJAN BASTI TEHANGUR | Completed | 357416.5 | 192648 | 2021-07-01 | 2025-05-08
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1702002056/LD/22012034593931 — MERI MATI MERA GWAN BRAKSHAROPAN KARAY GRAM PANCYAT TEHANGUR | Closed | 57779.84 | 0 | 2023-04-14
BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/234 — मेड बन्‍धान कार्य छोटेलाल / टुण्‍डे | Completed | 15000 | 8000 | 2010-07-23 | 2010-02-11
BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/235 — मेड बन्‍धान कार्य रविन्‍द्र / वेजू | Completed | 14000 | 2700 | 2010-08-01 | 2010-02-20
BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002056/LD/236 — मेड बन्‍धान कार्य कलन्‍दर / उदय सिंह | Completed | 17000 | 8124 | 2010-08-01 | 2011-12-21
BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002056/OP/9425889343 — CATTALE PROTECTION WALL NIRMAN GOVT. SHALA BHAVAN | Completed | 127907 | 84492 | 2016-06-07 | 2019-09-30
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002056/OP/9425889426 — NALI NIRMAN VIDYARAM SARAPANCH KE GHAR SE AGE TAK | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002056/OP/9425889429 — SHANTI DHAM NADI KE KINARE TEHANGUR | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002056/PG/9425888163 — KHEL MEDAN TEHANGUR | Completed | 373500 | 58014 | 2016-03-22 | 2019-02-01
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034158321 — c.c. road ram swaroop ke makan se pachori tak | Completed | 86300 | 73400 | 2013-02-21 | 2013-12-12
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034158324 — c.c. road rajkumar ke makan se laxmi gupta se jagp | Completed | 39800 | 36837 | 2013-02-21 | 2015-06-24
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034185369 — C.C.ROAD NARI THOK GUDDU KE MAKAN SE TAWOR KI AUR | Completed | 129190 | 127242 | 2013-10-01 | 2014-05-26
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034205486 — C.C.ROAD SCHOOL SE OM BASUDEV KI AUR | Completed | 109220 | 99823 | 2014-02-15 | 2014-05-19
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034206880 — C.C.ROAD RAJU SINGH KE DWAR SE GUDDU KE CHABUTARA | Completed | 92416 | 83142 | 2014-02-20 | 2014-07-20
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034208685 — C.C.ROAD GRAM KHODAN SEVARAM KE DWAR SE RAM LAKHAN | Completed | 50408 | 45987 | 2014-03-03 | 2014-06-20
BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034220647 — C.C.ROAD MAIN ROAD SE BALRAM KE DWAR TAK | Completed | 84028 | 75603 | 2014-06-10 | 2016-06-05
BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034220727 — C.C.ROAD SHIV BALAK KE DWAR SE PALIWAL TAK | Completed | 105036 | 77646 | 2014-06-10 | 2017-01-09
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034284079 — C.C.ROAD RAJENDRA NAI KE DWAR SE MANDIR TAK | Deleted | 0 | 0 | 2015-04-15
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034284080 — C.C.ROAD RAJENDRA NAI KE DWAR SE MANDIR TAK | Completed | 110685 | 100700 | 2015-09-08 | 2018-07-30
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034291004 — C.C.ROAD NIRMAN SCHOOL SE PARSURAM KE GHAR TAK KHODAN | Completed | 143734 | 106871 | 2015-12-08 | 2017-10-10
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034299784 — cc road nirman mohan ke gahar tak | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002056/RC/22012034303893 — MITTI BAJARI SADAK NIRMAN UJAGAR KE DWAR SE RAPRATAP KE GHODA TAK | Completed | 666600 | 57167 | 2016-03-22 | 2017-10-08
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034305850 — CC ROAD NIRMAN UJAGAR KE GHAR SE RAMVEER KE GHAR TAK | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034305852 — CC ROAD NIRMAN SARAMAN KE GODA SE MAIN SER TAK | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034305853 — CC ROAD NIRMAN MANGALPURI | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034305854 — CC ROAD NIRMAN BASANTE KE DARBAJE SE SURENDRA KE DARWAJE TAK | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034305855 — CC ROAD NIRMAN LALLA THOK DANA | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034305856 — CC ROAD NIRMAN LALBAHADUR KE GHAR SE SHRIRAM BHAGHEL KHODAN | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002056/RC/22012034305859 — MITTI SADAK NIRMAN MAIN ROAD KHERE SE SODIN KE KHET TAK | Deleted | 0 | 0 | 2016-01-27
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002056/RC/22012034305860 — MITTI SADAK NIRMAN UPARBAKHAR SE AGANWADI BHAVAN TAK | Deleted | 0 | 0 | 2016-01-27
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034349605 — CC ROAD NIRMAN MEIN ROAD SE KALAKA MATA MANDIR TEHANGUR | Completed | 87615 | 86748 | 2017-08-29 | 2018-05-04
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034360008 — CC ROAD NIRMAN KUA SE PULIYA KI AUR KHODAN | Completed | 36285 | 32936 | 2018-01-23 | 2018-05-04
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034360009 — CC ROAD NIRMAN PARMAR KE DWAR SE KARAN KE GODA TAK KODHAN | Completed | 23010 | 21720 | 2018-02-20 | 2018-05-04
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034378318 — C.C.ROAD NIRMAN SODEEN KE DWAR SE MANGALPURI CHAURAH TAK | Completed | 55800 | 54828 | 2018-01-02 | 2018-05-01
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034378324 — C.C.ROAD NIRMAN RAMPRATAP KE DWAR SE GUDDU KE DWAR TAK | Completed | 135375 | 134160 | 2018-01-02 | 2018-05-01
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034378573 — CC ROAD NIRMAN MAIN ROAD SE MAGALPURI TAK TEHANGUR | Completed | 40267 | 34260 | 2018-01-09 | 2018-05-01
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034378578 — CC ROAD NIRMAN SODIN KE DWAR SE VIDHYARAM SARPANCH KE DWAR TAK TEHANGUR | Completed | 17257 | 14508 | 2018-01-09 | 2018-05-04
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034396037 — CC ROAD EVAM NALI NIRMAN KARAY PANI KI TANKI SE NADI KI AUR TEHANGUR | Completed | 28365 | 46980 | 2018-12-11 | 2019-02-01
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034396050 — CC ROAD EVAM NALI NIRMAN KARYA MAIN ROAD SE SHRI BHAGWAN KE GHAR TAK | Completed | 20460 | 28188 | 2018-12-11 | 2019-02-01
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034396055 — CC ROAD EVAM NALI NIRMAN KARYA RAMVEER KE DWAR SE RAMKARAN KE DWAR TAK | Completed | 71145 | 72558 | 2018-12-11 | 2019-08-01
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034433162 — CC ROAD EVAM NALI NIRMAN BAR KE PED SE SHANKAR JI KE MANDIR TAK TEHANGUR | Completed | 24180 | 24436 | 2019-02-12 | 2019-08-01
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034433188 — CC ROAD EVAM NALI NIRMAN SURESH KE DWAR SE BAGARANGI KE MANDIR TAK TEHANGUR | Completed | 21855 | 21808 | 2019-02-12 | 2019-08-01
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034441839 — CC ROAD EVAM NALI NIRAMAN LAXMI BANIYA KE DWAR SE VINOD SINGH KE DWAR KI AUR TEHANGUR | Completed | 76725 | 75328 | 2019-03-05 | 2021-03-14
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034442748 — cc road | Deleted | 0 | 0 | 2019-01-26
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034463199 — CC ROAD EVAM NALI NIRMAN KARYA VISHESHWAR KE DWAR SE MANI ROAD TAK | Completed | 23250 | 18360 | 2022-08-10 | 2023-02-04
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034463201 — CC ROAD EVAM NALI NIRMAN KARYA MANTOLIYA SE BARU TAK | Deleted | 51150 | 0 | 2018-08-15
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034463202 — CC ROAD EVAM NALI NIRMAN KARYA RAJAN KE DWAR SE VINAY KE DWAR TAK | Completed | 18600 | 19296 | 2019-05-29 | 2021-03-14
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034477114 — Cc Road Evam Nali Nirman Karya Raju shrivas Ke Dwar Se Main Road Tak | Completed | 65000 | 61200 | 2022-08-02 | 2022-11-02
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034477117 — Cc Road Evam Nali Nirman Karya Mantoliya Se Baru Tak Tehangur | Completed | 60000 | 59916 | 2020-01-31 | 2021-03-14
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034516315 — C C ROAD PRMAR KE DWAR SE KRAN KE GODA TAK KHODAN | Completed | 70000 | 58506 | 2020-10-22 | 2022-11-02
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034516319 — C C ROAD RAMLAKHAN KE MAKAN SE GANGARAM KE MAKAN KI AUR KHODAN | Completed | 28000 | 37620 | 2020-05-11 | 2021-07-08
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034532686 — C C ROAD GANGARAM KE GHAR SE HAITRAM KE GHAR KI AUR | Completed | 87000 | 86286 | 2021-04-22 | 2022-11-02
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Bitumen Top Roads for Comm / Repair and maintenance of Bitumen Top Roads for Community | Repair & maint of Road | 1702002056/RC/22012034532787 — nala nirman karya harijan collony | Closed | 0 | 0 | 2020-04-01
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034551846 — C C ROAD EVAM NALI NIRMAN MANTOLIYA SE JAGMOHAN KE GHAR KI AUR | Completed | 87000 | 86784 | 2021-01-25 | 2021-07-08
BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/22012034551850 — C C ROAD BIRJENDRA KE DUAR SE INDAL KE GHAR KI AUR | Completed | 43000 | 35802 | 2023-07-31 | 2024-03-11
BHIND | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002056/RC/26 — सी0सी0 रोड निर्माण कार्य विशुन सिंह के द्वार से रा | Completed | 298413 | 103365 | 2012-03-21 | 2013-02-21
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/22012034187098 — MARYADA ABHIYAN BHAGIRATH | Completed | 4500 | 4427 | 2013-12-24 | 2013-12-30
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/22012034187145 — MARYADA ABHIYAN CHUNNA SINGH | Completed | 4500 | 4427 | 2013-12-24 | 2013-12-30
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/22012034187146 — MARYADA ABHIYAN MAHENDRA | Completed | 4500 | 4427 | 2013-12-24 | 2013-12-30
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/22012034187147 — MARYADA ABHIYAN MAGAN / RAGHUNATH | Completed | 4500 | 4427 | 2013-12-24 | 2013-12-30
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/22012034192316 — MARYADA ABHIYAN RAKESH SINGH | Completed | 4500 | 4427 | 2014-01-01 | 2014-04-13
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/22012034192319 — MARYADA ABHIYAN JAINANDA MISHRA | Completed | 4500 | 4427 | 2014-01-07 | 2014-04-13
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/22012034192335 — MARYADA ABHIYAN ROOP NARAYAN SINGH | Completed | 4500 | 4427 | 2014-01-07 | 2014-04-13
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/22012034192337 — MARYADA ABHIYAN RAM KISHOR | Completed | 4500 | 4427 | 2014-01-07 | 2014-04-13
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/22012034192342 — MARYADA ABHIYAN GIRJA DEVI | Completed | 4500 | 4427 | 2014-01-07 | 2014-04-13
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/22012034192347 — MARYADA ABHIYAN OM PRAKASH | Completed | 4500 | 4427 | 2014-01-01 | 2014-04-13
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702002056/RS/22012034503421 — CONSTRUCTION WORK COMMUNITY TOILET GP TEHANGUR | Completed | 43000 | 41040 | 2021-01-11 | 2021-07-08
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/32358 — MARYADA ABHIYAN SODEEN | Completed | 4500 | 4427 | 2013-12-24 | 2013-12-30
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/32360 — MARYADA ABHIYAN KALANDAR SINGH / UDAY SINGH | Completed | 4500 | 4427 | 2013-12-24 | 2013-12-30
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/32362 — MARYADA ABHIYAN BRIJENDRA SINGH | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/32365 — MARYADA ABHIYAN LOKENDRA SINGH / BALVEER SINGH | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/32366 — MARYADA ABHIYAN GAJENDRA SINGH /JASMANT SINGH | Completed | 4500 | 4427 | 2013-12-03 | 2014-03-30
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/32367 — MARYADA ABHIYAN BHANU SINGH / RADHESHYAM SINGH | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/32369 — MARYADA ABHIYAN GIRJA DEVI / RAMNATH SINGH | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/32371 — MARYADA ABHIYAN LOVEKUSH SINGH / NARAYAN SINGH | Completed | 4500 | 4427 | 2013-12-03 | 2013-12-09
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/32373 — MARYADA ABHIYAN GANGA SINGH / KESAV SINGH | Completed | 4500 | 4427 | 2013-12-03 | 2013-12-09
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/32374 — MARYADA ABHIYAN RAMNARESH / SURESH | Completed | 4500 | 4427 | 2013-12-03 | 2013-12-09
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/32376 — MARYADA ABHIYAN VIDHYARAM /KASHIRAM | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/32377 — MARYADA ABHIYAN DINESH SINGH | Completed | 4500 | 4427 | 2013-12-24 | 2013-12-30
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/32378 — MARYADA ABHIYAN TULSIRAM /GYADEEN | Completed | 4500 | 4427 | 2013-12-03 | 2013-12-30
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002056/RS/32380 — MARYADA ABHIYAN HARI SINGH /NARAYAN SINGH | Completed | 4500 | 4427 | 2013-12-03 | 2013-12-09
BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1702002056/WC/22012034293899 — TALAB GAHARIKARAN KARAYA COLONY KE PASS TEHANGUR | Deleted | 98300 | 0 | 2016-05-24
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002056/WC/22012034330563 — TALAB NIRMAN KARYA MATA KE PASS TEHANGUR | Completed | 97000 | 83220 | 2020-06-08 | 2021-07-08
BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002056/WC/22012034355787 — BORI BANDHAN KARYA SINDH NADI PAR TEHANGUR | Completed | 67000 | 28208 | 2017-09-26 | 2018-02-02
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1702002056/WC/22012034563939 — talab nirman karay bhuder chinka tehangur | Completed | 923960.86 | 520674 | 2020-07-21 | 2025-05-08
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002056/WC/22012034587076 — nala nirman harijan collony | Deleted | 0 | 0 | 2020-04-01
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702002056/WC/22012034773820 — SOKPIT NIRMAN KARYA GOV SCHOOL GRAM TEHANGUR | Deleted | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702002056/WC/22012034773824 — SOKPIT NIRMAN KARYA GOV SCHOOL HARIJAN COLLONY TEHANGUR | Deleted | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702002056/WC/22012034773827 — SOKPIT NIRMAN KARYA GOV SCHOOL BARU TEHANGUR | Deleted | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002056/WC/22012034775063 — ROOF WATER HARVESTING GOV SCHOOL GRAM TEHANGUR | Deleted | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002056/WC/22012034775067 — ROOF WATER HARVESTING GOV SCHOOL HARIJAN COLLONY GRAM TEHANGUR | Deleted | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002056/WC/22012034775070 — ROOF WATER HARVESTING GOV SCHOOL BARU GRAM TEHANGUR | Deleted | 0 | 0 | 2021-04-14
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002056/WC/22012034937312 — TALAB NIRMAN KARYA KAMLESH KE KHET KE PASS | Deleted | 0 | 0 | 2022-04-01
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002056/WC/22012034937325 — KHET TALAB NIRMAN KARYA RAMDEEN HARIJAN KE KHET PAR | Deleted | 0 | 0 | 2022-04-01
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002056/WC/22012034937348 — TALAB NIRMAN KARYA KOD PAR | Deleted | 0 | 0 | 2022-04-01
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002056/WC/22012034937353 — CHECK DAM PIPRA BALE PAR | Deleted | 0 | 0 | 2022-04-01
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002056/WC/22012034944127 — CHECK DAM PIPRA BALE PAR | Deleted | 0 | 0 | 2022-04-01
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002056/WC/22012034963620 — TALAB NIRMAN KARYA AMRAT MAHOTSAV TEHANGUR | Deleted | 0 | 0 | 2022-04-01
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002056/WC/22012035025709 — AMRAT SAROVER DAG POND KHAR KA BHARKA TEHANGUR | Deleted | 0 | 0 | 2022-10-02
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002056/WC/22012035112898 — NAVEEN TALAB NIRMAN DANIYA VALI TEHANGUR | Deleted | 0 | 0 | 2023-04-14
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002056/WC/22012035112900 — NAVEEN TALAB NIRMAN MUDRA KE NARI TEHANGUR | Physically Completed | 1493401.55 | 1031451 | 2023-10-07 | 2026-05-05
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002056/WC/22012035112903 — NAVEEN TALAB NIRMAN KHARAK BHARK TEHANGUR | Deleted | 0 | 0 | 2023-04-14
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002056/WC/22012035112904 — NAVEEN TALAB NIRMAN KOD KE NARI TEHANGUR | Deleted | 0 | 0 | 2023-04-14
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002056/WC/22012035115271 — DAGPOND NIRMAN NAI TOR KE PAS | Deleted | 0 | 0 | 2023-08-15
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002056/WC/22012035127839 — DAGPOND NIRMAN NAI TOR KE PAS | Physically Completed | 1421960.25 | 529070 | 2023-10-04 | 2026-06-10
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002056/WC/22012035130473 — EARTHEN BUND NIRMAN KATI NARIYA KE PAS | Physically Completed | 1420264.34 | 1108519 | 2023-10-04 | 2026-05-26
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002056/WC/22012035130485 — EARTHEN BUND NIRMAN BADI NARIYA KE PAS | Physically Completed | 1464919.56 | 1048275 | 2023-10-04 | 2026-06-10
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002056/WC/22012035130495 — EARTHEN BUND NIRMAN MIN BALI NARIYA KE PAS | Physically Completed | 1491779.24 | 1031504 | 2023-10-04 | 2026-05-26
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002056/WC/22012035130504 — DAGPOND NIRMAN HARJAN KALONI KE PAS | Physically Completed | 1448946.25 | 443989 | 2023-10-07 | 2026-04-20
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002056/WC/22012035171940 — EARTHEN BUND NIRMAN CHARKHA VALI NARIYA KE PASTEHANGUR | Physically Completed | 1464678.31 | 369524 | 2024-03-04 | 2026-06-09
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002056/WC/22012035171945 — EARTHEN BUND NIRMAN DULAIYA VALI NARIYA KE PAS TEHANGUR | Ongoing | 1477207.87 | 173334 | 2024-03-04
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002056/WC/22012035171947 — EARTHEN BUND NIRMAN SAMAL BABA KE KHET KE PAS TEHANGUR | Ongoing | 1477707.87 | 747707 | 2024-03-04
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002056/WC/22012035171953 — EARTHEN BUND NIRMAN ARU VALI NARIYA KE PAS TEHANGUR | Ongoing | 1455232.23 | 788030 | 2024-03-04
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002056/WH/22012034907203 — talv mammat kary miana bali bhuder ke pas | Closed | 0 | 0 | 2022-01-21