## Work List
Exported on: 2026-10-20 22:02:09
Filters applied:
Data source: MGNREGA
District: BHIND
Block: All
Panchayat: MADNAI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702002061/AV/22012034375432 — PANCHAYAT BHAVAN MADANAI | Completed | 579200 | 578238 | 2018-08-13 | 2019-02-22
BHIND | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1702002061/AV/22012034506244 — GAUSHALA NIRMAN MADNAI | Ongoing | 2963512.13 | 56007 | 2023-06-20
BHIND | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1702002061/AV/22012034515480 — GAU SHALA NIRMAN MADNAI | Deleted | 0 | 0 | 2020-01-26
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1702002061/AV/22012034516268 — नवीन गौशाला निर्माण कार्य मडनई | Ongoing | 3937502.34 | 3649475.18 | 2020-09-19
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002061/AV/22012034534459 — ANGANWADI BHAVAN NIRMAN MADNAI | Completed | 180000 | 179930 | 2020-09-19 | 2021-11-23
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702002061/AV/22012034534481 — BAUNDARY WALL NIRMAN PANCHAYAT BHAVAN MADNAI | Completed | 99000 | 58140 | 2020-12-09 | 2022-02-26
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702002061/AV/22012034606602 — BOUNDARY WALL BAJRANG WALI MANDIR KE CHRO AUR | Closed | 0 | 0 | 2021-06-02
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702002061/AV/22012034606603 — BOUNDARY WALL BAJRANG WALI MANDIR KE CHRO AUR | Physically Completed | 46000 | 14076 | 2022-08-23 | 2026-04-17
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702002061/AV/22012034616077 — CONSTRUCTION WORK OF RETAINING WALL PITHAURA BABA KE THAN KE PASS | Physically Completed | 573000 | 495328 | 2022-05-25 | 2026-04-17
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construct building for federation of women SHG / Construction of SHG/Federation Building for Groups | Construction of building/workshed for SHG | 1702002061/AV/5181 — AGANWADI BAWAN RURAN | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Building for Gram Panchayats / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702002061/AV/5184 — agawadi ruran | Deleted | 0 | 0 | 2016-01-26
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002061/DP/22012034595832 — वृक्षारोपण कार्य वसुधैव बंधन अमृत वाटिका माता मन्दिर ग्राम पंचायत मदनई | Closed | 55847.4 | 0 | 2023-06-08
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002061/FP/22012034369788 — KACHCHA NALA NIRMAN PAPPU KE KHET SE RAMESH BHADAURIYA KE BEHAD TAK | Completed | 495905.57 | 353190 | 2021-04-01 | 2021-11-23
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002061/FP/22012034369789 — KACHCHA NALA NIRMAN BAKEEL KE KHET SE BUDHSINGH KE KHET TAK | Deleted | 0 | 0 | 2021-01-26
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002061/FP/22012034624278 — KACHCHA NALA BAKEEL KE KHET SE PAPPU KE KHET KI OR | Completed | 392286.24 | 348558 | 2021-05-21 | 2021-11-23
BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702002061/FP/22012034633076 — NALA NIRMAN KARYA THAKUR KE MAKAN SE SHIV MANGAL KE MAKAN KI OR | Deleted | 0 | 0 | 2023-04-14
BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702002061/FP/22012034633077 — NALA NIRMAN GUDDI BHADAURIYA KE MAKAN SE JASMANT KE MAKAN KI OR | Deleted | 0 | 0 | 2023-04-14
BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702002061/FP/22012034633774 — NALA NIRMAN GUDDU KE MAKAN SE JASVANT KE GONDA KI OR | Closed | 822000 | 0 | 2023-06-22
BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002061/IF/22012034352823 — BRAKSHA ROPAN KARYA MATA KE MANDIR PER RURAN | Physically Completed | 335000 | 9880 | 2017-08-14 | 2026-04-15
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702002061/IF/22012034388479 — nadep tanka | Closed | 0 | 0 | 2017-10-02
BHIND | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002061/IF/22012034506571 — KHET TALAB BUDH SINGH/RUSTAM SINGH | Closed | 0 | 0 | 2019-10-02
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002061/IF/22012034538735 — KHET TALAB NIRMAN PREM SINGH KE KHET PER | Completed | 210104.98 | 205200 | 2020-06-23 | 2020-08-24
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/22012034647437 — PASHU SHED NIRMAN SANJAY SINGH | Closed | 0 | 0 | 2020-11-20
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/22012034647438 — PASHU SHED NIRMAN BHUPENDRA SINGH | Closed | 0 | 0 | 2020-11-20
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/22012034647439 — PASHU SHED NIRMAN RAMBARAN SINGH | Closed | 0 | 0 | 2020-11-20
BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/22012034647440 — PASHU SHEN NIRMAN PUSHPENDRA SINGH | Completed | 101804.91 | 88064.3 | 2021-06-28 | 2022-08-28
BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/22012034647441 — PASHU SHED NIRMAN RAMVIR SINGH | Closed | 0 | 0 | 2020-11-20
BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002061/IF/22012034762603 — KHET TALAB NIRMAN RAMBALI KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002061/IF/22012034762608 — KHET TALAB NIRMAN JAGMOHAN KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002061/IF/22012034762614 — MED BANDHAN RAJKUMAR KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002061/IF/22012034762616 — MED BANDHAN CHHOTE KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002061/IF/22012034762622 — MED BANDHAN TINKAL KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002061/IF/22012034762623 — MED BANDHAN RAJU KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002061/IF/22012034762626 — MED BANDHAN HOM SINGH KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002061/IF/22012034762629 — MED BANDHAN KUAR SINGH KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002061/IF/22012034762632 — MED BANDHAN NANDKISHOR KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002061/IF/22012034762633 — KHET TALAB NIRMAN RAMVEER KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002061/IF/22012034830897 — KHET TALAB NIRMAN VISHRAM SINGH KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002061/IF/22012034830902 — KHET TALAB NIRMAN PAPPU KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002061/IF/22012035578550 — KHET TALAB NIRMAN RAJKUMAR / GORELAL SINGH KE KHET PER | Deleted | 0 | 0 | 2025-04-14
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002061/IF/22012035619185 — EK BAGIYA MAA KE NAAM KIRAN / DEVIDAYAL SINGH | Approved | 266577.25 | 0 | 2025-08-15
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002061/IF/22012035619480 — EK BAGIYA MAA KE NAAM KIRAN/ DEVI DAYAL SINGH | Deleted | 266577.25 | 0 | 2025-08-15
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002061/IF/22012035620019 — EK BAGIYA MAA KE NAAM ARTI / KISHAN SINGH | Approved | 271706.87 | 0 | 2025-08-15
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002061/IF/22012035620024 — EK BAGIYA MAA KE NAAM KUSUMLATA/ HARBHAN SINGH | Approved | 263510.03 | 0 | 2025-08-15
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002061/IF/22012035622447 — KHET TALAB NIRMAN RAJKUMAR / GORELAL SINGH KE KHET PER | Deleted | 0 | 0 | 2025-08-15
BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002061/IF/22012035643244 — KHET TALAB NIRMAN RAJKUMAR / GORELAL SINGH KE KHET PER | Approved | 0 | 0 | 2025-10-02
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/9993695804 — PASHU SHAT RAMDATT SINGH S/O NARAYAN SINGH RURAN | Closed | 115900 | 0 | 2015-08-15
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/9993728535 — CATTLE SHED MAHENDRA S/O RAMSWAROOP | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/9993728538 — CATTLE SHED UDAYSINGH S/O RAMSWAROOP | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/9993728541 — CATTLE SHED KALU S/O JADUNATH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/9993728544 — CATTLE SHED RAMDUTT S/O NARAYAN | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/9993728548 — CATTLE SHED MUNNA S/O UJAGAR | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/9993728549 — CATTLE SHED JALSINGH S/O RAMSWAROOP | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/9993728550 — CATTLE SHED BIRENDRA S/O SAGDU | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/9993728551 — CATTLE SHED GOBINDRA S/O MOHAR SINGH | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/9993728553 — CATTLE SHED ANIL S/O SOWRAN | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/9993728554 — CATTLE SHED RAMKISHOR S/O BAUHRAN | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/9993740024 — cattle shed ramkishor s/o bahoran madhupura | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/9993740025 — cattle shed jalsingh/ramshrop | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/9993740026 — veerendra/sambhu | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/9993740027 — ramdyal//narayansingh | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/9993740028 — chunni/pachoo | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/9993740029 — anil/sovaran | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/9993740030 — cattle shed jadunath/ativalsingh | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/9993740031 — cattle shed kamlesh devi/vaijnath | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/9993740032 — cattle shed ramnresh/harisingh | Closed | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002061/IF/9993740033 — cattle shed sanjaysingh/pratapsingh | Closed | 0 | 0 | 2016-01-26
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002061/IF/IAY/120853 — Construction of IAY House -IAY REG. NO. MP-02-002-061-001/60 | Completed | 14310 | 9018 | 2016-07-05 | 2018-08-27
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002061/IF/IAY/4377436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103128445 | Closed | 18360 | 0 | 2022-10-14
BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002061/IF/IAY/4379021 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131820487 | Closed | 18360 | 0 | 2022-10-19
BHIND | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002061/IF/IAY/4395155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103436379 | Closed | 19890 | 0 | 2023-07-08
BHIND | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002061/IF/IAY/4396468 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106944826 | Closed | 19890 | 0 | 2023-07-08
BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002061/IF/IAY/82330 — Construction of IAY House -IAY REG. NO. MP-02-002-061-001/58 | Completed | 14310 | 11022 | 2016-08-01 | 2018-08-24
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002061/LD/22012034555879 — Med bandhan kalu | Closed | 0 | 0 | 2021-04-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002061/LD/22012034555882 — Med bandhan Nandkishor | Closed | 0 | 0 | 2021-04-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002061/LD/22012034555883 — Med bandhan Nandkishor | Closed | 0 | 0 | 2021-04-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002061/LD/22012034555885 — Med bandhan rajkumar | Closed | 0 | 0 | 2021-04-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002061/LD/22012034555886 — Med bandhan narsingh | Closed | 0 | 0 | 2021-04-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002061/LD/22012034555888 — Med bandhan govindra singh | Closed | 0 | 0 | 2021-04-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002061/LD/22012034555889 — Med bandhan Rabindra | Closed | 0 | 0 | 2021-04-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002061/LD/22012034555890 — Med bandhan bade | Closed | 0 | 0 | 2021-04-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002061/LD/22012034555892 — Med bandhan Rajendra | Closed | 0 | 0 | 2021-04-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002061/LD/22012034555893 — Med bandhan kalyan | Closed | 0 | 0 | 2021-04-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002061/LD/22012034555894 — Med bandhan virendra | Closed | 0 | 0 | 2021-04-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002061/LD/22012034555896 — Med bandhan jagmohan | Closed | 0 | 0 | 2021-04-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002061/LD/22012034555897 — Med bandhan pappu | Closed | 0 | 0 | 2021-04-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002061/LD/22012034555899 — Med bandhan tulsiram | Closed | 0 | 0 | 2021-04-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002061/LD/22012034555900 — Med bandhan Raju | Closed | 0 | 0 | 2021-04-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002061/LD/22012034555902 — Med bandhan radhu | Closed | 0 | 0 | 2021-04-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002061/LD/22012034555903 — Med bandhan radhu | Closed | 0 | 0 | 2021-04-02
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002061/LD/22012034555905 — Med bandhan Ramvir | Closed | 0 | 0 | 2021-04-02
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002061/OP/9425890202 — SHANTI DHAM MADANAI | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002061/OP/9425890203 — SHANTI DHAM RURAN | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002061/OP/9425890207 — bandriwal ruran | Deleted | 0 | 0 | 2016-01-26
BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002061/OP/9425891172 — SHANTIDHAM NIRMAN VIKASH KARYA | Deleted | 597000 | 0 | 2016-12-16
BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002061/OP/9425892839 — SHANTI DHAM NIRMAN KARYA MADNAI | Completed | 245000 | 243272.95 | 2017-03-25 | 2018-02-21
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002061/PG/22012034365450 — KHEL MAINDAN NIRMAN MADNAI | Completed | 353000 | 249899.65 | 2017-10-30 | 2019-02-15
BHIND | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002061/RC/13 — पहुचंमार्ग मिटटी बजरीकरण रूरन से माता मन्दिर तक | Completed | 0 | 1500 | 2011-01-18 | 2016-12-26
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034201812 — C.C.ROAD PANCHAYAT BHAWAN SE RAJU SINGH KE DWAR KI | Completed | 123191 | 46612 | 2014-02-03 | 2016-10-18
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034201813 — C.C.ROAD KUNWAR SINGH KE MAKAN SE LAKHAN SINGH KE | Completed | 123191 | 46612 | 2014-02-03 | 2017-01-09
BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034227787 — C.C.ROAD BRIJKISHOR SINGH KE MAKAN SE JASMAT KE MA | Deleted | 88921 | 0 | 2014-09-08
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034285417 — C.C.ROAD MUKHYA SADAK SE JAL SINGH KE GHAR KU AUR MADHUPURA | Completed | 63156 | 38475.9 | 2015-09-28 | 2016-05-18
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034285419 — C.C.ROAD RURAN SE BABA MATA KE MANDIR KI AUR | Completed | 210468 | 183081 | 2015-09-28 | 2016-05-18
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1702002061/RC/22012034290257 — C.C.ROAD MUKHYA SADAK SE ASHOK HARIJAN KI VASTI KI AUR | Completed | 126297 | 104275 | 2015-12-09 | 2016-08-18
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002061/RC/22012034292864 — C.C.ROD MEN ROD SE DEEP KE GHAR KEE OR | Deleted | 0 | 0 | 2015-04-14
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034294302 — C.C.ROD MEN ROD SE DEEP KE GHAR KEE OR | Completed | 126000 | 86741 | 2015-12-30 | 2016-07-20
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034309202 — CC ROAD INDRAPAL KE GHAR KI OR | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034309203 — CC ROAD JALSINGH KE GHAR SE FAUJDAR KE GHAR KI OR | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034309204 — CC ROAD KAMAL KE GHAR SE PRATHAMIK SHALA KI OR | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034309205 — CC ROAD RANBIR KE MAKAN SE KALLU KE GHAR OR RURAN | Deleted | 0 | 0 | 2016-01-26
BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034309206 — CC ROAD MEN ROAD SE MADHYAMIK SHALA KI OR MADHUPURA | Deleted | 0 | 0 | 2016-01-26
BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034327757 — C C ROD HARIJAN VASTI RAMNARAYAN KE MAKAN SE SUKHRAM KE MAKAN TAK MADNAI | Completed | 81125 | 27054 | 2017-02-19 | 2017-04-02
BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034327761 — c c rod harijan basti mukhy sadak se santram jatav ke makan tak | Completed | 122425 | 73314 | 2017-02-26 | 2017-08-04
BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034333391 — C C ROD SHANTI KE MAKAN SE PS SCHOOL TAK MADNAI | Completed | 75000 | 44720 | 2017-03-25 | 2017-09-15
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034351363 — CC road santram ke Makan se Mulayam ke Makan ki or | Completed | 31000 | 32164 | 2017-08-28 | 2017-10-17
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034351364 — CC ROAD MUKHYA SADAK SE GAJENDRA KE MAKAN KI RO | Completed | 48700 | 63640 | 2017-08-28 | 2017-10-25
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034363960 — CC ROAD DOCTOR KE MAKAN SE SHAILENDRA KE MAKAN KI OR | Completed | 44300 | 44204 | 2017-10-16 | 2017-10-25
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034365393 — CC ROAD RAVINDRA KE MAKAN SE BARI KI OR | Completed | 44300 | 42468 | 2017-10-30 | 2019-03-27
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002061/RC/22012034365396 — SUDOOR SAMPARK SADAK RURAN SE MADNAI PRADHAN MANTI SADAK TAK | Completed | 2682000 | 2405214.1 | 2017-10-30 | 2019-09-18
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002061/RC/22012034381262 — SUDOOR SADAK MUKHYA MANTRI SADAK SE SHANTIDHAM TAK | Closed | 650000 | 0 | 2017-10-03
BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034383187 — CC ROAD MAIN ROAD SE VISHRAM KE MAKAN KI OR | Deleted | 93000 | 0 | 2017-01-26
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034386559 — CC ROAD MAIN ROAD SE VISHRAM KE MAKAN KI OR | Completed | 93000 | 119088 | 2018-04-16 | 2019-12-04
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034442726 — cc road | Closed | 0 | 0 | 2019-01-26
BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034448629 — CC ROAD MAIN ROAD SE SHAMSHAN GHAT KI OR | Completed | 138000 | 137104 | 2019-03-18 | 2020-05-12
BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034503889 — CC ROAD VISHRAM KE MAKAN SE BHAGWAN SINGH KE MAKAN KI OR | Closed | 93000 | 0 | 2017-08-23
BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002061/RC/22012034532667 — SUDOOR GRAM SAMPARK SADAK SHAMSHAN GHAT SE PICHORA BABA KI OR | Closed | 0 | 0 | 2020-01-26
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002061/RC/22012034533707 — SUDOOR GRAM SAMPARK SADAK SHANTIDHAM SE SANJAY (PAPPU) KE KHET TAK | Completed | 1451473.51 | 1335514.4 | 2020-08-14 | 2022-04-04
BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002061/RC/22012034533708 — SUDOOR GRAM SAMPARK SADAK SANJAY KE KHET SE PTHAURA BABA MANDIR TAK | Physically Completed | 1473404.28 | 908876.34 | 2020-08-15 | 2026-04-17
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002061/RC/22012034614995 — CC ROAD GUDDU KE MAKAN SE MUNNA KE MAKAN KI OR MADHUPURA | Closed | 92000 | 0 | 2022-04-01
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1702002061/RS/22012034603928 — RCC NAALI NIRMAAN SHIVMANGAL KE GONDA SE NAVAV KE GHAR KI TARAF MADHUPURA | Deleted | 0 | 0 | 2021-06-02
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1702002061/RS/22012034603929 — RCC NAALI NIRMAAN SHIVMANGAL KE GONDA SE NAVAV KE GHAR KI TARAF MADHUPURA | Deleted | 0 | 0 | 2021-06-02
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1702002061/RS/22012034603930 — RCC NAALI NIRMAAN SHIVMANGAL KE GONDA SE NAVAV KE GHAR KI TARAF MADHUPURA | Deleted | 0 | 0 | 2021-06-02
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1702002061/RS/22012034603932 — RCC NAALI NIRMAAN SHIVMANGAL KE GONDA SE NAVAV KE GHAR KI TARAF MADHUPURA | Closed | 0 | 0 | 2021-06-02
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1702002061/RS/22012034603936 — RCC NAALI NIRMAAN SHIVMANGAL KE GONDA SE NAVAV KE GHAR KI TARAF | Closed | 0 | 0 | 2021-06-02
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1702002061/RS/22012034603937 — RCC NAALI NIRMAAN SHIVMANGAL KE GONDA SE NAVAV KE GHAR KI TARAF | Closed | 0 | 0 | 2021-06-02
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1702002061/RS/22012034604250 — RCC NAALI NIRMAN SHIVMANGAL KE GONDA SE NAVAV KE GHAR KI TARAF | Closed | 39000 | 0 | 2022-06-02
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1702002061/RS/22012034604302 — RCC NAALI NIRMAN GUDDU KE MAKAN SE MUNNA KE GONDA KI AUR | Closed | 39000 | 0 | 2022-06-08
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702002061/RS/22012034624579 — COMMUNITY TOILET GP MADNAI | Completed | 43000 | 42024 | 2022-04-19 | 2022-10-25
BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1702002061/RS/22012034693170 — Nala nirman kary bade ghar se nathu sachiv k makan ki or madhupura | Physically Completed | 443021.24 | 399690.24 | 2023-05-25 | 2026-04-17
BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soakage Channel for Community / Construction of Soakage Channel for Community | Solid and Liquid Waste Management | 1702002061/RS/22012034693171 — Nala nirman kary guddu k makan se jasvant k gonda ki or madhupura | Closed | 0 | 0 | 2022-10-02
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002061/RS/42944 — MARYADA ABHIYAN MAHIPAL / DALJEET SINGH | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002061/RS/42947 — MARYADA ABHIYAN BHURE SINGH / SUKHYO SINGH | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002061/RS/42958 — MARYADA ABHIYAN BADE MUNNA SINGH / RAJA SINGH | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002061/RS/42960 — MARYADA ABHIYAN RAM BHAROSE / DEVLAL | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002061/RS/42965 — MARYADA ABHIYAN RAM AVTAR SINGH / MURAT SINGH | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002061/RS/42967 — MARYADA ABHIYAN BRIJESH SINGH / BABU SINGH | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002061/RS/42969 — MARYADA ABHIYAN RAM PRATAP SINGH / SEKH BAHADUR SINGH | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002061/RS/42972 — MARYADA ABHIYAN SHIVKANT/ RAMCHADRA / RAM ROOP SINGH | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002061/RS/42975 — MARYADA ABHIYAN SANTRAM / KALICHARAN | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002061/RS/42979 — MARYADA ABHIYAN MUNNA SINGH / KADORE SINGH | Completed | 4500 | 2628 | 2013-07-29 | 2016-08-11
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002061/RS/42983 — MARYADA ABHIYAN RAHUL / VEER SINGH | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002061/RS/42986 — MARYADA ABHIYAN BEBA NIRMLA DEVI / DEEP SINGH | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002061/RS/42989 — MARYADA ABHIYAN BALDU / GHANSHYAM | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002061/RS/42991 — MARYADA ABHIYAN SANJAY SINGH / RANJEET SINGH | Completed | 4500 | 2628 | 2013-07-29 | 2016-08-11
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002061/RS/42994 — MARYADA ABHIYAN RAM NARESH / TULSIRAM | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002061/RS/42996 — MARYADA ABHIYAN RAMVATI / SUKHHE | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002061/RS/42998 — MARYADA ABHIYAN LALTA / CHOTE | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002061/RS/43001 — MARYADA ABHIYAN RAM KRIPAL / BAJNATH SINGH | Completed | 4500 | 2628 | 2013-07-29 | 2016-08-11
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002061/RS/43007 — MARYADA ABHIYAN GUDDU / DEEP SINGH / BAHGWAN SINGH | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002061/RS/43009 — MARYADA ABHIYAN MUNNA SINGH / KOK SINGH | Deleted | 4500 | 0 | 2012-08-15
BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002061/WC/22012034293632 — TALAB GAHARIKARAN KARYA MADHUPURA | Deleted | 100000 | 0 | 2016-05-21
BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002061/WC/22012034324317 — TALAB MARAMMAT KARYA MADHUPURA | Completed | 91000 | 75336 | 2017-05-15 | 2017-07-18
BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1702002061/WC/22012034494678 — REPAIRING OF POND RURAN | Closed | 0 | 0 | 2019-08-15
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002061/WC/22012034545324 — budh singh / rushtam | Completed | 262827.96 | 256544.2 | 2020-05-12 | 2020-10-29
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002061/WC/22012034546869 — new talab mata mandir madnai | Closed | 0 | 0 | 2020-04-21
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coast Line Plntation-Coastal Shelter Belt-Comm / Along the coast Line Plantation of Coastal Shelter Belt Trees for Community | Plantation | 1702002061/WC/22012034570695 — Ran singh/ kadhore | Completed | 332572.21 | 300743.97 | 2020-08-19 | 2020-11-19
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002061/WC/22012034594874 — med bandhan surendra singh madnai | Completed | 35049.22 | 34200 | 2020-12-09 | 2021-01-01
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002061/WC/22012034595760 — Naveen talab madnai | Closed | 0 | 0 | 2020-11-19
BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002061/WC/22012034596996 — naveen talab bela mandir ke pass madnai | Completed | 316441.08 | 148010 | 2020-12-17 | 2021-01-13
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1702002061/WC/22012034608220 — Saundari Karan talab madhupura | Completed | 2484274.24 | 2375951.11 | 2021-09-29 | 2022-09-29
BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Earthen Spur for Community / Construction of Earthen Spur for Community | Construction of Spur | 1702002061/WC/22012034803294 — NAVEEN TALAB NIRMAN GAOSHALA KE PASS | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002061/WC/22012034835856 — STOP DAM NIRMAN BELAMATA MADIR KE PASS | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002061/WC/22012034835865 — STOP DAM PAPPU KE KHET KE PASS | Closed | 0 | 0 | 2021-04-14
BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002061/WC/22012034835868 — STOP DAM VISHRAM SINGH KE KHET KE PASS | Closed | 0 | 0 | 2021-04-14
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002061/WC/22012034961554 — ARTHEN BUND GAUSHALA KE PASS | Closed | 0 | 0 | 2022-04-14
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002061/WC/22012034961559 — CHECK DAM NIRMAN GAUSHALA KE PASS | Closed | 0 | 0 | 2022-04-14
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002061/WC/22012035016891 — Arthen Bund Ramdatt ke khet ke pass Ruran | Ongoing | 1352710.33 | 376380 | 2022-12-27
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002061/WC/22012035019461 — ARTHAN BUND RAMNARESH SINGH KE KHET KE PASS | Closed | 0 | 0 | 2022-10-02
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002061/WC/22012035019475 — ARTHAN BUND RAGHOLE KE KHET KE PASS | Closed | 0 | 0 | 2022-10-02
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002061/WC/22012035030371 — AMRAT SAROVAR DUG TANK NIRMAN KARYA GAUSHALA MADNAI KE PASS | Closed | 0 | 0 | 2022-10-02
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002061/WC/22012035036151 — Arthen bund Govind Ke Khet Ke Pass | Closed | 0 | 0 | 2022-10-02
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002061/WC/22012035036153 — Arthen Bund tulsiram ke banth ke pass | Closed | 0 | 0 | 2022-10-02
BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002061/WC/22012035036158 — Arthen Bund Nathu ke bandh ke pass | Closed | 0 | 0 | 2022-10-02
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002061/WC/22012035071549 — ARTHAN DAM RAMNARESH KE BANDH KE PASS | Ongoing | 1357479.14 | 38454 | 2023-08-31
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002061/WC/22012035071553 — ARTHAN DAM TULSIRAM KE BANDH KE PASS | Ongoing | 1110068.08 | 24310 | 2023-09-15
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002061/WC/22012035092455 — CHECKDEM NIRMAN KARYA NABAB SINGH KE KHET KE PASS MADHUPURA | Closed | 1174000 | 0 | 2023-09-26
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002061/WC/22012035096228 — ARTHEN BUND NIRMAN SANJAY URF PAPPU KE KHET KE PASS | Closed | 1161126.55 | 0 | 2023-04-14
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002061/WC/22012035096229 — ARTHEN CHECK DAM VISHERAM KE KHET KE PASS | Closed | 0 | 0 | 2023-04-14
BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002061/WC/22012035106508 — Khet talab vishram/nexsan k khet par madnai | Closed | 346836.59 | 0 | 2023-06-08