## Work List
Exported on: 2026-09-10 19:32:57
Filters applied:
Data source: MGNREGA
District: BHIND
Block: All
Panchayat: PAROSA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1702003003/AV/22012034564160 — navin chabutara nirman karya gehu uparjan kendra rawatpura | Closed | 0 | 0 | 2021-01-26
MEHGAON | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1702003003/AV/22012034565698 — navin chabutara nirman karya pds rawatpura | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1702003003/AV/22012034566187 — navin chabutara nirman karya gehu uparjan kendra(pds) rawatpura | Closed | 308412.93 | 0 | 2021-04-14
MEHGAON | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1702003003/AV/22012034602681 — सेग्रिगेसन शेड निर्माण | Ongoing | 38000 | 13510 | 2021-11-08
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702003003/AV/22012034620126 — MAA KE BAGIYA P.S.M | Closed | 17000 | 0 | 2022-04-04
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702003003/AV/22012034622914 — Shanti Dham Nirman Nadi ke paas parosa | Closed | 0 | 0 | 2022-08-18
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702003003/AV/2479 — Aanganbadi Bhavan Nirman Sewa Kendra,PAROSA | Completed | 330000 | 321413 | 2014-10-10 | 2016-01-09
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702003003/AV/4017 — Aanganbadi/Other Rural Infrastructure,PAROSA | Completed | 330000 | 316991 | 2015-11-25 | 2016-05-13
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003003/DP/22012034239732 — Brachya Ropan Karya Parosa | Completed | 335000 | 3096 | 2017-05-08 | 2021-12-05
MEHGAON | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Afforestation using forstry Trees for Comm / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702003003/DP/22012034626679 — Vraksharopan karya shree hanuman ji mandir parisar | Approved | 0 | 0 | 2024-06-08
MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003003/FP/22012034364486 — pakka nala nirman karya basti se uchit mulya ki dukan ki oor | Closed | 0 | 0 | 2019-06-26
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003003/FP/22012034624925 — cc nala nirman karya jagat singh ke makan se main road ki oor | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003003/FP/22012034624926 — kachha nala nirman karya deendayal ke makan se siloli ki oor | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003003/FP/22012034624927 — cc nala nirman karya rakesh foji ke makan se malkhan ke makan ki oor | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1702003003/FP/22012034629869 — kool nirman mathuri singh ke khet se aydhyaprasad ke khet tak | Ongoing | 179415.96 | 99365 | 2022-11-03
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1702003003/FP/22012034629870 — kool Nirman munni singh ke khet se Ramniwas sharma ke khet tak | Ongoing | 260233.46 | 191573 | 2022-10-02
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1702003003/FP/22012034629871 — Kool nirman Suresh Sharma ke Khet Se Ramprakash Dngroliya ke khet tak | Ongoing | 182927.96 | 102969 | 2022-10-02
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1702003003/FP/22012034629873 — Kool Nirman Dinesh sharma ke khet se Budhdhan Valmik ke khet tak | Ongoing | 182927.96 | 114121 | 2022-10-02
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702003003/FP/22012034630202 — RCC Nala Nirman Middle school Se Nadi ki oor | Closed | 0 | 0 | 2022-08-19
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003003/FP/22012034634620 — flood diversion chanel for community Balister singh ke makan se nadi tak | Closed | 67549.62 | 0 | 2023-04-14
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003003/FP/22012034640312 — flood diversion sankar ji ke mandir se mata ke mandir ke or | Closed | 0 | 0 | 2024-03-15
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003003/FP/22012034640313 — flood diversion hanuman ji ke mandir se bani ke pura ke or | Closed | 0 | 0 | 2024-03-15
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1702003003/IC/22012034883021 — Construction of water course field channel shreevarnarayan ke khet se shyambihari ke khet tak | Ongoing | 196793.11 | 25716 | 2024-03-16
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1702003003/IC/22012034883022 — Construction of water course field channel Dheer Singh ke khet se Ramniwas ke khet tak | Ongoing | 210104.11 | 29915 | 2024-03-16
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1702003003/IC/22012034883023 — Construction of water course field channel Ramniwas ke khet se shivcharan ke khet tak | Ongoing | 230203.71 | 8840 | 2024-03-16
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003003/IF/22012034352854 — Brachya Ropan Karya Schkool Or Shanti Dham Per Ravat Pura | Completed | 335000 | 27864 | 2017-09-09 | 2021-12-05
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003003/IF/22012034368993 — Brachya Ropan Karaya Road Kinare Or Mata Mandir Ke Pass | Deleted | 0 | 0 | 2017-06-01
MEHGAON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1702003003/IF/22012034430469 — vruksha ropan Omprakesh | Closed | 188000 | 0 | 2018-04-14
MEHGAON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1702003003/IF/22012034432801 — vruksharopan Kanhaiyalal Sharma | Closed | 188000 | 0 | 2018-08-22
MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/22012034584624 — pashu shed munni / mangal singh | Deleted | 0 | 0 | 2020-04-14
MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/22012034584625 — pashu shed amol singh / cheetu singh | Deleted | 0 | 0 | 2020-04-14
MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/22012034584626 — pashu shed bhikhari / khyali | Deleted | 0 | 0 | 2020-04-14
MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/22012034584627 — pashu shed dharshanlal / ghulai | Deleted | 0 | 0 | 2020-04-14
MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/22012034584628 — pashu shed mahesh singh / suresh singh | Deleted | 0 | 0 | 2020-04-14
MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003003/IF/22012034584782 — braksharopan karya chetram ke pura ke pass school kebagal me | Physically Completed | 677985.75 | 416862 | 2020-08-31 | 2026-05-14
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702003003/IF/22012034743008 — medbandhan barsha katare | Completed | 17347.34 | 15054 | 2021-05-28 | 2021-07-05
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702003003/IF/22012034743012 — nadep mohan kushwah | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702003003/IF/22012034743016 — nadep devendra / deewan singh | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702003003/IF/22012034743022 — nadep shiroman / lal singh | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702003003/IF/22012034743028 — nadep dharmendra / vijay singh | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702003003/IF/22012034743033 — nadep shankar singh | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702003003/IF/22012034743040 — nadep lal singh / patiram | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Gully Plugs for Individual / Construction of Earthen Gully Plugs for Individuals | Boulder Check/Gully Plug | 1702003003/IF/22012034743042 — medbandhan shishupal singh | Completed | 43759.53 | 44004 | 2021-06-04 | 2021-07-05
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702003003/IF/22012034743045 — nadep dharmendra singh | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702003003/IF/22012034743049 — nadep ramu singh | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Stone contour Bund for Individuals / Construction of Stone contour Bund for Individuals | Construction of Bund | 1702003003/IF/22012034788530 — samtalikaran ramgopal / chetram | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1702003003/IF/22012034788533 — samtalikaran pohap singh / ajudhhi singh | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702003003/IF/22012034788535 — samtalikaran shrinivas / chetram | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702003003/IF/22012034788537 — samtalikaran narendra / chetram | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702003003/IF/22012034788540 — samtalikaran sulekha / vishwanath | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Gully Plugs for Individual / Construction of Earthen Gully Plugs for Individuals | Boulder Check/Gully Plug | 1702003003/IF/22012034788542 — samtalikaran basant singh / ran singh | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Gully Plugs for Individual / Construction of Earthen Gully Plugs for Individuals | Boulder Check/Gully Plug | 1702003003/IF/22012034788544 — samtalikaran gandarf singh / ran singh | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702003003/IF/22012034809491 — nadep jahar singh | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702003003/IF/22012034809497 — nadep vimlesh singh | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702003003/IF/22012034809503 — nadep RANVEER SINGH | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702003003/IF/22012034809515 — NADEP ROOP SINGH | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702003003/IF/22012034809520 — NADEP DESHRAJ SINGH | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702003003/IF/22012034809522 — NADEP JABAR SINGH | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702003003/IF/22012034809524 — NADEP MANOJ SINGH | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702003003/IF/22012034809526 — NADEP MAHENDRA SINGH | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702003003/IF/22012034809528 — NADEP RAGHURAJ SINGH | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702003003/IF/22012034809529 — NADEP DHARA SINGH | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702003003/IF/22012034809532 — NADEP MUNNI BALMIKI | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702003003/IF/22012034834724 — SHOKTA GADDA RAY SINGH | Closed | 8780 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702003003/IF/22012034849587 — nadep taka shishupal singh / khusali singh | Closed | 1627 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702003003/IF/22012034849771 — nadep jatan singh | Closed | 1627 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702003003/IF/22012034849850 — nadep tanka veer singh | Closed | 1627 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702003003/IF/22012034849853 — nadep tanka jahar singh | Closed | 1627 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702003003/IF/22012034849856 — nadep tanka kanhaiyalal sharma | Closed | 1627 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702003003/IF/22012034849859 — nadep tanka dheer singh | Closed | 1627 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702003003/IF/22012034849863 — nadep tanka vinaypratap | Closed | 1627 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702003003/IF/22012034849874 — shokhta gadda shashkiya prathmik vidhyalaya parosa | Closed | 8780 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702003003/IF/22012034849880 — shkota gadda shshkiya school hotam singh ka pura | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702003003/IF/22012034849889 — shokhta gadda shashkiya prathmik vidhyalaya hamire ka pura | Closed | 8780 | 0 | 2021-04-14
MEHGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003003/IF/22012035655496 — Ek bagiya maa ke naam mousammi bai gram Rawatpura | Ongoing | 263511.37 | 26732 | 2026-06-10
MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993652232 — pashu shed ramvivek sharma son of mavasi sharma | Completed | 89000 | 85824 | 2014-09-04 | 2015-01-03
MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993652401 — pashu shet ramvinod / mavasi | Completed | 89000 | 83783 | 2014-09-04 | 2015-02-04
MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993652414 — pashu shet ramadhar / mavasi | Completed | 89000 | 83626 | 2014-09-04 | 2015-01-04
MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993652417 — pashu shet mangal singh / lakhan singh | Completed | 89000 | 79544 | 2014-09-04 | 2016-04-20
MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993652421 — pashu shet girraj sharma / munnalal sharma | Completed | 89000 | 86452 | 2014-09-04 | 2015-01-03
MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993652437 — pashu shet satyanarayan / sevaram sharma | Completed | 89000 | 71537 | 2014-09-04 | 2015-01-03
MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993652441 — pashu shet maniram sharma / harishankar sharma | Completed | 89000 | 81052 | 2014-09-04 | 2016-04-11
MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993652442 — pashu shet rambhog / ramroop | Completed | 89000 | 85039 | 2014-09-04 | 2015-01-03
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704617 — cattle shed manoj / sobran | Completed | 115900 | 108853 | 2016-01-29 | 2016-05-10
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704622 — cattle shed mathuri / matadin | Completed | 115900 | 113782 | 2016-01-29 | 2016-05-11
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704625 — cattle shed balram / ray bahadur | Completed | 115900 | 111397 | 2016-02-18 | 2016-05-11
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704630 — cattle shed ravindra / sarman singh | Completed | 115900 | 113782 | 2016-01-29 | 2016-05-13
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704631 — cattle shed rambaran / santoshi | Completed | 115900 | 111874 | 2016-01-29 | 2016-05-13
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704642 — cattle shed rushtam / ramlakhan | Completed | 115900 | 108694 | 2016-01-29 | 2016-05-10
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704644 — cattle shed girendra / jatar singh | Deleted | 115000 | 0 | 2016-01-10
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704653 — cattle shed rajveer/ prakash | Completed | 115900 | 112507 | 2016-03-19 | 2016-05-13
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704662 — cattle shed surendra / tilak singh | Completed | 115900 | 111715 | 2016-02-18 | 2016-05-11
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704669 — cattle shed sankar /ahivaran singh | Completed | 115900 | 110443 | 2016-02-18 | 2016-05-11
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704671 — cattle shed hawaldar / surjan singh | Completed | 115900 | 110443 | 2016-02-18 | 2016-05-11
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704673 — cattle shed ashok / vasudev | Completed | 116000 | 112680 | 2016-04-06 | 2017-01-18
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704677 — cattle shed suresh / bharat | Deleted | 115000 | 0 | 2015-12-02
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704680 — cattle shed pawan / ramnaresh | Deleted | 115000 | 0 | 2016-01-10
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704684 — cattle shed shivcharan / dinanath | Deleted | 115000 | 0 | 2015-12-02
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704686 — cattle shed ramvaran / shiv singh | Deleted | 115000 | 0 | 2016-01-10
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704690 — cattle shed mathuri / chaingutte | Deleted | 115000 | 0 | 2016-01-10
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704694 — cattle shed devendra / sri krishna | Completed | 115000 | 113348 | 2016-05-10 | 2017-04-17
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704696 — cattle shed bhagvandas / sri krishna | Deleted | 115000 | 0 | 2016-01-10
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704697 — cattle shed shashibai / ramgyan | Deleted | 115000 | 0 | 2016-01-10
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704704 — cattle shed radhacharan / ratiram | Completed | 115900 | 112828 | 2016-02-18 | 2016-05-11
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704707 — cattle shed prem singh / lakhan | Deleted | 115000 | 0 | 2016-01-10
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704708 — cattle shed kamlesh / ramswaroop | Deleted | 115000 | 0 | 2016-01-10
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704710 — cattle shed vacharam / harswaroop | Deleted | 115000 | 0 | 2015-12-02
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704711 — cattle shed ramsevak / satyaram | Deleted | 115000 | 0 | 2016-01-10
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993722241 — pashu shed mukesh sharma | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993722246 — pashu shed nirmad ajit singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993722248 — cattle shed kailash baghel | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724499 — cattle shed mukesh / mahesh thapak | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724502 — cattle shed ajeet shing / ramsaran | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724505 — cattle shed jayendra / ummed singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724508 — cattle shed ramgopal /chetram | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724509 — cattle shed brajkisor / kok singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724512 — cattle shed ulfat singh/ rambharose | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724513 — cattle shed angad baghel / harnarayan | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724515 — cattle shed manoj / prabhunath singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724517 — cattle shed badalu / matadin baretha | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724519 — cattle shed hari prasad / ramvaran | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724521 — cattle shed charan singh / chitra singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724522 — cattle shed anurudh singh / sarnaam | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724527 — cattle shed vimlesh devi / gajraj singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724530 — cattle shed anvesh / prahlaad sharma | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724532 — cattle shed ramkumar / baburam tiwari | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724533 — cattle shed naresh / chhote singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724534 — cattle shed naresh /bhikam singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724535 — cattle shed kaliyan singh / shishupal | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724537 — cattle shed harendra singh / ramnarayan | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724539 — cattle shed shivraj / bhagwan singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724541 — cattle shed ashutosh / ramji lal | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724542 — cattle shed harendra / krishnpal singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724544 — cattle shed sanjay singh / purusottam | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724545 — cattle shed munni devi / shyam prakash | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724547 — cattle shed dinesh / hakim singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724548 — cattle shed dalveer singh / hari singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724550 — cattle shed ganga singh / mullu singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724551 — cattle shed satyaprakash / rajendra singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724554 — cattle shed dinesh / sri narayan | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724555 — cattle shed mukut singh / maharaj singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724556 — cattle shed raju / asharam baghel | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724557 — cattle shed ravindra singh / diwaan singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724558 — cattle shed ramotar / asharam dhanuk | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724560 — cattle shed somta bai / raghuvir singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724561 — cattle shed sangita bai / narendra singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724562 — cattle shed ramlakhan / kunji baghel | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724564 — cattle shed atar singh / ramsahay singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724565 — cattle shed sher singh / asharam | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724566 — cattle shed manju | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724567 — cattle shed rambharose / baijnath | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724568 — cattle shed tehsildar / totaram | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724569 — cattle shed hari pyari / chhitu singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724570 — cattle shed shyambihari / rajaram | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724673 — cattle shed ajodhya prasad / matadin | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724675 — cattle shed chhatrapal / ahivaran singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724676 — cattle shed roop singh / shyam singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724678 — cattle shed kunwar singh / tilak singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724679 — cattle shed mahesh / bharat singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724680 — cattle shed ravindra / lakhan singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724684 — cattle shed lokendra /hazuri singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724685 — cattle shed munni bai / radheshyam | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724686 — cattle shed ramdas / ramnarayan | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724687 — cattle shed prahlad / nihaal singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724688 — cattle shed kishori / kanhai kuswah | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724689 — cattle shed anita / rammurti | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724690 — cattle shed suratram / matadin balmik | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724692 — cattle shed surendra /mohar singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724693 — cattle shed santosh / omprakash | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724695 — cattle shed gayatri devi / pratipal | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724696 — cattle shed veerpal / jagdish singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724698 — cattle shed ranveer / diwaan singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724699 — cattle shed lokesh / prahlad sharma | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993724700 — cattle shed lal singh / patiram | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/118352 — Construction of IAY House -IAY REG. NO. MP-02-003-003-001/14 | Completed | 14310 | 15248 | 2016-07-28 | 2018-08-15
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/203831 — Construction of IAY House -IAY REG. NO. MP-02-003-003-001/74 | Ongoing | 23490 | 522 | 2025-09-23
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/203851 — Construction of IAY House -IAY REG. NO. MP-02-003-003-001/73 | Ongoing | 23490 | 0 | 2016-07-28
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/318353 — Construction of IAY House -IAY REG. NO. MP1065812 | Deleted | 15030 | 0 | 2017-02-01
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/321723 — Construction of IAY House -IAY REG. NO. MP1073128 | Deleted | 15030 | 0 | 2017-02-01
MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/3256934 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3193878 | Physically Completed | 17370 | 13464 | 2022-05-22 | 2024-11-21
MEHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/3270342 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4983742 | Physically Completed | 17370 | 2652 | 2023-09-27 | 2024-11-21
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/378591 — Construction of IAY House -IAY REG. NO. MP1671143 | Completed | 15030 | 15188 | 2017-02-01 | 2017-11-16
MEHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/3788327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120862566 | Physically Completed | 18360 | 9810 | 2023-09-26 | 2024-11-21
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/422890 — Construction of IAY House -IAY REG. NO. MP1346715 | Completed | 15030 | 15168 | 2017-02-08 | 2018-08-13
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/478585 — Construction of IAY House -IAY REG. NO. MP1046399 | Completed | 15030 | 15180 | 2017-07-28 | 2018-09-21
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/544824 — Construction of IAY House -IAY REG. NO. MP3208223 | Completed | 15030 | 15294 | 2017-03-23 | 2018-07-30
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/546041 — Construction of IAY House -IAY REG. NO. MP3242947 | Completed | 15030 | 14970 | 2017-07-01 | 2018-08-05
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/546321 — Construction of IAY House -IAY REG. NO. MP3252955 | Completed | 15030 | 15306 | 2017-03-23 | 2018-08-13
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/546728 — Construction of IAY House -IAY REG. NO. MP3264315 | Completed | 15030 | 15174 | 2017-07-01 | 2018-08-13
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/587087 — Construction of IAY House -IAY REG. NO. MP3226074 | Completed | 15030 | 15136 | 2017-07-01 | 2017-09-07
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/751871 — Construction of IAY House -IAY REG. NO. MP2608371 | Completed | 15030 | 15174 | 2017-07-28 | 2018-08-13
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/916447 — Construction of IAY House -IAY REG. NO. MP2368497 | Completed | 15480 | 11868 | 2017-07-28 | 2018-10-25
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/987410 — Construction of IAY House -IAY REG. NO. MP2568825 | Completed | 15480 | 15204 | 2017-07-28 | 2018-08-23
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/987590 — Construction of IAY House -IAY REG. NO. MP3241789 | Completed | 15480 | 15164 | 2017-07-28 | 2018-08-13
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/987591 — Construction of IAY House -IAY REG. NO. MP3241952 | Completed | 15480 | 15164 | 2017-07-28 | 2018-08-13
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1702003003/LD/22012034593732 — Amrat Vatika Parosa | Closed | 55847.4 | 0 | 2023-04-14
MEHGAON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003003/LD/796 — मेढबंधान राकेश / बच्‍चु मेंहतर | Completed | 20000 | 17568 | 2011-09-07 | 2012-10-01
MEHGAON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003003/LD/885 — खेल का मैदान निर्माण क्रीण्‍णंगन रावतपुरा | Completed | 0 | 19900 | 2012-02-15 | 2015-04-20
MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702003003/OP/9425892780 — Shanti Dham Nirman[ Ravat pura] Parosa | Completed | 180000 | 180268.99 | 2017-03-25 | 2017-10-25
MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702003003/PG/9425896267 — Khel Medan[ Ravat pura ] Parosha | Completed | 353000 | 332794 | 2017-03-25 | 2019-01-10
MEHGAON | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003003/RC/131 — पहुंचमार्ग मिटटी कार्य भिण्‍ड मुरैना रोड से अतरदास बाबा की खेरी तक | Completed | 185000 | 124440 | 2011-12-06 | 2011-12-30
MEHGAON | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003003/RC/150 — सीृसीृ रोड करसोलियन का पुरा परोसा | Completed | 0 | 166481 | 2012-04-02 | 2012-10-29
MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034169146 — c c road lachman singh ke makan sekasadiya mohlla | Completed | 212600 | 211430 | 2013-06-05 | 2014-10-27
MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034173262 — c c road nirman kary ramprakash shrma ke drwaje se | Completed | 145500 | 147386 | 2013-06-29 | 2013-10-31
MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034191467 — cc road panchparmeshavar tejpura road se deendyal | Completed | 197500 | 217733 | 2014-03-04 | 2014-10-27
MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034191471 — panchparmeshvar cc road rajkumar k makn s badai mo | Completed | 201500 | 203857 | 2014-03-04 | 2014-10-27
MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034212263 — panchpar.ccroad nakul singh ke makan se hebran ke | Completed | 236600 | 235729 | 2014-03-05 | 2014-10-27
MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034212275 — panchpar. cc road majara lavera ka pura | Completed | 236600 | 228743 | 2014-03-05 | 2014-10-27
MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034212487 — panchpar cc road main road se kartar singh ke dwar | Completed | 207000 | 150991 | 2014-03-05 | 2014-10-27
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034231058 — Khet sadak yojana Gandharv ke makan se nahar ki oo | Completed | 1456000 | 612509.7 | 2014-10-03 | 2016-10-01
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034231059 — khet sadak yojana main road se nahar tak | Completed | 1344000 | 62643 | 2014-10-03 | 2016-08-08
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034231695 — antarik gsb Shishupal ke makan se raghuveer ke makan ki oor | Completed | 709000 | 4710 | 2014-10-20 | 2014-12-15
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034231696 — antrik gsb Angad valmik ke makan se chetram ke makan ki oor | Completed | 446000 | 4710 | 2014-10-20 | 2014-12-15
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034231697 — panch par, cc road Ajmer ke makan se dhaniram ke makan ki oor | Completed | 91400 | 87896 | 2014-10-20 | 2015-01-09
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034231698 — panch par c c raod nirmad Bhup singh ke makan se mahesh rathor ke makan ki oor | Completed | 78500 | 76176 | 2014-10-20 | 2015-01-09
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034231699 — GSB road main road se atardas baba ke ashram ki oor | Completed | 1390000 | 956044.7 | 2014-10-21 | 2015-11-06
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034231910 — Antrik Gsb panchayat bhavan se angad valmik ke ghar ki oor | Completed | 446000 | 7693 | 2014-10-20 | 2014-12-15
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034231911 — antrik gsb rawatpura se shishupal ke makan ki oor | Completed | 446000 | 4710 | 2014-10-20 | 2014-12-15
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034231912 — C C road nirmad kalka mandir se gambhir ke makan ki oor | Completed | 52700 | 54398 | 2014-10-20 | 2015-01-09
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034285804 — c c road panchayat bhavan tirahe se shivcharan singh k mkan ki or | Completed | 230000 | 216973 | 2015-10-22 | 2016-05-11
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034305990 — khet sadak lakhan singh k pura se bammaki puliya tk | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034307345 — khet sadak main road se lavera k pura ki taraf | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034307347 — khet sadak lakhan singh k pura bamma ki puliya tk | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034307348 — khet sadak tejpura road se mahipati baghel k makan ki or | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034307349 — khet sadak balu singh k pura se jagat singh k makan bmma tk | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034307350 — GSB road atardas baba marg se jodharam k purra ki or | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034307352 — GSB road shivprasad k pura se damir baghel k pura ki or | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034307355 — c.c.road main road se angad singh k makan ki or | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034307358 — c.c.road jodharam k darwaje se shyam prakash k makan ki or | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034307359 — c.c.road omprakash k kua se rameshwar k mandir ki or | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034307361 — c.c.road lakhan k pura se balmik muhalla ki or | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034307362 — c.c.road chetram k pura se lakhan singh k pura ki or | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034307363 — c.c.road balmik muhalla se babu singh k pura panchayat bhavan ki or | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034307365 — c.c.road baltar singh k duar se hakim singh k makan tk | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034307366 — c.c.road prabhunath singh k makan se narottam k makan tk | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034325331 — C C Road Ramveer Ke Darbaje Se Thakur Baba Mandir Kee Or | Completed | 159200 | 155811 | 2017-02-08 | 2017-05-30
MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034325332 — C C Road Hari Singh Ke Darbaje Se Angad Balmik Ke Makan Kee Or | Completed | 420000 | 396460 | 2017-02-04 | 2017-05-30
MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034333207 — C C Road Munna Kushwah Ke Makan Mathuri Kushwah Ke Makan kee or | Completed | 110250 | 95448 | 2017-03-25 | 2017-05-30
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034334122 — C C Road Panchyat Bhavan Se Kamlesh Balmik Ke Makan Kee Or | Completed | 265000 | 243140 | 2017-04-02 | 2017-05-30
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034336904 — C C Road Main Road Se Middle Sckool Tak | Completed | 29500 | 28944 | 2017-05-03 | 2017-05-30
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034343721 — Sudoor Samparak Sadak Yojana Main Road Se Labera pura tak | Ongoing | 1100000 | 1004860.26 | 2017-07-26
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034347910 — C C Road Raghunandan Ke Makan Se Naresh Ke Makan Tak | Completed | 160000 | 2064 | 2017-08-01 | 2017-08-19
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034372983 — C C Road Chetram Ke Pura Se Angad Balmik Ke Makan Ke Or | Completed | 320000 | 217548 | 2019-01-04 | 2021-12-05
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034396190 — C C Road Angad Ke Makan Se Ramsaran Ke Makan Kee Or | Ongoing | 348000 | 158688 | 2018-12-05
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034396192 — C C Road Ulaphat Singh Ke Makan Se Prabhoonath Ke Makan Kee Or | Completed | 320000 | 75696 | 2019-01-27 | 2021-12-05
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034396203 — C C Road Rashal Singh Ke Makan Se Vasti Kee Or | Closed | 140000 | 0 | 2022-02-15
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034434273 — C C Road Chetram Ke Pura Se Lakhan Singh Ke Pura Ke Or | Completed | 282000 | 154467 | 2019-01-04 | 2021-12-05
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034442179 — cc road | Deleted | 0 | 0 | 2019-01-26
MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034514503 — Cc Road Shishupal Ke Makan Se Gaon Ki Oor | Completed | 93000 | 88730 | 2020-04-22 | 2020-06-09
MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034516216 — Cc Road Lal Singh Ke Makan Se Rajbahadur Ke Makan Ki Oor | Completed | 93000 | 89642 | 2020-02-03 | 2021-01-01
MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034516755 — sudoor sadak gadhar singh ke pura se prathmik shala chetram ke pura tak | Deleted | 0 | 0 | 2019-06-26
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034563085 — cc road deshraj ke makan se deewan singh ke makan tak | Ongoing | 71100 | 11580 | 2021-04-20
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034563086 — cc road ramlakhan ke makan se mathuri ke makn ki oor | Ongoing | 71100 | 11580 | 2021-04-28
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034587283 — CC Road Nirman main road se govt primary school hote hue tomaran ke pura tak | Deleted | 139500 | 0 | 2021-09-15
MEHGAON | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003003/RC/65 — पहुचमार्ग परोसा रावतपुरा से शंरपुरा होते हुये परोसा बम्‍बा तक | Completed | 0 | 113280 | 2010-10-03 | 2011-01-03
MEHGAON | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003003/RC/96 — पहुचमार्ग परोसा रावतपुरा से भिण्‍ड , मुरैना रोड तक | Completed | 398803 | 291336 | 2011-04-10 | 2011-10-17
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702003003/RS/22012034528647 — segregation shed nirman karya gram panchayat parosa | Closed | 57000 | 0 | 2021-09-08
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1702003003/RS/22012034584791 — Nala Nirman Gopal ke makan se shishupal ke makan ki or | Ongoing | 1488501.57 | 1359834 | 2021-11-08
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702003003/RS/22012034593473 — सामुदायिक स्वच्छता परिसर निर्माण | Ongoing | 43000 | 965 | 2021-11-09
MEHGAON | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702003003/WC/22012034324240 — Talab Nirman Karya Mata Mandir Ke Pass Parosa | Completed | 869000 | 551361 | 2017-05-12 | 2018-04-04
MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702003003/WC/22012034612015 — navin talab nirman karya hanumanji ke mandir ke pass parosa | Deleted | 0 | 0 | 2020-08-15
MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1702003003/WC/22012034665651 — DUG TANK NIRMAN KARYA SHANTIDHAM | Completed | 1414219.95 | 1209306.17 | 2021-05-12 | 2022-03-03
MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003003/WC/22012034693282 — naveen talab nirman karya hanumanji ke mandir ke pass parosa | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003003/WC/22012034949189 — Naveen Talab Nirman Shree hanuman ji mandir ke pas parosa | Closed | 0 | 0 | 2022-04-14
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1702003003/WC/22012034974520 — अम्रत सरोवर निर्माण श्री हनुमान जी मंदिर के पास परोसा | Ongoing | 1138000 | 69768 | 2022-05-19
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1702003003/WC/22012034974521 — अम्रत सरोवर निर्माण श्री हनुमान जी मंदिर के पास परोसा | Closed | 0 | 0 | 2022-04-14
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1702003003/WC/22012034993924 — Naveen Talab Nirman khere wali mata ke mandir ke paas | Ongoing | 1490359.92 | 835669 | 2022-11-03
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702003003/WC/22012035199431 — water harvesting gandharv ke khet ke paas | Closed | 0 | 0 | 2024-03-15
MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003003/WH/22012034935207 — तालाब जीर्णोद्धार कार्य परोसा | Closed | 18000 | 0 | 2022-04-14
MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003003/WH/22012034935213 — तालाब जीर्णोद्धार कार्य रावतपुरा | Closed | 18000 | 0 | 2022-04-14