## Work List
Exported on: 2026-10-14 03:39:08
Filters applied:
Data source: MGNREGA
District: BHIND
Block: All
Panchayat: ARELEKAPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702003011/AV/22012034620086 — MAA KI BAGIYA P.S.V HASANPURA | Closed | 17000 | 0 | 2022-04-04
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1702003011/AV/22012034620087 — Maa ki bagiya anganvadi shreekapura | Closed | 17000 | 0 | 2022-04-14
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1702003011/AV/22012034620193 — Maa ki bagiya anganvadi shreekapura | Closed | 17000 | 0 | 2022-04-14
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003011/DP/22012034239690 — Brachya Ropan Karya Road Kinare Arele ka pura | Completed | 335000 | 6192 | 2017-05-08 | 2021-12-13
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1702003011/DP/22012034598249 — प्लांटेशन वर्क शांतिधाम एवं स्कूल अरेलेका पुरा | Closed | 0 | 0 | 2023-04-14
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1702003011/DP/22012034598315 — मेरी माटी मेरा देश प्लांटेशन वर्क शांति धाम एवं स्कूल के पास | Closed | 55847.4 | 0 | 2023-07-01
MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003011/FP/22012034363381 — Kachha Nala Nirman Karya Gao Se Bahar Kee Or | Completed | 498019.58 | 464972 | 2019-10-26 | 2020-07-24
MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1702003011/FP/22012034363818 — KACCHA NALA NIRMAN CC ROAD SE NAHAR KI ORE | Closed | 0 | 0 | 2019-10-06
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003011/FP/22012034368706 — Patar Nala Nirman Jagdeesh Ke Goda Se Talab Ki Oor 15Vitt | Completed | 177600 | 176016 | 2021-05-25 | 2021-06-25
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003011/FP/22012034625610 — Kool nirman narottam ke khet se sahib singh ke khet ki or | Completed | 344423.53 | 288342 | 2021-06-25 | 2022-10-31
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003011/FP/22012034625611 — Kaccha nala shreekapura omprakash ke khet se Raja bhaiya ke khet ki or | Completed | 329536.19 | 266340 | 2021-10-11 | 2022-10-31
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003011/FP/22012034632260 — Pakka nala panchayat bhavan ke pass se Randhir ki or | Ongoing | 1160127.81 | 110908 | 2023-03-11
MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1702003011/IC/22012034389375 — Kool nirman Omprakash ke khet se Jagdeesh ke khet kee or | Closed | 0 | 0 | 2021-03-08
MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1702003011/IC/22012034389376 — kaccha nala nirman Vakeel ke khet se Sahab singh ke khet ki or | Closed | 0 | 0 | 2021-03-08
MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Lining of distributary Canal for Community / Lining of distributary Canal for Community | Lining of Canal | 1702003011/IC/22012034389785 — Kaccha nala nirman kedar singh ke khet se Om singh ke khet ki or | Completed | 641010.44 | 520714 | 2021-08-12 | 2023-04-20
MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Lining of distributary Canal for Community / Lining of distributary Canal for Community | Lining of Canal | 1702003011/IC/22012034389786 — Kool nirman prag singh ke khet se keshav ke khet ki or | Completed | 445003.81 | 374034 | 2021-06-16 | 2023-04-20
MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Lining of distributary Canal for Community / Lining of distributary Canal for Community | Lining of Canal | 1702003011/IC/22012034390080 — Distributary cannel surendra ke khet se barnam ke khet ki or | Completed | 546888.67 | 182091 | 2022-04-10 | 2024-10-21
MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1702003011/IC/22012034881755 — Kool nirman nirman Asharam ke khet se shovaran ke khet ki or | Completed | 275903.4 | 229636 | 2022-11-16 | 2024-10-24
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1702003011/IC/22012034882735 — Distributary channel Prem singh ke khet se bhagwan singh ke khet ki or | Ongoing | 318152.21 | 103428 | 2023-07-27
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1702003011/IC/22012034883019 — Distributary channel kelash ke khet se bhikaram panda ke khet ki or | Physically Completed | 314572.35 | 184314 | 2023-10-09 | 2026-05-08
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003011/IF/22012034353347 — Brachya Ropan Karya Samudayak Sthal [P S / M S School And Panchyat Bhavan Or Aganbadi Bhavan ]Per | Completed | 335000 | 17000 | 2017-07-30 | 2021-10-25
MEHGAON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1702003011/IF/22012034439828 — vruksha ropan ashok singh | Closed | 188000 | 0 | 2018-10-01
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003011/IF/22012034754267 — MED BANDHAN NAROTTAM SINGH | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003011/IF/22012034754285 — MED BANDHAN JAGMOHAN SINGH | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003011/IF/22012034754290 — MED BANDHAN OMPRAKASH SINGH | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003011/IF/22012034754339 — MED BANDHAN ABHILAKH SINGH | Closed | 31687.06 | 0 | 2021-04-14
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003011/IF/22012034754357 — MED BANDHAN PRAG SINGH | Closed | 31705.26 | 0 | 2021-04-14
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003011/IF/22012034816509 — MED BANDHAN UPENDRA SINGH | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003011/IF/22012035461196 — Khet talab Prakash ke khet pr | Ongoing | 147621.16 | 522 | 2025-05-18
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003011/IF/22012035461488 — Khet talab naresh singh ke khet pr | Ongoing | 147621.16 | 38106 | 2025-05-18
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003011/IF/22012035533028 — Khet talab vinod ke khet ke pass | Ongoing | 147621.16 | 26622 | 2025-06-21
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003011/IF/22012035533510 — Khet talab karan singh ke khet pr | Approved | 147621.16 | 0 | 2025-04-15
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003011/IF/22012035533604 — Khet talab jagdeesh singh ke khet pr | Ongoing | 147621.16 | 43587 | 2025-06-03
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003011/IF/22012035538694 — Khet talab sonkalee ke khet ke pass | Approved | 147621.16 | 0 | 2025-04-15
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003011/IF/22012035550243 — Khet talab Jahan singh ke khet pr | Approved | 147621.16 | 0 | 2025-04-15
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003011/IF/22012035550302 — Khet talab sughar singh ke khet pr | Approved | 147621.16 | 0 | 2025-04-15
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003011/IF/22012035550318 — Khet talab Ramsevak singh ke khet pr | Approved | 147621.16 | 0 | 2025-04-15
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003011/IF/22012035550333 — Khet talab ramdhun ke khet pr | Approved | 147621.16 | 0 | 2025-04-15
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003011/IF/22012035553196 — Khet talab ranjeet singh ke khet pr | Approved | 147621.16 | 0 | 2025-04-15
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003011/IF/22012035553217 — Khet talab Deshraj singh ke khet pr | Approved | 147621.16 | 0 | 2025-04-15
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003011/IF/22012035553256 — Khet talab deewan singh ke khet pr | Approved | 147621.16 | 0 | 2025-04-15
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993700084 — Pashu Shed Narottam/Garjan Singh | Completed | 116000 | 8586 | 2016-01-04 | 2016-01-27
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993700085 — Pashu Shed Lal singh/Shivnath | Completed | 116000 | 112410.71 | 2016-01-04 | 2016-05-09
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993700086 — Pashu Shed Barnam /Kaptan singh | Completed | 116000 | 111456.71 | 2016-01-04 | 2016-05-09
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993700087 — Pashu Shed Biswnath /Lajjaram | Completed | 116000 | 9540 | 2016-01-04 | 2016-01-27
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993700445 — Pashu shed Lal singh S/O kedar singh | Completed | 116000 | 101555.61 | 2016-05-29 | 2016-10-12
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993700448 — pashu shed Ram nivas singh S/O Aasharam singh | Deleted | 115900 | 0 | 2015-11-28
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993702271 — Pashu Shed Shovaran /Sumer singh | Completed | 116000 | 110141.61 | 2016-01-04 | 2016-09-30
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993702273 — Pashu Shed Roop singh /Darshan singh | Completed | 116000 | 112569.71 | 2016-01-04 | 2016-05-12
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993702281 — Pashu shed Sarjan / Lachmi singh | Completed | 116000 | 112410.71 | 2016-01-04 | 2016-05-09
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993702282 — Pashu Shed Gandhrav singh / Gorishankar singh | Completed | 116000 | 112410.71 | 2016-01-04 | 2016-05-12
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993702283 — Pashu shed Abhilakh / Bahadur singh | Completed | 116000 | 8586 | 2016-01-04 | 2016-01-27
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993702286 — Pashu shed Bishmbar / Bejnath singh | Completed | 116000 | 111297.71 | 2016-01-04 | 2016-05-09
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993702300 — Pashu Shed Hevran singh /Lakhpati singh | Completed | 116000 | 111095.61 | 2016-01-04 | 2016-09-30
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993702301 — Pashu Shed Naresh/ Nepal singhj | Completed | 116000 | 14310 | 2016-01-04 | 2016-04-17
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993702303 — Pashu shed Sanjay /Ajmer singh | Completed | 116000 | 111615.71 | 2016-01-04 | 2016-05-09
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993702304 — Pashu shed Dayacharan /Asharam singh | Completed | 116000 | 111456.71 | 2016-01-04 | 2016-05-12
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993702306 — Pashu shed Maneeram /sonpal singh | Completed | 116000 | 112410.71 | 2016-01-04 | 2016-05-09
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993702309 — Pashu shed Jaban singh /Ram singh | Completed | 116000 | 112410.71 | 2016-01-04 | 2016-05-09
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993702310 — Pashu shed Purshotam/ Harnarayan singh | Completed | 116000 | 111456.71 | 2016-01-04 | 2016-05-09
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993708720 — Pashu Shed Jaghdeesh / Gyadeen singh | Closed | 116000 | 0 | 2016-01-30
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725347 — Pashu Shed Sikandar singh /Nabal | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725348 — Pashu Shed Vikram singh /Madhav singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725349 — Pashu Shed Beerendra /Randheer singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725350 — Pashu Shed Betal singh /Gauri shankar | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725351 — Pashu Shed Surendra /Ramratan | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725352 — Pashu Shed Gokaran singh /Ramratan | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725353 — Pashu Shed Somaraj /Karatal singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725354 — Pashu Shed Garsingh /Dulare singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725355 — Pashu Shed Charan singh /Bachan singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725357 — Pashu Shed Tek singh Shivnath singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725358 — Pashu Shed Pfate singh /Shivnath | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725359 — Pashu Shed Batan shree /Jaysingh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725362 — Pashu Shed Sher singh /Darshan | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725365 — Pashu Shed Kripa ram /Kishor | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725368 — Pashu Shed Ramshevak /Gulab | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725371 — Pashu Shed Radhe singh /Ramsingh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725374 — Pashu Shed Samarath /Ramsingh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725480 — Pashu Shed Vimala bai /Angad | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725485 — Pashu Shed Manishvar /Hardayal | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725488 — Pashu Shed Madhuraj /Hardayal | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725489 — Pashu Shed Ajamer /Kaliyan | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725492 — Pashu Shed Munna singh /Pahalad | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725493 — Pashu Shed Gyan singh /Badree | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725494 — Pashu Shed Ray singh /Chote | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725495 — Pashu Shed Rajendra /Moharaman | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725496 — Pashu Shed Ahivaran /Majaram | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725497 — Pashu Shed Dhara singh /Majaram | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725498 — Pashu Shed Soobalal /Jagannath | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725499 — Pashu Shed Shreedhar singh /Mansingh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725501 — Pashu Shed Veerendra /Lajjaram | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725505 — Pashu Shed Janak singh /haripal | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725509 — Pashu Shed Rakesh /Parimal | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725512 — Pashu Shed Rajveer /Mukutsingh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725515 — Pashu Shed Meera bai /Mardan singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725516 — Pashu Shed Harigyan /Kanhi | Closed | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725517 — Pashu Shed Brajendra /Chote | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725518 — Pashu Shed Karan singh /Hariprashad | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725519 — Pashu Shed Bheem sen /Ramji lal | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725520 — Pashu Shed Mahesh Prag singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725521 — Pashu Shed Malkhan /LAXMAN | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725524 — Pashu Shed Murli Maharaj singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725526 — Pashu Shed Deevan singh /Matadeen | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725528 — Pashu Shed Rakesh /Jabar singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725536 — Pashu Shed Surendra /Ajamer | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725537 — Pashu Shed Kaptan singh /Girdharee | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725538 — Pashu Shed Hameer singh /Ket singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725539 — Pashu Shed Siddar /Ket singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725540 — Pashu Shed Ashok / Sarnam | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725541 — Pashu Shed Manveer /Sarnam | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725542 — Pashu Shed Ramesh singh /Uday | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725543 — Pashu Shed Narendra /Uday | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725544 — Pashu Shed Mohar singh /Nathu | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725545 — Pashu Shed Sultan singh /Vidya ram singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725546 — Pashu Shed Suresh /Hargovind | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725547 — Pashu Shed Braj raj /Hargovind | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725548 — Pashu Shed Naresh /Gyadeen | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725549 — Pashu Shed Surendra /Chote | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725551 — Pashu Shed Darshan /Vishram | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725552 — Pashu Shed Gyan singh /Ratan lal | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725553 — Pashu Shed Nand ram /Heera lal | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725554 — Pashu Shed Bindravan /Nathu | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725555 — Pashu Shed Raj veer /Bhoop singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725557 — Pashu Shed Balveer /Bhoop | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725558 — Pashu Shed Data ram /Sumer | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725559 — Pashu Shed | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725560 — Pashu Shed Narendra /Asha ram | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725561 — Pashu Shed Shiv singh /Baboo | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725562 — Pashu Shed Dharmveer /Kaptan | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725563 — Pashu Shed Ataraj /Arjun | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725564 — Pashu Shed Ramnaresh /Kelash | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993725565 — Pashu Shed Ramnivash /Rajendra | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993726044 — Pashu Shed Manoj singh /Mahendra | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993726046 — Pashu Shed Ramkumar /Jagdeesh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993726988 — Pashu Shed Ravi /Ramratan | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993726989 — Pashu Shed Rachpal /Rashal singh | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993726990 — Pashu Shed Ramvaran /Nehpal | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003011/IF/9993726991 — Pashu Shed Suneeta /Roopendra | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003011/IF/IAY/1899449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4880268 | Completed | 15660 | 15312 | 2018-11-05 | 2019-03-14
MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003011/IF/IAY/3942587 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124532273 | Completed | 18360 | 18360 | 2022-10-13 | 2023-04-20
MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003011/IF/IAY/3942591 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124535481 | Completed | 18360 | 18360 | 2022-09-20 | 2023-04-20
MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003011/IF/IAY/4349590 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124537502 | Completed | 18360 | 17833 | 2023-01-19 | 2023-08-14
MEHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003011/IF/IAY/4349591 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124538042 | Completed | 18360 | 16884 | 2023-04-10 | 2024-11-10
MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003011/IF/IAY/4384931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127462443 | Ongoing | 23490 | 15266 | 2023-03-11
MEHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003011/IF/IAY/4411032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124536560 | Completed | 23490 | 19752 | 2024-01-10 | 2025-10-28
MEHGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003011/IF/IAY/4769779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124530567 | Completed | 23490 | 21798 | 2024-12-29 | 2026-04-17
MEHGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003011/IF/IAY/4769792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124534938 | Completed | 23490 | 22473 | 2024-11-13 | 2026-04-17
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003011/IF/IAY/4769799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124537017 | Ongoing | 23490 | 20097 | 2025-04-24
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003011/IF/IAY/4773320 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125593050 | Ongoing | 23490 | 14336 | 2025-09-15
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003011/IF/IAY/4773416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125620797 | Ongoing | 23490 | 20880 | 2025-06-01
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003011/IF/IAY/4773428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125624419 | Ongoing | 23490 | 14616 | 2025-04-24
MEHGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003011/IF/IAY/4779037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127532336 | Ongoing | 23490 | 21447 | 2025-02-24
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003011/IF/IAY/4779321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127500648 | Ongoing | 23490 | 18792 | 2025-05-05
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003011/IF/IAY/4915702 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125619576 | Completed | 23490 | 21141 | 2025-11-30 | 2026-05-23
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003011/IF/IAY/552386 — Construction of IAY House -IAY REG. NO. MP3431325 | Completed | 15030 | 15300 | 2017-02-01 | 2017-11-17
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003011/IF/IAY/552399 — Construction of IAY House -IAY REG. NO. MP3431493 | Completed | 15030 | 15450 | 2017-02-01 | 2018-05-15
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003011/IF/IAY/768950 — Construction of IAY House -IAY REG. NO. MP3383385 | Completed | 15030 | 15228 | 2017-07-04 | 2018-07-07
MEHGAON | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003011/LD/126 — मेड बंधान निर्माण जगदीश / कालीचरण अरेले का पुरा | Completed | 25050 | 6370 | 2009-06-09 | 2009-06-09
MEHGAON | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003011/LD/485 — मेढबंधान अरेलेकापुरा रामवरन / मानिक सिह | Completed | 30000 | 2821 | 2009-10-04 | 2009-10-04
MEHGAON | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003011/LD/486 — मेढबंधान अरेलेकापुरा अशोक सिह / सिरनाम | Completed | 30000 | 9282 | 2009-07-18 | 2009-07-18
MEHGAON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003011/LD/628 — मेढबंधान अरेलेकापुरा दीवान सिह / मातादीन | Completed | 11000 | 10300 | 2010-06-15 | 2010-06-15
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702003011/OP/22012034342269 — Shanti Dham Nirman Karaya Arele ka Pura | Completed | 180000 | 179266.99 | 2017-08-20 | 2018-05-10
MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702003011/OP/9425892791 — Shanti Dham Nirman Shree Ka Pura | Completed | 254000 | 177676 | 2017-03-25 | 2021-12-08
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702003011/PG/22012034366415 — Khel Medan Arele Ka Pura | Completed | 353000 | 350214 | 2018-04-01 | 2019-03-27
MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034179095 — C C ROAD GABBAR SINGH KE MAKAN SE BADE KE KUA KI O | Completed | 160900 | 159734 | 2013-08-24 | 2014-03-05
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034192462 — Part-1 cc road Uday singh ke makan se school ki oo | Completed | 221666 | 220811 | 2014-04-06 | 2014-05-26
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034192467 — part-2 cc road Uday singh ke makan se school ki oo | Completed | 197016 | 194770 | 2014-04-02 | 2014-06-05
MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003011/RC/22012034197143 — mitti bajarikaran sughar singh k makan s bachu k m | Completed | 298000 | 281745.45 | 2014-01-03 | 2014-05-28
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034216450 — c croad ramsevak ke makan se bhaghirath ke makan k | Completed | 207000 | 199037 | 2014-04-16 | 2014-05-26
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003011/RC/22012034224654 — sudoor gram sampark sadak yojana nathu singh ke kh | Completed | 1043000 | 772131.72 | 2014-07-11 | 2015-12-14
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003011/RC/22012034228011 — khet sadak yojana surendra ke khaet se bamba ki or | Completed | 1046000 | 637021.95 | 2014-08-27 | 2015-12-14
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034231835 — c c road narendra ke makan se jatbeer ke makan purvi mohalla ke or | Completed | 207500 | 12246 | 2014-10-18 | 2016-08-09
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003011/RC/22012034231889 — khet sadak ramswroop ke khet se dulare ke khet kee or | Completed | 812000 | 541271.93 | 2014-10-10 | 2015-12-14
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003011/RC/22012034231893 — khet sadak main road se surendra ke khet kee or | Completed | 1104000 | 776725.85 | 2014-10-10 | 2015-10-17
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003011/RC/22012034231914 — khet sadak main road se kelash ke khet kee or | Completed | 954000 | 625289.37 | 2014-10-10 | 2015-12-14
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003011/RC/22012034231916 — khet sadak daleep ke khet se narendra ke khet kee or | Completed | 942000 | 668732.48 | 2014-10-10 | 2015-12-14
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003011/RC/22012034231917 — khet sadak narendra ke khet se asharam kekhet kee or | Completed | 1004000 | 720285.55 | 2014-10-10 | 2015-12-14
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003011/RC/22012034231918 — khet sadak binod ke khet se kedar ke khet kee or | Completed | 1403000 | 922971.18 | 2014-10-10 | 2015-10-17
MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034307680 — C C Road Main Road Se Bharat singh Ke Makan Kee Or | Completed | 496000 | 472824 | 2016-12-24 | 2017-05-25
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034307682 — C C Road Pooran Ke Makan Se Kali Mata Ke Mandir Kee Or | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003011/RC/22012034308397 — Khet Sadak Ramnivash Ke Khet Se Rajkumar Ke Khet Ki Or | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003011/RC/22012034308399 — Khet Sadak Pulandar Ke Khet Se Rashal Ke Khet Ki Or | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003011/RC/22012034308401 — Khet Sadak Mukhy Nahar Se Sahib Ke Khet Ki Or r | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003011/RC/22012034308402 — Khet Sadak Kaptan singh Ke Khet Se M adhav singh Ke Khet Ki Or | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003011/RC/22012034308404 — Khet Sadak Rakesh Ke Khet Se Nale Ki Or | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034315373 — C C Road Main Road Se Bharat Singh Ke Makan Kee Or | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034334049 — C C Road Jaghdeesh Ke Gonda Se Shkool Kee Or | Completed | 184000 | 149172 | 2017-04-02 | 2017-05-25
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034334050 — C C Road Bharat Ke Makan Se Madhuraj Ke Makan Kee Or | Completed | 148000 | 134992 | 2017-04-23 | 2017-06-05
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003011/RC/22012034342738 — Sudoor Samparak Sadak Yojana Shree Ke Pura Se Jaghdeesh Pura Tak | Completed | 1430000 | 1499616.78 | 2017-06-25 | 2018-05-30
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034372825 — c c road | Deleted | 0 | 0 | 2017-10-02
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034392687 — C C Road Pooran Ke Makan Se Main Road Kee Or | Completed | 450000 | 223440 | 2018-12-16 | 2019-10-01
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034392692 — C C Road Subalal Ke Makan Se Bakeel Ke Makan Kee Or | Completed | 116000 | 55332 | 2019-01-10 | 2020-05-18
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034392693 — C C Road Shridhar Ke Makan Se Ajamer Ke Makan Kee Or | Completed | 194000 | 93960 | 2019-01-03 | 2019-10-01
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034392694 — C C Road Mata Mandir Se Beeraval Ke Makan Kee Or | Completed | 140000 | 66816 | 2019-01-29 | 2021-12-14
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034392695 — C C Road Karan Singh Ke Makan Se Layak Singh Kee Kotee Kee Or | Completed | 282000 | 135720 | 2019-01-29 | 2020-05-18
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034439736 — cc road | Closed | 0 | 0 | 2019-01-26
MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034510335 — C C Road Main Road Se Kishor Ke Ghar Ke Or | Completed | 325000 | 221598 | 2020-02-03 | 2021-12-14
MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034510336 — C C Road Kishor Ke Darbaje Se Gram Ke Or | Completed | 325000 | 196554 | 2020-02-03 | 2021-12-14
MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034510337 — C C Road C C Road Se Ravindra Ke Ghar Ke Or | Completed | 30000 | 3168 | 2020-02-03 | 2022-04-11
MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034510401 — C C Road Main Road Se Layak Singh Ke Makan Ke Or | Closed | 25000 | 0 | 2019-08-15
MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003011/RC/22012034536079 — Khet sadak Geeta bai ke khet se Rakesh ke khet tak | Completed | 1497872.53 | 1041694.72 | 2020-09-07 | 2022-10-28
MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1702003011/RC/22012034544550 — Cc Road Se Kelash Narwariya Ke Makan Ki Oor | Completed | 70480 | 68400 | 2020-12-26 | 2021-12-13
MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1702003011/RC/22012034544552 — Cc Road Putu Ke Makan Se Keshav Ke Makan Ki Oor | Completed | 34875 | 34200 | 2020-11-29 | 2021-12-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034563438 — C C Road Main Road Se Harijan Vasti Kee Or | Completed | 93000 | 81098 | 2021-11-08 | 2025-06-26
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034590499 — CC Road shobran ke makan se Devan ke mkan ki or & samudayik bhavan prisar | Completed | 43000 | 41302 | 2021-11-08 | 2022-01-06
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034593670 — Main Road se Ramniwas ke ghar ki or | Completed | 93000 | 92640 | 2021-11-10 | 2022-01-11
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003011/RC/22012034600816 — Main road se nahar Lalpura moje ki or | Ongoing | 1760925.35 | 1324208 | 2021-12-02
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003011/RC/22012034600817 — Main road se nahar Lalpura moje ki or | Deleted | 0 | 0 | 2021-10-02
MEHGAON | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/22012034838816 — cc road nirman karya hakim ke ghar se pramod ke ghar ki oor | Ongoing | 26688 | 10962 | 2025-05-19
MEHGAON | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003011/RC/262 — सीसी रोड शिवनाथ के गौडा से स्‍कूल की ओर | Completed | 134733 | 109706 | 2012-09-18 | 2014-03-29
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702003011/RS/22012034693877 — SAMUDAYIK SWACCHATA PARISAR ARELEKAPURA | Completed | 43000 | 42211 | 2023-05-05 | 2023-12-01
MEHGAON | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003011/WC/22012034550177 — Dang Tank Arele ka pura | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003011/WC/22012034550197 — Kachha Nala Nriman Ramjilal Ke Khet Se Jagmohan Ke Khet Kee Or | Completed | 465945.57 | 408120 | 2020-08-05 | 2021-12-14
MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003011/WC/22012034550201 — Kachha Nala Nriman Dev Singh Ke Khet Se Radhe Singh Ke Khet Kee Or | Completed | 242664.87 | 212340 | 2020-08-07 | 2021-12-13
MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003011/WC/22012034550202 — Kachha Nala Nriman Bhoop Singh Ke Khet Se Ahibaran Singh Ke Khet Kee Or | Completed | 262049.04 | 226842 | 2021-01-15 | 2021-12-14
MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003011/WC/22012034550203 — Kachha Nala Nriman Prem Singh Ke Khet Se Jatveer Singh Ke Khet Kee Or | Closed | 0 | 0 | 2020-04-01
MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003011/WC/22012034550204 — Kachha Nala Nriman Kishori Ke Khet Se Suresh Singh Ke Khet Kee Or | Closed | 0 | 0 | 2020-04-01
MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003011/WC/22012034550205 — Kachha Nala Nriman Lakhan Singh Ke Khet Se Madho Singh Ke Khet Kee Or | Completed | 232972.79 | 204250 | 2020-07-16 | 2020-09-06
MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003011/WC/22012034557213 — Kaccha Nala Nriman Gandharv Ke Khet Se Seeta Ram Ke Lavan Kee Or | Completed | 755472.9 | 669370 | 2020-07-01 | 2021-12-14
MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702003011/WC/22012034572766 — Pakka nala Subalal ke makan se Talab ki or | Closed | 775449.29 | 0 | 2020-06-09
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702003011/WC/22012035112374 — Dug pond Kaliyan Ke khet ke Pass | Closed | 0 | 0 | 2023-08-16
MEHGAON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702003011/WC/22012035299891 — Dug pond shanti dham ke pass | Approved | 0 | 0 | 2025-04-24
MEHGAON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702003011/WC/22012035306313 — Dag well recharge pit Shreekapura | Ongoing | 30099.53 | 21774.85 | 2025-05-31