## Work List
Exported on: 2026-09-11 09:56:11
Filters applied:
Data source: MGNREGA + VBGRAMG
District: BHIND
Block: All
Panchayat: KUTHONDA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702003076/AV/22012034391122 — Shanti dham nirman karya gram sarsed GP kuthonda | Closed | 180000 | 0 | 2017-01-26
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Constr of Infra for Azola cultivation for Comm / Construction of Infrastructure for Azola cultivation for Community | Bio-Fertilizer | 1702003076/AV/22012034614893 — Maa ki bagiya shashkiya madhyamik vidhyalaya kuthoda | Closed | 0 | 0 | 2022-01-25
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Constr of Infra for Azola cultivation for Comm / Construction of Infrastructure for Azola cultivation for Community | Bio-Fertilizer | 1702003076/AV/22012034614894 — Maa ki bagiya shashkiya madhyamik vidhyalaya kuthoda | Closed | 0 | 0 | 2022-01-25
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Constr of Infra for Azola cultivation for Comm / Construction of Infrastructure for Azola cultivation for Community | Bio-Fertilizer | 1702003076/AV/22012034614895 — Maa ki bagiya shashkiya madhyamik vidhyalaya kuthoda | Closed | 0 | 0 | 2022-01-25
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Constr of Infra for Azola cultivation for Comm / Construction of Infrastructure for Azola cultivation for Community | Bio-Fertilizer | 1702003076/AV/22012034614897 — Maa ki bagiya shashkiya prathmik vidhyalaya sarsed | Closed | 0 | 0 | 2022-01-25
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Constr of Infra for Azola cultivation for Comm / Construction of Infrastructure for Azola cultivation for Community | Bio-Fertilizer | 1702003076/AV/22012034614899 — Maa ki bagiya shashkiya prathmik vidhyalaya sarsed | Closed | 0 | 0 | 2022-01-25
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Constr of Infra for Azola cultivation for Comm / Construction of Infrastructure for Azola cultivation for Community | Bio-Fertilizer | 1702003076/AV/22012034614901 — Maa ki bagiya shashkiya prathmik vidhyalaya sarsed | Closed | 0 | 0 | 2022-01-25
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Constr of Infra for Azola cultivation for Comm / Construction of Infrastructure for Azola cultivation for Community | Bio-Fertilizer | 1702003076/AV/22012034614902 — Maa ki bagiya shashkiya prathmik vidhyalaya sarsed | Closed | 0 | 0 | 2022-01-25
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702003076/AV/22012034624488 — Construction of Play field for Community | Closed | 0 | 0 | 2022-08-17
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702003076/AV/22012034636018 — Construction of Play Field for Community Gram Sarsed | Ongoing | 447226.84 | 129303 | 2023-09-23
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702003076/AV/22012034636459 — Construction of Play Field for Community Mata ke mandir ke pass Gram Sarsed | Closed | 0 | 0 | 2023-05-15
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702003076/AV/22012034638768 — Shanti dham nirman karya Sarsed | Closed | 330972.38 | 0 | 2022-08-17
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation of Forestry-Community / Along the coast Block Plantation of Forestry Trees for Community | Plantation | 1702003076/DP/22012034580257 — Vraksharopan karya Mukhya road kinare | Ongoing | 427106.07 | 50609 | 2023-08-25
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1702003076/DP/22012034597060 — Plantation work Amrit Vatika Bhagat Baba Sthan par | Ongoing | 55847.4 | 13039 | 2023-08-25
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1702003076/DP/22012034608594 — Vraksha ropan karya Beejasen mata mandir ke pass | Closed | 0 | 0 | 2023-06-08
MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1702003076/FP/22012034363313 — Nala nirman karya Shantidham se Nariya ki oor gram Kuthonda | Completed | 203925.14 | 188834 | 2020-01-16 | 2021-12-18
MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003076/FP/22012034363646 — Kachcha Nala nirman karya Bamba se Kuthonda tak | Closed | 0 | 0 | 2019-06-27
MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003076/FP/22012034363647 — Kachcha Nala nirman Main road ki puliya se Phuta Tal ki oor keshav ke khet tak | Closed | 0 | 0 | 2019-06-27
MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003076/FP/22012034365246 — Nala Bandhan karya Kuthonda | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003076/FP/22012034625221 — Construction of Flood Diversion chanal Naveen Talab ke pass ke Main road tak | Ongoing | 319759.36 | 182546 | 2023-09-23
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1702003076/FP/22012034625801 — Nali nirman Gyan singh ke makan se Rajveer ke makan ki or | Ongoing | 8250 | 6948 | 2022-02-11
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1702003076/FP/22012034628116 — NALI NIRMAN RAMBIHARI BAGHEL KE DWAR SE JATAV MOHALLA KUAA KI OR | Ongoing | 30000 | 28914 | 2022-03-26
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003076/FP/22012034630536 — Construction of Diversion field channel Mata prasad In front of Mata Prasad house to Naria | Closed | 0 | 0 | 2022-08-19
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003076/FP/22012034630538 — Construction of Diversion field channel form Bamba to Naria | Deleted | 0 | 0 | 2022-08-17
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003076/FP/22012034630541 — Construction of Diversion field channel form culvert of Bamba to Naria | Deleted | 0 | 0 | 2022-08-17
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003076/FP/22012034630574 — Construction of Diversion field channel near Bamba From Virendra Shukla k khet to Main road tk 2site | Closed | 0 | 0 | 2022-08-17
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003076/FP/22012034630624 — Construction of Flood Diversion channel form Bamba ki puliya to Naria | Physically Completed | 597843.78 | 447168 | 2022-12-14 | 2026-06-10
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003076/FP/22012034630625 — Construction of Flood Diversion channel form Bamba to Naria | Physically Completed | 591303.37 | 464406 | 2022-12-14 | 2026-06-10
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003076/FP/22012034633513 — Construction of flood diversion chanel Main road se Ray singh ke khet tak | Ongoing | 559746.55 | 439790 | 2023-07-16
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003076/FP/22012034633514 — Construction of flood diversion chanel Ray singh ke khet se Ranchhor singh ke khet ki or | Ongoing | 795197.58 | 460122 | 2023-08-06
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003076/FP/22012034633967 — Construction of flood diversion chanel Kuthonda Moja se Sarsed ki or | Ongoing | 761099.56 | 211055 | 2023-12-24
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003076/IF/22012034353362 — braskha ropan nirman madhyamik shala kuthonda | Completed | 335000 | 66508 | 2017-06-26 | 2019-09-04
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003076/IF/22012034353366 — braskha ropan nirman mata mandir ke pass sarsed | Closed | 335000 | 0 | 2017-06-20
MEHGAON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1702003076/IF/22012034432738 — vruksharopan ramdharsingh | Closed | 188000 | 0 | 2018-08-22
MEHGAON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003076/IF/22012034469772 — Khet Talab nirman Karya Brajesh kumar son of Bachhulal Sarsed | Completed | 288000 | 87408 | 2019-03-05 | 2020-07-21
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003076/IF/22012034558485 — Khet Talab nirman karya Man singh son of Gyaprasad kushwah | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003076/IF/22012034558486 — Khet Talab nirman karya Bhagwati son of Vidhyaram | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003076/IF/22012034558488 — KHet Talab nirman karya Meghraj son of Pannalal | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003076/IF/22012034584365 — Medbandhan karya Jashram son of Munshilal | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003076/IF/22012034584366 — Medbandhan karya Bhavar singh, Gangaram,Mahaveer,Kalicharan son of Hakim singh | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003076/IF/22012034584367 — Medbandhan karya Narayan son of Radhelal | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003076/IF/22012034584368 — Medbandhan karya Baladeen son of Pancham singh | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003076/IF/22012034584370 — Medbandhan karya Renuka wife of Man singh | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003076/IF/22012034585184 — Medbandhan karya Bahadur son of Beniram | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003076/IF/22012034585185 — Medbandhan karya Ramkaran son of Beniram | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003076/IF/22012034585186 — Medbandhan karya Pujari son of Beniram | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590417 — Pashu shet nirman karya Kallu son of Majboot singh | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590419 — Pashu shet nirman Ajamer singh son of Jhargad | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590420 — Pashu shet nirman karya Omkar son of Kehari jatav | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590421 — Pashu shet nirman karya Nehani bai wife of Jaykam singh | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590422 — Pashu shet nirman karya Bhoori bai wife of Lachchiram jatav | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590423 — Pashu shet nirman karya Karan singh son of Sobharam kushwah | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590424 — Pashu shet nirman karya Chhakkilal son of Fundi | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590425 — Pashu shet nirman karya Shyam singh son of Ramcharan | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590426 — Pashu shet nirman karya Bharat singh son of Gyaram | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590427 — Pashu shet nirman karya Adiram son of Nathuram | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590428 — Pashu shet nirman karya Suresh son of Ramnath | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590429 — Pashu shet nirman karya Munnesh singh | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590430 — Pashu shet nirman karya Bedari son of Girvar | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590431 — Pashu shet nirman karya Raghunath son of Harnarayan | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590432 — Pashu shet nirman karya Bachchan singh | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590434 — Pashu shet nirman karya Man singh son of Gyaprasad | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590435 — Pashu shet nirman karya Hakim singh son of Govind singh | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590436 — Pashu shet nirman karya Pooja wife of Vijay singh | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590437 — Pashu shet nirman karya Ramnaresh son of Vijay singh | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590438 — Pashu shet nirman karya Amar singh son of Rambharose | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590439 — Pashu shet nirman karya Banshilal son of Bhajanlal | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590440 — Pashu shet nirman karya Rajendra singh son of Bedari | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Raising of Nursery for Individuals / Raising of Nursery for Individuals | Nursery Development | 1702003076/IF/22012034590441 — Pashu shet nirman karya Rajesh singh son of Bedari | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590442 — Pashu shet nirman karya Baladeen | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034590444 — Pashu shet nirman karya Dhakeli | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034594190 — Pashu shet nirman karya Surendra sharma son of Ram avtar | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034594197 — Pashu shet nirman karya Beerendra sharma son of Gunnarayan | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034594227 — Pashu shet nirman karya Sanjeev kumar son of Shankar lal | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/22012034594232 — Pashu shet nirman karya Man singh son of Jagnnath | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003076/IF/22012034594239 — Medbandhan karya Bhagwanti beba Kaptan | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003076/IF/22012034594248 — Medbandhan karya Meghnath , Pooran son of Pannalal | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003076/IF/22012034594249 — Medbandhan karya Deenanath son of Mathuri | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003076/IF/22012034595497 — Medbandhan Karya Man singh son of Gyaprasad | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/22012035125148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143382669 | Completed | 18000 | 16176 | 2023-07-09 | 2024-09-09
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003076/IF/22012035476450 — Khet talab nirman Ramkumar/kaptan singh jatav any kuthondha | Ongoing | 147621.16 | 261 | 2025-05-20
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003076/IF/22012035476476 — Khet talab nirman mayaram jasmant/ motiram kuthonda | Ongoing | 147621.16 | 261 | 2025-05-20
MEHGAON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1702003076/IF/22012035486322 — khet talab nirman rajkumar putra kaptan singh | New | 0 | 0 | 2025-04-14
MEHGAON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1702003076/IF/22012035486323 — khet talab nirman rajkumar putra kaptan singh | Deleted | 0 | 0 | 2025-04-14
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/9993679126 — pashu shed bharatsingh s/o mataprasad | Deleted | 0 | 0 | 2015-06-24
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/9993679151 — pashu shed BharatSingh S/O mataprasad | Deleted | 0 | 0 | 2015-06-24
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/9993699068 — pashu shed chotelal son of hardayal | Completed | 115900 | 185220 | 2015-12-22 | 2019-09-04
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003076/IF/9993727034 — MEDBHADANBANBARIS/OSOBARAM | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003076/IF/9993727037 — MEDBADANMUNDHEES/OKEDAR | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003076/IF/9993727039 — MEDBADANKALLUS/OCHIMAN | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003076/IF/9993727041 — MEDBADANNETRAMS/OPACHAM | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003076/IF/9993727042 — MEDBADANKESHVSINGHS/OMATHAPRASAD | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003076/IF/9993727044 — MEDBADANBANCHILALS/OVAJANLAL | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003076/IF/9993727045 — MEDMADANNATHURAMS/OGAYARAM | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003076/IF/9993727046 — pashuSHETMOTIRAMS/OCHATURI | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003076/IF/9993727048 — pashudetramkishans/obudhelal | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/9993727051 — PASHUSETNARESHS/OVEJNATH | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/9993727053 — PASHUSHED NIRMAN MAYA W/O MANSHARAM | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/9993727061 — PASHUSETNATHURAMS/OGYARAM | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/9993727062 — PASHUSETLAKHANS/OKALIYAN | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/9993727064 — PASHUSETKALLU KHAN S/OCHIMAN | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/9993727066 — PASHUSETSUJANSINGH S/O KUNDAN | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/9993727072 — pashuset banbaris/obanvaris/oshovaram | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003076/IF/9993735517 — PASHU SET KALLU KHA S/O GHIMAN KHA | Completed | 115900 | 112574 | 2016-05-07 | 2017-09-29
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/1000952 — Construction of IAY House -IAY REG. NO. MP3166508 | Completed | 15480 | 12900 | 2017-08-11 | 2018-09-25
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/133814 — Construction of IAY House -IAY REG. NO. MP-02-003-076-001/75 | Completed | 14310 | 14028 | 2016-09-16 | 2018-03-31
MEHGAON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/1872054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5138283 | Completed | 15660 | 15660 | 2018-11-19 | 2019-03-27
MEHGAON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/1872357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4645225 | Completed | 15660 | 14816 | 2018-11-19 | 2019-09-04
MEHGAON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/1872462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5534102 | Completed | 15660 | 14616 | 2018-10-17 | 2018-12-26
MEHGAON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/1899522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5367054 | Completed | 15660 | 15660 | 2018-11-19 | 2018-12-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/2117488 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4476819 | Completed | 15840 | 15752 | 2020-02-12 | 2020-06-15
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/2341761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5186887 | Completed | 15840 | 16176 | 2020-01-24 | 2020-06-15
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/2341889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5232603 | Completed | 15840 | 16246 | 2020-01-24 | 2020-06-15
MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/2353500 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5247112 | Completed | 15840 | 15960 | 2020-04-21 | 2020-06-15
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/315487 — Construction of IAY House -IAY REG. NO. MP1059777 | Completed | 15030 | 14418 | 2017-03-01 | 2018-02-15
MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/3255258 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2671863 | Completed | 17370 | 17136 | 2022-11-04 | 2023-05-13
MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/3258742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3701668 | Completed | 17370 | 17196 | 2022-05-13 | 2024-09-09
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/379781 — Construction of IAY House -IAY REG. NO. MP1783260 | Completed | 15030 | 15340 | 2017-02-18 | 2018-03-19
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/380728 — Construction of IAY House -IAY REG. NO. MP1886758 | Completed | 15030 | 15330 | 2017-02-27 | 2018-04-05
MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/3886209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143143607 | Completed | 18360 | 18360 | 2023-01-19 | 2024-01-10
MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/4164543 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143376629 | Completed | 18360 | 18318 | 2022-11-17 | 2024-09-09
MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/4164551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143398374 | Completed | 18360 | 17136 | 2022-11-03 | 2023-05-13
MEHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/4164555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143730942 | Completed | 18360 | 16900 | 2023-04-24 | 2024-09-09
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/443428 — Construction of IAY House -IAY REG. NO. MP1493200 | Completed | 15030 | 15300 | 2017-02-27 | 2018-04-05
MEHGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/4804194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143393246 | Ongoing | 27000 | 18954 | 2025-01-25
MEHGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/4805679 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143746409 | Physically Completed | 23490 | 19494 | 2025-02-13 | 2026-06-14
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/485756 — Construction of IAY House -IAY REG. NO. MP2075122 | Completed | 15030 | 15475 | 2017-03-01 | 2018-03-20
MEHGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/4857774 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143416662 | Ongoing | 27000 | 18954 | 2025-02-05
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/5275961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143736055 | Ongoing | 27000 | 6264 | 2025-06-04
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/541740 — Construction of IAY House -IAY REG. NO. MP3116206 | Completed | 15030 | 15340 | 2017-03-24 | 2018-07-01
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/689808 — Construction of IAY House -IAY REG. NO. MP1237213 | Completed | 15030 | 16512 | 2017-07-22 | 2018-03-15
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/723779 — Construction of IAY House -IAY REG. NO. MP1793608 | Completed | 15030 | 14448 | 2017-08-11 | 2018-03-31
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/734753 — Construction of IAY House -IAY REG. NO. MP2099777 | Completed | 15030 | 14792 | 2017-08-10 | 2018-03-31
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/752777 — Construction of IAY House -IAY REG. NO. MP2639986 | Completed | 15030 | 16168 | 2017-07-22 | 2018-02-13
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/753402 — Construction of IAY House -IAY REG. NO. MP2666163 | Completed | 15030 | 15480 | 2017-07-19 | 2017-12-12
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/753650 — Construction of IAY House -IAY REG. NO. MP2677016 | Completed | 15030 | 15480 | 2017-07-22 | 2017-12-12
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/758722 — Construction of IAY House -IAY REG. NO. MP2900328 | Completed | 15030 | 14104 | 2017-08-11 | 2018-08-10
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/764183 — Construction of IAY House -IAY REG. NO. MP3153690 | Completed | 15030 | 12040 | 2017-08-10 | 2018-09-10
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/764210 — Construction of IAY House -IAY REG. NO. MP3155195 | Completed | 15030 | 14964 | 2017-07-19 | 2018-03-15
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/764417 — Construction of IAY House -IAY REG. NO. MP3165607 | Completed | 15030 | 14196 | 2018-02-06 | 2018-09-10
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003076/IF/IAY/775571 — Construction of IAY House -IAY REG. NO. MP3706786 | Completed | 15030 | 13072 | 2017-06-27 | 2018-09-10
MEHGAON | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003076/LD/177 — मेडबन्‍धान मेघनाथ / पन्‍नालाल | Completed | 27000 | 10920 | 2009-08-07 | 2009-09-29
MEHGAON | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003076/LD/178 — मेडबन्‍धान दिल्‍लीराम/ बटुरी | Completed | 19000 | 5915 | 2009-06-26 | 2009-06-26
MEHGAON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003076/LD/22012034228235 — med bandhan bhagvati w/ovidhyaram | Completed | 44850 | 42456 | 2015-08-27 | 2017-09-29
MEHGAON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003076/LD/22012034228239 — Med bandhan ganpati S/O Dhanu | Completed | 61750 | 59916 | 2015-08-24 | 2017-09-29
MEHGAON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003076/LD/22012034228241 — mad bandan Bharatsingh s/o Mataprasad | Completed | 25250 | 22896 | 2015-08-27 | 2016-01-11
MEHGAON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003076/LD/22012034228453 — मेड बंधान दुर्गाशरण s/oमेवाराम | Completed | 44400 | 42222 | 2015-09-01 | 2017-09-29
MEHGAON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003076/LD/22012034228965 — मेड़ बंधान राजेंद्र s/o कप्तान | Completed | 20200 | 9780 | 2015-09-10 | 2017-09-29
MEHGAON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003076/LD/22012034233031 — Med bandhan Bhagvansingh s/o jagannath jatav | Completed | 15600 | 12402 | 2015-10-14 | 2015-10-21
MEHGAON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003076/LD/22012034237160 — med bandh rajesh-rahul S/O lakharam | Completed | 19300 | 18126 | 2015-11-09 | 2015-11-17
MEHGAON | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003076/LD/22012034291447 — MEDBADAN RAJENDRA S/O DURGHA SARAD | Completed | 18200 | 17034 | 2016-07-13 | 2017-09-29
MEHGAON | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003076/LD/22012034291448 — medbandhan keshav singh s/o matadeen | Completed | 43500 | 41082 | 2016-07-13 | 2017-09-29
MEHGAON | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003076/LD/22012034291449 — MEDBADAN BANBARIS/O SHOBHRAM | Completed | 73900 | 39078 | 2016-07-13 | 2017-09-29
MEHGAON | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003076/LD/22012034291450 — MEDBADAN MAHABEER S/O MEBARAM | Completed | 15000 | 14028 | 2016-07-13 | 2017-09-29
MEHGAON | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003076/LD/22012034291568 — MEDBADAN MULA DEVI W/O GAGHA SINGH | Completed | 35000 | 9018 | 2016-08-01 | 2017-09-29
MEHGAON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003076/LD/22012034291569 — MEDBADAN GAGHA SINGH S/O RAMKISHAN | Deleted | 27700 | 0 | 2015-07-15
MEHGAON | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003076/LD/22012034291570 — MEDBADAN GIRRAJ S/O DANSHYAM | Completed | 16500 | 13026 | 2016-08-01 | 2017-09-29
MEHGAON | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003076/LD/22012034291572 — MEDBADAN SYAMLAL S/O RAMCHRAN | Completed | 28000 | 13026 | 2016-08-01 | 2017-09-29
MEHGAON | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003076/LD/22012034291574 — MEDBADAN VISMBAR S/O RAMDEEN | Completed | 22000 | 19038 | 2016-08-01 | 2017-09-29
MEHGAON | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003076/LD/22012034291575 — MEDBADAN MUNSHILAL S/O BAJAN | Completed | 26700 | 21042 | 2016-08-01 | 2017-09-29
MEHGAON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003076/LD/283 — मेढबंधान कुठोंदा मोतीराम , सुखराम / चतुरी के खेत पर | Completed | 0 | 19800 | 2010-05-09 | 2010-05-09
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702003076/OP/9425887670 — shantidham mata ke pass kuthonda | Completed | 1499000 | 1502872 | 2015-08-07 | 2018-04-07
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702003076/OP/9425888804 — Nala nirmankary murarilal sharma ke makan se kelash ke khet tak | Completed | 1445000 | 1426517 | 2016-01-15 | 2019-09-04
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702003076/OP/9425889930 — SANTIDHAMNIRMAD | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702003076/PG/9425896095 — KHEL MEDAN KUTHONDA | Completed | 353000 | 266448 | 2017-03-23 | 2020-07-21
MEHGAON | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003076/RC/141 — सीसी रोड प्राणेश के मकान से गोदाम की ओर | Completed | 193000 | 180864 | 2012-07-05 | 2013-02-27
MEHGAON | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003076/RC/16 — पहुंचमार्ग मिटटी कार्य कुठोदा से कोडरा तक | Completed | 168000 | 4004 | 2009-06-01 | 2006-10-18
MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034169140 — c c road pradesh ke makan se kalichran kadere ki o | Completed | 138067 | 122092 | 2013-07-24 | 2013-12-11
MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034200356 — vidhyak nidhi cc road kalicharan kadere ka amkan s | Completed | 167360 | 164738 | 2014-01-23 | 2014-03-31
MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034209552 — panchpar.ccroad gapu ke makan se atar singh ki gon | Completed | 132783 | 132503 | 2014-02-28 | 2014-05-09
MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034209573 — panchpar.ccroad kamlesh shrama ke dwar se sardar s | Completed | 224405 | 222259 | 2014-02-28 | 2014-06-30
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034230025 — panchpar.ccroad kasudev baba se kalicharan kadere | Completed | 260861 | 259170 | 2014-09-23 | 2014-11-25
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034231624 — C c Rod Suresh ke makan se hanuman ji manidr (sarsed) | Completed | 212780 | 184060 | 2014-10-13 | 2014-11-25
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034231625 — C c Rod Durga sharan ke makan se Bheekam ke makan | Completed | 239010 | 234342 | 2014-10-15 | 2015-01-20
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034287329 — cc road girraj ke makan se ramgovind ke makan tak | Completed | 318000 | 149222 | 2015-10-21 | 2015-11-29
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034291183 — cc road suresh ke makan se sirdar ke makan ki oor | Completed | 293000 | 265376 | 2015-12-07 | 2019-09-04
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003076/RC/22012034308412 — munsikemakansemaharajsinghmakantak | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003076/RC/22012034308414 — atarsinghkemakansemenroadkior | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003076/RC/22012034308415 — CCROADRAMJIKEMAKANKEMENROADTAK | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003076/RC/22012034308416 — CCROADTARJANSINGHKEMAKANSERAMDANSINGHMAKANTAK | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003076/RC/22012034308417 — CCROADBHARATSINGHKEMAKANSEGAGHARAMKEMAKANTAK | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003076/RC/22012034308419 — ketSADAKRAMPRAKSHKETPADREKETKHETTAK | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034312552 — CC ROAD HARIGAYAN KE MAKAN SE MAHARAJ SINGH JATAV B MUNSI LAL KE MAKAN KE OR | Completed | 228000 | 218189 | 2016-11-16 | 2017-09-29
MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034317963 — panchpar cc road harijan basti me Kaptan singh ke makan se Rajesh dhanuk ke makan ki oor & ummed k | Completed | 106835 | 99868 | 2016-12-17 | 2017-09-29
MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034330502 — c c road nirman harijan basti Kelash jatav ke makan se Bharat mehtar ke makan ki oor | Completed | 222216 | 68664 | 2017-03-11 | 2019-09-04
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003076/RC/22012034343355 — SUDUR SAMPAK SADAK NIRMAN KARY KUTHONDA SE SARSED TAK | Completed | 3500000 | 3294471 | 2017-07-03 | 2019-09-04
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003076/RC/22012034347717 — Omprakash ke makan se kok singh ke makan tak sarsed | Completed | 96000 | 58356 | 2017-08-17 | 2019-09-04
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003076/RC/22012034347905 — CC ROAD JAGDEESH KE DUR SE MEN ROAD TAK | Closed | 66875 | 0 | 2017-07-31
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003076/RC/22012034351993 — CC ROAD BASUDEV KE DUR SE HARNARYAN KE DUR TAK | Completed | 73750 | 31008 | 2017-09-06 | 2019-09-04
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003076/RC/22012034352006 — CC ROAD NIRMAN HARNARYAN KE MAKAN SE KAPTAN KE DUR TAK | Completed | 76875 | 40248 | 2017-09-06 | 2019-09-04
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003076/RC/22012034361864 — CC ROAD MEN SE NATHU RAM KE MAKAN SE BAJRANG BALI MANDIR SE PANCHAYAT BABAN TAK | Completed | 40125 | 35136 | 2017-09-27 | 2019-09-04
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034372957 — cc road | Deleted | 0 | 0 | 2017-10-02
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003076/RC/22012034380883 — CC ROAD SALA BAVAN SE SEVA SAHKARI SANSASTHA TAK | Completed | 37500 | 2088 | 2018-10-04 | 2021-10-14
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034395420 — Cc Road Baladin Ke Makan Se Gangha Ram Ke Makan Ki Or | Completed | 60000 | 36540 | 2018-10-06 | 2020-05-10
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034396526 — Cc Road Nirman Men Road Se Ramakant Ke Makan Tak | Completed | 116250 | 69948 | 2018-10-06 | 2020-05-08
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034438349 — C C Road Nirman Baburam Ke Makan Se Man Singh Ke Makan Ki Oor | Completed | 46500 | 22092 | 2019-03-02 | 2020-05-08
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034442102 — cc road | Deleted | 0 | 0 | 2019-01-26
MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003076/RC/22012034469627 — Sudur sadak nirman karya Gram Sarsed se Baghelpura ki oor | Closed | 0 | 0 | 2019-06-27
MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003076/RC/22012034478614 — Sudur sadak nirman Gram sarsed Gaon se nadi ke pass shantidham sarsed tak | Closed | 0 | 0 | 2019-06-27
MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003076/RC/22012034478804 — Sudur sampark sadak Kuthounda se Raviyapura main road tak | Closed | 0 | 0 | 2019-06-27
MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003076/RC/22012034478805 — Sudur Sampark Sadak Sarsed se Baghelpura hoti huyi simar wali Main road tak | Closed | 0 | 0 | 2019-06-27
MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034509581 — c c road nirman Main road se Mata mandir ki oor | Completed | 46500 | 33792 | 2019-12-11 | 2020-05-08
MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003076/RC/22012034522900 — Sudur Sadak Main road Adhar ke khet se Shasakiya madhyamik vidhyalay Rabiyapura tak | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003076/RC/22012034522917 — KHET SADAK NIRMAN SHRIKRISHN SHARMA KE KHET SE MUNSHILAL KE KHET TAK | Completed | 1408489.66 | 1345270 | 2020-06-21 | 2023-09-13
MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034529966 — c c road nirman Main road se Kaliyan singh Bhadoriya ke makan tak sarsed | Completed | 105900 | 84360 | 2020-07-15 | 2021-10-14
MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003076/RC/22012034535827 — Sudur Sampark Sadak Sarsed se Baghelpura Main road tak | Completed | 2480131.52 | 1578060 | 2020-09-03 | 2024-08-04
MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034546556 — C C ROAD NIRMAN JATVEER KE DWAR SE MAHAVEER KE DWAR TAK | Completed | 56625 | 59802 | 2020-11-20 | 2021-10-14
MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034546557 — C C ROAD NIRMAN MEN ROAD SE VISAMBAR KE DWAR TAK | Completed | 55800 | 60934 | 2020-11-20 | 2021-10-14
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003076/RC/22012034574683 — c c road nirman Main road se Shaskiya madhyamik vidhyalay ki or | Ongoing | 69750 | 55584 | 2021-08-31
MEHGAON | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003076/RC/42 — पहुच मार्ग निर्माण कुठोदा से कोडरा तक | Deleted | 0 | 0 | 2008-07-10
MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1702003076/RS/22012034442985 — Nali nirman karya Main road se Radheshyam ke Makan ki oor | Closed | 0 | 0 | 2019-06-27
MEHGAON | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1702003076/WC/22012034294033 — talab nirman kuthonda | Completed | 1467000 | 44548 | 2016-05-24 | 2017-09-29
MEHGAON | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003076/WC/22012034357279 — BORI BANDHAN NIRMAN KARAY MEN ROAD KI PULIYA KE PASS | Deleted | 36000 | 0 | 2017-10-06
MEHGAON | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1702003076/WC/22012034427412 — Naveen Talab Nirman Kuthonda | Completed | 1494000 | 1461130 | 2018-10-10 | 2020-05-08
MEHGAON | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1702003076/WC/22012034472811 — Naveen Talab nirman karya Kuthonda | Closed | 0 | 0 | 2019-06-27
MEHGAON | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702003076/WC/22012034552475 — Chek Dam nirman karya Khel Medan ke pass | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1702003076/WC/22012034552476 — Talab nirman karya Gram Kuthonda | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1702003076/WC/22012034552477 — Talab nirman Karya Sarsed | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003076/WC/22012034898141 — तालाब रिनोवेशन / मरम्मत कार्य कुटोदा नरिया के पास | Closed | 0 | 0 | 2021-10-02
MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003076/WC/22012034898148 — तालाब रिनोवेशन / मरम्मत कार्य कुटोदा भगत बाबा के पास | Closed | 0 | 0 | 2021-10-02
MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Terracing | 1702003076/WC/22012034898151 — तालाब रिनोवेशन / मरम्मत कार्य कुटोदा मोती राम के द्वारे के पास | Closed | 0 | 0 | 2021-10-02
MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003076/WC/22012035033046 — Dreg Talab nirman karya Kuthonda | Deleted | 0 | 0 | 2022-11-25
MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003076/WC/22012035038912 — Construction of Dug Pond Gram Kuthonda | Closed | 0 | 0 | 2022-11-26
MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003076/WC/22012035075227 — Construction of Community water harvesting pond Dug Tank nirman | Closed | 0 | 0 | 2022-11-25
MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003076/WC/22012035075228 — Construction of Community water harvesting pond Naveen Talab Nirman Gram Sarsed | Closed | 0 | 0 | 2022-11-25
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003076/WC/22012035075230 — Construction of Community water harvesting pond Naveen Talab Nirman Gram Sarsed2 | Closed | 0 | 0 | 2023-05-11
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003076/WC/22012035078452 — Construction of Community water harvesting pond Dug Tank nirman Kamlesh ke khet ke pass Kuthonda | Ongoing | 1478911.42 | 955162 | 2023-06-26
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003076/WC/22012035078460 — Construction of Community water harvesting pond Navin Talab Nirman Mahesh prasad ke khet pas Sarsed | Ongoing | 1492628.94 | 635879 | 2023-06-26
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702003076/WC/22012035130762 — Construction of Earthen graded bund for Community Hanuman ji mandir ke peechhe | Ongoing | 1487520.5 | 212969 | 2023-10-14
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702003076/WC/22012035174170 — Construction of Dug Tank Near Mata mandir Sarsed | Ongoing | 1481079.32 | 203662 | 2024-03-13
MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003076/WH/22012034449692 — Talab Renovation Gram kuthonda | Physically Completed | 742927.11 | 341700 | 2022-06-18 | 2026-06-10
MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003076/WH/22012034456849 — तालाब रिनोवेशन / मरम्मत कार्य कुटोदा नरिया के पास | Closed | 0 | 0 | 2021-10-02
MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003076/WH/22012034937667 — Koop Ghat marammut Bhagat Baba Sthan par | Closed | 0 | 0 | 2022-11-25