## Work List
Exported on: 2026-09-08 09:06:18
Filters applied:
Data source: VBGRAMG
District: BHIND
Block: All
Panchayat: SAYPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702003083/AV/22012034627499 — Samudayak swachata parisar saypura | Ongoing | 43000 | 0 | 2023-06-20
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1702003083/DP/22012034583308 — Braksha ropan karya shala parishar saypura | Ongoing | 427106.07 | 0 | 2023-09-18
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1702003083/DP/22012034595054 — Basudha bandhan ke taht amrit vatika Hanuman Ji mandir saypura | Ongoing | 55847.4 | 0 | 2023-08-28
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003083/FP/22012034634288 — Construction for canal of flood diversion for cumunitty main road se talab ki or | Ongoing | 419106.9 | 0 | 2023-09-11
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1702003083/IF/22012035152527 — Khet talab nirman karya dasharth Singh ke khet pr | Ongoing | 385261.22 | 0 | 2023-10-02
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Infra for Lqud Biomanure for Indviduals / Construction of Infrastructure for Liquid Biomanure for Individuals | Bio-Fertilizer | 1702003083/IF/22012035171748 — Khet talab nirman karya nathu singh s/o babu singh ke khet pr | Ongoing | 385261.22 | 0 | 2023-11-09
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Compost Pit for Individual / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702003083/IF/22012035171756 — Khet talab nirman karya sitaram s/o chote lal ke khet pr | Ongoing | 385261.22 | 0 | 2024-01-15
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1702003083/IF/22012035173866 — Khet talab nirman karya jayveer s/o munshi ke khet pr | Ongoing | 385261.22 | 0 | 2024-03-04
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003083/IF/22012035519127 — Construction of farm pond PAN SINGH SON OF PHOOL SINGH MIRDHA | Ongoing | 147621.16 | 0 | 2025-05-25
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003083/IF/IAY/193328 — Construction of IAY House -IAY REG. NO. MP-02-003-083-002/26 | Approved | 27000 | 0 | 2016-02-21
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003083/IF/IAY/193329 — Construction of IAY House -IAY REG. NO. MP-02-003-083-002/34 | Approved | 27000 | 0 | 2016-02-21
MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003083/IF/IAY/2536537 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4945822 | Approved | 27000 | 0 | 2020-05-04
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003083/IF/IAY/3263335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4421164 | Ongoing | 27000 | 0 | 2025-05-10
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003083/IF/IAY/3384960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5710941 | Approved | 27000 | 0 | 2021-11-17
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003083/IF/IAY/843656 — Construction of IAY House -IAY REG. NO. MP1406472 | Approved | 27000 | 0 | 2017-04-01
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003083/RC/22012034447613 — c c road nirman Arbind ke dwar se parialmal ke gonda tak | Ongoing | 55800 | 0 | 2019-03-09
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003083/RC/22012034447616 — c c road nirman C C ROAD SE HUKAM SINGH KE DWAR TAK | Ongoing | 23250 | 0 | 2019-03-08
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003083/RC/22012034447618 — c c road nirman P M ROAD SE SIYARAM KE GONDA TAK SAYPURA | Ongoing | 37200 | 0 | 2019-03-08
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003083/RC/22012034447620 — c c road nirman OM SINGH KE DWAR SE HANUMAN MANDIR TAK | Ongoing | 60450 | 0 | 2019-03-08
MEHGAON | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1702003083/WC/22012034446213 — Talab jirnodhar Sha Pra Scholl ke pass saypura | Ongoing | 379000 | 0 | 2019-03-10
MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Farm Forestry Trees for Community | Plantation | 1702003083/WC/22012035012357 — construction of community water harvesting SAYPURA | Ongoing | 1495265.77 | 0 | 2022-11-23
MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Canal Line Plantation-Horticulture - Community / Canal Line Plantation of Horticulture Trees for Community | Plantation | 1702003083/WC/22012035023275 — Amrit sarobar duck tenk nirman karya goram road ke pass Saypura | Ongoing | 1495951.72 | 0 | 2022-12-20
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1702003083/WC/22012035098484 — Khet talab nirman karya veer singh ke khet pr depura | Ongoing | 385261.22 | 0 | 2023-08-25