## Work List
Exported on: 2026-09-08 12:56:02
Filters applied:
Data source: MGNREGA
District: BHIND
Block: All
Panchayat: GORAM
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702003091/AV/22012034563012 — SHANTIDHAM NIRMAN GORAM | Closed | 0 | 0 | 2021-01-26
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702003091/AV/22012034621599 — शांति धाम निर्माण कार्य गोराम | Ongoing | 289050.92 | 208177.43 | 2022-10-03
MEHGAON | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702003091/DP/22012034241723 — hanuman mandir par goram | Deleted | 335000 | 0 | 2017-04-30
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003091/DP/22012034241734 — MAIN ROAD SE GAON TAK | Completed | 335000 | 1032 | 2017-05-16 | 2018-10-10
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003091/FP/22012034629762 — फ्लड डायवर्सन चेनल रामप्यारी के द्वार से नाथूराम शर्मा के खेत तक | Closed | 0 | 0 | 2022-08-19
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003091/FP/22012034630391 — flad dayvarsan chenal rampyari baretha ke ghar se nathoo ram sharma ke khet ki or | Completed | 303221.23 | 239530 | 2022-11-04 | 2024-09-09
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702003091/FP/22012034630519 — RCC NALA NIRMAN BHAGVATI SHARMA KE GHAR SE AMAR SINGH BAGHEL KE GHAR KI OR | Completed | 258000 | 254150 | 2023-06-05 | 2024-11-11
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003091/FP/22012034633403 — RCC NALA NIRMAN LAJJARAM JATAV KE GHAR SE VIRENDRA JATAV KE GHAR KI OR | Completed | 37000 | 36244 | 2023-06-18 | 2024-09-09
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003091/IF/22012034353026 — braksharopan goram 1 | Closed | 335000 | 0 | 2017-06-17
MEHGAON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003091/IF/22012034353030 — braksharopan chitawali 1 | Ongoing | 335000 | 18044 | 2019-01-13
MEHGAON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1702003091/IF/22012034435412 — Vruksharopan Mukhram Singh | Ongoing | 188000 | 8352 | 2018-10-29
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012034569337 — KHET TALAB MAN SINGH / RATAN SINGH KE KHET PER | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012034569338 — KHET TALAB BHURE SINGH / NARAYAN SINGH KE KHET PER | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012034569339 — KHET TALAB RAJENDRA SINGH / HARNAM SINGH KE KHET PER | Closed | 0 | 0 | 2020-01-26
MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012034569340 — KHET TALAB VIRENDRA SINGH / KARAN SINGH KE KHET PER | Completed | 332572.21 | 259212 | 2020-09-22 | 2021-05-08
MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003091/IF/22012034672239 — PASHU SHED NIRMAN MANOJ / BALVANT | Closed | 0 | 0 | 2021-01-26
MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003091/IF/22012034672240 — PASHU SHED NIRMAN KAMAL SINGH / LALJI | Closed | 0 | 0 | 2021-01-26
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702003091/IF/22012034778751 — MED BANDHAN GIRVAR SINGH/JASMANT KE KHET PER | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702003091/IF/22012034778759 — MED BANDHAN RAMESHWAR SINGH / JANVED SINGH KE KHET PER | Deleted | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702003091/IF/22012034778764 — MED BANDHAN GAJENDRA SINGH /SHROTAM SINGH KE KHET PER | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012034778772 — KHET TALAB RAJENDRA / RAMSHEWAK KE KHET PER | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012034778777 — KHET TALAB UTTAM SINGH / RAMSWAROOP KE KHET PER | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012034778784 — KHET TALAB KALUTI / YADURAJ SINGH KE KHET PER | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702003091/IF/22012034778790 — MED BANDHAN MUKESH / AHIVARAN KE KHET PER | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702003091/IF/22012034778819 — MED BANDHAN RAMSEVAK / JAHAR SINGH KE KHET PER | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012034778828 — KHET TALAB MATAPRASAD / BANKELAL KE KHET PER | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012034778841 — KHET TALAB PURAN SINGH / RATAN SINGH KE KHET PER | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702003091/IF/22012034803201 — MED BANDHAN AJMER SINGH / HABALDAR SINGH KE KHET PER | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012034809413 — KHET TALAB RAMESHWAR / JANVED KE KHET PER | Closed | 0 | 0 | 2021-04-14
MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012035000243 — खेत तालाब निर्माण गिरवर सिंह/जसवंत सिंह चिटावाली | Closed | 0 | 0 | 2022-04-14
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702003091/IF/22012035020300 — खेत तालाब निर्माण रामदत्त शर्मा/महावीर प्रसाद शर्मा | Physically Completed | 356296.9 | 224536 | 2023-10-02 | 2026-06-05
MEHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012035125425 — हरप्रसाद / सुखलाल के खेत पर गोरम | Closed | 0 | 0 | 2023-04-24
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012035486547 — KHET TALAB NIRMAN KARYA GYAN SINGH / TULSIRAM KE KHET PER | Ongoing | 147621.16 | 47241 | 2025-05-12
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012035486558 — KHET TALAB NIRMAN RAMNARESH / DEENANATH KE KHET PER | Closed | 147621.16 | 261 | 2025-05-12
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012035527564 — KHET TALAB NIRMAN HARPRASHAD / SUKHALAL KE KHET PAR | Approved | 0 | 0 | 2025-04-27
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012035542358 — KHET TALAB NIRMAN AJMER SIGNH | Closed | 55865.38 | 261 | 2025-06-20
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012035542372 — KHET TALAB NIRMAN JASMANT SINGH | Closed | 147621.16 | 261 | 2025-06-20
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012035542383 — KHET TALAB NIRMAN LAKHPAT SINGH | Closed | 55865.38 | 261 | 2025-06-20
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012035542395 — KHET TALAB NIRMAN RAJKUMARI/VIRENDRA SINGH | Closed | 147621.16 | 261 | 2025-06-20
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012035542403 — KHET TALAB NIRMAN DUKH HARAN SINGH KE KHET PAR | Approved | 55865.38 | 0 | 2025-04-27
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012035542423 — KHET TALAB NIRMAN UDAY SINGH SINGH KE KHET PAR | Approved | 147621.16 | 0 | 2025-04-27
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012035542449 — KHET TALAB NIRMAN SHYAM KISHOR SHRIVASTAV KE KHET PAR | Closed | 147621.16 | 261 | 2025-06-20
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012035542463 — KHET TALAB NIRMAN PRAG SINGH KE KHET PAR | Closed | 147621.16 | 261 | 2025-06-20
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012035542481 — KHET TALAB NIRMAN SHRI RAM KE KHET PAR | Closed | 55865.38 | 261 | 2025-06-20
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012035552317 — खेत तालाब निर्माण प्रमोद पुत्र बुधु के खेत पर | Closed | 55865.38 | 261 | 2025-06-20
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012035552337 — Khet talab Tularam/Patiram ke khet par | Closed | 55865.38 | 261 | 2025-06-20
MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/IF/22012035552358 — खेत तालाब निर्माण नाहर पुत्र रामस्वरूप के खेत पर | Closed | 55865.38 | 261 | 2025-06-20
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003091/IF/9993709848 — pashu shed balbeer s/o prahalad | Deleted | 115900 | 0 | 2016-01-10
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003091/IF/9993709914 — pashu shed harnam singh s/o hardayal singh | Completed | 115900 | 105664 | 2016-08-01 | 2017-10-10
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003091/IF/9993709916 — pashu shed ajamer khan s/o bhure khan | Deleted | 115900 | 0 | 2016-01-12
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003091/IF/9993709922 — pashu shed virendra s/o ramshwaroop | Deleted | 115900 | 0 | 2015-08-15
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003091/IF/9993709925 — pashu shed suneel s/o narayan singh | Deleted | 115900 | 0 | 2015-08-15
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003091/IF/9993709927 — pashu shed karan s/o vidyaram | Deleted | 115900 | 0 | 2016-01-10
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003091/IF/9993709929 — pashu shed lakhan s/o chhote | Deleted | 115900 | 0 | 2015-08-15
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003091/IF/9993709931 — pashu shed malkhan s/o kauarpal | Deleted | 115900 | 0 | 2015-08-15
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003091/IF/9993709932 — pashu shed kamlesh devi w/o kaptan singh | Completed | 115900 | 103660 | 2016-08-01 | 2017-10-10
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003091/IF/9993709935 — pashu shed veerendra singh s/o mohar singh | Completed | 115900 | 103660 | 2016-08-01 | 2017-10-10
MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003091/IF/9993727995 — pashu shed hakim s/o tikole | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/118421 — Construction of IAY House -IAY REG. NO. MP-02-003-091-001/88 | Completed | 14310 | 15163 | 2017-02-11 | 2017-11-30
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/193333 — Construction of IAY House -IAY REG. NO. MP-02-003-091-001/26 | Completed | 14310 | 15068 | 2017-02-27 | 2017-11-28
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/193334 — Construction of IAY House -IAY REG. NO. MP-02-003-091-001/3451 | Completed | 14310 | 14208 | 2017-02-27 | 2017-10-10
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/203815 — Construction of IAY House -IAY REG. NO. MP-02-003-091-001/1 | Completed | 15030 | 14420 | 2017-08-20 | 2019-01-03
MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/2255696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4843156 | Closed | 17100 | 0 | 2019-07-13
MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/2256054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5557405 | Completed | 17100 | 15772 | 2020-04-23 | 2021-06-21
MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/2256060 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5571827 | Completed | 17100 | 14440 | 2020-04-23 | 2020-09-25
MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/2256079 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5608667 | Completed | 17100 | 14820 | 2020-04-23 | 2020-09-04
MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/2256087 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5620219 | Completed | 17100 | 14820 | 2020-04-23 | 2020-09-04
MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/2334196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4699500 | Completed | 17100 | 16962 | 2023-01-29 | 2024-07-14
MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/2334236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4222386 | Completed | 17100 | 16804 | 2020-04-23 | 2021-12-14
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/274594 — Construction of IAY House -IAY REG. NO. MP3204351 | Completed | 15030 | 15260 | 2017-02-27 | 2018-11-17
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/274717 — Construction of IAY House -IAY REG. NO. MP3217823 | Completed | 15030 | 15236 | 2017-02-27 | 2018-11-17
MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/3259597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3952700 | Completed | 17370 | 14994 | 2022-09-18 | 2024-11-11
MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/3268030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4829050 | Completed | 17370 | 16116 | 2022-05-21 | 2024-11-11
MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/3268202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4845577 | Completed | 17370 | 17187 | 2022-11-30 | 2024-08-04
MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/3278857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5569225 | Completed | 17370 | 15516 | 2022-02-18 | 2022-10-30
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/376938 — Construction of IAY House -IAY REG. NO. MP1515801 | Completed | 15030 | 8120 | 2017-09-14 | 2023-05-28
MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/378786 — Construction of IAY House -IAY REG. NO. MP1691810 | Completed | 15030 | 13884 | 2017-02-27 | 2019-07-01
MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/4347029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122818641 | Completed | 18360 | 17136 | 2022-10-26 | 2023-04-26
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/533243 — Construction of IAY House -IAY REG. NO. MP2883236 | Completed | 15030 | 13268 | 2017-08-04 | 2019-07-01
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/857561 — Construction of IAY House -IAY REG. NO. MP1582216 | Completed | 15480 | 12308 | 2017-08-20 | 2019-07-01
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/942248 — Construction of IAY House -IAY REG. NO. MP2851092 | Completed | 15480 | 11104 | 2017-08-20 | 2019-07-01
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/957884 — Construction of IAY House -IAY REG. NO. MP3235686 | Completed | 15480 | 15624 | 2017-09-14 | 2018-11-17
MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003091/IF/IAY/977369 — Construction of IAY House -IAY REG. NO. MP3776199 | Completed | 15480 | 15476 | 2017-10-14 | 2018-11-17
MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1702003091/LD/22012034574859 — MAA KI BAGIYA NIRMAN PS/MS SCHOOL GORAM | Closed | 0 | 0 | 2021-10-02
MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1702003091/LD/22012034574861 — MAA KI BAGIYA GOVT PS SCHOOL CHUTAWALI | Closed | 0 | 0 | 2021-10-02
MEHGAON | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003091/LD/40 — मेढबंधान कालीचरण / शम्‍भूदयाल गोरम | Completed | 102000 | 15925 | 2009-06-13 | 2009-01-26
MEHGAON | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003091/LD/7 — मेढबंधान तिलक कुमार/शम्‍भू दयाल गोरम | Completed | 54000 | 15925 | 2009-06-13 | 2009-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702003091/OP/9425890045 — shanti dham | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702003091/OP/9425892747 — shanti dham goram | Completed | 245000 | 2064 | 2017-05-16 | 2021-12-13
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702003091/OP/9425892749 — shanti dham chutawali | Completed | 180000 | 178644 | 2017-05-16 | 2019-03-27
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702003091/OP/9425893057 — shanti dham chitawli | Deleted | 0 | 0 | 2017-04-17
MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/22012034177822 — c c road ka nirman veerendra jatab ke mkan se chot | Completed | 213000 | 211347 | 2013-08-07 | 2014-10-01
MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/22012034190922 — c c road nirman man singh mirgh ke makan se rajend | Completed | 193000 | 186428 | 2013-10-25 | 2015-10-01
MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/22012034213401 — panchpar.ccroad prathmik vidhlay se jayram jatav k | Completed | 255000 | 253398 | 2014-03-08 | 2015-12-01
MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/22012034213410 — panchpar.ccroad tikole batham ke makan se munna la | Completed | 215000 | 209072 | 2014-03-08 | 2015-12-01
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/22012034223357 — panchpar.ccroad shankar baghel ke makn se shyam si | Completed | 191000 | 184140 | 2014-08-05 | 2016-08-07
MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/22012034228896 — panchpar.ccroad shankar sharma ke makan se bahadur | Completed | 524000 | 451970 | 2014-10-08 | 2016-08-07
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/22012034289755 — cc road hr. basti ramkishan ke dwar se lajjaram ke ghar ta | Completed | 273000 | 246816 | 2015-11-23 | 2017-10-10
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/22012034298374 — c.c. road rajaram ke makan se vijayram ke makan tak | Completed | 210000 | 171984 | 2016-02-09 | 2018-10-10
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/22012034308885 — c.c. road hanuman ji mandir se ramshankar ke ghar tak | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/22012034308886 — c.c. road | Deleted | 0 | 0 | 2016-01-26
MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/22012034311166 — c.c. road main road se udal singh ke dwar tak | Deleted | 151000 | 0 | 2016-04-02
MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/22012034314956 — c.c.road main road se udal ke darwaje tak | Completed | 151000 | 145798 | 2016-04-21 | 2018-10-10
MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/22012034316933 — c.c.road (man singh mirdha ke gonda se ajab singh mirdha ke ghar tak) | Completed | 204000 | 215564 | 2016-11-30 | 2018-10-10
MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/22012034332988 — c.c. road manoj sharma ke ghar se ramavatar sharma ke ghar tak | Deleted | 0 | 0 | 2017-01-26
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/22012034332990 — c.c. road manoj sharma ke ghar se ramavatar sharma ke ghar tak | Completed | 70000 | 43344 | 2017-06-01 | 2018-10-10
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/22012034360085 — c.c.road ramadhar ke ghar se jagdeesh jamadar ke ghar tak | Completed | 35000 | 34400 | 2017-09-14 | 2018-10-10
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003091/RC/22012034366049 — sudoor sampark (main road se shiv charan singh ke pura se &tirah se mangal singh ke pura tak) | Completed | 1564000 | 1300284.8 | 2017-10-31 | 2020-05-29
MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/22012034366055 — c.c.road hanuman ji se dukhharan ke ghar tak | Deleted | 70000 | 0 | 2016-10-02
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/22012034366062 — c.c.road main road se ramswaroop ke ghar tak | Completed | 21000 | 17712 | 2017-10-31 | 2019-07-01
MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/22012034372888 — c c road. hanuman ji se dukharan ke makan tak | Closed | 0 | 0 | 2017-10-02
MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/22012034442078 — cc road | Closed | 0 | 0 | 2019-01-26
MEHGAON | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/22012034839795 — CC ROAD EVAM NALI NIRMAN KARYA BABU BABA KE MAKAN SE RAMKRAPAL KE GHAR KI OR | Approved | 28000 | 0 | 2025-01-28
MEHGAON | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003091/RC/315 — 1702003091/RC/315 | Completed | 168000 | 159399 | 2013-03-02 | 2016-08-07
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702003091/RS/22012034670764 — samudayak nadep nirman SH. MA. VI. GORAM | Deleted | 5000 | 0 | 2022-10-08
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702003091/RS/22012034672621 — CONSTRUCTION OF SAMUDAYAK SOKHTA AJAB PARIHAR KE GHAR KE SAMNE | Closed | 6600 | 0 | 2022-10-03
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702003091/RS/22012034672971 — CONSTRUCTION OF SAMUDAYAK NADEP NIRMAN GOVT SCHOOL GORAM | Completed | 5000 | 4896 | 2022-11-30 | 2024-09-09
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702003091/RS/22012034672972 — CONSTRUCTION OF SAMUDAYAK NADEP NIRMAN SWASTH KENDRA GORAM | Completed | 5000 | 3672 | 2022-11-30 | 2024-11-11
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702003091/RS/22012034673449 — CONSTRUCTION OF SAMUDAYAK SOKTA CHHABIRAM PARIHAR KE GHAR KE SAMANE | Completed | 6600 | 6188 | 2023-08-14 | 2024-11-13
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702003091/RS/22012034673505 — CONSTRUCTION OF SAMUDAYAK SOKTA RAJENDRA JATAV KE GHAR KE SAMANE | Completed | 6600 | 6188 | 2023-08-14 | 2024-09-09
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702003091/RS/22012034673520 — CONSTRUCTION OF SAMUDAYAK SOKTA BETAL JATAV KE GHAR KE SAMANE | Completed | 6600 | 6409 | 2023-08-21 | 2024-09-09
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702003091/RS/22012034673522 — CONSTRUCTION OF SAMUDAYAK SOKTA RAJARAM JATAV KE GHAR KE SAMANE | Completed | 6600 | 6409 | 2023-08-21 | 2024-09-09
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702003091/RS/22012034673524 — CONSTRUCTION OF SAMUDAYAK SOKTA DOLAT RAM SHARMA KE GHAR KE SAMANE | Completed | 6600 | 4862 | 2023-08-28 | 2024-11-11
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702003091/RS/22012034673527 — CONSTRUCTION OF SAMUDAYAK SOKTA RAMNARESH PARIHAR KE GHAR KE SAMANE | Completed | 6600 | 5083 | 2023-09-24 | 2024-09-09
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702003091/RS/22012034673528 — CONSTRUCTION OF SAMUDAYAK SOKTA VASUDEV SHRMA KE GHAR KE SAMANE | Ongoing | 6600 | 6188 | 2023-09-10
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702003091/RS/22012034673529 — CONSTRUCTION OF SAMUDAYAK SOKTA GIRJESH SHARMA KE GHAR KE SAMANE | Ongoing | 6600 | 6188 | 2023-10-09
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702003091/RS/22012034673530 — CONSTRUCTION OF SAMUDAYAK SOKTA DEEPAK SHARMA KE GHAR KE SAMANE | Closed | 6600 | 0 | 2022-10-28
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702003091/RS/22012034675011 — CONSTRUCTION OF samudayik Nadep Nirman Prakash vatham ke ghar ke paS | Closed | 5000 | 0 | 2022-11-10
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702003091/RS/22012034675019 — CONSTRUCTION OF samudayik Nadep Nirman AMAR SINGH BAGHEL ke ghar ke paS | Closed | 5000 | 0 | 2022-11-10
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702003091/RS/22012034675020 — CONSTRUCTION OF samudayik Nadep Nirman NAHAR SINGH JATAV ke ghar ke paS | Completed | 5000 | 3672 | 2022-11-30 | 2024-09-09
MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702003091/RS/22012034678000 — CONSTRUCTION OF SAMUDAYAK SOKHTA GOV. SCHOOL KE PAS | Completed | 6600 | 6188 | 2023-10-09 | 2024-09-09
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702003091/RS/22012034678747 — CONSTRUCTION OF samudayik Nadep Nirman VASUDEV SHARMA ke ghar ke paS | Closed | 5000 | 0 | 2022-12-05
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702003091/RS/22012034678749 — CONSTRUCTION OF samudayik Nadep Nirman GOPAL BAGHEL ke ghar ke paS | Closed | 0 | 0 | 2022-08-19
MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702003091/RS/22012034678750 — CONSTRUCTION OF samudayik Nadep Nirman GOPAL BAGHEL ke ghar ke paS | Closed | 5000 | 0 | 2022-12-05
MEHGAON | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702003091/WC/22012034328206 — talab jeernoddhar goram | Completed | 43000 | 41280 | 2017-06-01 | 2018-01-10
MEHGAON | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702003091/WC/22012034328208 — naveen talab nirman chitauli | Completed | 884000 | 4128 | 2017-06-10 | 2018-10-10
MEHGAON | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1702003091/WC/22012034356371 — bori bandhan chitawali(gaon ke upar) | Completed | 29100 | 4644 | 2017-09-29 | 2018-02-15
MEHGAON | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1702003091/WC/22012034356379 — bori bandhan shanti dham ke pash chitawali | Completed | 27300 | 3612 | 2017-09-29 | 2018-02-15
MEHGAON | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702003091/WC/22012034426838 — talab nirman chutawali | Ongoing | 1145000 | 75168 | 2019-01-21
MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702003091/WC/22012034557842 — NAVEEN TALAB NIRMAN RAJENDRA SINGH KE KHET KE PASS | Completed | 1449175.5 | 833586 | 2020-06-24 | 2022-10-31
MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702003091/WC/22012034619593 — STOP DAM NIRMAN SHANTIDHAM KE PASS CHUTAWALI | Closed | 0 | 0 | 2021-01-26
MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702003091/WC/22012034897167 — TALAB JIRDODHAR NIRMAN GORAM | Closed | 0 | 0 | 2021-10-02
MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1702003091/WC/22012035038167 — GOVT NAVEEN TALAB NIRMAN GORAM | Closed | 0 | 0 | 2022-08-19
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1702003091/WC/22012035047781 — DUG POND NIRMAN RAMBHAROSE KE KHET KE PASS | Closed | 1499924.95 | 0 | 2023-10-02
MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003091/WC/22012035136739 — DUG POND NIRMAN PRAG OJHA KE KHET KE NICHE GORAM KRAMANK 6 | Closed | 0 | 0 | 2023-08-19
MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702003091/WC/9993653750 — Naveen talab nirman morai ke paas goram | Completed | 431000 | 194994 | 2014-07-29 | 2016-08-05
MEHGAON | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702003091/WH/22012034389502 — r.c.c. nala nirman goram | Closed | 60000 | 0 | 2018-08-15
MEHGAON | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702003091/WH/22012034389503 — r.c.c.nala nirman chitawali | Closed | 120000 | 0 | 2018-08-15