## Work List
Exported on: 2026-09-15 12:29:54
Filters applied:
Data source: MGNREGA + VBGRAMG
District: BHIND
Block: All
Panchayat: BANIPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702004039/AV/22012034537526 — पंचायत भवन निर्माण कार्य बनीपुरा ग्राम पंचायत बनीपुरा | Completed | 579200 | 533735 | 2020-09-28 | 2022-08-26
GOHAD | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702004039/AV/22012034598684 — शांतीधाम निर्माण कार्य अंगनूपुरा ग्राम पंचायत बनीपुरा | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702004039/AV/22012034598686 — शांतीधाम निर्माण कार्य अंगनूपुरा ग्राम पंचायत बनीपुरा | Closed | 0 | 0 | 2021-04-14
GOHAD | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702004039/AV/22012034622483 — शांतीधाम निर्माण कार्य अंगनूपुरा ग्राम पंचायत बनीपुरा | Closed | 0 | 0 | 2022-04-14
GOHAD | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702004039/AV/22012034622670 — शांतीधाम निर्माण कार्य अंगनूपुरा ग्राम पंचायत बनीपुरा | Completed | 198735.26 | 179087.19 | 2022-11-04 | 2023-06-24
GOHAD | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1702004039/DP/22012034427514 — Plantation Work - Shantidham banipura GP Banipura | Closed | 335000 | 0 | 2018-04-14
GOHAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1702004039/DP/22012034556861 — मां की बगिया शा.मा.वि.अंग्नूपुरा बनीपुरा | Closed | 12000 | 0 | 2022-04-14
GOHAD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1702004039/DP/22012034579654 — वृक्षारोपण कार्य एम0एस0अंगनूपुरा ग्राम पंचायत बनीपुरा | Completed | 260371.47 | 120003 | 2023-07-12 | 2024-02-18
GOHAD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1702004039/DP/22012034579655 — वृक्षारोपण कार्य पी0एस0 कंचनसिंहकापुरा ग्राम पंचायत बनीपुरा | Closed | 0 | 0 | 2023-04-14
GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004039/FP/22012034365038 — PAKKA NALA NIRMAN MATAPRASAD KE MAKAN SE TALAB KI OR AGNUPURA GP BANIPURA | Physically Completed | 1332259.42 | 1150813.44 | 2020-06-09 | 2026-04-13
GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004039/FP/22012034365039 — PAKKA NALA NIRMAN TALAB SE RAGHUNATH SINGH KI GHAR KI OR GP BANIPURA | Physically Completed | 1299189.43 | 1118867.29 | 2020-06-09 | 2026-04-13
GOHAD | 2019-2020 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004039/FP/22012034365251 — KACHCHA NALA NIRMAN STAOPDAM AGNOPOORA SE NADI KI OR GP BANIPURA | Closed | 0 | 0 | 2020-01-26
GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004039/FP/22012034365489 — Kaccha nala nirman stopdam agnoopura se nadi ki gp banipurar | Completed | 1471496.15 | 1396668 | 2020-06-15 | 2022-01-05
GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004039/FP/22012034366535 — KACHCHA NALA NIRMAN BANIPURA SE SUKHRAM KE KHET TAK GP BANIPURA | Completed | 1486371.98 | 1407088 | 2020-08-03 | 2022-02-05
GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004039/FP/22012034366536 — PAKKA NALA NIRMAN KALYAN KE GHAR SE VINOD KE GHAR HOTE HUYE PULIYA TAK GP BANIPURA | Closed | 0 | 0 | 2020-05-01
GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004039/FP/22012034367395 — NALA NIRMAN SHIVSINGH KE GHAR SE NAHAR KI OR GP BANIPURA | Completed | 471700 | 504400 | 2020-09-25 | 2022-02-05
GOHAD | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004039/FP/22012034624718 — KACCHA NALA NIRMAN PULIYA SE LEKAR AGANOPURA KI OR GP BANIPURA | Closed | 0 | 0 | 2021-04-01
GOHAD | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004039/FP/22012034624719 — KACHCHA NIRMAN PUL SE BANIPURA KI OR GP BANIPURA | Closed | 0 | 0 | 2021-04-01
GOHAD | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004039/FP/22012034624720 — PAKKA NALA NIRMAN RAMVEER KE GHAR SE TALAB KI OR GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004039/FP/22012034626699 — Flood Control Channel Work अंगनुपुरा मोड से बगुलरी की ओर ग्राम पंचायत बनीपुरा | Closed | 0 | 0 | 2021-04-14
GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004039/FP/22012034633728 — Flood Control Channel Work माताप्रसाद के घर से पुलिया की ओर GP Banipura | Completed | 331785.15 | 118014 | 2023-08-25 | 2025-06-26
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034302929 — NADEP TAKA NIRMAN WORK MATAPRASAD SO CHALLURAM | Completed | 13800 | 13664.6 | 2016-11-09 | 2017-05-15
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034302930 — NADEP TAKA NIRMAN WORK MATAPRASAD SO FODAL | Completed | 13800 | 13664.6 | 2016-11-09 | 2016-12-25
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034302932 — NADEP TAKA NIRMAN WORK RAMKRIPAL SINGH SO HOTAM SINGH | Completed | 13800 | 13664.6 | 2016-11-09 | 2016-12-25
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303030 — NADEP TAKA NIRMAN WORK YOGENRDA SINGH SO VEERENDRA SINGH | Completed | 13800 | 13664.6 | 2016-11-09 | 2016-12-25
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303032 — NADEP TAKA NIRMAN WORK PARIKSHAT SO HARGOVIND | Completed | 13800 | 13664.6 | 2016-11-09 | 2016-12-25
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303034 — NADEP TAKA NIRMAN WORK UMMED SINGH SO VAKEEL SINGH | Completed | 13800 | 13664.6 | 2016-11-09 | 2016-12-25
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303035 — NADEP TAKA NIRMAN WORK MUKESH SO NATHURAM | Completed | 13800 | 13664.6 | 2016-11-09 | 2016-12-25
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303036 — NADEP TAKA NIRMAN WORK NARESH SO GYADEEN | Completed | 13800 | 13664.6 | 2016-11-09 | 2016-12-25
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303037 — NADEP TAKA NIRMAN WORK JAISHRIRAM SO HARIGOVIND | Completed | 13800 | 13664.6 | 2016-11-09 | 2016-12-25
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303038 — NADEP TAKA NIRMAN WORK PRADEEP SO MATAPRASAD | Completed | 13800 | 12328.6 | 2016-11-09 | 2016-12-25
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303207 — NADEP TAKA NIRMAN WORK MANGAL SINGH SO JAGNNATH | Completed | 13800 | 3006 | 2016-11-16 | 2019-03-30
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303208 — NADEP TAKA NIRMAN WORK BETAL SO GEGAD PRASAD | Completed | 13800 | 12662.6 | 2016-11-16 | 2016-12-25
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303264 — NADEP TAKA NIRMAN MAN SINGH SO BUDDHE RAM | Completed | 13800 | 12662.6 | 2016-11-16 | 2016-12-25
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303265 — NADEP TAKA NIRMAN CHAMELI BAI WO AMAR SINGH | Deleted | 0 | 0 | 2016-10-19
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303266 — NADEP TAKA NIRMAN CHAMELI BAI SO AMAR SINGH | Deleted | 0 | 0 | 2016-10-19
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303267 — NADEP TAKA NIRMAN CHAMELI BAI DO AMAR SINGH | Deleted | 0 | 0 | 2016-10-19
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303498 — NADEP TAKA NIRMAN SURAJ PRATAP SINGH SO TOTARAM | Completed | 13800 | 12662.6 | 2016-11-16 | 2016-12-25
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303500 — NADEP TAKA NIRMAN ASHOK SO MATAPRASAD | Completed | 13800 | 12662.6 | 2016-11-16 | 2016-12-25
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303503 — NADEP TAKA NIRMAN CHAMELI BAI WO AMAR SINGH | Completed | 13800 | 12662.6 | 2016-11-16 | 2016-12-25
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303505 — NADEP TAKA NIRMAN KESHAV SO PATIRAM | Completed | 13800 | 12662.6 | 2016-11-16 | 2016-12-25
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303506 — NADEP TAKA NIRMAN RADHA KISHAN SO PATIRAM | Completed | 13800 | 12662.6 | 2016-11-16 | 2016-12-25
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303507 — NADEP TAKA NIRMAN GYADEEN SO DEVI SINGH | Completed | 13800 | 12662.6 | 2016-11-16 | 2016-12-25
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303508 — NADEP TAKA NIRMAN DEVENDRA SO SARMAN SINGH | Completed | 13800 | 12662.6 | 2016-11-16 | 2016-12-25
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303509 — NADEP TAKA NIRMAN BHOORE SINGH SARNAM SINGH | Completed | 13800 | 12662.6 | 2016-11-16 | 2016-12-25
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303510 — NADEP TAKA NIRMAN RAMSWROOP SO NARAYAN SINGH | Completed | 13800 | 12662.6 | 2016-11-16 | 2016-12-25
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034303511 — NADEP TAKA NIRMAN VEERENDRA SINGH SO NARAYAN SINGH | Completed | 13800 | 12662.6 | 2016-11-16 | 2016-12-25
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034308464 — NADEP TAKA NIRMAN SURAJ SINGH SO MAYARAM | Completed | 13800 | 2505 | 2016-12-21 | 2019-03-30
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034308467 — NADEP TAKA NIRMAN RAVINDRA SO BHAGWAN SINGH | Completed | 13800 | 3132 | 2016-12-28 | 2019-03-30
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034308490 — NADEP TAKA NIRMAN RAJVEER SINGH SO KARAR SINGH | Deleted | 13800 | 0 | 2016-12-28
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034308492 — NADEP TAKA NIRMAN DATARAM SO RAGHUNATH SNGH | Completed | 13800 | 3006 | 2016-12-21 | 2019-03-30
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034308493 — NADEP TAKA NIRMAN RAKESH SO BEDRAM | Completed | 13800 | 3006 | 2016-12-21 | 2019-03-30
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034308495 — NADEP TAKA NIRMAN NARENDRA SINGH SO SARNAM | Completed | 13800 | 3006 | 2016-12-21 | 2019-03-30
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034308496 — NADEP TAKA NIRMAN SATENDRA SINGH SO KESHAV SINGH | Completed | 13800 | 3006 | 2016-12-21 | 2019-03-30
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034308497 — NADEP TAKA NIRMAN HUKUM SINGH SO RAJBAHADUR SINGH | Completed | 13800 | 3006 | 2016-12-21 | 2019-03-30
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034308500 — NADEP TAKA NIRMAN DARSHAN SO MEHTAB SINGH | Completed | 13800 | 3006 | 2016-12-21 | 2019-03-30
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004039/IF/22012034308501 — NADEP TAKA NIRMAN SARDAR SINGH SO HARIKANTH SINGH | Completed | 13800 | 3006 | 2016-12-21 | 2019-03-30
GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702004039/IF/22012034352376 — vrchharopan kary mukti dham banipura | Closed | 335000 | 0 | 2017-04-19
GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702004039/IF/22012034354105 — vrchharopan kary gov. school agnupura | Closed | 335000 | 0 | 2017-04-19
GOHAD | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1702004039/IF/22012034457132 — Talab | Closed | 0 | 0 | 2019-01-26
GOHAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plntation Horti-TreesIndividual / Wasteland Block Plantation of Horticulture Trees for Individuals | Plantation | 1702004039/IF/22012034586941 — नंदन फलोद्यान निर्माण कार्य - रामप्रकाश / टेकराम जाटव ग्राम पंचायत बनीपुरा | Ongoing | 197979.58 | 11825 | 2020-09-22
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004039/IF/22012034756148 — MEDBANDHAN KARAN SINGH/RAM SINGH GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702004039/IF/22012034756150 — MEDBANDHAN JASMANT SINGH/KARAN SINGH GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004039/IF/22012034756151 — MEDBANDHAN CHANDRAGUPT/SULTAN GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004039/IF/22012034756152 — MEDBANDHAN KRISHANMURARI/RAMDEEN GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004039/IF/22012034756153 — MEDBANDHAN GYAPRASAD /TEKRAM GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004039/IF/22012034756154 — MEDBANDHAN RAMPRAKASH/TEKRAM GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004039/IF/22012034756156 — MEDBANDHAN DATARAM/RAGHUWAR GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702004039/IF/22012034756157 — MEDBANDHAN PYARELAL/LAJJARAM GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004039/IF/22012034756158 — MEDBANDHAN MATAPRASAD / FODAL GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702004039/IF/22012034756159 — MEDBANDHAN MANSINGH/ BUDHE GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004039/IF/22012034756161 — MEDBANDHAN BADAMI/ MAN SINGH GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004039/IF/22012034756162 — MEDBANDHAN MULA BAI/ BABURAM GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004039/IF/22012034756164 — MEDBANDHAN DATARAM/ MATROOLAL GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004039/IF/22012034756167 — MEDBANDHAN RAMSINGH/ HARVILASH GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004039/IF/22012034756168 — MEDBANDHAN HAKIM/DHANIRAM GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004039/IF/22012034756170 — MEDBANDHAN SHANKARLAL/ HARMUKH GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004039/IF/22012034757192 — MEDBANDHAN VIRENDRA/SITARAM GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004039/IF/22012034757201 — MEDBANDHAN KAMLESH / DATARAM GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004039/IF/22012034757203 — MEDBANDHAN VIMLA/ RAJENDRA GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004039/IF/22012034757207 — MEDBADHAN RAMWATI/ VIJAYRAM GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004039/IF/22012034757212 — MEDBANDHAN BRAHMKUMARI/ MAHIPAT GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004039/IF/22012034757216 — MEDBANDHAN BRAHMKUMARI/ MAHIPAT GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004039/IF/22012034757223 — MEDBANDHAN MATAPRASAD /CHALLURAM GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004039/IF/22012034757229 — MEDBANDHAN BRAJESH / DWARIKAPARASAD GP BANIPURA | Closed | 0 | 0 | 2021-04-14
GOHAD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Afforestation of wasteland Forestry trees for individual | Plantation | 1702004039/IF/22012035136781 — अमृत वाटिका (वृक्षारोपण कार्य) मुक्तिधाम परिसर बनीपुरा ग्राम पंचायत बनीपुरा | Completed | 55847.4 | 21216 | 2023-08-25 | 2024-10-30
GOHAD | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004039/IF/22012035163096 — खेत तालाब निर्माण कार्य हरिज्ञान के खेत पर ग्रा0पं0बनीपुरा | Physically Completed | 385261.22 | 183182 | 2024-01-12 | 2026-05-16
GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004039/IF/22012035398218 — khet talab nirmad karya pyare lal ke khet par GP banipura | Physically Completed | 450885.64 | 194706 | 2025-05-12 | 2026-06-17
GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004039/IF/22012035528766 — JGSY Khet Talab nirman karya ramprakash / tekram agnupura gp banipura | Ongoing | 147621.16 | 28449 | 2025-05-21
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702004039/IF/9993694923 — मेडबंधान लालाराम पु० छ‍विराम बनीपुरा | Deleted | 17400 | 0 | 2015-08-18
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702004039/IF/9993694927 — MEDBANDHAN WORK RAMSEVAK S/O UDAY SINGH | Deleted | 17400 | 0 | 2015-12-16
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004039/IF/9993695208 — CATTELE SHED LALARAM S/O CHHAVIRA, JATAW | Completed | 95000 | 125093.1 | 2015-12-16 | 2018-07-01
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004039/IF/9993706601 — पशुशेड निर्माण कार्य पानसिंह पुत्र छविराम | Completed | 95000 | 94089 | 2016-01-20 | 2016-11-10
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004039/IF/9993706603 — पशुशेड‍ निर्माण कार्य शकुन्‍तला बाई पत्‍नी मुंशी | Completed | 95000 | 94819.04 | 2016-01-20 | 2017-02-25
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004039/IF/9993706605 — पशुशेड निर्माण कार्य बनवारीलाल पुत्र बाबूराम | Completed | 95000 | 94819.04 | 2016-02-03 | 2016-11-24
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004039/IF/9993707560 — मेडबंधान कार्य बदन सिंह पुत्र सरनाम सिंह | Deleted | 28900 | 0 | 2016-01-27
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004039/IF/9993707562 — मेडबंधान कार्य जसवीर पुत्र सरनाम सिंह | Deleted | 43700 | 0 | 2016-01-27
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004039/IF/9993707853 — मेडबंधान कार्य रामनाथ पुत्र तांतीराम | Deleted | 24000 | 0 | 2016-01-27
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004039/IF/9993708426 — पशुशेड निर्माण कार्य राकेश पुत्र जोहरीलाल | Completed | 95000 | 94087.6 | 2016-02-03 | 2016-11-24
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004039/IF/9993708427 — पशुशेड निर्माण कार्य सुरेश कुमार पुत्र ज्‍वाली प्रसाद | Completed | 95000 | 94818.55 | 2016-02-03 | 2016-11-24
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004039/IF/9993709716 — पशुशेड निर्माण कार्य भारत सिंह पुत्र बालमुकुन्‍द | Deleted | 95000 | 0 | 2015-10-03
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004039/IF/9993709717 — पशुशेड निर्माण कार्य आशाराम पुत्र मातादीन | Deleted | 95000 | 0 | 2015-10-03
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004039/IF/9993709718 — पशुशेड निर्माण कार्य कमलेश पुत्र टीकाराम | Deleted | 95000 | 0 | 2015-10-03
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004039/IF/9993709719 — पशुशेड निर्माण कार्य रामवरन पुत्र शंकरलाल | Deleted | 95000 | 0 | 2015-10-03
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004039/IF/9993709720 — पशुशेड निर्माण कार्य उम्‍मेद पुत्र वकील सिंह | Deleted | 95000 | 0 | 2015-10-03
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004039/IF/9993709722 — मेडबंधान कार्य रणवीर सिंह पुत्र बुद्धीलाल | Deleted | 8900 | 0 | 2016-02-10
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004039/IF/9993709724 — मेडबंधान कार्य सुजान सिंह पुत्र जगदीश सिंह | Deleted | 39200 | 0 | 2016-02-10
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004039/IF/9993709725 — मेडबंधान कार्य बेदराम पुत्र जगदीश सिंह | Deleted | 29200 | 0 | 2016-02-10
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004039/IF/9993709728 — मेडबंधान कार्य रामशंकर, रामशरन पुत्र जगत सिंह | Deleted | 49900 | 0 | 2016-02-10
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004039/IF/9993709730 — मेडबंधान कार्य दाखश्री बाई पत्‍नी जगत सिंह | Deleted | 15500 | 0 | 2016-02-10
GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004039/IF/9993729046 — CATTELE SHED HOTAM SINGH/AUTAR SINGH | Deleted | 0 | 0 | 2016-01-26
GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/134014 — Construction of IAY House -IAY REG. NO. MP-02-004-039-001/28229167 | Completed | 14310 | 13026 | 2016-08-10 | 2018-02-15
GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/134016 — Construction of IAY House -IAY REG. NO. MP-02-004-039-001/32776653 | Completed | 14310 | 13026 | 2016-08-10 | 2018-02-15
GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/134018 — Construction of IAY House -IAY REG. NO. MP-02-004-039-001/37014123 | Completed | 14310 | 13026 | 2016-08-10 | 2018-02-15
GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/134021 — Construction of IAY House -IAY REG. NO. MP-02-004-039-001/37070043 | Completed | 14310 | 15030 | 2016-08-10 | 2018-02-15
GOHAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/1901600 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4445308 | Completed | 15660 | 15614 | 2018-11-02 | 2020-06-01
GOHAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/1901657 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4485724 | Completed | 15660 | 15660 | 2018-09-22 | 2019-02-18
GOHAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/1902320 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4964464 | Completed | 17100 | 13716 | 2018-11-19 | 2022-03-30
GOHAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/1902585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5213205 | Completed | 15660 | 15720 | 2018-10-14 | 2019-12-01
GOHAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/1902746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5001710 | Completed | 15660 | 15834 | 2018-09-22 | 2019-01-01
GOHAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/1902948 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5263205 | Completed | 15660 | 15464 | 2018-10-14 | 2020-06-01
GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/195350 — Construction of IAY House -IAY REG. NO. MP-02-004-039-001/37072241 | Completed | 14310 | 13026 | 2016-08-10 | 2018-02-15
GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/195351 — Construction of IAY House -IAY REG. NO. MP-02-004-039-001/37072331 | Completed | 14310 | 13026 | 2016-08-10 | 2018-02-15
GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/195352 — Construction of IAY House -IAY REG. NO. MP-02-004-039-001/37072494 | Completed | 14310 | 13026 | 2016-08-10 | 2018-02-15
GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/252108 — Construction of IAY House -IAY REG. NO. MP1976121 | Completed | 15030 | 15253 | 2017-02-01 | 2018-02-15
GOHAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/4169428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127558445 | Completed | 18360 | 15177.6 | 2022-07-01 | 2023-01-20
GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/589941 — Construction of IAY House -IAY REG. NO. MP2085253 | Completed | 15030 | 14956 | 2017-02-15 | 2018-02-15
GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/589950 — Construction of IAY House -IAY REG. NO. MP2095041 | Completed | 15030 | 14926 | 2017-02-15 | 2018-02-15
GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/734481 — Construction of IAY House -IAY REG. NO. MP2092022 | Completed | 15030 | 14964 | 2017-05-17 | 2018-02-15
GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/734652 — Construction of IAY House -IAY REG. NO. MP2097100 | Approved | 27000 | 0 | 2017-03-19
GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/754656 — Construction of IAY House -IAY REG. NO. MP2715565 | Completed | 15030 | 15480 | 2017-05-24 | 2018-02-15
GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/765465 — Construction of IAY House -IAY REG. NO. MP3213295 | Completed | 15030 | 15480 | 2017-05-17 | 2018-02-15
GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004039/IF/IAY/778256 — Construction of IAY House -IAY REG. NO. MP3884600 | Completed | 15030 | 15504 | 2017-05-17 | 2018-06-28
GOHAD | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702004039/LD/22012034292109 — खेल मैदान निर्माण कार्य शा.मा.विद्यालय अगनूपुरा | Completed | 547000 | 232023 | 2016-09-14 | 2017-10-29
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702004039/LD/22012034292598 — MUKTIDHAM NIRMAN WORK BANIPURA | Completed | 1142000 | 1119164.25 | 2016-10-19 | 2019-03-30
GOHAD | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004039/LD/78 — मेड बन्‍धान कार्य प्‍यारेलाल / लज्‍जाराम | Completed | 17000 | 9600 | 2010-11-18 | 2010-06-11
GOHAD | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004039/LD/9926713414 — मेड बंधान कार्य लाल सिंह पुत्र राजेंद्र सिंह कचन स | Completed | 50730 | 38779 | 2014-08-27 | 2016-06-05
GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004039/RC/22012034197435 — AGNUPURA CC ROAD HANUMAAN MANDIR SE RAMESHWER DAYA | Completed | 117000 | 116859 | 2014-01-08 | 2016-06-05
GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004039/RC/22012034197437 — AGNUPURA MAIN ROAD SE GABDU KE GHAR HOKER RAMCHARA | Completed | 146200 | 130620 | 2014-02-05 | 2016-06-05
GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004039/RC/22012034197786 — CCROAD GOPIRAM KE GHAR SE SULTAN KE GHAR KI OR AGN | Completed | 122000 | 92240.5 | 2014-01-08 | 2016-06-05
GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004039/RC/22012034197796 — CCROAD MAIN ROAD SE BAIJNATH SINGH KE GHAR HOTE HU | Completed | 97166 | 52113 | 2014-02-26 | 2016-08-14
GOHAD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004039/RC/22012034206778 — CC ROAD NIRMAAN KARYA RAMSWAROOP KE GHAR SE BACCHU SINGH KE MAKAAN KI OR AGNUPURA | Completed | 194332 | 124322 | 2014-05-28 | 2016-08-06
GOHAD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004039/RC/22012034219477 — CC ROAD NIRMAAN KARYA NATHURAM KE GHAR SE GYARAM B | Completed | 97166 | 65533.6 | 2014-05-28 | 2016-08-06
GOHAD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004039/RC/22012034219568 — CC ROAD NIRMAAN KARYA RAMNATH KE GHAR SE DHOULATRA | Completed | 97166 | 100585 | 2014-05-28 | 2016-08-06
GOHAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004039/RC/22012034283327 — मिटटी बजरी रोड निर्माण कार्य खेत सडक योजना अगनूपुरा रोड से बनीपुरा रोड की ओर (अगनूपुरा) बनीपुरा | Completed | 1473000 | 630555.5 | 2015-08-19 | 2017-01-16
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004039/RC/22012034328060 — सुदूर ग्राम सम्‍पर्क सडक बनीपुरा से कठुवांगुर्जर की ओर | Completed | 1200000 | 1179928.16 | 2017-03-01 | 2020-05-30
GOHAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004039/RC/22012034340060 — SUDUR SAMPARK ROAD AGANUPURA SE BANIPURA ROAD TAK | Deleted | 699000 | 598224.5 | 2017-05-29
GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004039/RC/22012034375935 — Sudur Sampark Sadak Work - Banipura | Closed | 0 | 0 | 2017-01-26
GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004039/RC/22012034530560 — Sudur road banipura se siyaram ke khet ki or gp banipura | Completed | 2457508.53 | 2324544.07 | 2020-07-30 | 2025-05-09
GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004039/RC/22012034530561 — Sudur road Chhareta nahar ki puliya se Fatehpura ki or gp banipura | Closed | 0 | 0 | 2020-05-01
GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004039/RC/22012034531773 — SUDOOR ROAD BANIPURA PULIYA SE PUL KE PASS SIYARAM KHET KI OR GP BANIPURA | Closed | 0 | 0 | 2020-05-01
GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004039/RC/22012034532171 — सुदूर संपर्क सडक बनीपुरा पुलिया से पुल के पास सियाराम के खेत की ओर ग्राम पंचायत बनीपुरा | Closed | 0 | 0 | 2020-04-14
GOHAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004039/RC/22012034569666 — SUDOOR ROAD NIRMAN PULIYA SE LEKAR NADI KI OR GP BANIPURA | Closed | 0 | 0 | 2021-04-01
GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004039/RC/22012034636136 — CC NALI NIRMAN KARYA ASHOK KE GHAR SE DINESH KE GHAR KI AUR GRAM AGNUPURA GP BANIPURA | Deleted | 88940 | 0 | 2023-04-01
GOHAD | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004039/RC/246 — रामअख्‍त्‍यार गुर्जर के मकान से रामेश्‍वर गुर्जर के मकान तक बनीपुरा पंचपरमेश्‍वर | Deleted | 0 | 0 | 2012-02-15
GOHAD | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702004039/RC/295 — मि0मुरम बनीपुरा रोड से अगनूपुरा तक | Completed | 0 | 170760 | 2012-03-22 | 2013-08-06
GOHAD | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702004039/RC/33 — MittyMurmeekard | Deleted | 276000 | 0 | 2008-01-26
GOHAD | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702004039/RC/83 — खंरजा निर्माण मैनरोड से महेन्‍द्र सिह के मकान की ओर | Deleted | 65000 | 139332.56 | 2010-08-26
GOHAD | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702004039/RC/94 — मुरमीकरण कंचनपुरा मोड से गोहद की ओर बनीपुरा रोड तक | Completed | 0 | 478763.78 | 2010-10-06 | 2016-06-05
GOHAD | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702004039/RC/96 — खरंजा निर्माण कंचन पुरा | Deleted | 0 | 0 | 2010-04-10
GOHAD | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702004039/RC/97 — खरंजा निर्माण कंचन पुरा | Completed | 0 | 31000 | 2010-08-26 | 2010-08-26
GOHAD | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702004039/RC/98 — अर्थ वर्क एवं मुरमी करण वनीपुरा रोड से कंचनपुरा तक | Completed | 0 | 447422.8 | 2010-05-15 | 2016-06-05
GOHAD | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702004039/RC/99 — अर्थ वर्क एवं मुरमी करण कंचन पुरा से कठमा रोड तक | Completed | 0 | 367232.8 | 2010-09-12 | 2011-02-11
GOHAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004039/RS/22012034419636 — SBM INDIVIDUAL LATRIN NIRMAN MAN SINGH S/O BEDRI AGNUPURA | Closed | 12000 | 0 | 2018-06-20
GOHAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004039/RS/22012034419649 — SBM INDIVIDUAL LATRIN LAJJARAM S/O GAMBHEER AGNUPURA | Closed | 12000 | 0 | 2018-06-20
GOHAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004039/RS/22012034419653 — SBM INDIVIDUAL LATRIN NIRMAN - BETAL SINGH S/O BAIJNATH GP BANIPURA | Closed | 12000 | 0 | 2018-06-20
GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702004039/RS/22012034496717 — ग्रामीण सामुदायिक स्‍वच्‍छता परिसर बनीपुरा ग्राम पंचायत बनीपुरा | Completed | 43000 | 41040 | 2020-09-29 | 2022-02-05
GOHAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1702004039/RS/22012034584386 — CC NALA NIRMAN VINOD KE GHAR SE PULIYA HOTE HUA RAYSINGH KE GHAR KI OR | Completed | 90000 | 75077 | 2021-10-14 | 2022-08-26
GOHAD | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1702004039/RS/22012034683203 — सीसी नाला/नाली निर्माण कार्य मैनरोड से दिनेश के घर की ओर अंगनूपुरा ग्राम पंचायत बनीपुरा | Completed | 47644 | 42636 | 2022-12-31 | 2023-05-13
GOHAD | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702004039/WC/100 — सौकपिट निर्माण्‍ा कार्य रोड के किनारे अगनूपुरा हैण्‍डपम्‍प के पास | Completed | 4000 | 9700 | 2010-04-22 | 2009-10-04
GOHAD | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702004039/WC/101 — सौकपिट निर्माण कार्य रामेश्‍वर के घर के पास वाले कूप के पास | Completed | 4000 | 9700 | 2010-05-22 | 2009-10-04
GOHAD | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702004039/WC/102 — सौकपिट निर्माण कार्य कुंआ के पास अगनूपुरा | Completed | 4000 | 8200 | 2010-04-22 | 2009-10-04
GOHAD | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702004039/WC/140 — सोकपिट निर्माण कुऑके पास अगनुपुरा | Deleted | 0 | 0 | 2009-10-04
GOHAD | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702004039/WC/141 — सोकपिट निर्माण कुऑके पास अगनुपुरा | Deleted | 0 | 0 | 2009-10-04
GOHAD | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702004039/WC/144 — तालाव निर्माण अगनुपुरा | Completed | 0 | 81000 | 2010-04-23 | 2010-05-15
GOHAD | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stone Bund / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1702004039/WC/22012034323245 — TANK RENOVATION BUND STRANTHNING KARYA GRAM BANIPURA SCHOOL KE PASS | Completed | 42850 | 20468 | 2017-05-03 | 2018-02-14
GOHAD | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702004039/WC/22012034381610 — Talab Work GP Banipura | Closed | 0 | 0 | 2017-01-26
GOHAD | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702004039/WC/22012034425850 — Dagtank Work - Banipura GP Banipura | Completed | 336000 | 313824 | 2019-01-24 | 2025-05-09
GOHAD | 2019-2020 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702004039/WC/22012034540530 — कच्‍चानाला निर्माण कार्य बनीपुरा मैन रोड से अंगनूपुरा तालाब की ओर GP बनीपुरा | Closed | 0 | 0 | 2019-08-15
GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702004039/WC/22012034548518 — STOPDAM NIMAN GRAM AGNUPURA GP BANIPURA | Closed | 0 | 0 | 2020-04-01
GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702004039/WC/22012034556686 — Kachcha nala nirman stopdam agnoopura se nadi ki or gp banipura | Closed | 0 | 0 | 2020-04-02
GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702004039/WC/22012034560514 — Stopdam / Checkdam Work - Aganupura GP Banipura | Completed | 1496285.55 | 1140093.57 | 2020-07-20 | 2022-07-01
GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702004039/WC/22012034567887 — STOP DAM NIRMAN NADI KE PASS JAGANPURA GP BANIPURA | Closed | 0 | 0 | 2020-05-15
GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702004039/WC/22012034568274 — STOP DAM/CHEK DAM NADI KE PASS AGNUPURA GP BANIPURA | Closed | 0 | 0 | 2020-05-01
GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702004039/WC/22012034621204 — Stop dam Nadi ke pass agnoopura gp banipura | Completed | 1465033.59 | 1269662.82 | 2021-03-14 | 2025-05-09
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004039/WC/22012034674269 — DANK TANK NIRMAN SHANKARLAL KE KHET KE PASS GP BANIPURA | Closed | 0 | 0 | 2021-04-01
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004039/WC/22012034674295 — DANK TANK NIRMAN PYARELAL KE KHET KE PASS GP BANIPURA | Closed | 0 | 0 | 2021-04-01
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702004039/WC/22012034674305 — SOK PIT NIRMAN RAMKUMAR KHET KE PASS GP BANIPURA | Closed | 0 | 0 | 2021-04-01
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004039/WC/22012034711920 — DANK TANK NIRMAN RAMSINGH KE GHAR KE PASS AGNUPURA GP BANIPURA | Completed | 1372065.34 | 821022 | 2021-06-16 | 2025-04-18
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702004039/WC/22012034922959 — KOOL NIRMAN KARYA RANVEER SINGH KE KHET SE MAHESH KE KHET KI AUR BANIPURA | Closed | 0 | 0 | 2021-04-01
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702004039/WC/22012034922960 — KOOL NIRMAN KARYA AGNUPURA MOD SE BAGULARI KI AUR | Closed | 0 | 0 | 2021-04-01
GOHAD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004039/WC/22012035040234 — सामुदायिक जल संचयन तालाब निर्माण कार्य शांतीधाम के पास अंगनूपुरा ग्राम पंचायत बनीपुरा | Completed | 991610.87 | 363069 | 2023-04-12 | 2026-04-13
GOHAD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004039/WC/22012035126281 — सामुदायिक जल संचयन तालाब निर्माण कार्य शंकरलाल के खेत के पास ग्रा0पं0बनीपुरा | Completed | 608887.32 | 206473 | 2023-12-28 | 2026-04-13
GOHAD | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702004039/WC/98 — सौकपिट निर्माण रोड के किनारे वाला कूप कंचनपुरा | Completed | 4000 | 9724.8 | 2010-05-29 | 2009-10-04
GOHAD | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702004039/WC/99 — सौकपिट निर्माण कार्य लज्‍जाराम के घर के पास वाले कूप के पास कंचनपुरा | Completed | 3600 | 8093.27 | 2010-05-29 | 2009-10-04
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702004039/WH/22012034455705 — तालाब जीर्णोध्‍दार कार्य बनीपुरा तालाब ग्राम पंचायत बनीपुरा | Completed | 36105.24 | 36284 | 2022-01-24 | 2022-04-02
GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702004039/WH/22012034455708 — तालाब जीर्णोध्‍दार कार्य अंगनूपुरा तालाब ग्राम पंचायत बनीपुरा | Completed | 47059.15 | 42126 | 2022-01-25 | 2025-05-09