## Work List
Exported on: 2026-09-04 14:22:58
Filters applied:
Data source: VBGRAMG
District: BHIND
Block: All
Panchayat: JHANKARI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
GOHAD | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702004060/AV/22012034625989 — Boundrywall work Govt. Primary School Makrenta GP Jhankari | Ongoing | 1411000 | 0 | 2022-12-11
GOHAD | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702004060/AV/22012034630183 — बाउन्ड्रीबाल निर्माण कार्य शासकीय हाईस्कूल झांकरी | Ongoing | 1337000 | 0 | 2023-03-19
GOHAD | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702004060/AV/22012034630184 — बाउन्ड्रीबाल निर्माण कार्य शासकीय प्रा0 / मा0 स्कूल झांकरी ग्रा0पं0झांकरी | Ongoing | 1337000 | 0 | 2023-03-19
GOHAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004060/IF/22012034643167 — PASHUSED NIRMAN KARYA DARSAN SINGH SO BAIJNATH | Ongoing | 63830.2 | 0 | 2021-01-30
GOHAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004060/IF/22012034643169 — PASHU SET NIRMAN KARYA MUNNI BAI WO PRATAP | Ongoing | 63830.2 | 0 | 2021-01-30
GOHAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004060/IF/22012034643173 — PASHUSED NIRMAN KARYA RAMSEVAK SO MATADIN | Ongoing | 63830.2 | 0 | 2021-01-30
GOHAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004060/IF/22012034643174 — PASHUSED NIRMAN KARYA RAJENDRA SO SANTOKHI LAL KUSHWAH | Ongoing | 63830.2 | 0 | 2021-01-30
GOHAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004060/IF/22012034643175 — PASHUSED NIRMAN KARYA SALEEM KHAN SO GUTTI KHA | Ongoing | 63830.2 | 0 | 2021-01-30
GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004060/IF/22012035337722 — khet talav nirman kary aneeta ke khet par jhankari | New | 0 | 0 | 2025-04-01
GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004060/IF/22012035337766 — khet talav nirman kary poran ke khet par jhankari | New | 0 | 0 | 2025-04-01
GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004060/IF/22012035337786 — khet talav nirman kary gandrav ke khet par jhankari | New | 0 | 0 | 2025-04-01
GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004060/IF/22012035337796 — khet talav nirman kary mayaram ke khet par jhankari | New | 0 | 0 | 2025-04-01
GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004060/IF/22012035337806 — khet talav nirman kary sudhama lal ke khet par neerpura | New | 0 | 0 | 2025-04-01
GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004060/IF/22012035337816 — khet talav nirman kary mohan ke khet par neerpura | New | 0 | 0 | 2025-04-01
GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004060/IF/22012035340420 — JGSY Khet talav nirman kary gandarv ke khet par Jhankari | Approved | 0 | 0 | 2025-04-01
GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004060/IF/22012035340444 — JGSY Khet talav nirman kary mayaram ke khet par neerpura | New | 0 | 0 | 2025-04-01
GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004060/IF/22012035341038 — JGSY Khet talav nirman kary mayaram ke khet par neerpura | Approved | 0 | 0 | 2025-04-02
GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004060/IF/22012035344154 — JGSY Khet talav nirman kary gandarv ke khet par Jhankari | New | 0 | 0 | 2025-04-02
GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004060/IF/22012035554218 — JGSY KHET TALAB NIRMAN KARYA ALOK KE KHET KE PASS GRAM NEERPURA GP JHANKARI | Approved | 0 | 0 | 2025-04-01
GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004060/IF/22012035554228 — JGSY KHET TALAB NIRMAN KARYA ANEETA KE KHET PAR GP JHANKARI | Approved | 0 | 0 | 2025-04-01
GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702004060/IF/22012035617555 — Ek Bagiya Maa ke Naam Mayadevi GP Jhankri | Approved | 0 | 0 | 2025-08-15
GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702004060/IF/22012035617561 — Ek Bagiya Maa ke Naam RINKI GP Jhankari | Ongoing | 258506.05 | 3600 | 2025-12-13
GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004060/IF/IAY/5880175 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131288438 | Ongoing | 27000 | 0 | 2026-02-06
GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004060/IF/IAY/5880184 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131288503 | Ongoing | 27000 | 0 | 2026-02-06
GOHAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004060/IF/IAY/6021966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141689241 | Ongoing | 27000 | 0 | 2026-05-14
GOHAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702004060/WC/22012035260118 — khet talab nirman karya yogesh ke khet par neerpura | New | 0 | 0 | 2025-04-01
GOHAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702004060/WC/22012035260120 — khet talab nirman kaya mayaram ke khet par neerpura | New | 0 | 0 | 2025-04-01
GOHAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702004060/WC/22012035260125 — khet talab nirman karya chokhelal ke khet ke pass neerpura | New | 0 | 0 | 2025-04-01
GOHAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702004060/WC/22012035260130 — khet talab nirman karya sudama ke khet ke par neerpura | New | 0 | 0 | 2025-04-01
GOHAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702004060/WC/22012035275558 — perculation tank nirman karya chandan ke khet par pass gram neerpura gp jhankari | New | 0 | 0 | 2025-04-01
GOHAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702004060/WC/22012035295987 — डगवैल रिचार्ज पिट जाटव मौहल्ला वाले कूप पर ग्राम पंचायत झांकरी | Approved | 0 | 0 | 2025-04-14
GOHAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004060/WC/22012035311049 — तालाब निर्माण कार्य चंदन के खेत के पास ग्राम नीरपुरा ग्राम पंचायत झांकरी | Approved | 0 | 0 | 2025-04-01
GOHAD | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702004060/WC/VB/22012035333932 — Counstruction of Contour Trench work sundarnath pahadi par GP Jhankri | Approved | 0 | 0 | 2026-04-14