## Work List
Exported on: 2026-10-26 23:53:51
Filters applied:
Data source: MGNREGA
District: BHIND
Block: All
Panchayat: NANDNA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
RON | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702005019/AV/22012034573932 — retarning wall masan baba avam asok singh road ke bagal me nadana | Ongoing | 32250 | 25440 | 2021-10-29
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1702005019/AV/22012034620242 — Ma Ki BAGIYA Anganwadi Kendra Nandna | Closed | 5600 | 0 | 2022-04-24
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1702005019/AV/22012034620245 — Ma Ki BAGIYA MS SCHOOL Nandna | Closed | 5600 | 0 | 2022-04-24
RON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Canal Line Plantation-Horticulture - Community / Canal Line Plantation of Horticulture Trees for Community | Plantation | 1702005019/DP/22012034598557 — Meri Mati Mera Desh Vraksharopan nandna | Closed | 54564.94 | 0 | 2023-04-14
RON | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1702005019/FP/22012034367528 — nala nirman r amshankar ke ghar ke pass se govind ke ghar ki or nadana | Completed | 102300 | 100674 | 2020-09-24 | 2022-11-13
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702005019/FP/22012034630932 — Kachcha Nala Nirman Mean Road se Kadere ki khadiya ki or nandan | Ongoing | 49720.14 | 4896 | 2023-01-05
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702005019/FP/22012034630933 — Kachcha Nala Nirman Mean Road se Kadere ki khadiya ki or nandan | Closed | 0 | 0 | 2022-10-02
RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702005019/IF/22012034351720 — vriksharopan road kinare nandna | Completed | 335000 | 20096 | 2017-06-25 | 2021-12-23
RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702005019/IF/22012034353617 — vriksharopan mata mandir etc | Completed | 335000 | 18032 | 2017-07-19 | 2021-12-23
RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702005019/IF/22012034370006 — PLANTATION | Closed | 0 | 0 | 2017-04-01
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005019/IF/22012034616000 — medbandhan baburam/lalaram | Completed | 33881.33 | 33584 | 2020-09-29 | 2021-06-30
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005019/IF/22012034651332 — pashushed Shyam Singh | Completed | 101804.91 | 99291.4 | 2021-04-23 | 2024-03-03
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005019/IF/22012034655688 — pashused vimlesh / rakesh singh | Completed | 102033.26 | 90393.25 | 2021-05-20 | 2024-03-03
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005019/IF/22012034655689 — pashused rajesh/ prabal singh | Completed | 102033.26 | 89428.25 | 2021-05-20 | 2024-03-03
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005019/IF/22012034655690 — pashused brajesh singh/ravindra singh | Completed | 102033.26 | 90200.25 | 2021-05-20 | 2024-03-03
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005019/IF/22012034759558 — khet talab vimlesh/rakesh nadna | Closed | 337715.44 | 0 | 2021-08-27
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005019/IF/22012034759561 — khet talab rajesh/prabal | Closed | 337715.44 | 0 | 2021-04-14
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005019/IF/22012034787509 — khet talab sattole/pancham | Deleted | 0 | 0 | 2021-04-14
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005019/IF/22012034787526 — medbandhan radheshyam/lalaram | Closed | 0 | 0 | 2021-04-14
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005019/IF/22012034787546 — medbandhan Indra singh/malkhan singh | Closed | 0 | 0 | 2021-04-14
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005019/IF/22012034787553 — Medbandhan kedar/Chhotelal | Closed | 0 | 0 | 2021-04-14
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005019/IF/22012034826096 — khet talab sunil/bhagwandas nadna | Closed | 0 | 0 | 2021-04-14
RON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005019/IF/22012035216356 — Khet Talab Ramotar singh | Closed | 385261.22 | 0 | 2024-01-27
RON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005019/IF/22012035216358 — Khet Talab Munnesh singh/Dulare Singh | Closed | 385261.22 | 0 | 2024-01-27
RON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005019/IF/22012035217641 — Khet Talab Bannam Singh | Closed | 385261.22 | 0 | 2024-01-27
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005019/IF/22012035530330 — Khet Talab Ray Singh /Rampal Singh Nandana | Approved | 147620.89 | 0 | 2025-04-14
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005019/IF/22012035530344 — Khet Talab Omprakash /Chhakkilal Nandana | Approved | 147621.16 | 0 | 2025-04-14
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005019/IF/22012035530351 — Khet Talab Balvir / Chhakkilal Nandana | Approved | 147621.16 | 0 | 2025-04-14
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005019/IF/22012035552529 — Khet Talab Chhakkilal / Pancham Nandana | Approved | 0 | 0 | 2025-04-14
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005019/IF/22012035552536 — Khet Talab Ramnarayan / Manpal Nandana | Deleted | 0 | 0 | 2025-04-14
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005019/IF/22012035552578 — Khet Talab Ramnarayan / Manpal Nandana | Approved | 0 | 0 | 2025-04-14
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005019/IF/22012035552584 — Khet Talab Sattole / Pancham Nandana | Deleted | 0 | 0 | 2025-04-14
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005019/IF/22012035552616 — Khet Talab Nirman Sattole / Pancham Nandana | Approved | 0 | 0 | 2025-04-14
RON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005019/IF/9993723875 — cattlshed amar singh/tejpal | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005019/IF/9993723884 — cattleshed laltaprasad/tjpal | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005019/IF/9993724847 — cattleshed jagmohan/badriprasad | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005019/IF/9993724859 — cattleshed jay singh/chandrabhan | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005019/IF/9993724865 — cattleshed guddi devi/uday singh | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005019/IF/9993724872 — cattleshed balveer/chhakkilal | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005019/IF/9993724875 — cattleshed omprakash/chhakkilal | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005019/IF/9993724880 — cattleshed kashiram/brandavan | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005019/IF/9993724885 — cattleshed chhutte/dhanpat | Deleted | 0 | 0 | 2016-01-26
RON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/121523 — Construction of IAY House -IAY REG. NO. MP-02-005-019-001/71 | Completed | 14310 | 4175 | 2016-07-30 | 2021-09-14
RON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/1907219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4275029 | Completed | 15660 | 15453.6 | 2018-09-11 | 2019-08-13
RON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/1907920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4981981 | Completed | 15660 | 15660 | 2018-09-11 | 2018-12-16
RON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/3810491 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105557548 | Physically Completed | 18360 | 17544 | 2022-11-06 | 2024-11-21
RON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/3925377 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105568713 | Physically Completed | 18360 | 14718 | 2023-06-06 | 2024-11-21
RON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/544740 — Construction of IAY House -IAY REG. NO. MP3205884 | Completed | 15030 | 14364 | 2017-02-12 | 2018-11-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/5570546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105561066 | Ongoing | 23490 | 12267 | 2025-06-05
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/5570975 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105565058 | Ongoing | 23490 | 15660 | 2025-06-05
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/5570976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105565759 | Ongoing | 23490 | 12528 | 2025-06-05
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/5571520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105558894 | Ongoing | 23490 | 12528 | 2025-06-05
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/5571608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102642040 | Ongoing | 23490 | 7830 | 2025-06-05
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/5571612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105567288 | Physically Completed | 23490 | 20358 | 2025-04-30 | 2026-06-14
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/5571733 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105571288 | Ongoing | 23490 | 15660 | 2025-06-05
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/5571734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105564217 | Ongoing | 23490 | 12528 | 2025-06-05
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/5572213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100790086 | Ongoing | 23490 | 4959 | 2025-12-20
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/5572474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105561877 | Ongoing | 23490 | 12528 | 2025-06-05
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/5706812 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105559712 | Ongoing | 23490 | 12528 | 2025-09-12
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/5707103 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105570970 | Ongoing | 23490 | 10962 | 2025-09-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/5707564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105569769 | Ongoing | 23490 | 12528 | 2025-09-12
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/5707848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113631141 | Ongoing | 23490 | 12528 | 2025-09-12
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/5708079 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105566264 | Ongoing | 23490 | 6264 | 2025-09-12
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/5708255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102654672 | Approved | 23490 | 0 | 2025-03-25
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/5932288 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151347795 | Ongoing | 23490 | 1566 | 2026-05-26
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/5933523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113631090 | Ongoing | 23490 | 1566 | 2026-05-26
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/6051964 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102640490 | Approved | 23490 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/6055819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151358534 | Approved | 23490 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/6056041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105571964 | Approved | 23490 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/6056662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151343134 | Approved | 23490 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/6058418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151354031 | Approved | 23490 | 0 | 2026-02-10
RON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005019/IF/IAY/651785 — Construction of IAY House -IAY REG. NO. MP3899134 | Completed | 15030 | 14424 | 2017-03-07 | 2018-09-29
RON | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/173 — मेडबंधान मुन्‍नास्रिह/हरी सिंह | Completed | 22993 | 3640 | 2009-07-10 | 2013-11-10
RON | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/174 — मेडबंधान | Completed | 26658 | 4641 | 2009-07-10 | 2013-11-15
RON | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/175 — मेडबंधान | Completed | 22993 | 3640 | 2009-07-10 | 2013-11-16
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005019/LD/22012034226398 — medbandhan kashiram/vrindawan nandna | Completed | 50100 | 48336 | 2015-06-24 | 2017-10-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005019/LD/22012034251022 — MEDBANDHAN JAY SINGH /PAN SINGH | Completed | 3200000000 | 23282 | 2016-01-20 | 2017-10-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005019/LD/22012034251120 — medbandhan maharaj singh/tulae | Deleted | 3680000000 | 0 | 2015-10-02
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262398 — medbandhan | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262400 — medbandhan | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262402 — medbandhan ramprakash/mangal | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262407 — medbandhan sattole/pancham | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262408 — medbandhan ramesh /khyali | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262409 — medbandhan rajabeti/laltaprasad | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262410 — medbandhan munnalal/phundilal | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262411 — medbandhan ramnarayan/manpal | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262412 — medbandhan laltaprasad/tejpal | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262413 — medbandhan murti devi /gajraj | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262414 — medbandhan mevaram /lalaram | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262416 — medbandhan parmhansh /kehari | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262418 — medbandhan prahlad singh /seetaram | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262420 — medbandhan shrikrashan/rajpal | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262421 — medbandhan shyam singh /rajpal | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262424 — medbandhan marjad singh /parshuram | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262425 — medbandhan gya singh /gandharv singh | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262837 — medbhandhan ran singh/munshi | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262852 — medbandhan munnesh/jhundan | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262853 — medbandhanphul singh/sukhu | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262854 — medbandhan baburam/lalaram | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262858 — medbandhanradheshyam/lalaram | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262862 — medbandhandakuri prasad/lalaram | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262865 — medbandhan munnalal/mangal | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262866 — medbandhan bhero/maniram | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262867 — medbandhan ganesh/jhundan | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262868 — medbandhan ramdah/khyali | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262869 — medbandhan sattole/pancham | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262872 — medbandhan ramesh/ranveer | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262874 — medbandhan ravendra/ranveer | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262875 — medbandhan brajraj/gulab singh | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262876 — medbandhan indar singh/gulab singh | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262878 — medbandhan ramnaresh/phul singh | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262880 — medbandhan abhilakh/phul singh | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262881 — medbandhan ramesh/uday singh | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262882 — medbandhan ramotar/trilok singh | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262883 — medbandhan bannam/pan singh | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262889 — medbandhan gajendra singh/bhagvan singh | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262890 — medbandhan janved/jagganath | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262893 — medbandhan veerendra/malkhan | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262900 — medbandhan rajesh/praval singh | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262902 — medbandhan sunil/bhagvan singh | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262904 — medbandhan indrajeet/makhan singh | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262906 — medbandhan beta/kedar | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034262907 — medbandhan kok singh/jwala | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034263236 — medbandhan keshav singh/amar singh | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034263237 — medbandhan prem singh/ramnath | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034263238 — medbandhan surjan/duwarika | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034263239 — medbandhan ramdayal/hanumant | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034263240 — medbandhan balram/tunde | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034263241 — medbandhan udhaybhan/vijay singh | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034263242 — medbandhan girvar/hom singh | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034263243 — medbandhan jugraj/surat singh | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034263244 — medbandhan ramdash/tikaram | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034263245 — medbandhan ramrup/tikaram | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034263248 — medbandhan rambabu/bhavani | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034263249 — medbandhan shimbhu/gundhari | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034263250 — medbandhan raguveer/matae | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034263251 — medbandhan charan singh/vidhyaram | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034263252 — medbandhan tej singh/bindole | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034263253 — medbandhan raghuraj/la | Deleted | 0 | 0 | 2016-01-26
RON | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/22012034291512 — Medbandhan rambabu/bhawani nandna | Deleted | 0 | 0 | 2016-04-01
RON | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702005019/LD/22012034291513 — Medbandhan rambabu /bhawani nandna | Completed | 42100 | 21376 | 2016-08-13 | 2017-10-26
RON | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702005019/LD/22012034296232 — SHANTIDHAM NIRMAN NANDNA | Completed | 180000 | 168614 | 2017-01-01 | 2020-08-21
RON | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/3799402561 — medbandhan Lakhan singh/Bheekam singh | Completed | 19500 | 8760 | 2013-09-04 | 2014-09-09
RON | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/3799404132 — medbandhan amar singh raghunath nandna | Completed | 10900 | 7536 | 2014-05-21 | 2014-05-26
RON | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/3799404151 — menbandhan kaptan singh/hari Singh nandna | Completed | 24500 | 22192 | 2013-09-18 | 2014-07-07
RON | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/3799410309 — medbandhan jabar singh/gyadeen nandna | Completed | 50600 | 48199 | 2013-10-23 | 2014-06-23
RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/395 — मेड्बंधान धर्माबाई/छक्‍कीलाल नदना | Completed | 28688 | 21000 | 2010-07-12 | 2010-08-24
RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/408 — मेड्बंधान श्रीराम/करंजू नदना | Completed | 26611 | 17000 | 2010-07-12 | 2010-07-24
RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/409 — मेड्बंधान गोमती/झुण्‍डन नदंना | Completed | 25227 | 25000 | 2010-08-12 | 2010-08-24
RON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/499 — मेड्बंधान हरगोविन्‍द /नरायन नदना | Completed | 30699 | 30012 | 2011-07-07 | 2011-08-21
RON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/500 — मेड्बंधान केदारनाथ/छोटेलाल नदना | Completed | 25738 | 3660 | 2011-07-13 | 2015-04-15
RON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/501 — मेड्बंधान राजाराम/सुमेर नदना | Completed | 50498 | 48312 | 2011-07-14 | 2011-09-27
RON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/736 — मेड्बंधान मटरूलाल/मनीराम नदना | Completed | 38129 | 24888 | 2011-09-24 | 2011-11-18
RON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/737 — मेड्बंधान हरसेवक/नारायण नदना | Completed | 33662 | 14640 | 2011-09-14 | 2015-04-15
RON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/738 — मेड्बंधान लक्ष्‍मीनारायण/करंजू नदना | Completed | 33662 | 28506 | 2011-09-13 | 2015-04-15
RON | 2014-2015 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702005019/LD/9926711698 — KHEL MAIDAN NIRMAN NANDNA | Completed | 368800 | 139879 | 2014-07-02 | 2017-10-26
RON | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/9926712596 — MEDBANDHAN RAJA SINGH HEERA SINGH | Completed | 27700 | 25434 | 2014-07-09 | 2014-07-21
RON | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005019/LD/9926712602 — medbandhan jagdeesh / baijnath | Completed | 24300 | 21352 | 2014-07-09 | 2014-07-21
RON | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/102 — सीसी रोड पंचपरमेशवर करोडे के घर से नाथूराम के दरवाजे तक नदना | Completed | 72034 | 77236 | 2012-09-05 | 2013-02-26
RON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034189954 — panchparmeshwar converjan cc road ramroop rajawat | Completed | 149800 | 116439 | 2014-02-12 | 2014-07-11
RON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034189958 — vidhayak converjan cc road purva se nirmit road se | Completed | 58600 | 55840 | 2014-02-05 | 2014-04-24
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034291253 — cc road panchparmeswar kishor singh ke darwaje se raju ke ghar ki or nandna | Completed | 80600 | 79500 | 2015-12-23 | 2017-10-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034305622 — cc road | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034305624 — cc road | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034305640 — cc road | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034305642 — cc road | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034305644 — cc road | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034305645 — cc road | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034305646 — cc road | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034305647 — cc road | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034305649 — cc road | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034305650 — cc road | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702005019/RC/22012034310447 — kachcha pahuch marg | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702005019/RC/22012034310448 — kachcha pahuch marg | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702005019/RC/22012034310449 — kachcha pahuch marg | Deleted | 0 | 0 | 2016-01-26
RON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034328325 — cc road panchparmeswar mukhya marg se kashiram harijan ke ghar tak nandna | Completed | 70800 | 70176 | 2017-03-01 | 2017-09-20
RON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034349516 — CC ROAD MUKHYA MARG SE MAHARAJ SINGH KE GHAR KI OR | Completed | 33000 | 24768 | 2017-09-10 | 2020-07-14
RON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034349522 — cc road mukyamarg se jaypal ke ghar tak | Completed | 26500 | 25800 | 2017-10-26 | 2019-07-03
RON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034349525 — cc road ramesh ke ghar se sureshbagel ki ghar ki or nandna | Completed | 26550 | 20640 | 2017-10-26 | 2019-07-03
RON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034366033 — CC ROAD MUNNESH KE GHAR SE RAMBAHADUR KE GHAR TAK KORI MOHALLA NANDNA | Completed | 26500 | 24012 | 2017-11-01 | 2019-07-03
RON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034373021 — CC raod | Closed | 0 | 0 | 2017-10-02
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034385899 — cc road parvat harijan ke goda se munnilal ke ghar tak nandna | Completed | 27900 | 20706 | 2018-07-13 | 2020-07-14
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034385900 — cc road prem singh hairjan ke ghar se jagram harijan ke ghar tak nandna | Completed | 27900 | 26100 | 2018-07-13 | 2020-07-14
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034385901 — cc road vinod ke goda se ram singh ke ghar tak nandna | Completed | 53475 | 54984 | 2018-10-09 | 2020-07-14
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034393969 — PANCH PARMESWHAR CC ROAD PRADIP KE GHAR SE ASHOK KE GHAR KI ORE | Completed | 49725 | 46416 | 2018-10-02 | 2020-07-14
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034393970 — PANCH PARMESHWAR CC ROAD ARVIND KE GHAR SE MEWARAM KE GHAR KI ORE | Completed | 17408 | 15660 | 2018-10-02 | 2020-07-14
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034395805 — पंच परमेश्वर सीसी रोड मुख्य मार्ग से राम बिहारी के घर की ओर | Completed | 32550 | 34400 | 2018-10-02 | 2020-08-21
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034395823 — पंच परमेश्वर सीसी रोड चरण सिंह के घर से रंजीत के घर की ओर | Completed | 23250 | 22116 | 2018-10-02 | 2020-07-14
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034395825 — पंच परमेश्वर सीसी रोड लालता के घर से नेहाने के घर तक | Completed | 23250 | 21924 | 2018-10-02 | 2020-07-14
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034436561 — PANCH PARMESHWAR CC ROAD MAY NALI NIRMAN SHANKAR JI KE MANDIR SE KIRAT SINGH KE GHAR TAK | Completed | 46500 | 47496 | 2019-03-07 | 2020-07-14
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034442315 — cc road | Closed | 0 | 0 | 2019-01-26
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034449027 — पंच परमेश्वर सी सी रोड नाली निर्माण कल्लू भदौरिया के घर से किशोर सिंह के घर ओर | Completed | 39525 | 36936 | 2019-03-07 | 2020-07-14
RON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034476770 — cc road | Closed | 0 | 0 | 2019-04-14
RON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034507828 — cc road ganesh kori ke ghar se dev singh ke ghar ki or | Completed | 71100 | 70128 | 2019-12-05 | 2021-05-11
RON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034507830 — cc road beta singh ke ghar se shyam singh ke ghar ki or | Completed | 6885 | 5616 | 2019-12-05 | 2020-07-14
RON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034510617 — cc road ramnarayan ke dwar se ramlakhan baghel ke ghar ki or | Completed | 51150 | 45600 | 2020-04-23 | 2021-06-15
RON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034520037 — Cc road Ramvihari ke makan se kadere ki khandiya ki or | Completed | 40950 | 36480 | 2020-09-03 | 2022-11-13
RON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034520038 — cc road shreekishan tomar ke ghar se men road ki or | Closed | 16575 | 0 | 2020-01-26
RON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034537179 — cc road matamandir darwaje se rashankar shrivas ke ghar ki or nadana | Completed | 67200 | 63840 | 2020-09-10 | 2022-11-13
RON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034537180 — cc road ramshankar ke ghar ke samne se govind ki ghar ki or nadana | Completed | 44900 | 44722 | 2020-09-10 | 2022-11-13
RON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005019/RC/22012034576915 — cc road men road se mata ki or nadana | Ongoing | 69000 | 28848 | 2022-03-03
RON | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702005019/RC/55 — पहुचमार्ग बंसतपुरा नहर पुलिया से जसावली रोड तक नदना | Completed | 421342 | 8000 | 2010-07-26 | 2011-07-31
RON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Community / Construction of Berkeley Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702005019/RS/22012034492930 — sarvjanik shochalya jasawali mandir ke pass nadana | Completed | 100000 | 47880 | 2020-12-10 | 2022-11-13
RON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1702005019/RS/22012034494626 — nali nirman upsuasth kendre se kadere ki kandiya ki or nadana | Completed | 28350 | 28590 | 2020-12-18 | 2021-05-11
RON | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1702005019/RS/22012034684525 — sarigation set nadana | Completed | 50040 | 33813 | 2023-07-11 | 2025-05-19
RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702005019/WC/22012034384007 — NAVEEN TALAB NIRMAN | Closed | 0 | 0 | 2017-10-02
RON | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702005019/WC/22012034438978 — तालाब जीर्णोद्धार भुजरिया तालाब | Completed | 150227 | 107308 | 2019-07-05 | 2022-11-13
RON | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702005019/WC/22012034438979 — परकुलेशन टैंक सत्तोले के खेत के पास सरकारी जगह पर | Completed | 126072 | 67296 | 2019-03-07 | 2021-09-14
RON | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702005019/WC/22012034438981 — परकुलेशन टैंक सुनील सिंह के खेत के पास सरकारी जगह पर | Closed | 124112 | 0 | 2019-07-05
RON | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702005019/WC/22012034490847 — khet talab | Closed | 0 | 0 | 2019-04-14
RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702005019/WC/22012034790669 — talab nirman Bhujariyai talab nadna | Closed | 0 | 0 | 2021-04-14
RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702005019/WC/22012034790672 — Naveen talab sudam kori ke khet ke pass nadna | Closed | 0 | 0 | 2021-04-14
RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702005019/WC/22012034790674 — check dem kachcha shantidham ke pass nadna | Closed | 0 | 0 | 2021-04-14
RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702005019/WC/22012034790675 — check dem kachcha shantidham ke pass nadna | Closed | 0 | 0 | 2021-04-14
RON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1702005019/WC/22012035034447 — Amratsarowar dagpond nirman nandna | Closed | 1462870.71 | 0 | 2022-10-02
RON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702005019/WC/22012035045458 — Check dem Nirman dharm singh ki tor ke pass nandna | Ongoing | 1484300.26 | 1142982.59 | 2023-04-11
RON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702005019/WC/22012035182691 — Dag Pond Nirman Nandna | Closed | 1008624.99 | 0 | 2024-01-27
RON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1702005019/WC/22012035195033 — Kachcha Nala Nirman Pakke Danda Se Lakhan Singh Ki Tor Ki Or Nandna | Closed | 0 | 0 | 2024-01-27
RON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702005019/WC/22012035302028 — Krishan singh ke Darwaje ke samne nadna | Approved | 0 | 0 | 2025-04-14
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Model Talab / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702005019/WH/19955472 — TALAB GAHARIKARAN BHUJARIYA TAL | Deleted | 0 | 0 | 2016-01-26
RON | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702005019/WH/19959152 — talab bandh sudrikaran nandna | Completed | 85000 | 45064 | 2017-05-13 | 2018-01-20
RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702005019/WH/22012034456951 — Talab Jidyodhar ranveer singh ke ghar ke pass nandna | Closed | 0 | 0 | 2021-10-02
RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702005019/WH/22012034456953 — Talab Jidyodhar Harijan mohhalla ke pass nandna | Closed | 0 | 0 | 2021-10-02
RON | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702005/DP/22012034627234 — Samudhayak Vraksharopan karya jasawali mandir nadna | Approved | 453563.17 | 0 | 2024-06-08