## Work List
Exported on: 2026-09-11 14:02:25
Filters applied:
Data source: MGNREGA
District: BHIND
Block: All
Panchayat: BONAPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1702005024/AV/22012034516068 — gaushala nirman bonapura | Ongoing | 4119948.02 | 3908949.99 | 2020-08-24
RON | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702005024/AV/22012034544683 — boundary wall primary and midle school bonapura | Completed | 405900 | 124593 | 2021-02-26 | 2024-10-25
RON | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702005024/AV/22012034550657 — Boundary Ball Nirman- Samudayak Bhawan , Bonapura | Closed | 54375 | 0 | 2021-01-24
RON | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702005024/AV/22012034563412 — Boundary Ball Nirman- Govt. Middle Shala Evam Govt. Primary Shala bhawan, Bonapura | Closed | 53700 | 0 | 2021-01-26
RON | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702005024/AV/22012034563658 — shantidham | Closed | 0 | 0 | 2021-03-18
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702005024/AV/22012034620302 — Maa KI Bagiya Govt. PrimaryMiddle School, Bonapura | Closed | 5600 | 0 | 2022-04-14
RON | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702005024/AV/22012034659178 — shaanthidham nirman dimoleki madaiya | New | 0 | 0 | 2024-06-08
RON | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702005024/AV/22012034662561 — shantidhan dimole ki madaiya | New | 0 | 0 | 2024-11-15
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Building for Gram Panchayats / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702005024/AV/5187 — AGANWADI BHAWAN | Closed | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Building for Gram Panchayats / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702005024/AV/5188 — AGANWADI BHAWAN | Closed | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Building for Gram Panchayats / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702005024/AV/5189 — AGANWADI BHAWAN | Closed | 0 | 0 | 2016-01-26
RON | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702005024/DP/2 — व़क्षारोपण,सड्क के किनारे,बोनापुरा | Completed | 16000 | 8500 | 2008-09-15 | 2014-01-12
RON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1702005024/DP/22012034601382 — Meri mati Mera desh basudha vandhan Amrit vatika Bonapura | Ongoing | 54564.94 | 13260 | 2023-09-18
RON | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation-Horticulture-Community / Along the coast Block Plantation of Horticulture Trees for Community | Plantation | 1702005024/DP/22012034627795 — Samudhayak Vraksharopan high and middle school parishar bonapura | Approved | 0 | 0 | 2024-06-08
RON | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702005024/FP/22012034367381 — nala nirman dimole ki madaiya se behad ki or bonapura | Closed | 261008.96 | 0 | 2020-08-15
RON | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702005024/FP/22012034369366 — RCC Nala Nirman Puliya Se Prabhu Dayal Ke Ghar Ke Aage Ki Or, Bonapura | Closed | 67350 | 0 | 2021-02-12
RON | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702005024/IF/22012034303927 — nadep taka kashiram/kartali bonapura | Completed | 12000 | 10827 | 2017-01-09 | 2019-07-03
RON | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702005024/IF/22012034303928 — nadep taka mahesh/tejpal bonapura | Completed | 12000 | 11163 | 2017-01-23 | 2019-07-03
RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702005024/IF/22012034349128 — vriksharopan gov. ps,ms school dhimolemadaya | Completed | 335000 | 7816 | 2017-06-15 | 2021-05-20
RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702005024/IF/22012034350174 — vriksharopan hanuman mandir sadak ke kinare bonapura | Completed | 335000 | 5752 | 2017-06-15 | 2021-05-20
RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702005024/IF/22012034353698 — vriksharopan Bonapura se bagiya pura rod par | Deleted | 335000 | 0 | 2017-09-18
RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702005024/IF/22012034354380 — vriksharopan road side madhaiya se lallupura | Closed | 0 | 0 | 2017-05-01
RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702005024/IF/22012034367650 — vriksharopan road side madai se lallu pura | Completed | 335000 | 7128 | 2017-07-28 | 2021-05-20
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005024/IF/22012034584838 — medbandhan rajkumar/kisunvihari | Closed | 0 | 0 | 2020-04-14
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005024/IF/22012034584863 — medbandhan ramveer/gulab singh bonapura | Completed | 42351.66 | 41040 | 2020-12-08 | 2022-10-28
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005024/IF/22012034615171 — medbandhan mahendra singh/param singh bonpura | Closed | 0 | 0 | 2020-08-15
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616030 — Pashu Shed Nirman-Kumbar Singh/Sobran Singh, Bonapura | Ongoing | 101804.91 | 90833.5 | 2021-05-22
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616032 — Pashu Shed Nirman-Sunil Kumar/Ram Kishun, Bona Pura | Ongoing | 101804.91 | 88517.5 | 2021-05-22
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616034 — Pashu Shed Nirman-Sudha/ Dinesh Singh, Bonapura | Ongoing | 101804.91 | 93149.5 | 2021-05-22
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616035 — Pashu Shed Nirman-Ram Karan/Munnalal,Bonapura | Closed | 101804.91 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616037 — Pashu Shed Nirman-Jitendra/ Dinesh Singh | Closed | 101804.91 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616039 — Pashushed Nirman-Amit/ Rakesh, Bonapura | Closed | 101804.91 | 0 | 2020-08-15
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616040 — Pashu Shed Nirman-Brijmohan/Surendra Kumar | Ongoing | 101804.91 | 93149.5 | 2021-05-22
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616041 — Pashushed Nirman-Ram Prakash/Tijole, Bonapura | Ongoing | 101804.91 | 93149.5 | 2021-05-22
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616042 — Pashu Shed Nirman-Chandraveer/Mulu,Bonapura | Completed | 101804.91 | 97036.4 | 2021-03-01 | 2025-05-19
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616043 — Pashu Shed Nirman-Pramod/Jagdish, Bonapura | Ongoing | 101804.91 | 93149.5 | 2021-04-08
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616044 — Pashu Shed Nirman-Narendra/Nirupat, Bonapura | Closed | 101804.91 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616045 — Pashu Shed Nirman-Jayveer/Malkhan, Bonapura | Closed | 101804.91 | 0 | 2020-08-15
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616047 — Pashu Shed Nirman-Anil Kumar/Bhagirath, Bonapura | Ongoing | 101804.91 | 93149.5 | 2021-05-22
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616048 — Pashu Shed Nirman-Mukesh/Ramsobran, Bonapura | Closed | 101804.91 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616049 — Pashu Shed Nirman-Amrudan/Aasin Khan, Bonapura | Closed | 101804.91 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616050 — Pashu Shed Nirman-Fareed/Usmaan, Bonapura | Closed | 101804.91 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616172 — Pashu Shed Nirman-Amit Kumar/Hari shankar | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616174 — Pashu Shed Nirman-Anil Kumar/Ram Narayan, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616176 — Pashu Shed Nirman-Sudama/Radhelal, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616178 — Pashu Shed Nirman-Geeta/Ramotar, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616179 — Pashu Shed Nirman-Mukesh/Sobran, Bonapua | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616181 — Pashu Shed Nirman-Parvati/Gupal, bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616183 — Pashu Shed Nirman-Rajesh/Darwari, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616184 — Pashu Shed Nirman-Saroj/Rajesh, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616186 — Pashu Shed Nirman-Rajeev/Siyasharan, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616187 — Pashu Shed Nirman- Dileep/RAghuraj, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616188 — PAshu Shed Nirman-Rajendra/Shyam Bahadur, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616190 — Pashu Shed Nirman-Pooja Devi/Gjendra, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616231 — Pashu Shed Nirman-Shivkumar/Mehrvan, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616233 — Pashu Shed Nirman-Mahendra Singh/Param Singh, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616234 — Pashu Shed Nirman-Ram Saran /Subedar, Bona Pura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616235 — Pashu Shed Nirman-Chandrasekhar/atar Singh, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616238 — Pashu Shed Nirman-Narendra/Baburam, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616239 — Pashu Shed Nirman-Ramveer/ Baburam, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616241 — Pashu Shed Nirman-Ram Sebak / Baburam, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616242 — Pashu Shed Nirman-Pankaj/Ramveer, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616244 — Pashu Shed Nirman-Pintu/ Subedar, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616245 — Pashu Shed Nirman-Prem Prakash/Ayodhyaprasad, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616246 — Pashu Shed Nirman-Shashikant/Baburam, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616247 — Pashu shed Nirman-Bacchu Singh/Hakim Singh, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616248 — Pashu Shed Nirman-Babu Singh/Subedar, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616249 — Pashu Shed Nirman- Raj kumar/Krishna bihari, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616573 — Pashu Shed Nirman-Ran Ji/Santosh,Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616574 — Pashu Shed Nirman-Brijraj/Govind Singh,Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616575 — Pashu Shed Nirman-Ganga Prasad/Krishna Gopal, Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/22012034616576 — Pashu Shed Nirman-Virendra/Lalaram,Bonapura | Closed | 0 | 0 | 2020-08-15
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005024/IF/22012034768367 — khet talab rambeer singh/gulab singh | Closed | 337715.44 | 0 | 2021-07-06
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005024/IF/22012034768374 — khet talab satendra singh/deshraj singh | Completed | 337715.44 | 289500 | 2021-06-24 | 2022-10-28
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005024/IF/22012034768392 — medbandhan rakesh/ramnaresh | Closed | 39499.98 | 0 | 2021-04-14
RON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005024/IF/22012034971662 — khet talab Baburam/manphoole bonapura | Closed | 356340.1 | 0 | 2022-04-14
RON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005024/IF/22012035026281 — khet talab ramvaran singh/angad singh | Deleted | 0 | 0 | 2022-08-15
RON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702005024/IF/22012035375965 — Khet Talab Nirman Amar/setu | Approved | 147621.16 | 0 | 2025-04-20
RON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702005024/IF/22012035385966 — Khet Talab Nirman Amar/setu | New | 0 | 0 | 2025-04-22
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005024/IF/22012035531276 — Khet Talab Nirman Amar/setu | Approved | 0 | 0 | 2025-05-18
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005024/IF/22012035534756 — Khet Talab Nirman amar setu Dharmendra Narwariya | New | 0 | 0 | 2025-05-19
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005024/IF/22012035535612 — Khet Talab Nirman amar setu Ramvaran Singh | Approved | 147621.16 | 0 | 2025-05-20
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005024/IF/22012035535679 — Khet Talab Nirman amar setu Brajendra Singh | Approved | 0 | 0 | 2025-05-20
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005024/IF/22012035536511 — khet Talab Nirman amar setu Lakshman | Closed | 147621.16 | 0 | 2025-06-30
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005024/IF/22012035538455 — Khet Talab Nirman amar setu Rajendra | Closed | 147621.16 | 0 | 2025-06-30
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702005024/IF/22012035655307 — ek bagiya ma ke naam renu sarma/maithali sarama | Approved | 0 | 0 | 2025-04-14
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702005024/IF/22012035655533 — Ek bagiya maa ke naam ramasumirani/Vinod kumar | Approved | 266578.64 | 0 | 2025-12-27
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702005024/IF/22012035655536 — Ek Bagiya Maa ke naam Usha devi w/o dinesh | Approved | 266578.64 | 0 | 2025-12-27
RON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/9993728806 — PASHU SED JAGDESH/MATAI | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/9993728807 — PASHU SED JAGRAM/SAHTU | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/9993728808 — PASHU SED DINESH/UDYABEER | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/9993728810 — PASHU SED CHHOTELAL/PARMOLE | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/9993728811 — PASHU SED RMPRAKASH/TIJOLE | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/9993728812 — PASHU SED DINESH/KASEEPRASAD | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005024/IF/9993728818 — PASHU SED MANSIGH/MULU | Deleted | 0 | 0 | 2016-01-26
RON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/121527 — Construction of IAY House -IAY REG. NO. MP-02-005-024-001/69 | Completed | 14310 | 14195 | 2016-07-29 | 2018-04-05
RON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/133781 — Construction of IAY House -IAY REG. NO. MP-02-005-024-001/54 | Completed | 14310 | 14863 | 2016-07-29 | 2017-12-07
RON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/3672440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106941199 | Completed | 18360 | 10608 | 2023-08-28 | 2024-03-14
RON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/3908157 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150056999 | Completed | 18360 | 13260 | 2023-08-28 | 2024-03-14
RON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/3908159 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150057532 | Completed | 18360 | 7548 | 2022-07-11 | 2024-03-14
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/4518748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106758990 | Ongoing | 23490 | 21276 | 2025-01-28
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/4518749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106759052 | Ongoing | 23490 | 21276 | 2025-01-28
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/4765308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115398719 | Ongoing | 23490 | 21645 | 2025-01-27
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5246033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147670690 | Ongoing | 23490 | 10179 | 2025-09-12
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5247027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106758798 | Ongoing | 23490 | 14877 | 2025-09-23
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5253504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150057167 | Ongoing | 23490 | 6525 | 2025-09-29
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5254034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151253263 | Ongoing | 23490 | 1827 | 2025-12-18
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5257971 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125840829 | Ongoing | 23490 | 8874 | 2026-05-23
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5258103 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106941093 | Ongoing | 23490 | 0 | 2026-01-04
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5273263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115397996 | Ongoing | 23490 | 6786 | 2025-09-12
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5277377 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150056875 | Ongoing | 23490 | 0 | 2026-05-28
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5290869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115398165 | Ongoing | 23490 | 23229 | 2025-09-12
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5294969 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150056612 | Approved | 23490 | 0 | 2025-03-16
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5305350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148609485 | Ongoing | 23490 | 19575 | 2025-09-12
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5308185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106758674 | Ongoing | 23490 | 8091 | 2025-12-18
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5312875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125873017 | Ongoing | 23490 | 10962 | 2025-11-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5319318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147670879 | Ongoing | 23490 | 13311 | 2026-01-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5319400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115398298 | Ongoing | 23490 | 8874 | 2025-11-02
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5330153 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125832661 | Ongoing | 23490 | 3132 | 2026-06-14
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5338111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150056746 | Ongoing | 23490 | 12528 | 2025-11-24
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5570157 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148199845 | Approved | 23490 | 0 | 2025-03-16
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5570196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147670548 | Ongoing | 23490 | 13311 | 2025-09-12
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5570197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147670976 | Ongoing | 23490 | 18792 | 2025-11-02
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5570797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149240810 | Ongoing | 23490 | 3654 | 2025-12-18
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5571207 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125852102 | Approved | 23490 | 0 | 2025-04-09
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5571448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106941141 | Ongoing | 23490 | 4698 | 2026-05-23
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5571666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146628526 | Ongoing | 23490 | 12006 | 2025-09-12
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5572000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125831099 | Ongoing | 23490 | 0 | 2026-05-28
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5572216 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106758537 | Ongoing | 23490 | 18792 | 2025-09-12
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5573044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125835645 | Ongoing | 23490 | 9396 | 2025-12-18
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005024/IF/IAY/5707957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115398826 | Ongoing | 23490 | 11223 | 2025-11-02
RON | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005024/LD/1 — Medh Bandhan | Deleted | 0 | 0 | 2007-10-02
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005024/LD/22012034226491 — medbandhan mahesh/tejpal bonapura | Completed | 28000 | 25758 | 2015-06-19 | 2015-12-25
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005024/LD/22012034248641 — medbandhan baliram /raghunandan bonapura | Completed | 28700 | 24804 | 2016-01-08 | 2016-04-12
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005024/LD/22012034248647 — medbandhan hargovind /jalim bonapura | Deleted | 0 | 0 | 2015-04-14
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005024/LD/22012034248648 — medbandhan hargovind / jalim bonapura | Completed | 30000 | 26261 | 2016-01-08 | 2017-10-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005024/LD/22012034262041 — medbandhan jagdeesh/matai | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005024/LD/22012034262578 — MEDBANDHAN BABURAM/MANPHOOLE | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005024/LD/22012034262579 — MADBANDHAN MUNNALAL/GORELAL | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005024/LD/22012034262580 — MEDBANDHAN SONELAL/DEVIDEEN | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005024/LD/22012034262581 — MEDBANDHAN RAVINDRA/MATROO | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005024/LD/22012034262582 — MEDBANDHAN SUNIL/MAHRABAN | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005024/LD/22012034262667 — MEDBANDHAN MUNNILAL /MULU KADERE | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005024/LD/22012034262689 — MEDBANDHAN NARENDRA/MEHARBAN | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005024/LD/22012034263019 — MEDBANDHAN RAGHURAJ/MEHARBAN | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005024/LD/22012034263021 — MEDBHANDAN BARELAL/KALKU | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005024/LD/22012034263022 — MEDBANDHAN MANSINGH/MULU | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005024/LD/22012034263023 — MEDBANDHAN RAMESHWAR/CHHOTELAL | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005024/LD/22012034263024 — MEDBANDHAN NATHURAM/MOHANLAL | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005024/LD/22012034263025 — MEDBANDHAN BHOORE/MULU | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005024/LD/22012034263028 — MEDBANDHAN RAMSHANKAR/ANGAD SINGH | Deleted | 0 | 0 | 2016-01-26
RON | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702005024/LD/22012034299300 — shanti dham nirman bonapura | Completed | 245000 | 244859 | 2017-02-06 | 2018-07-05
RON | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702005024/LD/22012034316579 — shantidham nirman dhimole ki madaiya bonapura | Completed | 180000 | 29544 | 2017-08-14 | 2024-07-16
RON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702005024/LD/22012034529968 — guashala charagah part-2 Bonapura | Ongoing | 792213.45 | 508440 | 2020-12-19
RON | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005024/LD/3799394764 — मेडबंधान तेजपाल/हीरालाल बोनापुरा | Completed | 38000 | 17520 | 2013-06-14 | 2014-11-10
RON | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005024/LD/3799404065 — medbandhan gajendra/mohanlal bonapura | Completed | 50000 | 23506 | 2013-09-13 | 2014-11-10
RON | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005024/LD/3799409731 — medbandhan tularam/damroo bonapura | Completed | 26000 | 7300 | 2013-10-31 | 2014-11-10
RON | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005024/LD/3799409739 — mdbandhan pyarelal/bholaram bonapura | Deleted | 32000 | 0 | 2013-04-14
RON | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005024/LD/3799409755 — MEDBANDHAN HARKISHUN/BHAJAN BONAPURA | Deleted | 31000 | 0 | 2013-04-01
RON | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005024/LD/3799409756 — DEVLAL/BHAGVAN BONAPURA | Deleted | 35800 | 0 | 2013-04-01
RON | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005024/LD/38 — मेढ्बंधान गुबरेनाई के खेत पर,बोनापुरा | Completed | 24000 | 850 | 2008-10-30 | 2010-08-14
RON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005024/LD/485 — मेड्बंधान मटरू/धनीराम बोनापुरा | Completed | 32100 | 27312 | 2011-06-14 | 2013-03-14
RON | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005024/LD/97 — मेड बंधान निर्माण ब्रजेन्‍द्र /देवसिहं | Completed | 16000 | 15014 | 2009-08-03 | 2009-08-24
RON | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702005024/LD/9926714231 — shantidham nirman bonapura | Deleted | 0 | 0 | 2014-04-01
RON | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702005024/PG/22012034336323 — khel maidan dhimole ki madaia | Completed | 129000 | 73524 | 2017-08-10 | 2020-05-20
RON | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702005024/RC/20 — पहुच मार्ग निर्माण | Completed | 392000 | 373450 | 2009-09-01 | 2014-03-12
RON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034181060 — cc road panchparmeswa r dinesh singh ke ghar se ra | Completed | 85400 | 75912 | 2013-10-18 | 2014-03-20
RON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034186696 — PANCH PARMESHWAR C.C. ROAD DINESH KE DARWAJE SE RA | Completed | 76900 | 72987 | 2014-01-03 | 2014-10-10
RON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034212245 — cc road panchparmeswar gov pri school se pyarelal | Completed | 114200 | 108724 | 2014-03-07 | 2014-08-10
RON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702005024/RC/22012034212251 — kachca pahuch marg udayveer singh ke ghar se raipu | Deleted | 1490900 | 0 | 2014-03-07
RON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034223633 — cc road panchparmeswar mahaveer ke ghar se sanjeev | Completed | 46400 | 45024 | 2014-07-04 | 2014-08-05
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034282676 — CCROAD SIYASHARAN KE GHAR SE RAMNARESH KE GHAR KI OR | Completed | 59900 | 57103 | 2015-12-04 | 2017-10-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034291243 — cc road panchparmeswar bala baghel ke ghar se shivram baghel tak bonapura | Completed | 29600 | 23797 | 2015-12-04 | 2017-10-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034291246 — cc road panchparmeswar chhote lal ke ghar se ravindra ke ghar ki or bonapura | Completed | 81000 | 78387 | 2015-12-04 | 2017-10-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702005024/RC/22012034299003 — sudur sampark bonapura se bagiyapura ki or bonapura | Completed | 1197600 | 106041 | 2016-02-19 | 2017-11-13
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034309277 — CCROAD OMPRAKASH KE GHAR SE VIJAYSINGH KE GHAR KI OR | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034309283 — CCROAD | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034309285 — CCROAD | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034309287 — CCROAR | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034309288 — CCROAR | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034309289 — CCROAR | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034309294 — CCROAR | Deleted | 0 | 0 | 2016-01-26
RON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034330917 — cc road panchparmeswar shripal ke ghar se satendra ghar se omprakash ke ghar tak bonapura | Completed | 133400 | 80082 | 2017-03-21 | 2019-06-10
RON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034349446 — cc road harsevak ke ghar se ravindra ki ghar ki or bonapura | Completed | 21240 | 19608 | 2017-08-22 | 2019-06-10
RON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034349456 — cc road sudhama ke ghar se mataprasad ke ghar se hotehuye middalschool ki or dimole ki madaiya | Completed | 22500 | 33024 | 2017-08-22 | 2019-06-10
RON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034349616 — cc road chhinge ke ghar se baylal ke ghar ki or dimole ki madaiya | Completed | 44250 | 44100 | 2017-11-06 | 2019-06-10
RON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034349912 — cc road avinash ke ghar se mansingh kighar ki or dimole ki madiya | Completed | 31000 | 30804 | 2017-08-28 | 2019-06-10
RON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034349920 — cc road panchyat bhavan se jasmant ke ghar ki or bonapura | Completed | 44250 | 44118 | 2017-11-06 | 2019-06-10
RON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034349928 — cc road mahesh ke ghar se pratap ke ghar ki or bonapura | Closed | 30975 | 0 | 2017-04-14
RON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034372993 — CC raod | Closed | 0 | 0 | 2017-10-02
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034392802 — PANCH PARMESHWAR CC ROAD SUNIL KE GHAR SE SHELU KE GHAR KI ORE | Completed | 29295 | 30264 | 2018-10-02 | 2021-05-11
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034392803 — PANCHA PARMESHWAR CC ROAD SABLU KE GHAR SE PINTU KE GHAR KI ORE | Completed | 18806 | 34714 | 2018-10-02 | 2021-05-11
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034392804 — PANCHA PARMESHWAR CC ROAD JASMANT KE GHAR SE KABBAL KHA KE GHAR KI ORE | Completed | 34875 | 51824 | 2018-10-02 | 2021-05-11
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034392805 — PANCHA PARMESHWAR CC ROAD PYARE LAL KE GHAR SE SARMAN KE GHAR KI ORE | Completed | 18000 | 8258 | 2018-10-02 | 2020-09-30
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034439063 — CC ROAD | Closed | 0 | 0 | 2019-01-26
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034447862 — पंच परमेश्वर सीसी रोड नाली निर्माण राजा के घर से आंगनवाड़ी भवन की ओर | Completed | 46500 | 42618 | 2019-03-05 | 2021-05-11
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034447866 — पंच परमेश्वर सी सी रोड हनुमान जी मंदिर से मेन सड़क की ओर | Completed | 214200 | 210414 | 2019-03-05 | 2021-04-30
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034447992 — Panch Parmeshwar CC Road Nali Nirman Patre Tomar Ke Ghar Se Mahesh Ke Ghar Ki Ore | Completed | 34875 | 2088 | 2019-03-05 | 2019-03-30
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034447998 — Panch Parmeshwar CC Road Nali Nirman Prabhu Ke Ghar Se Agyaram Ke Ghar Ki Ore | Completed | 34875 | 2088 | 2019-03-04 | 2019-03-30
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034448002 — Panch Parmeshwar CC Raod Nali Nirman Jhallu Ke Dwar Se D.P. Ki Ore | Completed | 27900 | 20040 | 2019-03-04 | 2020-05-30
RON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702005024/RC/22012034526059 — sudur sadak Gram bonapura se rathorankapura ki or | Ongoing | 1445350.13 | 1115733.16 | 2020-07-02
RON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034541288 — cc road shivkumar ke ghar se maan singh ke ghar ki or bonapura | Completed | 45750 | 46550 | 2020-09-29 | 2021-05-11
RON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034560159 — C.C.Raod Nirman Prathmik Evam Middle School Prangad Mai, Bonapura | Completed | 92850 | 50160 | 2021-03-01 | 2024-04-17
RON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034564412 — C.C.Road Nirman Nirupat Patel Ke Darwaje Se Middle School Ki or, Bonapura | Deleted | 0 | 0 | 2021-01-26
RON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034564413 — C.C.Road Nirman Nirupat Patel Ke Darwaje Se Middle School Ki or, Bonapura | Completed | 163800 | 144750 | 2021-05-15 | 2024-10-25
RON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034581494 — C.C.Road Nirman C.C.Road Se School Tak, Bonapura | Closed | 109200 | 0 | 2021-04-14
RON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702005024/RC/22012034599589 — Sudur sampark sadak Bonapura se gaushala satimata ki or | Closed | 0 | 0 | 2021-10-02
RON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702005024/RC/22012034599761 — सुदूर संपर्क सड़क बोनापुरा से गौशाला सतीमाता की ओर | Ongoing | 2460426.23 | 585819 | 2021-11-23
RON | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034652993 — cc road nirman shivram ke ghar se agyaram ke ghar ki or bonapura | Ongoing | 67950 | 11270 | 2023-10-10
RON | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/22012034666820 — C.C. Road Mai Nali Fatima Ke Darwaje Se Pawan Ke Ghar Hote Hue Shankar Ke Ghar Ki Or, Bonapura | Ongoing | 203400 | 4420 | 2024-01-04
RON | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005024/RC/80 — पंचपरमेशवर सीसी रोड धार की पुलिया से बलीराम के घर | Completed | 80038 | 78312 | 2012-07-17 | 2014-08-20
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702005024/RS/22012034667633 — Soak Pit Nirman Satimata Mandir Par, Bonapura | Closed | 2700 | 0 | 2022-09-10
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702005024/RS/22012034667638 — Soak Pit Nirman Hanuman Ji Mandir Ke Pass, Bonapura | Closed | 2700 | 0 | 2022-09-10
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702005024/RS/22012034667645 — Soak Pit Nirman Badi Mata Mandir Ke Pass, Bonapura | Closed | 2700 | 0 | 2022-09-10
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702005024/RS/22012034667650 — Soak Pit Nirman Punchayat Bhawan Ke Pass, Bonapura | Closed | 2700 | 0 | 2022-09-10
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702005024/RS/22012034667653 — Soak Pit Nirman Middle School Par, Dimole Ki Madaiya, Bonapura | Closed | 2700 | 0 | 2022-09-10
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702005024/RS/22012034667658 — Soak Pit Nirman Jhallu Khan Ke Darwaje Ke Pass, Bonapura | Closed | 2700 | 0 | 2022-09-10
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702005024/RS/22012034667661 — Nandep Nirman Karya Amolak/ Harju Dayal, Bonapura | Closed | 1800 | 0 | 2022-09-10
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702005024/RS/22012034667665 — Nandep Nirman Karya Jaswant/ HArju Dayal, Bonapura | Closed | 1800 | 0 | 2022-09-10
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702005024/RS/22012034667667 — Nandep Nirman Karya Ram Kumar/ Harju Dayal, Bonapura | Closed | 1800 | 0 | 2022-09-10
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702005024/RS/22012034667669 — Nandep Nirman Karya Rambaran Singh/Angad Singh, Bonapura | Closed | 1800 | 0 | 2022-09-10
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702005024/RS/22012034667672 — Nandep Nirman Karya Dinesh Singh/ Dev Singh. Bonapura | Closed | 1800 | 0 | 2022-09-10
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702005024/RS/22012034667674 — Nandep Nirman Karya Mahesh SIngh/ Jagdish , Bonapura | Closed | 1800 | 0 | 2022-09-10
RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702005024/WC/22012034383978 — NAVEEN TALAB NIRMAN | Closed | 0 | 0 | 2017-10-02
RON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone contour Bund for Community / Construction of Stone contour Bund for Community | Construction of Bund | 1702005024/WC/22012034548818 — Talab nirman hanuman mandir ke pass behad me dimolo ki madaiya | Completed | 1468440.1 | 781660 | 2020-10-06 | 2024-03-14
RON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1702005024/WC/22012034548822 — talab nirman hanuman mandir ke pass behad me dimoli ki madauya | Closed | 0 | 0 | 2020-04-14
RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702005024/WC/22012034643287 — naveen talab goushala ke pass bonapura | Completed | 1024354.34 | 643076 | 2021-08-30 | 2025-05-13
RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1702005024/WC/22012034757921 — Roof water harvesting Govt PS/MS Bonapura | Ongoing | 40942.72 | 11580 | 2021-06-23
RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702005024/WC/22012034836885 — check dem sati mata mandir ke pass bonapura | Physically Completed | 1497619.62 | 1390777 | 2021-11-17 | 2026-04-25
RON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702005024/WC/22012035004475 — Ardhan Dem No-1 behad Bonapura | Ongoing | 1401868.29 | 150722 | 2023-07-24
RON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702005024/WC/22012035004477 — Eardhan Dem No 2 Behad Bonapura | Closed | 1340257.2 | 0 | 2022-08-15
RON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702005024/WC/22012035004478 — Earchan Dem No 3 Behad Bonapura | Closed | 0 | 0 | 2022-08-15
RON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702005024/WC/22012035004480 — Earthan Dem No 4 Behad Bonapura | Closed | 0 | 0 | 2022-08-15
RON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702005024/WC/22012035004484 — Naveen talab Gaushala ke pass Bonapura | Closed | 0 | 0 | 2022-08-15
RON | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Biodrainage- Gov blding premises / Block Plantation of Biodrainage Trees in Government building premises for Community | Plantation | 1702005024/WC/22012035218365 — Samudhayak Vraksharopan high and middle school parishar bonapura | Approved | 224638.43 | 0 | 2024-06-08
RON | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702005024/WH/19959048 — talab bandh sudrikaran hanuman mandir ke pass bonapura | Completed | 82000 | 81528 | 2017-05-15 | 2018-01-20
RON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702005024/WH/22012034456331 — hanuman mandir ke pass talab jirondhar | Completed | 46682.92 | 28152 | 2022-05-27 | 2024-07-16
RON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702005024/WH/22012034456332 — Moryau talab bonapura jirondhar | Closed | 43561.06 | 0 | 2022-05-27
RON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702005024/WH/22012034456333 — pikhar talab jirondhar dimole ki madaiya | Closed | 40180.05 | 0 | 2022-05-27
RON | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702/RC/22012034153074 — Gram Sampark Sadak Yojna | Completed | 1624000 | 405134 | 2011-01-31 | 2014-06-12