## Work List
Exported on: 2026-09-10 18:45:26
Filters applied:
Data source: VBGRAMG
District: BHIND
Block: All
Panchayat: MACHAND
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
RON | 2025-2026 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & maint of intrmediate & Lnk Drain for Comm / Repair and maintenance of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1702005034/FP/22012034635599 — kachcha nala nirman dono said ramesh ke ghar se amrat sarovar tak itai | Ongoing | 462479.1 | 0 | 2025-07-15
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005034/IF/22012035539500 — khet talab nirman yadunath kushwah s/o lakshaman kushwah machhand | New | 0 | 0 | 2025-04-14
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005034/IF/22012035539614 — khet talab nirman yadunath kushwah s/o lakshaman kushwah machhand | Ongoing | 147621.16 | 0 | 2025-05-29
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005034/IF/22012035540261 — Khet talab nirmad Aditya bohare s/o vinod bohare | Ongoing | 147621.16 | 0 | 2025-07-11
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005034/IF/22012035540527 — Khet talab nirmad veerendra s/o ramdyal machhand | Ongoing | 147621.16 | 0 | 2025-05-29
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005034/IF/22012035559980 — Khet talab tilak singh s/o bhadole rajpura machhand | Approved | 0 | 0 | 2025-04-04
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005034/IF/22012035560017 — Khet talab mahaveer s/o rabode machhand | Approved | 0 | 0 | 2025-04-04
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005034/IF/22012035564071 — Khet talab nirmad lokendra s/o sukhpal singh macchand | New | 0 | 0 | 2025-04-14
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005034/IF/22012035564081 — Khet talab nirmad sunddar Singh s/o mulu rajpura | Approved | 0 | 0 | 2025-04-14
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005034/IF/22012035564356 — Khet talab nirmad lokendra s/o sukhpal singh machhand | Approved | 0 | 0 | 2025-04-14
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005034/IF/22012035625618 — Ek bagiya ma ke name sushma w/o ramsingh | New | 0 | 0 | 2025-08-15
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005034/IF/22012035625627 — Ek bagiya ma ke name sushma w/o ramsingh | New | 0 | 0 | 2025-08-15
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005034/IF/22012035626017 — Ek bagiya ma ke name sushma w/o ramsingh | New | 0 | 0 | 2025-08-15
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005034/IF/22012035626041 — Ek bagiya ma ke name sushma w/o ramsingh | Ongoing | 266578.64 | 0 | 2026-01-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005034/IF/22012035657446 — ek bagiya ma ke name | New | 0 | 0 | 2025-08-15
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005034/IF/22012035657449 — ek bagiya ma ke nam phulan devi | Approved | 266578.64 | 0 | 2025-08-15
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005034/IF/22012035657458 — ek bagiya ma ke name sita devi | Approved | 266578.64 | 0 | 2025-08-15
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005034/IF/22012035660083 — ek bagiya ma naam asha devi | Approved | 0 | 0 | 2025-08-15
RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/1360380 — Construction of IAY House -IAY REG. NO. MP2803503 | Approved | 27000 | 0 | 2018-03-05
RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/1365421 — Construction of IAY House -IAY REG. NO. MP3829377 | Approved | 27000 | 0 | 2018-03-05
RON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/2351747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5075528 | Approved | 27000 | 0 | 2019-12-30
RON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/3672053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114138177 | Approved | 27000 | 0 | 2022-05-02
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/3712963 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117877507 | Ongoing | 27000 | 0 | 2024-04-22
RON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/3775563 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132911252 | Approved | 27000 | 0 | 2022-04-30
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4326227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120391275 | Ongoing | 27000 | 0 | 2024-04-21
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4359767 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113754580 | Ongoing | 27000 | 0 | 2025-01-20
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4740294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106669364 | Ongoing | 27000 | 0 | 2025-02-24
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4754700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118290477 | Ongoing | 27000 | 0 | 2025-01-04
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4755431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118058091 | Ongoing | 27000 | 0 | 2024-12-04
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4756450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117876116 | Ongoing | 27000 | 0 | 2024-12-04
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4756476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879113 | Physically Completed | 23490 | 0 | 2024-12-04 | 2026-08-02
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4761422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120835883 | Ongoing | 27000 | 0 | 2024-12-27
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4774383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126032121 | Ongoing | 27000 | 0 | 2025-04-15
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4786945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132910234 | Ongoing | 27000 | 0 | 2024-12-04
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4786946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132910474 | Ongoing | 27000 | 0 | 2024-12-04
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4786954 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132912899 | Ongoing | 27000 | 0 | 2024-12-04
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4854169 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113689888 | Ongoing | 27000 | 0 | 2025-02-24
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4855412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107081575 | Approved | 27000 | 0 | 2024-10-28
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4855915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123811532 | Ongoing | 27000 | 0 | 2025-02-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4887243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120949200 | Ongoing | 27000 | 0 | 2025-07-04
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4887249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120975110 | Physically Completed | 23490 | 0 | 2025-06-07 | 2026-07-12
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4887450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879963 | Ongoing | 27000 | 0 | 2025-09-21
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4887451 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117880072 | Ongoing | 27000 | 0 | 2025-04-29
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4887835 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106442284 | Approved | 27000 | 0 | 2024-11-26
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4889589 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113673596 | Ongoing | 27000 | 0 | 2025-10-05
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4934202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100852992 | Ongoing | 27000 | 0 | 2025-06-15
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4934753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102465556 | Ongoing | 27000 | 1800 | 2025-11-13
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4934874 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102201745 | Ongoing | 27000 | 0 | 2025-04-29
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4940202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107068452 | Ongoing | 27000 | 1800 | 2025-10-12
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4940725 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113679243 | Ongoing | 27000 | 0 | 2025-04-29
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4940730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113681588 | Ongoing | 27000 | 0 | 2025-04-29
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4940766 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113691476 | Ongoing | 27000 | 0 | 2025-07-27
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4942041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113659527 | Ongoing | 27000 | 0 | 2025-07-27
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4944366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115420493 | Ongoing | 27000 | 0 | 2025-07-27
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4952178 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879245 | Ongoing | 27000 | 0 | 2025-10-12
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4954999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120391108 | Ongoing | 27000 | 0 | 2025-04-29
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4955000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120391580 | Ongoing | 27000 | 0 | 2025-10-05
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4955002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120392760 | Physically Completed | 23490 | 0 | 2025-10-05 | 2026-07-12
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4961969 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126042540 | Ongoing | 27000 | 0 | 2025-08-27
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/4963072 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126236655 | Physically Completed | 23490 | 0 | 2025-04-29 | 2026-07-12
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5245540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117880414 | Ongoing | 27000 | 0 | 2025-06-07
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5246392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115335627 | Ongoing | 27000 | 1800 | 2025-11-13
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5253253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118309103 | Ongoing | 27000 | 0 | 2025-09-21
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5254315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879851 | Ongoing | 27000 | 5100 | 2025-07-27
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5263328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115114049 | Ongoing | 27000 | 0 | 2025-09-21
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5265603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117877975 | Ongoing | 27000 | 0 | 2025-10-12
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5265992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142787027 | Ongoing | 27000 | 0 | 2025-09-21
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5270780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120239324 | Ongoing | 27000 | 0 | 2025-04-29
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5273106 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120949017 | Ongoing | 27000 | 0 | 2025-10-05
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5277163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132912507 | Ongoing | 27000 | 0 | 2025-10-05
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5280434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123173107 | Ongoing | 27000 | 0 | 2025-04-29
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5281022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118306933 | Ongoing | 27000 | 0 | 2025-07-27
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5282547 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120393959 | Ongoing | 27000 | 0 | 2025-06-15
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5287866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120239862 | Ongoing | 27000 | 0 | 2025-06-07
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5289680 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142787944 | Ongoing | 27000 | 0 | 2025-08-27
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5291621 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132912949 | Ongoing | 27000 | 0 | 2025-06-15
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5297006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117877096 | Ongoing | 27000 | 0 | 2025-10-05
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5300023 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123449365 | Physically Completed | 23490 | 0 | 2025-09-21 | 2026-08-09
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5302757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120966296 | Ongoing | 27000 | 0 | 2025-06-07
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5303104 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107052151 | Ongoing | 27000 | 0 | 2025-07-27
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5306100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115344984 | Ongoing | 27000 | 0 | 2025-09-21
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5311630 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120835784 | Ongoing | 27000 | 0 | 2025-06-15
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5316397 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132913228 | Ongoing | 27000 | 0 | 2025-06-04
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5318113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117876248 | Physically Completed | 23490 | 0 | 2025-06-04 | 2026-07-12
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5321698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126251886 | Ongoing | 27000 | 0 | 2025-06-04
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5321911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123809779 | Ongoing | 27000 | 0 | 2025-04-29
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5324102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120840694 | Ongoing | 27000 | 0 | 2025-09-21
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5324889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126252716 | Ongoing | 27000 | 0 | 2025-05-28
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5326718 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126249554 | Ongoing | 27000 | 3600 | 2026-02-19
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5327936 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120391931 | Ongoing | 27000 | 0 | 2025-07-27
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5329771 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120967422 | Ongoing | 27000 | 0 | 2025-07-27
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5332448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132915847 | Ongoing | 27000 | 0 | 2025-04-29
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5333782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123817817 | Ongoing | 27000 | 3300 | 2025-07-27
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5333955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132913265 | Ongoing | 27000 | 0 | 2025-10-12
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5570432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124788299 | Ongoing | 27000 | 3300 | 2025-09-21
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5570445 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144103488 | Ongoing | 27000 | 0 | 2025-06-04
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5570446 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144103540 | Ongoing | 27000 | 0 | 2025-08-20
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5570568 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120949634 | Ongoing | 27000 | 0 | 2025-06-04
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5570569 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120975360 | Ongoing | 27000 | 0 | 2025-09-21
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5571363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879556 | Ongoing | 27000 | 0 | 2025-11-13
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5571391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126826690 | Ongoing | 27000 | 0 | 2025-09-21
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5571691 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120975836 | Approved | 27000 | 0 | 2025-04-22
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5571769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119076958 | Ongoing | 27000 | 1500 | 2026-05-12
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5571844 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124147584 | Physically Completed | 23490 | 0 | 2025-07-27 | 2026-08-09
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5571969 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132910887 | Physically Completed | 23490 | 0 | 2025-09-21 | 2026-08-09
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5571970 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132911336 | Ongoing | 27000 | 0 | 2025-09-21
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5571972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132912822 | Ongoing | 27000 | 3300 | 2026-02-19
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5571973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132913418 | Ongoing | 27000 | 0 | 2025-06-04
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5571974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132914079 | Ongoing | 27000 | 0 | 2025-09-21
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5572089 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123810320 | Ongoing | 27000 | 0 | 2025-05-28
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5572393 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142787134 | Ongoing | 27000 | 5100 | 2025-10-12
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5572524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102448014 | Ongoing | 27000 | 0 | 2025-07-27
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5572598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114106453 | Approved | 27000 | 0 | 2025-04-03
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5573092 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119077664 | Ongoing | 27000 | 0 | 2025-10-05
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5573203 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120835990 | Ongoing | 27000 | 0 | 2025-06-04
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5573204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120836152 | Ongoing | 27000 | 0 | 2025-08-20
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5573293 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117878540 | Ongoing | 27000 | 3600 | 2026-04-22
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5573337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126824467 | Ongoing | 27000 | 0 | 2025-06-04
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5573585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123444480 | Ongoing | 27000 | 0 | 2025-06-04
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5706557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117878663 | Ongoing | 27000 | 0 | 2025-09-21
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5706559 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120950284 | Ongoing | 27000 | 6600 | 2026-05-12
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5706581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121579596 | Physically Completed | 23490 | 0 | 2025-12-08 | 2026-08-09
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5706629 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124767511 | Ongoing | 27000 | 3300 | 2026-05-12
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5706689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120842742 | Physically Completed | 23490 | 0 | 2025-08-27 | 2026-07-12
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5706808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144103589 | Ongoing | 27000 | 0 | 2025-08-20
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5707007 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117877607 | Ongoing | 27000 | 0 | 2025-09-21
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5707038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132911319 | Ongoing | 27000 | 0 | 2025-07-27
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5707039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132912546 | Ongoing | 27000 | 0 | 2025-09-21
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5707040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132913182 | Approved | 27000 | 0 | 2025-04-29
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5707041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132913558 | Ongoing | 27000 | 1800 | 2025-09-21
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5707082 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127295180 | Ongoing | 27000 | 0 | 2025-09-21
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5707195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126250694 | Ongoing | 27000 | 3600 | 2026-04-22
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5707521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124846393 | Approved | 27000 | 0 | 2025-03-27
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5708095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119356927 | Physically Completed | 23490 | 0 | 2025-09-21 | 2026-08-02
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5708228 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119078177 | Ongoing | 27000 | 0 | 2025-09-21
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5708272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120966556 | Ongoing | 27000 | 0 | 2025-10-12
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5708276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114083660 | Ongoing | 27000 | 8100 | 2026-02-19
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5708318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149128412 | Ongoing | 27000 | 0 | 2025-09-21
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5805149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132911188 | Ongoing | 27000 | 0 | 2026-02-21
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/5805308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115419579 | Ongoing | 27000 | 3300 | 2026-02-19
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6050425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117881135 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6050606 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107067229 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6050622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126257813 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6050658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126247856 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6050717 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126248445 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6050745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119346353 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6050791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879361 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6050796 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119077915 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6050835 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124859844 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6050839 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106687297 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6050921 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126825563 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6050996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144104733 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6051245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879417 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6051522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127950073 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6051616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879677 | Approved | 27000 | 0 | 2025-05-11
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6051747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132913466 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6051748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132908841 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6051915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120965999 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6051933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102453963 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6052024 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128156580 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6052026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126683655 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6052029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107072294 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6052080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120393489 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6052202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132914015 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6052248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132913956 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6052249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132909093 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6052292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132913991 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6052315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126238717 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6052338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132914335 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6052340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106649792 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6052382 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132914201 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6052383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142787841 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6052384 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124106050 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6052401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126457263 | Approved | 27000 | 0 | 2026-02-26
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6052430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125290828 | Approved | 27000 | 0 | 2026-02-10
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6052571 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141337201 | Approved | 27000 | 0 | 2025-03-09
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6052649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142787723 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6052873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122402192 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6054723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133172044 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6054897 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124161416 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6054908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132912476 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6054941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124158874 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6055437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879182 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6055709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117880936 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6055998 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132910924 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6056038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132910337 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6056086 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132911352 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6056267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132915403 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6056278 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124112201 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6056311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132915135 | Approved | 27000 | 0 | 2026-03-24
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6056632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132915255 | Approved | 27000 | 0 | 2026-03-24
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6230994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126455496 | Ongoing | 27000 | 6600 | 2026-06-06
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6237614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118304443 | Approved | 27000 | 0 | 2026-02-10
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6237622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132911096 | Approved | 23490 | 0 | 2026-04-16
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6237623 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132913818 | Approved | 23490 | 0 | 2026-04-16
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6237624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132913876 | Approved | 23490 | 0 | 2026-04-16
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6237625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132914691 | Approved | 23490 | 0 | 2026-04-16
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6237641 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119356339 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6237774 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114100681 | Approved | 27000 | 0 | 2026-02-10
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6237904 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100868611 | Approved | 27000 | 0 | 2026-02-10
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6237906 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132909865 | Approved | 23490 | 0 | 2026-04-16
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6237909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106623090 | Approved | 23490 | 0 | 2026-04-16
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6353178 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122421297 | Approved | 27000 | 0 | 2026-07-14
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6353514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106621207 | Approved | 27000 | 0 | 2026-07-14
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6353736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132915533 | Approved | 27000 | 0 | 2026-07-14
RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/6373047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114074512 | Approved | 27000 | 0 | 2026-07-14
RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/943768 — Construction of IAY House -IAY REG. NO. MP2887816 | Approved | 27000 | 0 | 2017-04-15
RON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005034/IF/IAY/958666 — Construction of IAY House -IAY REG. NO. MP3254218 | Ongoing | 27000 | 0 | 2023-09-14
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005034/RC/22012034398607 — panch parmeshwar cc road fule nagar school se asharam kushwaha ki ore | Ongoing | 74400 | 0 | 2019-03-02
RON | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005034/RC/22012034462633 — Panch Parmeshwhar CC Road Nali Nirman Kadore Kushwaha se Main Road Viswari Bali Road Ki Ore | Ongoing | 177750 | 0 | 2024-01-15