## Work List
Exported on: 2026-10-11 06:56:24
Filters applied:
Data source: MGNREGA + VBGRAMG
District: BHIND
Block: All
Panchayat: GUDA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
RON | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702005039/AV/22012034509859 — Shantidaam guda | Completed | 283566.25 | 226644.55 | 2020-07-22 | 2024-10-03
RON | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702005039/AV/22012034509860 — Shantidaam bhakoti | Completed | 194312.08 | 158069.45 | 2022-02-15 | 2024-10-03
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702005039/AV/22012034619355 — maa ki bagiya p s school gurha | Closed | 0 | 0 | 2022-04-01
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702005039/AV/22012034619356 — maa ki bagiya aaganwadi gurha | Closed | 5600 | 0 | 2022-04-01
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702005039/AV/22012034620035 — maa ki bagiya p s school gurha | Closed | 5600 | 0 | 2022-04-01
RON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov building Block Plantation-Farm Forestry-Comm / Block Plantation of Farm Forestry Trees in Government building premises for Community | Plantation | 1702005039/DP/22012034599216 — meri mati mera desh basudha bandhan amret batika talav ke kinare gurha | Closed | 0 | 0 | 2023-08-01
RON | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702005039/FP/22012034366084 — nala nirman nevalal se rahu tak | Completed | 241833.25 | 110580 | 2020-07-23 | 2022-04-27
RON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702005039/FP/22012034627780 — Nala nirman karya nadel me ramraj ke khet se bhakoti ki or | Closed | 0 | 0 | 2021-12-31
RON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702005039/FP/22012034627781 — Nala nirman karya nadel me ramraj ke khet se bhakoti ki or | Completed | 1497382.45 | 991182 | 2022-01-25 | 2024-10-25
RON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702005039/FP/22012034627968 — nala nirman karya nadel me ramsaran ke khet se ramraj ke khet tak | Closed | 0 | 0 | 2022-01-26
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702005039/FP/22012034627969 — nala nirman karya kushwah mohhalla se karaua tak | Completed | 1390032 | 958188 | 2022-05-11 | 2024-10-25
RON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702005039/FP/22012034628231 — Nala nirman karya shivsaran se khet se ramraj ke khet tak gurha | Closed | 0 | 0 | 2022-01-26
RON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702005039/FP/22012034628232 — Nala nirman karya kushwah mohhala se kharaua tak | Closed | 0 | 0 | 2022-01-26
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702005039/FP/22012034628524 — nala nirman karya kushwah mohhalla se karaua tak | Closed | 0 | 0 | 2022-04-01
RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702005039/IF/22012034352419 — vriksharopan road side guda se bhakoti | Completed | 335000 | 14000 | 2018-01-17 | 2019-10-08
RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702005039/IF/22012034352422 — vriksharopan road side bhakoti se surghan | Closed | 335000 | 0 | 2017-06-10
RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702005039/IF/22012034353991 — vriksharopan road side guda se surghan | Completed | 335000 | 17000 | 2017-07-29 | 2019-10-08
RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702005039/IF/22012034354671 — vriksharopan road side surghan se bhakoti | Completed | 335000 | 17000 | 2017-07-29 | 2019-10-08
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702005039/IF/22012034678658 — medbandhan susheela rajendra | Deleted | 0 | 0 | 2021-01-26
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702005039/IF/22012034678659 — medbandhan meera devi shyam singh | Deleted | 0 | 0 | 2021-01-26
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702005039/IF/22012034678660 — medbandhan rameshwar jwali | Deleted | 0 | 0 | 2021-01-26
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702005039/IF/22012034678661 — medbandhan rambihari mulu | Completed | 40138.97 | 25476 | 2021-09-08 | 2022-04-27
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702005039/IF/22012034678662 — medbandhan bhagwandas mulu | Completed | 33800.04 | 25476 | 2021-07-10 | 2022-04-27
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702005039/IF/22012034678664 — medbandhan jaswant nathu | Deleted | 0 | 0 | 2021-01-26
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702005039/IF/22012034678665 — medbandhan kunji kashiram | Closed | 28517.6 | 0 | 2021-01-26
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702005039/IF/22012034678667 — medbandhan udayram parmole | Closed | 32743.56 | 0 | 2021-01-26
RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702005039/IF/22012034678671 — medbandhan samser khan bhure khan | Deleted | 0 | 0 | 2021-01-26
RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702005039/IF/22012034678673 — medbandhan jabbar khan bhure khan | Completed | 31687.06 | 25476 | 2021-09-01 | 2022-04-27
RON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005039/IF/22012035382720 — Khet Talab Nirman Chhote Singh /Uday Singh Gudha | Approved | 147621.16 | 0 | 2025-04-14
RON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702005039/IF/22012035392445 — Khet Talab Nirman Jashmant/Nathu SC Gudha | Approved | 147621.16 | 0 | 2025-04-14
RON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702005039/IF/22012035517977 — Khet Talab Nirman shivcharan / muloo Gudha | Deleted | 0 | 0 | 2025-04-14
RON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702005039/IF/22012035518025 — Khet Talab Nirman indraveer singh / vishwnath singh bhakoti | Deleted | 0 | 0 | 2025-04-14
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005039/IF/22012035527188 — Khet Talab Nirman Chhote Singh /Uday Singh Gudha | Deleted | 0 | 0 | 2025-04-14
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702005039/IF/22012035530765 — Khet Talab Nirman Indraveer Singh /Vishvanath Singh bhakoti | Approved | 147621.16 | 0 | 2025-04-14
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005039/IF/22012035530854 — Khet Talab Nirman shivcharan / muloo Gudha | Completed | 147621.16 | 73863 | 2025-05-22 | 2026-04-17
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702005039/IF/22012035530861 — Khet Talab Nirman Chhote Singh /Uday Singh Gudha | Ongoing | 147621.16 | 89523 | 2025-05-22
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702005039/IF/22012035530869 — Khet Talab Nirman Jashmant/Nathu SC Gudha | Ongoing | 147621.16 | 261 | 2025-05-22
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005039/IF/22012035626409 — ek bagiya ma ke naam deva/ram das sc | Ongoing | 266578.64 | 1566 | 2026-01-08
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005039/IF/22012035628125 — ek bagiya ma ke nam kushma / munesh sc bhakoti | Approved | 266578.64 | 0 | 2025-08-15
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1702005039/IF/22012035639717 — ek bagiya ma ke nam neha devi sc bhakoti | Approved | 0 | 0 | 2025-08-15
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005039/IF/22012035654398 — ek bagiya ma ke nam suman devi / chandrapal singh gudha | Approved | 266578.64 | 0 | 2025-10-02
RON | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702005039/IF/3 — मेढ वंधान कार्य माताप्रसाद/गोरेलाल | Deleted | 25500 | 0 | 2009-02-26
RON | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702005039/IF/4 — मेढ बंधान कार्य मेघसिंह / लटोरे | Deleted | 26500 | 0 | 2009-02-18
RON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/1907041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4126248 | Completed | 15660 | 15496 | 2018-09-19 | 2019-04-30
RON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/1907902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4962713 | Completed | 15660 | 15496 | 2018-10-03 | 2019-04-30
RON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/1911065 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4873135 | Completed | 15660 | 15496 | 2018-09-19 | 2019-04-30
RON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/1911261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5324459 | Completed | 15660 | 15508 | 2018-10-03 | 2019-04-30
RON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/1911285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5378958 | Completed | 15660 | 15496 | 2018-09-19 | 2019-04-30
RON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/1911286 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5379147 | Completed | 15660 | 15496 | 2018-10-03 | 2019-04-30
RON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/1911303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5403310 | Completed | 15660 | 15660 | 2018-09-19 | 2019-01-10
RON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/1911304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5403417 | Completed | 15660 | 15496 | 2018-10-03 | 2019-04-30
RON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/2228136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4885646 | Closed | 17100 | 0 | 2019-07-07
RON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/2228149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4911983 | Completed | 15840 | 15628 | 2019-09-04 | 2020-05-18
RON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/2228185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4505895 | Completed | 15840 | 15516 | 2019-09-19 | 2020-05-18
RON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/2228204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4987016 | Completed | 15840 | 15748 | 2019-09-04 | 2020-05-18
RON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/2228243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5018573 | Completed | 15840 | 15748 | 2019-08-07 | 2020-08-04
RON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/2228813 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5711813 | Completed | 15840 | 14952 | 2019-08-07 | 2020-08-04
RON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/2262434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4912101 | Completed | 15840 | 14952 | 2019-09-25 | 2020-08-04
RON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/2262472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5455341 | Completed | 17100 | 17046 | 2019-10-24 | 2024-05-13
RON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/2262590 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5054391 | Completed | 17100 | 17046 | 2019-10-24 | 2024-05-13
RON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/2262911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5466248 | Completed | 15840 | 14952 | 2019-10-24 | 2020-08-04
RON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/3709359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114798259 | Completed | 18360 | 18234 | 2022-11-08 | 2024-05-13
RON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/3777019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133373120 | Completed | 18360 | 18344 | 2022-11-08 | 2024-10-23
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/4325793 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133373339 | Physically Completed | 18360 | 14580 | 2024-04-30 | 2024-11-21
RON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/4326193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113441476 | Physically Completed | 18360 | 0 | 2023-06-30 | 2024-11-21
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/4521040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114786599 | Completed | 23490 | 22554 | 2025-01-07 | 2026-05-17
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005039/IF/IAY/4528273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133373779 | Ongoing | 27000 | 22986 | 2025-01-14
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005039/IF/IAY/4528274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133374454 | Ongoing | 27000 | 22599 | 2025-01-25
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/4528275 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133374738 | Completed | 23490 | 22554 | 2025-01-07 | 2026-05-17
RON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/465447 — Construction of IAY House -IAY REG. NO. MP1764897 | Completed | 15030 | 9198 | 2017-02-14 | 2018-11-09
RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005039/IF/IAY/4888388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114794221 | Ongoing | 27000 | 17118 | 2025-03-03
RON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/496091 — Construction of IAY House -IAY REG. NO. MP2208321 | Completed | 15030 | 14994 | 2017-02-14 | 2018-11-19
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005039/IF/IAY/5268230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133373285 | Ongoing | 27000 | 23490 | 2025-05-06
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005039/IF/IAY/5271995 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125785804 | Ongoing | 27000 | 23490 | 2025-08-02
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/5279996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114803221 | Completed | 23490 | 23490 | 2025-04-29 | 2026-05-17
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/5292355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114789406 | Completed | 23490 | 23490 | 2025-05-20 | 2026-05-17
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005039/IF/IAY/5295202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133374847 | Ongoing | 27000 | 23490 | 2025-04-22
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005039/IF/IAY/5303376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114791796 | Ongoing | 27000 | 23490 | 2025-05-06
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005039/IF/IAY/5330009 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123894815 | Ongoing | 27000 | 20880 | 2025-08-23
RON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/53341 — Construction of IAY House -IAY REG. NO. MP-02-005-039-001/31 | Completed | 14310 | 16328 | 2016-07-30 | 2018-12-22
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005039/IF/IAY/5340215 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114806495 | Ongoing | 27000 | 23490 | 2025-05-13
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/5342116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133374227 | Physically Completed | 23490 | 21402 | 2025-04-29 | 2026-01-09
RON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/550432 — Construction of IAY House -IAY REG. NO. MP3372487 | Completed | 15030 | 14430 | 2017-02-14 | 2018-09-05
RON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/552969 — Construction of IAY House -IAY REG. NO. MP3448843 | Completed | 15030 | 14442 | 2017-02-14 | 2018-09-07
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/5570305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114773105 | Completed | 23490 | 23490 | 2025-05-20 | 2026-05-17
RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005039/IF/IAY/5708163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133375082 | Ongoing | 27000 | 23490 | 2025-09-05
RON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/649077 — Construction of IAY House -IAY REG. NO. MP2490834 | Completed | 15030 | 15540 | 2017-03-21 | 2018-08-21
RON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/747767 — Construction of IAY House -IAY REG. NO. MP2461429 | Completed | 15030 | 15660 | 2018-09-04 | 2018-12-30
RON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/776733 — Construction of IAY House -IAY REG. NO. MP3778128 | Completed | 15030 | 15660 | 2018-09-04 | 2018-12-02
RON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/927133 — Construction of IAY House -IAY REG. NO. MP2547501 | Completed | 15480 | 15660 | 2018-10-28 | 2018-12-14
RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702005039/IF/IAY/965831 — Construction of IAY House -IAY REG. NO. MP3441102 | Approved | 27000 | 0 | 2017-04-15
RON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005039/IF/IAY/976664 — Construction of IAY House -IAY REG. NO. MP3747981 | Completed | 15480 | 15508 | 2018-10-28 | 2019-04-30
RON | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/122 — मेढ बन्‍धान | Deleted | 19000 | 0 | 2009-08-18
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/22012034229977 — medbandhan maniram/gangadeen guda | Completed | 27600 | 15423 | 2015-11-09 | 2017-11-17
RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/22012034229978 — medbandhan jhadu/khyali guda | Deleted | 19900 | 0 | 2015-09-23
RON | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702005039/LD/22012034296471 — shantidham nirman guda | Deleted | 180000 | 0 | 2017-06-25
RON | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/298 — मेडबंधान तिजोले गोयेलाल | Completed | 23500 | 0 | 2009-07-15 | 2011-04-01
RON | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/299 — मेढबन्‍धान मेघसिंह / लटोरे | Deleted | 0 | 0 | 2009-02-18
RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/375 — मेढबन्‍धान मंगल / ग्‍याप्रसाद | Completed | 0 | 12900 | 2010-09-29 | 2010-10-04
RON | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/3799405187 — MEDBANDHAN SUNDAR/CHOTE BHAKOTEE | Completed | 50500 | 46840 | 2013-09-25 | 2014-08-04
RON | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/3799405298 — MEDBANDHAN CHOTE/GYADEEN BHAKOTEE | Deleted | 41300 | 0 | 2013-04-01
RON | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/3799410374 — med bandhan tijole/goylal bhakotee | Deleted | 29500 | 0 | 2013-04-01
RON | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/3799410414 — Med bandhan ratibai/padku guda | Completed | 53600 | 46428 | 2014-01-15 | 2014-03-30
RON | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/3799434153 — med bandhan laxman/khargole bhakotee | Deleted | 25800 | 0 | 2013-04-01
RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/384 — मेढबन्‍धान लल्‍लू / बल सिंह | Completed | 0 | 7800 | 2010-08-01 | 2010-08-13
RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/385 — मेढबन्‍धान श्रीपाल / ख्‍याली | Completed | 0 | 6000 | 2010-07-14 | 2010-07-25
RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/386 — मेढबन्‍धान महेशसिंह/ लाखन | Completed | 0 | 8500 | 2010-06-17 | 2010-06-29
RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/388 — मेढबन्‍धान नाथू / श्‍यामलाल | Completed | 0 | 10200 | 2010-09-29 | 2010-10-04
RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/389 — मेढबन्‍धान छक्‍की / खुशाली | Completed | 0 | 4700 | 2010-07-01 | 2010-07-13
RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/410 — मेड्बंधान लल्‍लूराम/सोनपाल गुढा | Completed | 19280 | 7300 | 2010-07-07 | 2011-04-01
RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/436 — मेड्बंधान रामअवतार /परशुराम गुढा | Completed | 19280 | 5100 | 2010-05-20 | 2010-06-01
RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/437 — मेड्बंधान रमेश/रामनाथ गुढा | Completed | 13186 | 10500 | 2010-09-01 | 2010-09-13
RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/438 — लक्ष्‍मन/खरगोले गुढा | Completed | 15232 | 14500 | 2010-07-19 | 2011-04-01
RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/439 — मेड्बंधान सरजू/फुदी गुढा | Completed | 15232 | 12000 | 2010-08-15 | 2010-08-27
RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/440 — मेड्बंधान तिजोले/गोयेलाल गुढा | Completed | 13186 | 11200 | 2010-09-15 | 2011-07-27
RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/463 — मेड्बंधान कुजी/काशीराम गुढा | Completed | 17570 | 0 | 2010-06-03 | 2010-06-15
RON | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/49 — मेढ बंधान कार्य रघुनाथ के खेत पर | Deleted | 16000 | 0 | 2009-01-21
RON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/585 — मेड्बंधान मनीराम/गंगादीन गुढा | Deleted | 34000 | 0 | 2011-08-04
RON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/586 — मेड्बंधान उदयराम/परमोले गुढा | Deleted | 40596 | 0 | 2011-08-11
RON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/587 — मेड्बंधान रामंशकर/बेदरी गुढ्ा | Deleted | 50495 | 0 | 2011-08-04
RON | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/734 — मेड्बंधान कल्‍लू/रामस्‍वरूप गुढ्ा | Completed | 30000 | 9928 | 2013-10-16 | 2014-01-10
RON | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/9926713384 — medbandhan ramsanehi/dhansole guda | Completed | 57600 | 32970 | 2014-07-30 | 2014-08-20
RON | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/9926713402 — medbandhan chintai/bhagirath guda | Deleted | 57600 | 0 | 2014-04-01
RON | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/9926713403 — MEDBANDHAN BHARESHAH/DHANTOO GUDA | Deleted | 33000 | 0 | 2014-04-01
RON | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/9926713404 — MEDBANDHAN CHHOTE/GYADEEN GUDA | Deleted | 44300 | 0 | 2014-04-01
RON | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005039/LD/9926713482 — MEDBANDHAN TIJOLE/GOILAL GUDA | Completed | 31600 | 26763 | 2014-09-10 | 2015-10-20
RON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005039/RC/22012034170242 — पंचपरमेश्‍वरसीसीरोड मेन रोड से पंचायत भवन तक गुढा | Completed | 137700 | 135615.5 | 2013-06-19 | 2014-08-30
RON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005039/RC/22012034224991 — CC ROAD PANCHPARMESWAR CC ROAD SE DEVI MANDIR SE S | Completed | 162500 | 61858 | 2014-08-20 | 2014-12-30
RON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005039/RC/22012034229933 — cc road panchparmeswar raman singh ke ghar se panchayat hote huye chhote ke ghar tak guda | Deleted | 41800 | 0 | 2014-04-01
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005039/RC/22012034284932 — CC ROAD PANCHPARMESWAR CC ROAD SE MEWALAL KE GHAR TAK GUDA | Completed | 112000 | 50326 | 2015-09-28 | 2017-12-30
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702005039/RC/22012034298408 — sudur sampark road mewalal ke ghar se nala ki or bhakoti | Deleted | 1409000 | 0 | 2016-02-14
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005039/RC/22012034305446 — cc road samser kha ke makan se kali mata mandir ta | Deleted | 0 | 0 | 2016-01-26
RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005039/RC/22012034305449 — cc road | Deleted | 0 | 0 | 2016-01-26
RON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005039/RC/22012034373003 — CC raod | Closed | 0 | 0 | 2017-10-02
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005039/RC/22012034440171 — cc road | Closed | 0 | 0 | 2019-01-26
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005039/RC/22012034441040 — पंच परमेश्वर सीसी रोड माखन के घर से मरघट की ओर | Closed | 61875 | 0 | 2019-03-09
RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005039/RC/22012034441079 — पंच परमेश्वर सी सी रोड नाली निर्माण जगत सिंह के घर से माता मंदिर की ओर | Completed | 48675 | 11304 | 2019-03-09 | 2024-05-13
RON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702005039/RC/22012034506744 — cc road vishvanath ke ghar se sh. ma. vidhyalay tak | Ongoing | 97650 | 5280 | 2019-11-21
RON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005039/RC/22012034506750 — cc road karas dev ke sthan se ramsnehi ke ghar ki or bhakoti | Completed | 69750 | 69652 | 2019-11-21 | 2020-08-21
RON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005039/RC/22012034506751 — cc road nathu a j ke ghar se harnam ke ghar ki or bhakoti | Completed | 46500 | 1056 | 2019-11-21 | 2024-05-13
RON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005039/RC/22012034506754 — cc road sadak marrmat laxmi baghel ke ghar se kapoor singh ke ghar tak | Completed | 23085 | 22998 | 2019-11-21 | 2020-08-21
RON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005039/RC/22012034509527 — cc sadak marrmat deshraj kushwah ke ghar se govind rathore ke ghar tak guda | Completed | 38475 | 38344 | 2019-12-26 | 2020-08-21
RON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005039/RC/22012034509531 — cc road marrmat girand singh ke ghar se babli khan ke ghar tak guda | Completed | 51300 | 51198 | 2020-01-30 | 2020-08-21
RON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005039/RC/22012034509573 — cc road babu ke ghar se chitu ke ghar tak avm ratibai ke ghar se bhagirath ke ghar tak guda | Completed | 46500 | 29920 | 2019-12-19 | 2020-08-21
RON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005039/RC/22012034515212 — cc sadak puran ke ghar se gokli prasad ke ghar tak guda | Completed | 46500 | 41804 | 2020-01-30 | 2020-08-21
RON | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702005039/RC/33 — पहुंच मार्ग भकोटी से नडेल नाला तक | Completed | 265000 | 98280 | 2009-08-24 | 2013-11-17
RON | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005039/RC/74 — पंचपरमेशवर सीसी रोड नूरमौहम्‍मद के घर से किश्ुन के | Completed | 185098 | 137268 | 2012-07-01 | 2013-05-20
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702005039/RS/22012034688802 — samudayak nadep nirman ms school ke pass | Closed | 0 | 0 | 2022-08-15
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702005039/RS/22012034688803 — samudayak nadep nirman ms school ke pass | Closed | 2000 | 0 | 2023-01-10
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702005039/RS/22012034688969 — samudayak nadep laxmi/punu ke ghar ke pass | Closed | 2000 | 0 | 2023-01-10
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702005039/RS/22012034688971 — nadep nirman ps school ke pass guda | Closed | 2000 | 0 | 2023-01-10
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702005039/RS/22012034688973 — nadep nirman rahu par guda | Closed | 2000 | 0 | 2023-01-10
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702005039/RS/22012034688974 — nadep nirman ramnaresh ke ghar ke pass | Closed | 2000 | 0 | 2022-08-01
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702005039/RS/22012034689063 — nadep nirman ramendra ke darwaje ke pass | Closed | 10000 | 0 | 2022-08-15
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702005039/RS/22012034689064 — samudayak nadep nirman rahu ke handpaum par | Closed | 10000 | 0 | 2022-08-15
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702005039/RS/22012034689065 — samudayak nadep nirman ps handpamap par | Closed | 10000 | 0 | 2022-08-15
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702005039/RS/22012034689067 — samudayak nadep nirman ms school handpamp par | Closed | 10000 | 0 | 2022-08-15
RON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702005039/RS/22012034689068 — nadpep nirman jasmant ke darwaje par | Closed | 10000 | 0 | 2022-08-15
RON | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702005039/WC/22012034293862 — talab gahrikaran water shed wala talab guda | Deleted | 99000 | 0 | 2016-04-01
RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702005039/WC/22012034383989 — NAVEEN TALAB NIRMAN | Closed | 0 | 0 | 2017-10-02
RON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702005039/WC/22012034562196 — sashkiy talav guda me | Completed | 794647.31 | 491886 | 2020-08-13 | 2022-04-27
RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702005039/WC/22012034889399 — Check dem nirman karya nadel me prajapati ke khet ke pass | Closed | 0 | 0 | 2021-12-31
RON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702005039/WC/22012034905481 — naveen talav nirman karya seva prajapati ke khet ke pass | Completed | 1494671.45 | 1088952 | 2022-05-04 | 2024-10-25
RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702005039/WC/22012034920144 — Naveen talav nirman prajapat ke khet ke pass | Closed | 0 | 0 | 2022-01-26
RON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702005039/WC/22012034942408 — naveen talav nirman karya seva prajapati ke khet ke pass | Closed | 0 | 0 | 2022-04-01
RON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702005039/WC/22012034942433 — check dem nirman karya nadel me gurha | Closed | 0 | 0 | 2022-04-01
RON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1702005039/WC/22012035017189 — talav nirman karya nathu ke khet ke pas bhakoti | Ongoing | 1257219.56 | 305082 | 2022-12-29
RON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1702005039/WC/22012035313103 — Amrit Sarovar Nirman Karya Gram Guda | Ongoing | 2190000 | 261 | 2026-02-03
RON | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702005039/WH/19959177 — talab bandh sudrikaran kalimata mandir ke pass guda | Deleted | 91000 | 0 | 2017-05-13
RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702005039/WH/22012034456720 — talav jirdodhhar aaganwadi ke pass gurha | Completed | 49909.62 | 41676 | 2022-01-25 | 2022-05-20
RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702005039/WH/22012034456721 — talav jirdodhhar marghat ke pass gurha | Completed | 49781.02 | 43110 | 2022-01-25 | 2022-05-20
RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702005039/WH/22012034456724 — talav jirdodhhar mahaveer mandir ke pass bhakoti | Completed | 49731.97 | 1158 | 2022-01-25 | 2024-05-13