## Work List
Exported on: 2026-10-16 13:33:55
Filters applied:
Data source: MGNREGA + VBGRAMG
District: BHIND
Block: All
Panchayat: KHOOJA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
LAHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702006045/AV/22012034465726 — खेल मैदान स्कूल परिसर ग्राम खूजा ग्राम पंचायत खूजा | Completed | 134235.23 | 130243.65 | 2019-11-21 | 2021-11-03
LAHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702006045/AV/22012034509634 — kabrastan nirman khuja | Ongoing | 324542.88 | 12630 | 2020-05-30
LAHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702006045/AV/22012034515835 — आगनवाडी भवन निर्माण कार्य ग्राम पंचायत खूजा | Completed | 180000 | 179332 | 2020-08-17 | 2022-02-16
LAHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1702006045/FP/22012034364232 — कच्चा नाला निमार्ण सुरतान कुशबह के मकान से मरघट तक | Completed | 153000 | 77436 | 2020-01-03 | 2021-05-07
LAHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702006045/FP/22012034628494 — सी सी नाला निर्माण घनश्याम कुशवाह के माकन से सुदूर सड़क की ओर | Physically Completed | 77000 | 49368 | 2022-04-24 | 2026-04-20
LAHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702006045/FP/22012034630602 — प्रबलित सी सी नाला निर्माण कार्य सीताराम कुशवाह के मकान से मोहर कुशवाह के मकान तक | Physically Completed | 1387000 | 1289372 | 2023-01-25 | 2026-04-20
LAHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Flood Diversion Drain for Community | Works for Flood Control and Protection | 1702006045/FP/22012034637315 — सी सी नाला निर्माण कार्य रामदास गुप्ता के मकान से कल्लू के मकान की ओर | Ongoing | 77000 | 72930 | 2024-02-14
LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006045/IF/22012034305286 — nadep tanka nirman karya chatur singh s/o amar singh | Completed | 12000 | 10333 | 2016-12-02 | 2019-01-22
LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006045/IF/22012034305287 — NADEP TANKA NIRMAN KARYA MULAYAM S/O MALTHU | Deleted | 12000 | 0 | 2016-12-09
LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006045/IF/22012034305289 — NADEP TANKA KARYA SURTAN S/O ASHARAM | Completed | 12000 | 10333 | 2016-12-10 | 2019-01-22
LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006045/IF/22012034305290 — NADEP NIRMAN KARYA LAKHAN S/O RAMPRASAD | Deleted | 12000 | 0 | 2016-12-22
LAHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702006045/IF/22012034352006 — Braksharopan mata mandir per gram khooja | Completed | 335000 | 12288 | 2017-06-19 | 2021-10-11
LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702006045/IF/22012034718362 — खेत तालाब निर्माण कार्य बलवीर / विजय सिंह | Closed | 337715.44 | 0 | 2021-04-14
LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702006045/IF/22012034718363 — खेत तालाब निर्माण कार्य मुन्नालाल / विजय राम | Closed | 337715.44 | 0 | 2021-04-14
LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702006045/IF/22012034816802 — MED BANDHAAN NIRMAN KARY BALBEER / VIJAY SINGH | Closed | 70300.85 | 0 | 2021-04-14
LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702006045/IF/22012034816803 — MED BANDHAAN NIRMAN KARY TEJ SINGH / VIJAY SINGH | Closed | 71518.35 | 0 | 2021-04-14
LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702006045/IF/22012034816849 — MED BANDHAAN NIRMAN KARY RAMNARAYAN / SUKHNANDAN | Closed | 72735.84 | 0 | 2021-04-14
LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702006045/IF/22012034816850 — MED BANDHAAN NIRMAN KARY MANGAL SINGH / BHAGWAN DAS | Closed | 73953.15 | 0 | 2021-04-14
LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702006045/IF/22012034816852 — MED BANDHAAN NIRMAN KARY RAHUL / HARIRAM | Closed | 75170.65 | 0 | 2021-04-14
LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006045/IF/IAY/115309 — Construction of IAY House -IAY REG. NO. MP-02-006-045-001/014 | Completed | 14310 | 14196 | 2016-09-12 | 2018-10-26
LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006045/IF/IAY/115310 — Construction of IAY House -IAY REG. NO. MP-02-006-045-001/14 | Completed | 14310 | 14696 | 2016-09-12 | 2018-01-20
LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006045/IF/IAY/115311 — Construction of IAY House -IAY REG. NO. MP-02-006-045-001/38 | Completed | 14310 | 14322 | 2016-09-26 | 2018-10-26
LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006045/IF/IAY/115312 — Construction of IAY House -IAY REG. NO. MP-02-006-045-001/40 | Completed | 14310 | 14696 | 2016-06-27 | 2018-01-20
LAHAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006045/IF/IAY/1871893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4058890 | Completed | 15660 | 15496 | 2018-11-04 | 2019-09-01
LAHAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006045/IF/IAY/1872702 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5116861 | Completed | 15660 | 15690 | 2018-11-04 | 2019-10-17
LAHAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006045/IF/IAY/1872703 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5116879 | Completed | 15660 | 15502 | 2018-10-21 | 2019-09-01
LAHAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006045/IF/IAY/1872704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5116910 | Completed | 15660 | 15696 | 2018-10-21 | 2019-09-01
LAHAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006045/IF/IAY/1872729 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5156963 | Completed | 15660 | 15168 | 2018-10-28 | 2019-09-01
LAHAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006045/IF/IAY/1894815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5542473 | Completed | 15660 | 15672 | 2018-12-02 | 2019-07-24
LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006045/IF/IAY/240238 — Construction of IAY House -IAY REG. NO. MP1515071 | Completed | 15030 | 14769 | 2017-02-01 | 2018-09-07
LAHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006045/IF/IAY/3782214 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125829651 | Physically Completed | 18360 | 18343 | 2022-08-02 | 2024-11-21
LAHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006045/IF/IAY/3855163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128873328 | Physically Completed | 18360 | 18169 | 2022-08-17 | 2024-11-21
LAHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006045/IF/IAY/3855165 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128873478 | Completed | 18360 | 18326 | 2022-08-09 | 2024-11-05
LAHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006045/IF/IAY/4325851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126807925 | Completed | 18360 | 18330 | 2022-09-12 | 2024-11-05
LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006045/IF/IAY/476580 — Construction of IAY House -IAY REG. NO. MP1923799 | Completed | 15030 | 14298 | 2017-02-06 | 2018-09-07
LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5574043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128782786 | Ongoing | 27000 | 0 | 2025-07-28
LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5574044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128786401 | Approved | 27000 | 0 | 2025-03-15
LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5574045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128794053 | Approved | 27000 | 0 | 2025-03-21
LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5574046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128795158 | Ongoing | 27000 | 0 | 2025-03-21
LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5574179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127914432 | Ongoing | 27000 | 7830 | 2025-07-21
LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5574677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126796208 | Approved | 27000 | 0 | 2025-03-15
LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5574832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127120364 | Ongoing | 27000 | 14094 | 2025-08-11
LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5574913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129484513 | Ongoing | 27000 | 0 | 2025-07-14
LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5574915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129574434 | Ongoing | 27000 | 0 | 2025-07-14
LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5575331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128871009 | Approved | 27000 | 0 | 2025-03-15
LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5575832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129530018 | Ongoing | 27000 | 6264 | 2025-08-04
LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5575848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106674536 | Ongoing | 27000 | 11364 | 2025-07-28
LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5575928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131211299 | Approved | 27000 | 0 | 2025-03-21
LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5685319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125831671 | Approved | 27000 | 0 | 2025-03-21
LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5685404 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118028787 | Ongoing | 27000 | 1800 | 2025-03-21
LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5724487 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128871321 | Approved | 27000 | 0 | 2025-05-13
LAHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006045/IF/IAY/664508 — Construction of IAY House -IAY REG. NO. MP1930374 | Completed | 15030 | 15564 | 2017-08-16 | 2018-05-20
LAHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006045/IF/IAY/680886 — Construction of IAY House -IAY REG. NO. MP3518774 | Completed | 15030 | 14448 | 2017-06-24 | 2018-09-07
LAHAR | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702006045/LD/26 — ग्राम खूजा में मेडबंधान सूनू | Completed | 0 | 1456 | 2009-07-06 | 2009-07-04
LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702006045/PG/22012034365849 — खेल मैदान ग्राम पंचयत खुजा | Closed | 0 | 0 | 2018-04-01
LAHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034212767 — पंच परमेश्‍वर सीसी रोड अमत के मकान से कालका के मका | Completed | 103426 | 69058 | 2014-03-06 | 2015-04-28
LAHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034212770 — पंच परमेश्‍वर सरपंच के मकान से ठेकेदार के मकान तक | Completed | 55427 | 32141 | 2014-03-06 | 2015-04-28
LAHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034212773 — पंच परमेश्‍वर सीसी रोड रघुनाथ के मकान से बहादुर के | Completed | 151426 | 89598 | 2014-03-06 | 2015-04-27
LAHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034212776 — पंच परमेश्‍वर सीसी रोड विजय सिंह धाकड के मकान से र | Completed | 55427 | 34340 | 2014-03-06 | 2015-04-27
LAHAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034229123 — वि‍धायक नि‍धि‍ सीसी रोड रामजानकी मंदि‍र से रामकली | Completed | 39606 | 38047 | 2014-09-11 | 2015-08-10
LAHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034284693 — शी.सी. रोड मय नाली निर्माड सोवरन धाकड़ के मकान से मुलायम धाकड़ के मकान तक | Completed | 38211 | 37887 | 2015-09-17 | 2015-10-01
LAHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034288540 — PANCH PARMUSHSAWARC.C. ROAD LAKHAN SAVIT KI MAKANSE LALARAM PATAVA KE MAKAN KI OURI | Completed | 128689 | 78591 | 2015-11-05 | 2017-04-26
LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702006045/RC/22012034311703 — Sudoor Samparak Sadak Nirman Pradhan mantri Sadak Se Middle School Tak | Completed | 1440000 | 169672 | 2016-04-17 | 2019-11-14
LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034317105 — cc road & nali nirman karya gaud baba ke sthan se chandu jatav ke makan tak khooja | Completed | 38656 | 33874 | 2016-12-14 | 2018-01-20
LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034320532 — cc road & nali nirman karya panchyat bhawan se taliya tak gram khooja | Completed | 38656 | 28768 | 2017-01-18 | 2018-01-20
LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034333338 — cc road nali nirman karya munnalal dhakar ke makan se prabhu baretha ke makan tak | Completed | 34325 | 12771 | 2017-03-25 | 2018-01-20
LAHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702006045/RC/22012034341916 — SUDUR SAMPARK SADAK GRAM KHUJA SE KHERE BALI MATA MANDIR TAK | Completed | 1953000 | 1488402.06 | 2017-06-17 | 2020-05-15
LAHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702006045/RC/22012034344439 — SUDOOR SAMPARK SADAK MIDDLE SCHOOL SE PMGSY ROAD TAK | Completed | 688000 | 630806.18 | 2017-07-19 | 2020-05-15
LAHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034344754 — CC ROAD & NALI NIRMAN KARYA BHAGWAN SINGH DHAKAD KE MAKAN SE BABU DHAKAD KE MAKAN TAK | Completed | 5310000000 | 38184 | 2017-07-19 | 2019-08-25
LAHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034352750 — cc road & NALI NIRMAN KARYA MEGHARANI KUSHWAH KE MAKAN SE NANAI KUSHWAH KE MAKAN KI OR | Completed | 46068 | 38700 | 2017-09-08 | 2019-08-25
LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034376523 — C.C.Raod | Deleted | 0 | 0 | 2018-04-01
LAHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034383112 — CC ROAD & NALI NIRMAN KARYA KAPURE JATAV KE MAKAN SE RATIRAM JATAV KE MAKAN TAK | Completed | 53000 | 29232 | 2018-02-16 | 2019-08-25
LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034389167 — CC ROAD & NALI NIRMAN KARYA KALLU VISHKARMA KE MAKAN SE KADORE PAL KE MAKAN TAK | Completed | 92000 | 59508 | 2018-05-18 | 2019-03-08
LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034389168 — CC ROAD & NALI NIRMAN KARYA NARESH VISHKARMA KE MAKAN SE KAILASH DHAKAD KE MAKAN TAK AND GHANSHYAM | Closed | 54000 | 0 | 2018-04-26
LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034397437 — c c nali nirman kallu kushvah ke makan se atar singh parihar ke makan tak | Closed | 0 | 0 | 2018-09-20
LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034397715 — c c nali nirman kallu kushvah ke makan se atar singh parihar ke makan tak | Closed | 0 | 0 | 2018-04-26
LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034397915 — C.C. ROAD NALI NIRMAN KALLU KUSHWAH KE MAKAN SE ATAR SINGH PARIHAR KE MAKAN TAK | Completed | 133000 | 77604 | 2018-12-23 | 2019-08-25
LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034397926 — C.C. ROAD NALI NIRMAN KARY GOPAL DHAKAD KE MAKAN SE GENDALAL JHA KE MAKAN TAK | Closed | 93000 | 0 | 2018-08-15
LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034397928 — C.C. ROAD NALI NIRMAN KARY RAMESH DHAKAD KE MAKAN SE GOVINDDAS KUSHWAH KE MAKAN TAK | Completed | 70000 | 49476 | 2019-03-17 | 2019-08-25
LAHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034462803 — C.C. ROAD HARIRAM KE MAKAN SE RAJENDRA DHAKAD KE MAKAN TAK | Completed | 26000 | 23172 | 2019-04-10 | 2019-08-25
LAHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034477735 — C C NALI NIRMAN BADAM JATAV KE MAKAN SE MUSHAB KHAN KE MAKAN TAK | Completed | 59000 | 52800 | 2019-10-16 | 2020-03-02
LAHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034477737 — C C ROAD NIRMAN MIDIL SCHOOL SE KALKA KE MAKAN KI OR | Completed | 81000 | 69696 | 2019-12-23 | 2020-03-02
LAHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034507332 — C C ROAD MIDIL SCHOOL SE KALKA KE MAKAN KIOR | Closed | 0 | 0 | 2019-08-15
LAHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034507719 — C.C. ROAD NIRMAN KARY MIDDLE SCHOOL SE KALKA KE MAKAN KI OR | Physically Completed | 82000 | 12672 | 2019-12-12 | 2020-05-15
LAHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1702006045/RC/22012034525973 — sudur sampark khet sadak nirman bhagwan singh ke khet se nahar ki or gram khuja | Ongoing | 2453574.87 | 2315423.5 | 2020-06-20
LAHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034540367 — सीसी नाला निर्माण कार्य सुरतान कुशवाह के मकान से मरघट की ओर ग्राम खूजा | Completed | 92000 | 92340 | 2020-09-26 | 2022-10-29
LAHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034578978 — सी सी रोड नाली निर्माण कार्य रामसनेही के मकान से गोलू कर्ण के मकान की ओर | Completed | 28000 | 27792 | 2021-08-07 | 2022-01-25
LAHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034578984 — सी सी रोड निर्माण कार्य चरनसेवक के मकान से कामता कुशवाह के मकान की ओर | Completed | 50000 | 49794 | 2021-08-07 | 2022-01-25
LAHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034585240 — सी सी फर्श निर्माण कार्य माध्यमिक विद्यालय परिसर ग्राम खूजा | Closed | 32000 | 0 | 2021-04-14
LAHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Interlocking Paver Block Road for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034620155 — इंटरलोकिंग सीमेंट ब्लाक रोड निर्माण कार्य विंध्यवासिनी माता मंदिर प्रांगण में (पार्ट-1) ग्राम खूजा | Ongoing | 1447000 | 68952 | 2022-11-21
LAHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Interlocking Paver Block Road for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034620157 — इंटरलोकिंग सीमेंट ब्लाक रोड निर्माण कार्य विंध्यवासिनी माता मंदिर प्रांगण में (पार्ट-2) ग्राम खूजा | Ongoing | 1447000 | 84490 | 2022-11-21
LAHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034669797 — सी सी रोड एवं नाली निर्माण कार्य रामजानकी मंदिर से कारसदेव मंदिर की ओर | Ongoing | 41000 | 37798 | 2024-03-16
LAHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034683593 — सी सी रोड एवं नाली निर्माण कार्य कोमल धाकड के मकान से कारसदेव मंदिर की ओर ग्राम खूजा | Ongoing | 57000 | 24920 | 2024-03-16
LAHAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702006045/RC/237 — पंच परमेश्‍वर रमेश गुप्‍ता के मकान से दशरथ्‍ा के मकान की ओर ग्राम पंचायत खूजा 11-2 | Completed | 277000 | 58279.68 | 2012-09-20 | 2014-08-22
LAHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Multi Unit Toilets for School / Construction of Multi Unit Toilets for School | Construction of Toilets | 1702006045/RS/22012034571782 — नवीन सामुदायिक स्वच्छता परिसर निर्माण कार्य मिडिल स्कूल ग्राउंड ग्राम पंचायत खूजा | Completed | 43000 | 41688 | 2021-11-10 | 2023-12-11
LAHAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702006045/WC/22012034384111 — Talab Nirman | Closed | 0 | 0 | 2018-04-01
LAHAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702006045/WC/22012034437653 — Talab Nirman | Closed | 0 | 0 | 2019-04-01
LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1702006045/WC/22012034697873 — डग पौंड निर्माण कार्य ग्राम पंचायत खूजा | Closed | 1499062.18 | 0 | 2021-04-14
LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702006045/WC/22012034765642 — रूफ वाटर हार्वेस्टिंग आगनवाड़ी भवन खूजा | Closed | 0 | 0 | 2021-04-14
LAHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702006045/WH/22012034439490 — कुम्हरगढ़ा तालाब मरम्मत कार्य ग्राम खूजा | Physically Completed | 271000 | 185466 | 2021-02-16 | 2026-04-18
LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Repair & Maintenance of Fishery Pond for Community | Repair & maint of Pond/ Tank | 1702006045/WH/22012034456734 — तालाब जीर्णोद्वार कार्य हरिमोहन सविता के पास खूजा | Ongoing | 48412.04 | 5922 | 2022-02-14