## Work List
Exported on: 2026-10-15 09:53:28
Filters applied:
Data source: VBGRAMG
District: BHIND
Block: All
Panchayat: KHOOJA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
LAHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702006045/AV/22012034509634 — kabrastan nirman khuja | Ongoing | 324542.88 | 0 | 2020-05-30
LAHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Flood Diversion Drain for Community | Works for Flood Control and Protection | 1702006045/FP/22012034637315 — सी सी नाला निर्माण कार्य रामदास गुप्ता के मकान से कल्लू के मकान की ओर | Ongoing | 77000 | 0 | 2024-02-14
LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5574043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128782786 | Ongoing | 27000 | 0 | 2025-07-28
LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5574044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128786401 | Approved | 27000 | 0 | 2025-03-15
LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5574045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128794053 | Approved | 27000 | 0 | 2025-03-21
LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5574046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128795158 | Ongoing | 27000 | 0 | 2026-10-04
LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5574179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127914432 | Ongoing | 27000 | 0 | 2025-07-21
LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5574677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126796208 | Approved | 27000 | 0 | 2025-03-15
LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5574832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127120364 | Ongoing | 27000 | 0 | 2025-08-11
LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5574913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129484513 | Ongoing | 27000 | 0 | 2025-07-14
LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5574915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129574434 | Ongoing | 27000 | 0 | 2025-07-14
LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5575331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128871009 | Approved | 27000 | 0 | 2025-03-15
LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5575832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129530018 | Ongoing | 27000 | 0 | 2025-08-04
LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5575848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106674536 | Ongoing | 27000 | 5100 | 2025-07-28
LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5575928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131211299 | Approved | 27000 | 0 | 2025-03-21
LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5685319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125831671 | Approved | 27000 | 0 | 2025-03-21
LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5685404 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118028787 | Ongoing | 27000 | 1800 | 2026-09-20
LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006045/IF/IAY/5724487 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128871321 | Approved | 27000 | 0 | 2025-05-13
LAHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1702006045/RC/22012034525973 — sudur sampark khet sadak nirman bhagwan singh ke khet se nahar ki or gram khuja | Ongoing | 2453574.87 | 0 | 2020-06-20
LAHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Interlocking Paver Block Road for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034620155 — इंटरलोकिंग सीमेंट ब्लाक रोड निर्माण कार्य विंध्यवासिनी माता मंदिर प्रांगण में (पार्ट-1) ग्राम खूजा | Ongoing | 1447000 | 0 | 2022-11-21
LAHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Interlocking Paver Block Road for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034620157 — इंटरलोकिंग सीमेंट ब्लाक रोड निर्माण कार्य विंध्यवासिनी माता मंदिर प्रांगण में (पार्ट-2) ग्राम खूजा | Ongoing | 1447000 | 0 | 2022-11-21
LAHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034669797 — सी सी रोड एवं नाली निर्माण कार्य रामजानकी मंदिर से कारसदेव मंदिर की ओर | Ongoing | 41000 | 0 | 2024-03-16
LAHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702006045/RC/22012034683593 — सी सी रोड एवं नाली निर्माण कार्य कोमल धाकड के मकान से कारसदेव मंदिर की ओर ग्राम खूजा | Ongoing | 57000 | 0 | 2024-03-16
LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Repair & Maintenance of Fishery Pond for Community | Repair & maint of Pond/ Tank | 1702006045/WH/22012034456734 — तालाब जीर्णोद्वार कार्य हरिमोहन सविता के पास खूजा | Ongoing | 48412.04 | 0 | 2022-02-14