## Work List
Exported on: 2026-09-09 02:49:30
Filters applied:
Data source: VBGRAMG
District: GWALIOR
Block: All
Panchayat: LIDHORA(P)
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DABRA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kharanja (brick/stone) Roads for Comm / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1703003063/AV/22012034511382 — CPW Nirmad karya govt.p school babupur | Ongoing | 544100 | 0 | 2020-07-06
DABRA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1703003063/AV/22012034653721 — shanti dham nirmad lidhora | Ongoing | 330972.38 | 0 | 2024-03-11
DABRA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1703003063/DP/22012034595121 — Amrit vatika rajamaharaja prangan babupur | Ongoing | 55847.4 | 0 | 2023-08-28
DABRA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1703003063/IF/22012034428265 — samudayak plantation govt.m.s.pragan k piche babupur | Ongoing | 335000 | 0 | 2018-10-01
DABRA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/22012034854343 — बाढ़ ग्रस्त उप आवास योजना रविन्द्र/चिंटूराम जाटव लिधौरा | Ongoing | 17370 | 0 | 2021-09-06
DABRA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/22012034854395 — बाढ़ ग्रस्त उप आवास योजना लच्छो /बादाम सिंह नाई लिधौरा | Ongoing | 17370 | 0 | 2021-09-06
DABRA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/22012034855970 — बाढ़ ग्रस्त उप आवास योजना रामकिशन/छिम्मा कोरी बाबूपुर | Ongoing | 17370 | 0 | 2021-10-11
DABRA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/22012034856016 — बाढ़ ग्रस्त उप आवास योजना रामकुमार/गंगूराम कोरी बाबूपुर | Ongoing | 17370 | 0 | 2021-11-01
DABRA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/22012034861559 — बाढ़ ग्रस्त उप आवास योजना गिरधारी/ रामकिशन गिरधारी/ रामकिशन | Ongoing | 17370 | 0 | 2021-11-08
DABRA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/22012034862805 — बाढ़ ग्रस्त उप आवास योजना सूरज सिंह/कारन सिंह बाबूपुर | Ongoing | 17370 | 0 | 2021-10-18
DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703003063/IF/22012035355889 — khet latav nirmad karya gomti k khet per virrat | Approved | 0 | 0 | 2025-04-14
DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703003063/IF/22012035369561 — JGSA2025 Khet talav nirmad gomti baghel/mangal singh k ktet per virrat | New | 0 | 0 | 2025-04-14
DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703003063/IF/22012035467058 — JGSA 2025 KHET TALAV ANJLI BAGHEL/RANJIT K KHET PER LIDHORA | Approved | 0 | 0 | 2025-04-14
DABRA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/IAY/1892413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4199033 | Approved | 27000 | 0 | 2018-07-09
DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/IAY/5248317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124090913 | Physically Completed | 23490 | 0 | 2025-08-11 | 2026-08-02
DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/IAY/5316104 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146066633 | Ongoing | 27000 | 0 | 2025-04-28
DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/IAY/5702201 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146582625 | Ongoing | 27000 | 0 | 2026-01-12
DABRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/IAY/5967250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144313007 | Ongoing | 27000 | 0 | 2026-05-18
DABRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/IAY/5967251 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144313091 | Ongoing | 27000 | 1200 | 2026-05-18
DABRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/IAY/5967418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144040174 | Ongoing | 27000 | 0 | 2026-05-18
DABRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/IAY/5967593 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124088517 | Ongoing | 27000 | 0 | 2026-05-18
DABRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/IAY/5967832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127018922 | Ongoing | 27000 | 0 | 2026-05-18
DABRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/IAY/5967988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117653476 | Ongoing | 27000 | 0 | 2026-04-06
DABRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/IAY/5967989 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117653782 | Ongoing | 27000 | 0 | 2026-04-06
DABRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/IAY/5968227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142184918 | Ongoing | 27000 | 0 | 2026-04-06
DABRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/IAY/5968228 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142185182 | Ongoing | 27000 | 0 | 2026-04-13
DABRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/IAY/5968229 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142186402 | Ongoing | 27000 | 0 | 2026-06-01
DABRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/IAY/6231032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142183941 | Ongoing | 27000 | 0 | 2026-07-06
DABRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/IAY/6231036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146963607 | Ongoing | 23490 | 0 | 2026-07-06
DABRA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/IAY/71675 — Construction of IAY House -IAY REG. NO. MP-03-003-063-002/10 | Approved | 27000 | 0 | 2015-07-06
DABRA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703003063/IF/IAY/71676 — Construction of IAY House -IAY REG. NO. MP-03-003-063-003/69 | Approved | 27000 | 0 | 2015-07-06
DABRA | 2021-2022 | D--RURAL INFRASTUCTURE / Land Development | Drainage of Waterlogged Land for Community / Drainage of Community Waterlogged Land | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1703003063/LD/22012034567218 — singel pipe puliya nirmad sultan singh baghelk khet k pass babupur | Ongoing | 15000 | 0 | 2021-09-13
DABRA | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1703003063/PG/22012034312097 — grameen krinanakan(khel maidan)virrat | Ongoing | 186000 | 0 | 2017-06-05
DABRA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1703003063/RS/22012034506696 — ग्राम पंचायत लिधौरा में नवीन सामुदायिक स्वास्थ्य परिसर निर्माण कार्य पंचायत भवन के पास लिधौरा | Ongoing | 158000 | 0 | 2021-02-08
DABRA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703003063/WC/22012034295927 — khet talav nirmad meena w/o mehrwan k khet per lidhora | Ongoing | 85000 | 0 | 2016-06-13
DABRA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1703003063/WC/22012034295931 — khet talav nirmad mahadevi w/o rameshwar-babupur | Ongoing | 85000 | 0 | 2016-06-13
DABRA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703003063/WC/22012034295943 — kheth talav nirmad chunilal/navla -babupur | Ongoing | 85000 | 0 | 2016-06-13
DABRA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1703003063/WC/22012034445318 — naveen talav nirmad gouchar bhumi k pass babupur | Ongoing | 851000 | 0 | 2019-03-11
DABRA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1703003063/WC/22012034775651 — CRT सामुदायिक सोक पिट यात्री प्रतीक्षालय हैण्ड पम्प विर्राट | Ongoing | 11215 | 0 | 2021-07-05
DABRA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703003063/WC/22012035208009 — loose bolder nadi pul k pass lidhora | Approved | 198445.19 | 0 | 2024-06-15
DABRA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703003063/WC/22012035208023 — loose bolder pancham baghel k khet per virrat | Approved | 198445.19 | 0 | 2024-06-15
DABRA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703003063/WC/22012035265897 — loose bolder nirmad karya nadi pul k pass lidhora | Approved | 0 | 0 | 2025-04-14
DABRA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703003063/WC/22012035271955 — JUSA LOUSE BOLDER NIRMAD KARYA NADI K PASS LIDHORA | Approved | 0 | 0 | 2025-04-14
DABRA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1703003063/WC/22012035272111 — JGSA2025 loose boulder nirmad sindh nadi pul k pass lidhora | Approved | 0 | 0 | 2025-04-14
DABRA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1703003063/WC/22012035300197 — JGSA 2025 DEGWELL HARJAN COLANY K PASS LIDHORA | Approved | 0 | 0 | 2025-04-14