## Work List
Exported on: 2026-09-06 15:55:29
Filters applied:
Data source: VBGRAMG
District: GWALIOR
Block: All
Panchayat: PALAYCHHA(P)
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHITARWAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004018/IF/IAY/638580 — Construction of IAY House -IAY REG. NO. MP2370245 | Approved | 27000 | 0 | 2017-02-11
BHITARWAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1703004041/DP/22012034496083 — C.P.W. PURANA PANCHAYAT BHAVAN PALAYCHHA | Ongoing | 169500 | 0 | 2020-09-17
BHITARWAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1703004041/DP/22012034496084 — C.P.W.MASJID WALI KABRISTAN PALAYCHHA | Ongoing | 880500 | 0 | 2020-09-17
BHITARWAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1703004041/DP/22012034555998 — BLOCK PLANTATION HANUMAN MANDIR PARISAR BAMOR | Ongoing | 713191.92 | 0 | 2022-10-13
BHITARWAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1703004041/DP/22012034556343 — BLOCK PLANTATION KARYA KHEL MEDAN KE PASS PALAYCHHA | Ongoing | 713191.92 | 0 | 2022-10-06
BHITARWAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1703004041/DP/22012034563639 — BLOCK PLANTATION KARYA KHEL MEDAN KE PASS PALAYCHHA 2 | Ongoing | 715191.92 | 0 | 2022-11-18
BHITARWAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1703004041/DP/22012034567735 — plantation karya amrit sarovar bamor ke band par bamor palaychha | Ongoing | 409718.19 | 0 | 2023-01-19
BHITARWAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1703004041/DP/22012034567738 — PLANTATION KARYA AMRIT SAROVAR KE PASS ROAD KINARE PAR BAMOR 2 | Ongoing | 409718.19 | 0 | 2022-11-18
BHITARWAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1703004041/DP/22012034567739 — PLANTATION KARYA AMRIT SAROVAR BAMOR KE PASS NAALE PAR BAMOR PALAYCHHA 3 | Ongoing | 409718.19 | 0 | 2023-01-19
BHITARWAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1703004041/DP/22012034567740 — PALNTATION KARYA AMRIT SAROVAR BANJAR KE KINARE PAR BAMOR PALAYCHHA 4 | Ongoing | 409718.19 | 0 | 2022-11-16
BHITARWAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1703004041/DP/22012034576769 — Plantation Karya Karan Singh ke Khet se siddheswar Ghat ki Or Nadi Kinare par Palayachha | Ongoing | 431606.07 | 0 | 2023-08-10
BHITARWAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1703004041/DP/22012034587609 — Amrat Vatika Plantetion Middile School Parisar Palayachha | Ongoing | 55847.4 | 0 | 2023-08-24
BHITARWAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1703004041/IF/22012034584821 — NIJI KHET ME FALODHYAN- KHEMULAL/RAMRATAN | Ongoing | 144171 | 0 | 2020-09-03
BHITARWAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703004041/IF/22012034713194 — CTR KHET TALAB BEERENDRA SINGH /UDAY SINGH | Ongoing | 337715.44 | 0 | 2021-04-29
BHITARWAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1703004041/IF/22012035184419 — KHET TALAB NIRMAN KARYA MADAN LAL - PALAYACHHA | New | 0 | 0 | 2023-08-16
BHITARWAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1703004041/IF/22012035184420 — KHET TALAB NIRMAN KARYA POHAP SINGH - PALAYACHHA | New | 0 | 0 | 2023-08-16
BHITARWAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1703004041/IF/22012035186235 — KHET TALAB NIRMAN KARYA POHAP SINGH - PALAYACHHA | New | 0 | 0 | 2023-08-16
BHITARWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1703004041/IF/22012035378877 — JGSA 2025 Recharge Structure Rakesh Gurjar Ke Pass Bamor | Approved | 0 | 0 | 2025-04-14
BHITARWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1703004041/IF/22012035379077 — JGSA 2025 Recharge Structure Daddu Ka Kua Palayachha | New | 0 | 0 | 2025-04-14
BHITARWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1703004041/IF/22012035379078 — JGSA 2025 Recharge Structure Daddu Ka Kua Palayachha | Approved | 0 | 0 | 2025-04-14
BHITARWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1703004041/IF/22012035379091 — JGSA 2025 Recharge Structure Balaji Mandir Ke Pass kua Palayachha | Approved | 0 | 0 | 2025-04-14
BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703004041/IF/22012035463006 — JGSA 2025 Khet Talab Madan Singh Kushwah Ke Khet Par Palaychha | Approved | 0 | 0 | 2025-04-14
BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703004041/IF/22012035463028 — JGSA 2025 Khet Talab Nirman Gopal Ke Khet Par Palaychha | Approved | 0 | 0 | 2025-04-14
BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703004041/IF/22012035463044 — JGSA 2025 Khet Talab Narrotam Ke Khet Par Palaychha | Approved | 0 | 0 | 2025-04-14
BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1703004041/IF/22012035638815 — Ek Bagiya Maa Ki Nam Bharti / bachan Singh | Ongoing | 262863.2 | 0 | 2026-01-02
BHITARWAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/127380 — Construction of IAY House -IAY REG. NO. MP-03-004-041-002/4 | Approved | 27000 | 0 | 2015-06-01
BHITARWAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/1748610 — Construction of IAY House -IAY REG. NO. MP4034192 | Ongoing | 27000 | 0 | 2018-09-20
BHITARWAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/1748783 — Construction of IAY House -IAY REG. NO. MP4036601 | Ongoing | 27000 | 0 | 2018-11-22
BHITARWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/3233548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5685523 | Ongoing | 27000 | 0 | 2022-12-01
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4414078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151757294 | Ongoing | 27000 | 0 | 2024-03-03
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4421388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152008735 | Ongoing | 27000 | 0 | 2024-02-29
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4422105 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151757504 | Ongoing | 27000 | 0 | 2024-03-03
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4422136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151757577 | Ongoing | 27000 | 0 | 2024-03-04
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4422168 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151757675 | Ongoing | 27000 | 0 | 2024-02-29
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4422201 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151757772 | Ongoing | 27000 | 0 | 2024-03-03
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4422222 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151757845 | Ongoing | 27000 | 0 | 2024-03-03
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461892 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151768807 | Ongoing | 27000 | 0 | 2024-03-04
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152009754 | Ongoing | 27000 | 0 | 2024-03-10
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461904 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152009918 | Ongoing | 27000 | 0 | 2024-03-03
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461906 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152010642 | Ongoing | 27000 | 0 | 2024-04-11
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152010670 | Ongoing | 27000 | 0 | 2024-03-04
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152012034 | Ongoing | 27000 | 0 | 2024-03-10
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152012132 | Approved | 27000 | 0 | 2024-01-14
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152012198 | Approved | 27000 | 0 | 2024-02-08
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152012227 | Ongoing | 27000 | 0 | 2024-11-14
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461916 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152012488 | Ongoing | 27000 | 0 | 2024-03-04
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461917 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152012572 | Approved | 27000 | 0 | 2024-02-08
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461918 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152012613 | Ongoing | 27000 | 0 | 2024-03-04
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461919 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152012724 | Ongoing | 27000 | 0 | 2024-08-29
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152012970 | Ongoing | 27000 | 0 | 2024-03-03
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461921 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013059 | Approved | 27000 | 0 | 2024-01-14
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013082 | Ongoing | 27000 | 0 | 2024-03-10
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152014030 | Ongoing | 27000 | 0 | 2024-03-04
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461927 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152014055 | Ongoing | 27000 | 0 | 2024-03-04
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152014070 | Approved | 27000 | 0 | 2024-01-14
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461929 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152014090 | Approved | 27000 | 0 | 2024-01-14
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152014120 | Ongoing | 27000 | 0 | 2024-03-10
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152014126 | Ongoing | 27000 | 0 | 2024-03-10
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152014401 | Approved | 27000 | 0 | 2024-01-14
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461943 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152014637 | Ongoing | 27000 | 0 | 2024-03-04
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461948 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152014976 | Ongoing | 27000 | 0 | 2024-03-03
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152015018 | Ongoing | 27000 | 0 | 2024-03-03
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461975 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152019040 | Ongoing | 27000 | 0 | 2024-03-10
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4461976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152019063 | Ongoing | 27000 | 0 | 2024-03-04
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4467336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151757326 | Ongoing | 27000 | 0 | 2024-04-11
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4468887 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152012060 | Ongoing | 27000 | 0 | 2024-03-10
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4481312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152015064 | Ongoing | 27000 | 0 | 2024-08-29
BHITARWAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4494744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013015 | Approved | 27000 | 0 | 2024-02-24
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4496853 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152014877 | Approved | 27000 | 0 | 2024-06-25
BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4743027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113823228 | Ongoing | 27000 | 0 | 2026-01-16
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4743031 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113823918 | Ongoing | 27000 | 0 | 2025-01-02
BHITARWAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/475733 — Construction of IAY House -IAY REG. NO. MP1911928 | Ongoing | 27000 | 0 | 2018-09-06
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4795025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147044571 | Approved | 27000 | 0 | 2024-09-30
BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4798213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148785103 | Ongoing | 27000 | 0 | 2026-01-16
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4798777 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148819631 | Ongoing | 27000 | 0 | 2025-01-02
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4798819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148830866 | Approved | 27000 | 0 | 2024-09-14
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4799007 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148905592 | Ongoing | 27000 | 0 | 2025-01-02
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4799808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148925078 | Ongoing | 27000 | 0 | 2025-01-02
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4799826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148929608 | Ongoing | 27000 | 0 | 2025-01-02
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4799869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148950138 | Ongoing | 27000 | 0 | 2025-01-23
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4801163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151257424 | Approved | 27000 | 0 | 2024-10-14
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/4859978 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151245669 | Approved | 27000 | 0 | 2024-09-30
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/5359201 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148492639 | Approved | 27000 | 0 | 2025-03-03
BHITARWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/5505105 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113823549 | Ongoing | 27000 | 3600 | 2026-06-18
BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/5506375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151326779 | Ongoing | 27000 | 3600 | 2026-01-16
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/5507503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148895029 | Approved | 27000 | 0 | 2025-03-03
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/5513146 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148414122 | Approved | 27000 | 0 | 2025-03-03
BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/5591201 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147044432 | Ongoing | 27000 | 0 | 2025-12-04
BHITARWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/5591534 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148495397 | Ongoing | 27000 | 3600 | 2026-06-18
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/5591922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148895082 | Approved | 27000 | 0 | 2025-02-14
BHITARWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/5592169 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148785101 | Ongoing | 27000 | 0 | 2026-06-18
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/5592564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145371843 | Approved | 27000 | 0 | 2025-03-03
BHITARWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/5592642 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149552244 | Ongoing | 27000 | 0 | 2026-06-18
BHITARWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/5855959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113823345 | Ongoing | 27000 | 1800 | 2026-07-10
BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/5855960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113823848 | Approved | 27000 | 0 | 2025-05-24
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/5856044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148495467 | Approved | 27000 | 0 | 2025-03-03
BHITARWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/5856109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148819040 | Ongoing | 27000 | 0 | 2026-06-18
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/5856390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148813619 | Approved | 27000 | 0 | 2025-02-14
BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/6236058 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151274971 | Approved | 27000 | 0 | 2026-02-16
BHITARWAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/6236539 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151327005 | Ongoing | 27000 | 0 | 2026-07-10
BHITARWAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/71871 — Construction of IAY House -IAY REG. NO. MP-03-004-041-001/10 | Approved | 27000 | 0 | 2015-06-01
BHITARWAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/71872 — Construction of IAY House -IAY REG. NO. MP-03-004-041-001/19 | Approved | 27000 | 0 | 2015-07-06
BHITARWAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/71873 — Construction of IAY House -IAY REG. NO. MP-03-004-041-001/1p | Approved | 27000 | 0 | 2015-06-01
BHITARWAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/71874 — Construction of IAY House -IAY REG. NO. MP-03-004-041-001/43 | Approved | 27000 | 0 | 2015-06-01
BHITARWAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/71875 — Construction of IAY House -IAY REG. NO. MP-03-004-041-001/45 | Approved | 27000 | 0 | 2015-07-06
BHITARWAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/71876 — Construction of IAY House -IAY REG. NO. MP-03-004-041-002/1 | Approved | 27000 | 0 | 2015-06-01
BHITARWAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004041/IF/IAY/743452 — Construction of IAY House -IAY REG. NO. MP2330008 | Ongoing | 27000 | 0 | 2017-06-22
BHITARWAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004041/RC/22012034849369 — Cement concrete road nirmanmain road se Hotam singh and Bhoop singh parihar | Approved | 44000 | 0 | 2025-06-05
BHITARWAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004041/RC/22012034849499 — Cement concrete road with nali nirman main road se Ghansuram and andi ki or | Approved | 44000 | 0 | 2025-06-05
BHITARWAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004041/RC/22012034849500 — Cement concrete road with nali nirman main road dp se sahid ke ghar ki or | Approved | 50000 | 0 | 2025-06-05
BHITARWAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1703004041/RC/22012034849501 — Cement concrete road with nali nirman main road se masjid ki or | Approved | 54000 | 0 | 2025-06-05
BHITARWAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703004041/RS/22012034503001 — Nali Nirman Bhupendra Singh ke ghars e Khadi ki or | Ongoing | 1429718 | 0 | 2020-12-24
BHITARWAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1703004041/RS/22012034676544 — Nali Nirman Madanlal ke Ghar se Nadi ki Or Palaychha | Ongoing | 303400 | 0 | 2023-02-09
BHITARWAR | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1703004041/WC/22012034584155 — Nala DIvirsion Kadam singh se Nadi ki or | Ongoing | 542724.33 | 0 | 2020-12-24
BHITARWAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair maint of Stone boulder Gully Plugs for Comm / Repair and maintenance of Stone boulder Gully Plugs for Community | Repair & maint of Water Harvesting Structures | 1703004041/WC/22012034694111 — CTR Guly plug thakur baba ki taraf nale par 5 | Ongoing | 19047.38 | 0 | 2021-07-08
BHITARWAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair maint of Stone boulder Gully Plugs for Comm / Repair and maintenance of Stone boulder Gully Plugs for Community | Repair & maint of Water Harvesting Structures | 1703004041/WC/22012034698292 — CTR Gali plug thakur baba ki taraf nale par 6 | Ongoing | 19047.38 | 0 | 2021-07-08
BHITARWAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair maint of Stone boulder Gully Plugs for Comm / Repair and maintenance of Stone boulder Gully Plugs for Community | Repair & maint of Water Harvesting Structures | 1703004041/WC/22012034698302 — CTR Gali plug thakur baba ki taraf nale par 8 | Ongoing | 19047.38 | 0 | 2021-07-08
BHITARWAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair maint of Stone boulder Gully Plugs for Comm / Repair and maintenance of Stone boulder Gully Plugs for Community | Repair & maint of Water Harvesting Structures | 1703004041/WC/22012034698310 — CTR Gali plug thakur baba ki taraf nale par 9 | Ongoing | 19047.38 | 0 | 2021-07-08
BHITARWAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1703004041/WC/22012034740958 — CTR Loose Boulder Balveer ke khet ke pass | Ongoing | 586985.17 | 0 | 2021-12-02