## Work List
Exported on: 2026-09-13 15:08:25
Filters applied:
Data source: VBGRAMG
District: GWALIOR
Block: All
Panchayat: BASODI(P)
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHITARWAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004056/IF/22012034425881 — NADEP NIRMAN CHOKHESINGH/RAGHUNATH | Ongoing | 17000 | 0 | 2018-08-20
BHITARWAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004056/IF/22012034425884 — NADEP NIRMAN CHHOTA/DUBRIYA | Ongoing | 17000 | 0 | 2018-08-20
BHITARWAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004056/IF/22012034425890 — NADEP NIRMAN DHARMENDRA/CHHAUA | Ongoing | 17000 | 0 | 2018-09-24
BHITARWAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004056/IF/22012034425892 — NADEP NIRMAN SIRNAM/DHANIRAM | Ongoing | 17000 | 0 | 2018-08-06
BHITARWAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004056/IF/22012034425895 — NADEP NIRMAN GYANSINGH/GOPAL | Ongoing | 17000 | 0 | 2018-08-06
BHITARWAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004056/IF/22012034425896 — NADEP NIRMAN KAMLSIGH/MACHALSINGH | Ongoing | 17000 | 0 | 2018-08-06
BHITARWAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004056/IF/22012034425897 — NADEP NIRMAN JAGNNATH/DHANIRAM | Ongoing | 17000 | 0 | 2018-08-06
BHITARWAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004056/IF/22012034425898 — NADEP NIRMAN BHAGWATSHARAN/KAILASH | Ongoing | 17000 | 0 | 2018-09-24
BHITARWAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004056/IF/22012034425900 — NADEP NIRMAN RAJBAHADUR/LAKHANSINGH | Ongoing | 17000 | 0 | 2018-09-24
BHITARWAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004056/IF/22012034425901 — NADEP NIRMAN JAHARSINGH/GAJUA | Ongoing | 17000 | 0 | 2018-08-06
BHITARWAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004056/IF/22012034425949 — NADEP NIRMAN SRDARSINGH/GYASIYA | Ongoing | 17000 | 0 | 2018-10-01
BHITARWAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004056/IF/22012034425987 — NADEP NIRMAN JANAKSINGH/BALLABHSINGH | Ongoing | 17000 | 0 | 2018-10-01
BHITARWAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004056/IF/22012034425989 — NADEP NIRMAN BHURA/RAMESHVAR | Ongoing | 17000 | 0 | 2018-09-24
BHITARWAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1703004056/IF/22012034425990 — NADEP NIRMAN BHUPENDRA/RAMPRASAD | Ongoing | 17000 | 0 | 2018-08-20
BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703004056/IF/22012035378594 — JGSA 2025 Khet Talab Nirman Mohar Singh kamariya / Shankar Singh Basodi | Approved | 0 | 0 | 2025-04-14
BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703004056/IF/22012035465303 — JGSA 2025 Khet Talab Nirman Veerendra Singh Yadav / Seetaram Bansodi | Approved | 0 | 0 | 2025-04-14
BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703004056/IF/22012035554892 — JGSA 2025 Khet Talab Nirman Lachhiram Batham / Radhelal Machhariya | Approved | 450885.64 | 0 | 2025-04-14
BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703004056/IF/22012035554902 — JGSA 2025 Khet Talab Nirman Ajmer Jatav / Dubariya Basodi | Approved | 450885.64 | 0 | 2025-04-14
BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703004056/IF/22012035554944 — JGSA 2025 Khet Talab Nirman Shailendra kamariya / Balbhadra basodi | Approved | 147621.16 | 0 | 2025-04-14
BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1703004056/IF/22012035554948 — JGSA 2025 Khet Talab Nirman Khemraj Kushwah / Lalu basodi | Approved | 0 | 0 | 2025-04-14
BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1703004056/IF/22012035624764 — EK BAGIYA MAA KE NAME SEETA SHARMA/PRAMOD MACHHARIYA MP03004056/002/358 | New | 0 | 0 | 2025-08-15
BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1703004056/IF/22012035625465 — EK BAGIYA MAA KE NAME SEETA SHARMA/PRAMOD MACHHARIYA MP03004056/002/358 | Approved | 0 | 0 | 2025-08-15
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004056/IF/IAY/4519765 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114734586 | Ongoing | 27000 | 0 | 2025-02-17
BHITARWAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004056/IF/IAY/4790326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127108910 | Approved | 27000 | 0 | 2024-10-01
BHITARWAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004056/IF/IAY/54497 — Construction of IAY House -IAY REG. NO. MP-03-004-056-002/18 | Approved | 27000 | 0 | 2015-06-01
BHITARWAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004056/IF/IAY/637015 — Construction of IAY House -IAY REG. NO. MP1888596 | Approved | 27000 | 0 | 2017-02-10
BHITARWAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1703004056/IF/IAY/71925 — Construction of IAY House -IAY REG. NO. MP-03-004-056-001/62 | Approved | 27000 | 0 | 2015-06-01
BHITARWAR | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1703004056/RC/22012034854012 — gravel road nirmad basodi main road se gram machariya ki or | Ongoing | 1856396.51 | 2400 | 2026-08-06