## Work List
Exported on: 2026-10-27 16:57:05
Filters applied:
Data source: MGNREGA + VBGRAMG
District: DATIA
Block: All
Panchayat: MARSENIKHURD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1704001025/AV/22012034368957 — shanti dham nirmad kary bashi malik | Completed | 180000 | 172476.7 | 2017-10-11 | 2018-03-10
SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1704001025/AV/22012034369115 — shanti dham nirmad kary | Closed | 0 | 0 | 2017-08-10
SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1704001025/AV/22012034369116 — shanti dham nirmad kary bhadur pur | Closed | 180000 | 0 | 2017-08-10
SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Prduction of building material (Comm) / Production of building material for Community | Construction of Other Community Building/Assets | 1704001025/AV/22012034534265 — Gau shala nirman kary marseni khurd | Completed | 3784582.21 | 3775390.74 | 2020-09-30 | 2023-03-12
SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1704001025/AV/22012034546283 — Charahgah Nirmad karya | Ongoing | 1481213.55 | 395292 | 2021-01-27
SEONDHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Goat Shelter for Community / Construction of Goat Shelter for Community | Goat Shelter | 1704001025/AV/22012034565247 — CTR gauchar nirman work jhore ke pass | Closed | 0 | 0 | 2021-04-01
SEONDHA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1704001025/AV/22012034577592 — CTR Dayning Hall govt.ps. school marseni khurd | Closed | 19999.16 | 0 | 2021-04-14
SEONDHA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1704001025/AV/22012034579793 — CTR Dayning Hall Ms.school Bashai malik | Closed | 19999.16 | 0 | 2021-04-14
SEONDHA | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1704001025/AV/22012034601465 — CTR segreshan sed nirman kary marseni khurd | Closed | 0 | 0 | 2021-04-14
SEONDHA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1704001025/AV/22012034653523 — Baundribal Nirman Work Samshan Gram Marsenikhurd | Completed | 35000 | 34476 | 2024-03-13 | 2024-12-25
SEONDHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1704001025/DP/22012034229671 — नाली निर्माण कार्य | Deleted | 0 | 0 | 2016-01-27
SEONDHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001025/DP/22012034445472 — नाला निर्माण कार्य करनसिंह के मकान से अजमेर के मकान की ओर बहादुरपुर | Suspended | 361000 | 176 | 2019-06-05
SEONDHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001025/DP/22012034445628 — नाला निर्माण मंगली के मकान से नंदू के मकान के पीछे तक | Suspended | 361000 | 176 | 2019-06-05
SEONDHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1704001025/DP/22012034581933 — Elovera virksharopan kary gau shala ke pass marseni khurd | Closed | 133212.69 | 0 | 2023-04-14
SEONDHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1704001025/DP/22012034584256 — Meri mati Mera Desh abhiyan ke antargat vraksharopan kary | Closed | 321490.42 | 0 | 2023-04-14
SEONDHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1704001025/DP/22012034584259 — Meri mati Mera Desh abhiyan ke antargat vraksharopan kary gau shala ke pass | Closed | 0 | 0 | 2023-04-14
SEONDHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001025/DP/22012034615794 — nala nirman work main road tiraha se baghel muhalla ki aur | Closed | 136000 | 0 | 2023-04-14
SEONDHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of Feeder Canal for Community / Construction of Feeder Canal for Community | Construction of Canal | 1704001025/IC/22012034882161 — Viraksharopan kary or bhoomi samtalikarankary aganbadi or mandir parisarbahadurpur | Closed | 0 | 0 | 2022-10-02
SEONDHA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Groups / Construction of Irrigation Open Well for Groups | Construction of Well | 1704001025/IC/22012034883958 — Samudayik poshan vatika kaimai mandir ke pass | Closed | 241281.49 | 0 | 2024-01-29
SEONDHA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1704001025/IF/1000009813 — MADBANDHA KESKALI/RAMKISOR | Completed | 25000 | 17520 | 2013-05-08 | 2014-03-30
SEONDHA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1704001025/IF/1000009887 — BUMISILP BALWANT/BHAGIRATH | Deleted | 30000 | 0 | 2013-04-14
SEONDHA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1704001025/IF/1000065287 — pasu sed gyasi/garive | Completed | 84000 | 79432.9 | 2014-01-22 | 2014-07-21
SEONDHA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1704001025/IF/1000067670 — मेढबंधान कार्य कस्‍तुरी/जगदीश | Completed | 44000 | 42486 | 2014-01-29 | 2014-03-30
SEONDHA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1704001025/IF/1000067671 — मेढबंधान कार्य राजेन्‍द्रसिंह,सूरजसिंह,रामप्रताप/ग | Completed | 50000 | 23944 | 2014-01-29 | 2014-03-30
SEONDHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704001025/IF/22012034328718 — Kapildhara Kuan Khet talav Ramsingh/Rateeram Rajput Marseni Khurd | Completed | 230000 | 147664 | 2017-03-22 | 2018-12-30
SEONDHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1704001025/IF/22012034350660 — Plantation Basai malik se nadi ki oer Basai malik | Completed | 335000 | 10224 | 2017-06-20 | 2020-01-01
SEONDHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1704001025/IF/22012034354564 — Plantation Block plantation khasra no. 95 Marseni khurd | Completed | 535000 | 12288 | 2017-06-20 | 2018-03-30
SEONDHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1704001025/IF/22012034361434 — Plantation Kaimai mandir parisar | Completed | 335000 | 71030 | 2017-06-20 | 2021-02-23
SEONDHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Line Plantation Forstry Trees-Individual / Wasteland Line Plantation of Forestry Trees for Individuals | Plantation | 1704001025/IF/22012034423328 — वृक्षारोपण कार्य मरसेनीखुर्द से बसईमलक की ओर रोड किनारे | Completed | 342000 | 135824 | 2018-07-25 | 2022-10-30
SEONDHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Line Plantation Forstry Trees-Individual / Wasteland Line Plantation of Forestry Trees for Individuals | Plantation | 1704001025/IF/22012034423332 — वृक्षारोपण कार्य ग्राम बसईमलक से मरसेनीखुर्द की ओर | Physically Completed | 342000 | 167582 | 2018-07-25 | 2026-06-24
SEONDHA | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1704001025/IF/22012034435685 — नाडेप टांका निर्माण कार्य सीताराम कर्ण मरसेनीखुर्द | Suspended | 26000 | 0 | 2020-01-01
SEONDHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1704001025/IF/22012034473228 — खेत तालाब निर्माण कार्य रायसिंह | Suspended | 91000 | 0 | 2020-01-01
SEONDHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1704001025/IF/22012034473234 — खेत तालाब निर्माण कार्य उर्मिला | Completed | 288000 | 145408 | 2019-05-15 | 2020-07-31
SEONDHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704001025/IF/22012034550234 — Khet talab ramsingh/ratiram | Closed | 0 | 0 | 2020-05-02
SEONDHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1704001025/IF/22012034550305 — Khet talab Ramsingh/Ratiram | Completed | 108814.67 | 88730 | 2020-05-20 | 2020-07-01
SEONDHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704001025/IF/22012034572574 — med bandhan kary balvant parihar | Closed | 0 | 0 | 2020-01-26
SEONDHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704001025/IF/22012034572577 — med bandhan kary tejpal baghel | Completed | 43119.77 | 38000 | 2020-07-01 | 2020-08-25
SEONDHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704001025/IF/22012034572683 — med bandhan kary mangli karn | Closed | 0 | 0 | 2020-01-26
SEONDHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704001025/IF/22012034572688 — med bandhan kary jugal kishor | Closed | 0 | 0 | 2020-01-26
SEONDHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704001025/IF/22012034572696 — med bandhan kary Ramsingh jatav | Suspended | 0 | 0 | 2020-08-19
SEONDHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704001025/IF/22012034584131 — med bandhan kary ludhaka bai | Completed | 29484.62 | 28880 | 2020-09-30 | 2021-03-04
SEONDHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coast Line plntation of Forestry Trees-Individuals / Along the coast Line Plantation of Forestry Trees for Individuals | Plantation | 1704001025/IF/22012034585184 — Faloudhan nirman kary rammilan yadav or anya sahbhagi log | Suspended | 135219.86 | 0 | 2020-08-04
SEONDHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704001025/IF/22012034590383 — med bandhan kary Ramsingh jatav | Suspended | 43823.13 | 0 | 2020-08-19
SEONDHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704001025/IF/22012034590384 — med bandhan kary Ramesh jatav | Completed | 45628.24 | 38950 | 2020-09-30 | 2021-01-22
SEONDHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704001025/IF/22012034590386 — med bandhan kary Rmsingh jatav | Completed | 47433.45 | 39900 | 2020-09-30 | 2020-11-30
SEONDHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704001025/IF/22012034590388 — med bandhan kary balvant parihar | Closed | 49840.29 | 0 | 2020-01-26
SEONDHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1704001025/IF/22012034594197 — Faloudhayan kary Ramcharan baghel | Suspended | 135219.86 | 0 | 2020-08-04
SEONDHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1704001025/IF/22012034594203 — Faloudhan kary bharat singh yadav | Completed | 135219.86 | 65568 | 2020-08-12 | 2026-05-10
SEONDHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Block Plantation of Biodrainage Trees in Fields for Individuals | Plantation | 1704001025/IF/22012034599286 — Faloudhayan kary Banti Rajpoot | Closed | 116265.03 | 0 | 2020-01-26
SEONDHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704001025/IF/22012034617389 — Khet talab nirman kary Jagat Singh jatav | Closed | 0 | 0 | 2020-01-26
SEONDHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Gully Plugs for Individual / Construction of Earthen Gully Plugs for Individuals | Boulder Check/Gully Plug | 1704001025/IF/22012034669058 — Khet talab nirmad karya jagat Singh jatav ke khet par | Closed | 0 | 0 | 2021-01-21
SEONDHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704001025/IF/22012034702977 — CTR khet talab nirman work Jagatsingh jatav/gulli | Completed | 337715.44 | 222915 | 2021-08-26 | 2022-02-25
SEONDHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704001025/IF/22012034702983 — CTR khet talab nirman work Balvant jatav | Closed | 337715.44 | 0 | 2021-04-01
SEONDHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704001025/IF/22012034702986 — CTR khet talab nirman work Ramcharan baghel | Closed | 337715.44 | 0 | 2021-04-01
SEONDHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704001025/IF/22012034702990 — CTR khet talab nirman work ajmer jatav bagerah | Completed | 337715.44 | 127315 | 2021-10-06 | 2026-04-15
SEONDHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704001025/IF/22012034939374 — CTR.khet talab nirman kary vinod baghel | Closed | 0 | 0 | 2022-01-22
SEONDHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704001025/IF/22012034939375 — CTR.khet talab nirman kary vinod baghel | Closed | 0 | 0 | 2022-01-22
SEONDHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704001025/IF/22012034939377 — CTR.khet talab nirman kary vinod baghel | Closed | 0 | 0 | 2022-01-22
SEONDHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704001025/IF/22012034939379 — CTR.khet talab nirman kary vinod baghel | Closed | 0 | 0 | 2022-01-22
SEONDHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704001025/IF/22012034939382 — CTR.khet talab nirman kary Ramcharan baghel | Closed | 0 | 0 | 2022-01-22
SEONDHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1704001025/IF/22012035388286 — Dug well recharge kua nirman kary marseni khurd | New | 0 | 0 | 2025-04-14
SEONDHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1704001025/IF/22012035388768 — Dug well recharge kua nirman kary marseni khurd | Approved | 25899.46 | 0 | 2025-04-14
SEONDHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704001025/IF/22012035406037 — khet talab nirman kary vinod baghel/Ramnath baghel | Completed | 199457.43 | 125280 | 2025-05-02 | 2026-04-15
SEONDHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704001025/IF/22012035406167 — khet talab nirman kary Raguvanshi baghel/pannalal | Completed | 199457.43 | 128151 | 2025-05-02 | 2026-04-15
SEONDHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1704001025/IF/22012035486101 — Dug well recharge pit bahadurpure | Approved | 0 | 0 | 2025-04-14
SEONDHA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1704001025/IF/9926701139 — मेढबंधान कार्य भगवानसिंह/देवी परिहार | Completed | 21000 | 20440 | 2014-02-12 | 2014-03-30
SEONDHA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1704001025/IF/9926701140 — मेढबंधान कार्य बलवंतसिंह/देवी परिहार | Completed | 34000 | 17812 | 2014-02-12 | 2014-03-30
SEONDHA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1704001025/IF/9926724104 — बकरी सेड निर्माण कार्य पहलवान/मनीराम | Completed | 84000 | 56605.99 | 2014-04-16 | 2015-08-18
SEONDHA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1704001025/IF/9993672872 — नाडेप टांका निर्माण कार्य कल्‍यान/मन्‍ने प्रजापति मरसेनीखुर्द | Completed | 25000 | 16481.77 | 2015-08-27 | 2017-10-30
SEONDHA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1704001025/IF/9993699489 — नाडेप टांका निर्माण कार्य निहाल/रघुवीर यादव | Completed | 26000 | 21578 | 2015-12-23 | 2017-10-31
SEONDHA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1704001025/IF/9993718689 — nadep tanka-asharam/jagat singh | Deleted | 0 | 0 | 2016-01-26
SEONDHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1704001025/IF/9993723402 — भूमिशिल्‍प निर्माण कार्य | Deleted | 0 | 0 | 2016-01-26
SEONDHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/1897294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5096819 | Completed | 15660 | 15660 | 2018-08-08 | 2018-11-01
SEONDHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/1897660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5570348 | Completed | 15660 | 15660 | 2018-08-15 | 2018-10-23
SEONDHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/1897664 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5579766 | Completed | 15660 | 15660 | 2018-08-08 | 2018-12-05
SEONDHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/1908893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4218416 | Completed | 15660 | 14790 | 2018-08-15 | 2018-11-01
SEONDHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/1908944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4279985 | Completed | 15660 | 14790 | 2018-08-08 | 2018-11-01
SEONDHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/1909544 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5140793 | Completed | 15660 | 15660 | 2018-08-08 | 2018-12-01
SEONDHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/1912350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5697453 | Completed | 15660 | 15660 | 2018-08-15 | 2018-11-01
SEONDHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/1933896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4501754 | Completed | 15660 | 15660 | 2018-09-26 | 2018-12-01
SEONDHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/2143683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5103418 | Completed | 15840 | 14784 | 2019-07-10 | 2019-11-30
SEONDHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/2150327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5276142 | Completed | 15840 | 14784 | 2019-11-13 | 2020-03-26
SEONDHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/2161326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5549821 | Completed | 15840 | 14784 | 2019-07-10 | 2019-11-30
SEONDHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/217454 — Construction of IAY House -IAY REG. NO. MP1167076 | Completed | 15030 | 14532 | 2017-01-25 | 2018-07-20
SEONDHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/2275419 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2685698 | Completed | 15840 | 14784 | 2019-08-21 | 2019-11-30
SEONDHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/276312 — Construction of IAY House -IAY REG. NO. MP3451554 | Completed | 15030 | 17154 | 2017-01-25 | 2017-12-01
SEONDHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/3027700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5101553 | Completed | 17370 | 16212 | 2021-05-26 | 2022-04-14
SEONDHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/3724548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117994051 | Completed | 18360 | 17544 | 2022-07-11 | 2023-01-14
SEONDHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/3760530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126527320 | Completed | 18360 | 17544 | 2022-12-29 | 2023-08-14
SEONDHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/40344 — Construction of IAY House -IAY REG. NO. MP-04-001-025-003/9 | Completed | 14310 | 8016 | 2016-05-19 | 2018-04-10
SEONDHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1704001025/IF/IAY/416154 — Construction of IAY House -IAY REG. NO. MP1302086 | Approved | 27000 | 0 | 2017-01-17
SEONDHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/4326069 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126531100 | Completed | 18360 | 17136 | 2022-08-17 | 2023-03-12
SEONDHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/4365207 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125981131 | Completed | 18360 | 17442 | 2022-09-28 | 2023-08-14
SEONDHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/4713139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126633507 | Completed | 23490 | 20628 | 2024-10-23 | 2025-07-22
SEONDHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/485569 — Construction of IAY House -IAY REG. NO. MP2070878 | Completed | 15030 | 15480 | 2017-07-19 | 2018-01-22
SEONDHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/4955790 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121577764 | Completed | 23490 | 21924 | 2025-04-02 | 2025-07-22
SEONDHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1704001025/IF/IAY/4957544 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122397573 | Physically Completed | 23490 | 19989 | 2025-03-19 | 2026-08-02
SEONDHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/5315457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125977951 | Completed | 23490 | 21924 | 2025-04-09 | 2026-02-14
SEONDHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/5346162 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125977348 | Completed | 23490 | 21924 | 2025-04-09 | 2025-08-26
SEONDHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/5346180 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125975505 | Completed | 23490 | 21924 | 2025-04-09 | 2026-02-14
SEONDHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/5348065 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121578260 | Completed | 23490 | 21924 | 2025-04-09 | 2025-07-22
SEONDHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1704001025/IF/IAY/5350199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122397912 | Physically Completed | 27000 | 21060 | 2025-04-09 | 2026-09-27
SEONDHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/5354032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125974036 | Completed | 23490 | 21924 | 2025-04-09 | 2026-02-14
SEONDHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/5354033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125976092 | Completed | 23490 | 21924 | 2025-04-09 | 2026-02-14
SEONDHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1704001025/IF/IAY/563747 — Construction of IAY House -IAY REG. NO. MP3798274 | Approved | 27000 | 0 | 2016-12-26
SEONDHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001025/IF/IAY/63690 — Construction of IAY House -IAY REG. NO. MP-04-001-025-003/02 | Completed | 14310 | 8016 | 2016-05-19 | 2018-04-10
SEONDHA | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1704001025/LD/22012034232675 — धांतिधाम निर्माण कार्य मरसेनीखुुर्द | Completed | 992000 | 138918.69 | 2015-10-14 | 2018-04-10
SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1704001025/LD/22012034310551 — Shanti dham Basai malik | Deleted | 180000 | 0 | 2017-04-19
SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1704001025/LD/22012034310553 — Shanti Dham nirman Bahadurpur | Completed | 180000 | 174196.7 | 2017-04-19 | 2018-06-04
SEONDHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1704001025/LD/22012034536392 — Jai Kishan upyojna nirman kary Balvant parihar | Closed | 0 | 0 | 2020-04-14
SEONDHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1704001025/LD/22012034536393 — Jai Kishan upyojana nirman kary Deendayal prajapati | Closed | 0 | 0 | 2020-04-14
SEONDHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1704001025/LD/22012034536394 — Jai Kishan upyojna nirman kary sukhram dhanuk | Closed | 0 | 0 | 2020-04-14
SEONDHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1704001025/LD/22012034536395 — Jai Kishan upyojna nirman kary harvilas jatav | Closed | 0 | 0 | 2020-04-14
SEONDHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1704001025/LD/22012034944687 — samtalikaran nirman kary purana ganv marseni khurd | New | 0 | 0 | 2024-10-02
SEONDHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1704001025/LD/22012034944688 — block virksharopan nirman kary bashai malik | Ongoing | 145050.83 | 87420 | 2025-01-08
SEONDHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1704001025/LD/22012034944689 — samtalikaran nirman kary purana ganv marseni khurd | New | 0 | 0 | 2024-10-02
SEONDHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1704001025/LD/22012034945053 — samtalikaran nirman kary purana ganv marseni khurd | Approved | 0 | 0 | 2024-10-02
SEONDHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1704001025/LD/22012034945273 — samtalikaran nirman kary purana ganv marseni khurd | Ongoing | 375745 | 149382 | 2024-11-27
SEONDHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1704001025/LD/22012034947666 — SAMUDAYIK POSHAN VATIKA GAUSHALA KE PAS | Approved | 0 | 0 | 2024-10-02
SEONDHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1704001025/LD/22012034952323 — जल निकासी कार्य चतुर सिंह के मकानसे कल्‍लू के मकान की ओर बसईमलक | Approved | 13000 | 0 | 2024-08-15
SEONDHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1704001025/LD/22012034952328 — जल निकासी कार्य प्रकाश बघेल के मकान से राजेश के मकान की ओर बसईमलक | Approved | 26000 | 0 | 2024-08-15
SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1704001025/PG/22012034305375 — khel maidan Basai malak | Deleted | 186600 | 0 | 2017-04-19
SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1704001025/PG/22012034305379 — khel maidan Bahadurpur | Deleted | 186600 | 0 | 2017-04-19
SEONDHA | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1704001025/PG/22012034305381 — khel maidan Marseni khurd | Deleted | 186600 | 0 | 2016-10-02
SEONDHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/1043 — सीमेन्‍ट कंक्रीट रोड निर्माण कार्य नाली सहित मुकेश के मकान से गुलाब के मकान की ओर | Completed | 67000 | 50792 | 2012-08-25 | 2012-11-08
SEONDHA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal First coat / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704001025/RC/202 — र्काय का नाम पॅहुच र्माग हरी सोनी के खेत से ग्राम मरसेनीखुर्द सेवडा 202 | Completed | 300000 | 127775.89 | 2007-10-04 | 2013-03-23
SEONDHA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034224724 — सी0सी0रोड नाली न‍िर्माण मुख्‍य सडक से जगदीश बघेल क | Completed | 165000 | 157996 | 2014-07-16 | 2014-12-09
SEONDHA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034225171 — सी0सी0रोड नाली निर्माण मुख्‍य सडक से जगदीश बघेल के मकान तक | Deleted | 164000 | 0 | 2014-04-24
SEONDHA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034291079 — सी0सी0रोड राजाराम बघेल से राममिलन कडेरे की ओर बसईमलक | Completed | 75000 | 61635 | 2015-12-09 | 2016-03-27
SEONDHA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704001025/RC/22012034293237 — आंतरिक पथ निर्माण कार्य रतनगढ माता मार्ग से दाताराम कडेरे के मकान तक | Completed | 262000 | 195335.3 | 2015-12-16 | 2017-10-31
SEONDHA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704001025/RC/22012034306509 — सुदूर सम्‍पक्र कार्य बहादुरपुर तिराहा से मरघट की ओर | Deleted | 682000 | 0 | 2016-12-28
SEONDHA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034322748 — CC road nali nirman | Closed | 0 | 0 | 2016-10-02
SEONDHA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034330823 — सी0सी0रोड सह नाली निर्माण हनुमान जी मंदिर से रघुवंशी बघेल के मकान की ओर | Completed | 85000 | 69508 | 2017-03-15 | 2018-05-04
SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704001025/RC/22012034339117 — Sudoor gram sampark sadak Basaimalak se Dogarpur ki oer | Completed | 581000 | 342645.88 | 2017-05-24 | 2019-03-30
SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034348769 — cc rod atar baghel se rajendra shrma ki or | Completed | 42480 | 40592 | 2017-08-09 | 2018-05-04
SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034351574 — cc rod nali nirmad kary mukhmarg se prakas baghel ke makan tak bhadurpur | Completed | 5760000000 | 56760 | 2017-08-30 | 2018-03-10
SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034359961 — cc rod naliniramd kary rajaram bhagel ke makan se mannu lal jatav ki or marseni khurd | Completed | 2160000000 | 25800 | 2017-09-20 | 2018-03-10
SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034362852 — cc rod nali niramad kary man singh patava ke makan se kuwa tak marseni khurd | Completed | 3628500000 | 35088 | 2017-10-04 | 2018-03-10
SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034370085 — cc road | Closed | 0 | 0 | 2017-04-20
SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704001025/RC/22012034372664 — Sudur sampark Aantrik path (gravel road) Daataram ke makan se marghat ki or basai malak | Closed | 584000 | 0 | 2017-12-05
SEONDHA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034390652 — सी0सी0रोड सह नाली निर्माण कुंआ से रामप्रकाश बघेल के मकान की ओर | Completed | 74500 | 73776 | 2018-07-11 | 2020-07-31
SEONDHA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034393475 — सी0सी0रोड सह नाली निर्माण रघुवंशी बघेल के मकान से शैर की ओर बसईमलक | Completed | 23000 | 21924 | 2018-08-29 | 2018-09-27
SEONDHA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034447170 — c.c.road sah nali nirman work | Closed | 0 | 0 | 2019-01-26
SEONDHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034463060 — सी0सी0रोड सह नाली निर्माझा राधेश्‍याम शर्मा से कुंआ तक | Physically Completed | 74400 | 66000 | 2019-05-15 | 2021-03-25
SEONDHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034463061 — सी0सी0रोड सह नाली निर्माण सर्वेश यादव के मकान से रामसिया यादव के मकान तक | Completed | 23000 | 22352 | 2019-05-15 | 2020-07-31
SEONDHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034513793 — c.c.road | Closed | 0 | 0 | 2020-01-01
SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034535011 — सी0सी0रोड सह नाली निर्माण वीरन जाटव के मकान से शंकर जाटव के मकान तक बहादुरपुर | Completed | 14000 | 12920 | 2020-08-26 | 2020-09-19
SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034535014 — सी0सी0रोड सह नाली निर्माण तुलसी कर्ण के मकान से सूरज परिहार के मकान की ओर मरसेनीखुर्द | Completed | 23250 | 22800 | 2020-08-26 | 2020-09-19
SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034535015 — सी0सी0रोड सह नाली न‍िर्माण शंकर जी के मंद‍िर से गायत्री बढई के मकान की ओर मरसेनीखुर्द | Completed | 23250 | 22990 | 2020-09-02 | 2020-09-19
SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034538076 — सी0सी0रोड सह नाली निर्माण मेन रोड से हरिजन मुहल्‍ला की ओर बहादुर पुर | Closed | 0 | 0 | 2020-04-14
SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034538077 — सी0सी0रोड सह नाली निर्माण मेन रोड से हरिजन मुहल्‍ला की ओर बहादुर पुर | Completed | 30000 | 29830 | 2020-09-16 | 2020-10-08
SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034542408 — सी0सी0रोड सह नाली निर्माण द्वारका प्रसाद नामदेव के मकान से राधेश्‍याम राजपूत के मकान की ओर | Completed | 42000 | 40850 | 2020-09-30 | 2020-12-03
SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034542508 — सी0सी0रोड सह नाली निर्माण लक्ष्‍मीनारायण राजपूत के मकान से राकेश राजपूत के मकान की ओर मरसेनीखुर्द | Completed | 51000 | 30400 | 2020-09-30 | 2021-03-04
SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034542509 — सी0सी0रोड सह नाली निर्माण बलवीर यादव के मकान से रामसिया यादव के मकान की ओर मरसेनीखुर्द | Completed | 32500 | 30780 | 2020-09-30 | 2021-02-12
SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034561858 — सी0सी0रोड सह नाली न‍िर्माण कुंआ से तालाब की ओर | Completed | 56000 | 52440 | 2021-03-10 | 2021-03-31
SEONDHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034581745 — सी0सी0रोड सह नाली निर्माण जगदीश जाटव के मकान से आंगनवाडी की ओर बहादुरपुर | Completed | 60500 | 64848 | 2021-09-22 | 2022-04-13
SEONDHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034581747 — सी0सी0रोड सह नाली निर्माण मेन सी0सी0रोड से घनश्‍याम बघेल के मकान की ओर | Completed | 14000 | 11580 | 2021-09-29 | 2021-11-30
SEONDHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034604482 — c.c.road | Closed | 0 | 0 | 2021-10-02
SEONDHA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704001025/RC/22012034638913 — cc road nirman karya dulichandra ke makan se neelesh karn ke khet ke or | Completed | 57000 | 54145 | 2023-06-21 | 2024-01-18
SEONDHA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001025/RC/22012034645584 — c.c.road sah nali nirman work nilesh karan ke khet se laxminarayan ke makan ki aur marsenikhurd | Completed | 58000 | 56355 | 2023-08-02 | 2024-01-18
SEONDHA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1704001025/RC/ 259 — कार्य का नाम - पहुच मार्ग कार्य ग्राम पंचायत मरसेनीखुर्द 259 | Deleted | 300000 | 0 | 2007-10-04
SEONDHA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1704001025/RC/577 — पहुंचमार्ग मरसैनी खुर्द से नहर की ओर | Completed | 342000 | 104589 | 2007-12-21 | 2015-05-18
SEONDHA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1704001025/RC/931 — पहुंचमार्ग कार्य मुख्‍यसड्क से अजमेर के खेत तक | Completed | 406000 | 66494 | 2010-10-05 | 2014-12-03
SEONDHA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704001025/RS/22012034261554 — HOME SOCHALAY marsenikurd 1178-82 | Deleted | 27000 | 0 | 2014-08-20
SEONDHA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704001025/RS/22012034261555 — HOME SOCHALAY marsenikurd 1183-87 | Deleted | 27000 | 0 | 2014-08-20
SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1704001025/RS/22012034396833 — शौचालय निमार्ण कार्य माते वाल्मीक | Completed | 12000 | 11940 | 2018-02-14 | 2018-07-01
SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1704001025/RS/22012034399950 — SIYA SHARAN PUJARI KE PM AAWAS PAR SAUCHALAYA NIRMAN KARYA BASAI MALAK (MP1167076) | Closed | 12000 | 0 | 2018-02-21
SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1704001025/RS/22012034399951 — MANGAL SINGH KE PM AAWAS PAR SAUCHALAYA NIRMAN BAHADURPUR(MP2070878) | Closed | 12000 | 0 | 2018-02-21
SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1704001025/RS/22012034399953 — POORAN KE PM AAWAS PAR SAUCHALAY MARSENIKHURD (MP3451554) | Closed | 12000 | 0 | 2018-02-21
SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1704001025/RS/22012034510388 — सामुदायिक स्वछता परिसर निर्माण मरसेनीखुर्द | Completed | 44000 | 43320 | 2021-03-03 | 2021-11-30
SEONDHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001025/WC/22012034295127 — खेत तालाब निर्माण कार्य सिरोवनसिंह बघेल | Deleted | 80000 | 0 | 2016-06-02
SEONDHA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1704001025/WC/22012034323893 — Talab jeedhudhar Bahadurpur | Closed | 0 | 0 | 2017-04-14
SEONDHA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001025/WC/22012034423917 — आरएसएम निर्माण कार्य कैथे वाली नरिया बसईमलक | Completed | 861000 | 795279 | 2018-10-03 | 2019-08-26
SEONDHA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001025/WC/22012034425497 — आरएमएस निर्माण कार्य भूरे वाली नरिया में बसईलमलक | Completed | 590000 | 587320 | 2018-10-20 | 2019-08-26
SEONDHA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001025/WC/22012034425503 — आरएमएस निर्माण कार्य कैथे वाली नरिया में बसईमलक | Suspended | 861000 | 0 | 2018-10-02
SEONDHA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1704001025/WC/22012034425510 — नवीन तालाब निर्माण कार्य गौडे वाली नरिया बसईमलक | Completed | 233000 | 128186 | 2018-10-10 | 2019-06-09
SEONDHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1704001025/WC/22012034577623 — Sokpit nirman kary govt.p.school ke pass marseni kjurd | Closed | 17950.38 | 0 | 2020-01-26
SEONDHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1704001025/WC/22012034577624 — Sokpit nirman kary govt.m.s.ke pass bashai malik | Closed | 17950.38 | 0 | 2020-08-28
SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Gabion Check Dam for Community / Repair and Maintenance of Gabion Check Dam for Community | Repair & Maint of Check Dam/Stop Dam | 1704001025/WC/22012034650497 — CTR Rms.nirman work purane gaion ke pass | Closed | 0 | 0 | 2021-04-01
SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1704001025/WC/22012034650508 — CTR Roof water harvesting samudayik bhawan | Closed | 0 | 0 | 2021-04-01
SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1704001025/WC/22012034650510 — CTR Roof water harvesting aganbadi bhawan | Closed | 0 | 0 | 2021-04-01
SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001025/WC/22012034793465 — CTR R.M.S. nirman kary surendra singh yadav ke khet ke pass marseni khurd | Completed | 1421761.63 | 1391031 | 2021-09-08 | 2023-03-01
SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001025/WC/22012034793467 — CTR R.M.S. nirman kary Ramu Gupta ke khet ke pass bashai malik | Completed | 1421761.63 | 1400749 | 2021-11-03 | 2024-11-30
SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001025/WC/22012034793468 — CTR R.M.S. nirman kary Ramnath Baghel ke khet ke pass bashai malik | Ongoing | 1421761.63 | 1235925.12 | 2021-11-03
SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Fisheries Ponds for Comm / Repair and maintenance of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1704001025/WC/22012034906913 — Talab ka band vistar or sudrikaran | Closed | 0 | 0 | 2022-01-24
SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Fisheries Ponds for Comm / Repair and maintenance of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1704001025/WC/22012034906914 — Talab ka band vistar or sudrikaran | Closed | 0 | 0 | 2022-01-24
SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Fisheries Ponds for Comm / Repair and maintenance of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1704001025/WC/22012034906916 — Talab ka band vistar or sudrikaran | Closed | 0 | 0 | 2022-01-24
SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001025/WC/22012034908029 — Talab ka band vistar or saundrikaran | Closed | 0 | 0 | 2022-01-24
SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001025/WC/22012034908033 — Talab ka band vistar or saundrikaran | Closed | 0 | 0 | 2022-01-24
SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001025/WC/22012034908034 — Talab ka band vistar or saundrikaran | Closed | 0 | 0 | 2022-01-24
SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001025/WC/22012034908035 — Talab ka band vistar or saundrikaran | Closed | 0 | 0 | 2022-01-24
SEONDHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001025/WC/22012035017460 — Talab nirman kary kuwarbaba ke pass bashai malik | Completed | 360853.32 | 206958 | 2022-12-28 | 2024-12-17
SEONDHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001025/WC/22012035025792 — CTR.Talab Nirman Kary shanti dham ke pass | Closed | 0 | 0 | 2022-10-02
SEONDHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001025/WC/22012035025794 — CTR.Talab Nirman Kary karash dev ke pass | Closed | 0 | 0 | 2022-10-02
SEONDHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001025/WC/22012035025795 — CTR.Talab Nirman Kary Gau shala ke samne | Closed | 0 | 0 | 2022-10-02
SEONDHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001025/WC/22012035025796 — CTR.Talab Nirman Kary Gau shala ke samne | Closed | 0 | 0 | 2022-10-02
SEONDHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001025/WC/22012035025797 — CTR.Talab Nirman Kary Gau shala ke samne | Closed | 0 | 0 | 2022-10-02
SEONDHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1704001025/WC/22012035041221 — Talab Nirman Kary Gau shala ke samne marseni khurd | Closed | 0 | 0 | 2023-01-24
SEONDHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001025/WC/22012035074247 — nali nirman karya jagdish ke makan se talab ke or | Closed | 16000 | 0 | 2023-04-01
SEONDHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001025/WC/22012035074251 — nali nirman karya bharat ke makan ke or | Closed | 8000 | 0 | 2023-04-01
SEONDHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001025/WC/22012035084917 — Navin talab nirman kary purane ganv ke pass | Completed | 385261.22 | 163982 | 2023-09-06 | 2024-12-17
SEONDHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1704001025/WC/22012035084918 — Navin talab nirman kary daddu bay ke pass | Ongoing | 1431722.77 | 442 | 2023-09-27
SEONDHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001025/WC/22012035084921 — Navin talab nirman kary gada bali nariya | Closed | 1401617.17 | 0 | 2023-09-27
SEONDHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1704001025/WC/22012035086058 — kachcha Nala Nirman Karya Talab se nahar ki or | Closed | 355724.48 | 0 | 2023-10-05
SEONDHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1704001025/WC/22012035279667 — khet talab nirman kary Raguvanshi baghel | Approved | 199457.43 | 0 | 2025-04-14
SEONDHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1704001025/WC/22012035280023 — khet talab nirman kary vinod baghel etc. | Approved | 199457.43 | 0 | 2025-04-14
SEONDHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1704001025/WC/22012035281621 — Dug well Recharge pit bahadurpure | Approved | 25899.46 | 0 | 2025-04-14
SEONDHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1704001025/WC/22012035282924 — Dug well Recharge pit marseni khurd | Completed | 25899.46 | 23378.93 | 2025-05-06 | 2026-02-14
SEONDHA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001025/WC/579 — तालाब गहरी करण बसईमलिक | Completed | 1509000 | 4500 | 2007-12-26 | 2010-05-13
SEONDHA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1704001025/WC/6529 — सोखता गडडा रामप्रतापत के पास बहादुरपुर | Completed | 6759 | 6300 | 2010-07-13 | 2013-03-30
SEONDHA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001025/WC/664 — सोखता गडडा निर्माण पटवा मोहल्‍ला हेंड पंप के पास | Deleted | 69590 | 4000 | 2008-08-01
SEONDHA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001025/WC/665 — सोखता गडडे का निर्माण नाई मोहल्‍ला हेंड पंप के पास | Deleted | 69590 | 4000 | 2008-08-01
SEONDHA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001025/WC/666 — सोखता गडडे का निर्माण्‍ा तालाब वाले हैंड पंप के पास | Deleted | 69590 | 4000 | 2008-05-10
SEONDHA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001025/WC/667 — सोखता गडडे का निर्माण कारसदेव बाबा वाले हेंड पंप के पास | Deleted | 69590 | 4000 | 2008-07-01
SEONDHA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1704001025/WC/6779 — कपिलधारा कूप निर्माण कार्य हरिविलास जाटव | Completed | 267000 | 265836 | 2011-02-20 | 2014-12-31
SEONDHA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1704001025/WC/6887 — कपिलधारा कूप निर्माण फुन्‍दी / देवी | Completed | 267000 | 193560 | 2011-06-18 | 2013-03-23
SEONDHA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1704001025/WC/VB/22012035332872 — Recharge pits marseni khurd | Approved | 0 | 0 | 2026-08-07
SEONDHA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1704001025/WH/19958916 — talab gahrikaran | Completed | 48087 | 32164 | 2017-05-10 | 2017-11-01
SEONDHA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1704001025/WH/22012034333462 — तालाब बंड विस्‍तार शा0प्रा0वि0के पास मरसेनीखुर्द | Completed | 49000 | 41934 | 2018-06-21 | 2018-10-31
SEONDHA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1704001025/WH/22012034333463 — तालाब बंड विस्‍तार कैंमई माता के पास मरसेनीखुर्द | Completed | 43000 | 46806 | 2018-06-21 | 2018-08-25