## Work List
Exported on: 2026-10-20 04:24:48
Filters applied:
Data source: VBGRAMG
District: DATIA
Block: All
Panchayat: MARSENIKHURD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1704001025/AV/22012034546283 — Charahgah Nirmad karya | Ongoing | 1481213.55 | 0 | 2021-01-27
SEONDHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1704001025/IF/22012035388286 — Dug well recharge kua nirman kary marseni khurd | New | 0 | 0 | 2025-04-14
SEONDHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1704001025/IF/22012035388768 — Dug well recharge kua nirman kary marseni khurd | Approved | 25899.46 | 0 | 2025-04-14
SEONDHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1704001025/IF/22012035486101 — Dug well recharge pit bahadurpure | Approved | 0 | 0 | 2025-04-14
SEONDHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1704001025/IF/IAY/416154 — Construction of IAY House -IAY REG. NO. MP1302086 | Approved | 27000 | 0 | 2017-01-17
SEONDHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1704001025/IF/IAY/4957544 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122397573 | Physically Completed | 23490 | 0 | 2025-03-19 | 2026-08-02
SEONDHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1704001025/IF/IAY/5350199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122397912 | Physically Completed | 27000 | 5400 | 2025-04-09 | 2026-09-27
SEONDHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1704001025/IF/IAY/563747 — Construction of IAY House -IAY REG. NO. MP3798274 | Approved | 27000 | 0 | 2016-12-26
SEONDHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1704001025/LD/22012034944688 — block virksharopan nirman kary bashai malik | Ongoing | 145050.83 | 10200 | 2025-01-08
SEONDHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1704001025/LD/22012034944689 — samtalikaran nirman kary purana ganv marseni khurd | New | 0 | 0 | 2024-10-02
SEONDHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1704001025/LD/22012034945053 — samtalikaran nirman kary purana ganv marseni khurd | Approved | 0 | 0 | 2024-10-02
SEONDHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1704001025/LD/22012034945273 — samtalikaran nirman kary purana ganv marseni khurd | Ongoing | 375745 | 0 | 2024-11-27
SEONDHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1704001025/LD/22012034952323 — जल निकासी कार्य चतुर सिंह के मकानसे कल्‍लू के मकान की ओर बसईमलक | Approved | 13000 | 0 | 2024-08-15
SEONDHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Construction of Drainage Works in Waterlogged Land for Community | Land Development | 1704001025/LD/22012034952328 — जल निकासी कार्य प्रकाश बघेल के मकान से राजेश के मकान की ओर बसईमलक | Approved | 26000 | 0 | 2024-08-15
SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001025/WC/22012034793468 — CTR R.M.S. nirman kary Ramnath Baghel ke khet ke pass bashai malik | Ongoing | 1421761.63 | 0 | 2021-11-03
SEONDHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1704001025/WC/22012035084918 — Navin talab nirman kary daddu bay ke pass | Ongoing | 1431722.77 | 0 | 2023-09-27
SEONDHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1704001025/WC/22012035279667 — khet talab nirman kary Raguvanshi baghel | Approved | 199457.43 | 0 | 2025-04-14
SEONDHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1704001025/WC/22012035280023 — khet talab nirman kary vinod baghel etc. | Approved | 199457.43 | 0 | 2025-04-14
SEONDHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1704001025/WC/22012035281621 — Dug well Recharge pit bahadurpure | Approved | 25899.46 | 0 | 2025-04-14
SEONDHA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1704001025/WC/VB/22012035332872 — Recharge pits marseni khurd | Approved | 0 | 0 | 2026-08-07