## Work List
Exported on: 2026-10-19 00:21:27
Filters applied:
Data source: VBGRAMG
District: DATIA
Block: All
Panchayat: CHANDNI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHANDER | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1704003012/AV/22012034578494 — Maa ki bagiya Nirman New Madhyamik shala Chandni | Ongoing | 16000 | 0 | 2021-07-08
BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1704003012/FP/22012034365083 — Jal nikashi Nala nirman Chandan singh ke makan ke samne se Ashok Kori ke makan ki oar Chandini | Ongoing | 487460.75 | 0 | 2020-09-15
BHANDER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Forestry Trees for Individual | Plantation | 1704003012/IF/22012034590805 — Nandan phlodhan kayre Jasmant Dohare / Narayan Dohare Chandni | Ongoing | 139176.18 | 0 | 2020-08-13
BHANDER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Forestry Trees for Individual | Plantation | 1704003012/IF/22012034590807 — Nandan phlodhan kayre Chatursingh Dohare / Narayan Dohare Chandni | Ongoing | 139176.18 | 0 | 2020-08-13
BHANDER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1704003012/IF/22012034995833 — Khet Talab Nirman Santram/Raghuveer shakya Chandni | Ongoing | 356340.1 | 0 | 2022-05-30
BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1704003012/IF/22012035360527 — Khet Talab Nirman Ramesh/Raghuveer singh Shrivastava Kurgaon,GP Chandni | New | 0 | 0 | 2025-04-01
BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1704003012/IF/IAY/4526344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127681936 | Ongoing | 27000 | 0 | 2025-04-22
BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1704003012/IF/IAY/4713784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126196393 | Physically Completed | 27000 | 3600 | 2025-04-22 | 2026-10-11
BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1704003012/IF/IAY/4714496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127830315 | Ongoing | 27000 | 0 | 2025-04-22
BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1704003012/IF/IAY/4965780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127681573 | Physically Completed | 27000 | 0 | 2025-12-23 | 2026-09-02
BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1704003012/IF/IAY/4966048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127393583 | Ongoing | 27000 | 0 | 2025-06-05
BHANDER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1704003012/IF/IAY/4966051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127394893 | Ongoing | 27000 | 0 | 2026-10-02
BHANDER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1704003012/IF/IAY/4966267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127834892 | Physically Completed | 27000 | 0 | 2026-05-01 | 2026-09-02
BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1704003012/IF/IAY/4966271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127837096 | Physically Completed | 27000 | 0 | 2025-08-04 | 2026-09-02
BHANDER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1704003012/IF/IAY/4968865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128290582 | Physically Completed | 27000 | 0 | 2026-05-01 | 2026-09-02
BHANDER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1704003012/IF/IAY/4970137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128654020 | Approved | 27000 | 0 | 2025-02-19
BHANDER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034364023 — cc rode evm nali nirman chandan ke makan ke samane se prathimik school tak | Ongoing | 19000 | 0 | 2017-11-01
BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1704003012/RC/22012034524825 — Sudoor gram sadak nirman Gram Kurganv se Gram Khuja Distt.Bhind ki seema tak Kurganv | Ongoing | 1759855.99 | 0 | 2020-07-14
BHANDER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034590965 — Cc road avm nali nirman Kurgaon miner se MS School tak chandni 15vitt+nrega | Ongoing | 48000 | 0 | 2022-03-24
BHANDER | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034821846 — Cc road sah nali nirman kary-ramprasad dohre ke makan se ravindra dohre ke makan tak | Approved | 0 | 0 | 2024-06-08
BHANDER | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034837161 — CC Road av nali nirman Hariram Dohare ke makan se Manoj Dohare ke makan ki oar Chandni 05th vit+NRGS | Ongoing | 126000 | 0 | 2025-04-10
BHANDER | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034845078 — CC Road Sah Nali Nirman Karya Gopal Kori Ke Makan Se Hanuman Ji Prangad Ki OR | Ongoing | 162000 | 0 | 2026-08-07
BHANDER | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034847947 — CC road sah nali Shriram Pal ke makan se Hanuman mandir ke Prangan tak Kurganv 05th Vitt GP+N | Approved | 102000 | 0 | 2025-04-14
BHANDER | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Earthen Spur for Community / Construction of Earthen Spur for Community | Construction of Spur | 1704003012/WC/22012035176660 — Nala nirman kary-dwakra kaurav ke makan se arvindra kaurav ke makan tak kurgao | Ongoing | 45000 | 0 | 2024-03-16