## Work List
Exported on: 2026-10-28 10:36:29
Filters applied:
Data source: VBGRAMG
District: GUNA
Block: All
Panchayat: RAMDI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHANCHODA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1706008003/IF/22012035539405 — jgsa 2025 dagwell recharge karaya radheshyam ramdi | New | 0 | 0 | 2025-05-17
CHANCHODA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1706008003/IF/22012035569130 — jgsa 2025 dagwell recharge karaya dhori bai /takat singh ramdi | Approved | 0 | 0 | 2025-04-14
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1706008003/IF/22012035621971 — एक बगिया मॉं के नाम देवकी बाई / दीवान कुशवाह ग्राम रमडी | Approved | 0 | 0 | 2025-08-01
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1706008003/IF/22012035633158 — एक बगिया माँ के नाम रेखाबाई / प्रीतम मीना ग्राम रमडी | Ongoing | 264661.6 | 0 | 2025-11-11
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/5932039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125611857 | Physically Completed | 23490 | 4200 | 2026-04-10 | 2026-08-10
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/5932429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124958117 | Physically Completed | 27000 | 0 | 2026-03-25 | 2026-10-18
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/5932456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125615602 | Physically Completed | 23490 | 0 | 2026-03-25 | 2026-08-03
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/5932582 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122505747 | Physically Completed | 23490 | 0 | 2026-03-25 | 2026-08-03
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/5932856 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122502622 | Completed | 23490 | 3000 | 2026-03-25 | 2026-08-26
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/5933364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117872157 | Physically Completed | 23490 | 0 | 2026-03-25 | 2026-08-03
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/5933394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124960055 | Physically Completed | 23490 | 0 | 2026-03-25 | 2026-08-03
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/5933413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125098172 | Physically Completed | 27000 | 5700 | 2026-03-25 | 2026-09-13
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/5933865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124958908 | Physically Completed | 23490 | 0 | 2026-03-25 | 2026-08-03
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/5934194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126503594 | Physically Completed | 27000 | 0 | 2026-04-07 | 2026-09-13
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/5934876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125098581 | Physically Completed | 27000 | 17100 | 2026-05-13 | 2026-10-18
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/5934892 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123120169 | Physically Completed | 23490 | 5700 | 2026-03-25 | 2026-08-10
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/5935028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128114286 | Physically Completed | 23490 | 0 | 2026-03-25 | 2026-08-03
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/5935179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122699262 | Physically Completed | 23490 | 2100 | 2026-03-25 | 2026-08-09
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/5935225 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125612716 | Physically Completed | 23490 | 0 | 2026-03-25 | 2026-08-03
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/5935450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123121107 | Physically Completed | 23490 | 4200 | 2026-03-25 | 2026-08-02
CHANCHODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/599987 — Construction of IAY House -IAY REG. NO. MP3843433 | Ongoing | 27000 | 0 | 2017-02-27
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/6050501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122501670 | Ongoing | 27000 | 12900 | 2026-07-30
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/6051016 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123841903 | Ongoing | 27000 | 18600 | 2026-08-01
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/6051138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122502953 | Physically Completed | 23490 | 8400 | 2026-06-10 | 2026-08-10
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/6057185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124963171 | Ongoing | 27000 | 9000 | 2026-08-01
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/6260482 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123042759 | Ongoing | 27000 | 3600 | 2026-10-13
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/6260870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123195541 | Ongoing | 27000 | 8400 | 2026-10-06
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/6265872 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126556800 | Ongoing | 27000 | 1800 | 2026-10-13
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/6291800 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119836177 | Ongoing | 27000 | 4200 | 2026-10-06
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/6394942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125012242 | Ongoing | 27000 | 1800 | 2026-10-14
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/6395816 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122503255 | Ongoing | 27000 | 0 | 2026-10-19
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706008003/IF/IAY/6418318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126634631 | Approved | 27000 | 0 | 2026-02-01