## Work List
Exported on: 2026-09-03 07:54:24
Filters applied:
Data source: VBGRAMG
District: GUNA
Block: All
Panchayat: ANKHAKHEDI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1706008114/IF/22012035368210 — khet talab arjun/amarchand meena | Ongoing | 197290.25 | 0 | 2026-08-23
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1706008114/IF/22012035512953 — khet talab kamlesh/dhanna lal meena | Ongoing | 197109 | 0 | 2026-08-23
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1706008114/IF/22012035517402 — khet talab ghasi lal/budhram ahirwar | Ongoing | 299317.6 | 0 | 2026-08-24
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1706008114/IF/22012035520892 — khet talab gopal/chironji lal lodha | Ongoing | 195838.53 | 0 | 2026-08-22
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1706008114/IF/22012035520899 — khet talab lalchand/balmukand meena | Ongoing | 290669.45 | 0 | 2026-08-23
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1706008114/IF/22012035557231 — khet talab brijmohan/pushkar lal gupta | Approved | 296342.38 | 0 | 2025-04-14
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1706008114/IF/22012035557232 — khet talab kallu/moola meena | Ongoing | 298672.61 | 0 | 2026-08-23
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1706008114/IF/22012035558559 — khet talab brijmohan/balmukand meena | Ongoing | 295671.86 | 0 | 2026-08-23
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1706008114/IF/22012035606264 — एक बगिया मॉं के नाम रेखाबाई/ रंगलाल वेडावेह ग्राम पंचायत आंकखेडी | Ongoing | 263510.03 | 0 | 2025-09-18
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1706008114/IF/22012035610536 — एक बगिया माँ के नाम मीरा बाई / भंवरसिंह आँखखेड़ी | Ongoing | 263510.03 | 0 | 2025-09-18
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1706008114/IF/22012035611873 — एक बगिया माँ के नाम सावित्री बाई / भागचंद्र आँखखेड़ी | Ongoing | 263510.03 | 0 | 2025-09-18
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1706008114/IF/22012035617785 — एक बगिया माँ के नाम श्याम बाई / राजमल लोधा आँखखेड़ी | Ongoing | 263510.03 | 0 | 2025-09-20
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1706008114/IF/22012035620062 — एक बगिया माँ के नाम धापू बाई / राधेश्याम लोधा आँखखेड़ी | Ongoing | 263511.37 | 0 | 2025-11-12
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1706008114/IF/22012035620093 — एक बगिया माँ के नाम ममता बाई / राजेश शर्मा आँखखेड़ी | Ongoing | 263510.03 | 0 | 2025-09-20
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1706008114/IF/22012035632046 — एक बगिया माँ के नाम मुन्नी बाई / प्रभुलाल अहिरवार ग्राम पंचायत आँखखेड़ी | Ongoing | 263511.37 | 0 | 2025-11-01
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/4524974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124713621 | Physically Completed | 23490 | 0 | 2025-08-06 | 2026-07-12
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/4526511 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127017468 | Ongoing | 27000 | 0 | 2025-04-28
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/4530309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148506343 | Ongoing | 27000 | 0 | 2025-08-07
CHANCHODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/4822240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116545451 | Ongoing | 27000 | 0 | 2025-03-27
CHANCHODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/4827283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124932645 | Ongoing | 27000 | 0 | 2025-02-05
CHANCHODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/4880399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124701091 | Ongoing | 27000 | 0 | 2025-03-27
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5115933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124696032 | Ongoing | 27000 | 4200 | 2025-07-09
CHANCHODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5115934 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124697352 | Ongoing | 27000 | 0 | 2025-03-27
CHANCHODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5115935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124699629 | Ongoing | 27000 | 0 | 2025-03-27
CHANCHODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5115937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124701463 | Ongoing | 27000 | 8400 | 2025-03-27
CHANCHODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5117158 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151216632 | Physically Completed | 23490 | 0 | 2025-03-27 | 2026-08-06
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5118444 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125728412 | Ongoing | 27000 | 0 | 2025-07-09
CHANCHODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5127805 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127055080 | Ongoing | 27000 | 0 | 2025-03-27
CHANCHODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5133504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140560428 | Physically Completed | 23490 | 0 | 2025-03-27 | 2026-07-19
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5572579 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151418458 | Physically Completed | 23490 | 0 | 2025-07-09 | 2026-08-03
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5633870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118087767 | Physically Completed | 23490 | 0 | 2025-07-09 | 2026-08-10
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5684118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140983800 | Ongoing | 27000 | 0 | 2025-07-09
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5729122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124685363 | Physically Completed | 23490 | 0 | 2025-10-10 | 2026-07-12
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5842529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125735966 | Ongoing | 27000 | 0 | 2025-11-24
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5900398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125542626 | Ongoing | 27000 | 0 | 2026-04-06
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5900581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140984081 | Ongoing | 27000 | 0 | 2026-04-06
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5900724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127043038 | Ongoing | 27000 | 0 | 2026-04-06
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5900862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125641272 | Ongoing | 27000 | 9600 | 2026-04-06
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5901149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116546605 | Ongoing | 27000 | 19200 | 2026-04-06
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5901334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150918816 | Approved | 27000 | 0 | 2026-02-03
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5901378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140567081 | Ongoing | 27000 | 9600 | 2026-04-06
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5902002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116557624 | Ongoing | 27000 | 9600 | 2026-04-06
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5902054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124728367 | Ongoing | 27000 | 19200 | 2026-04-06
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5902095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125732990 | Ongoing | 27000 | 19200 | 2026-04-06
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5902336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125725700 | Ongoing | 27000 | 0 | 2026-04-06
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5934041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124712382 | Ongoing | 27000 | 9600 | 2026-04-06
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5934073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118087733 | Ongoing | 27000 | 19200 | 2026-04-06
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5982416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127804214 | Ongoing | 27000 | 19200 | 2026-04-06
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/5984861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127055454 | Ongoing | 27000 | 0 | 2026-04-06
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6050313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140985293 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6050402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140582266 | Ongoing | 27000 | 0 | 2026-07-30
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6050539 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140911870 | Ongoing | 27000 | 19200 | 2026-07-30
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6050677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140895000 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6050678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141056592 | Ongoing | 27000 | 0 | 2026-07-20
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6050753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124703826 | Ongoing | 27000 | 0 | 2026-08-09
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6050812 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140582437 | Ongoing | 27000 | 0 | 2026-08-24
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6050829 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147165266 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6050904 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140894867 | Ongoing | 27000 | 14400 | 2026-08-10
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6050905 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141056562 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6050970 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127033118 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6051068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105278661 | Approved | 27000 | 0 | 2026-02-13
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6051085 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140897597 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6051207 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124704689 | Ongoing | 27000 | 9000 | 2026-08-10
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6051302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124705090 | Ongoing | 27000 | 9000 | 2026-08-10
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6051343 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116557314 | Ongoing | 27000 | 4200 | 2026-05-12
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6051416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126651831 | Approved | 27000 | 0 | 2026-02-25
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6051417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127803840 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6051529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124705905 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6051650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127006972 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6052098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126615955 | Approved | 27000 | 0 | 2026-02-04
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6052203 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132909916 | Approved | 27000 | 0 | 2026-02-23
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6052293 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132909743 | Ongoing | 27000 | 4500 | 2026-08-11
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6052437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124685856 | Approved | 27000 | 0 | 2026-02-03
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6052538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140601245 | Ongoing | 27000 | 9000 | 2026-08-11
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6052565 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127043402 | Ongoing | 27000 | 9000 | 2026-05-12
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6052612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127053300 | Ongoing | 27000 | 0 | 2026-08-11
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6052702 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127036596 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6052734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127041532 | Approved | 27000 | 0 | 2026-01-31
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6052935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124685597 | Ongoing | 27000 | 9000 | 2026-05-12
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6052959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127419038 | Approved | 27000 | 0 | 2026-02-13
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6052973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127044473 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6053251 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118087795 | Ongoing | 27000 | 9000 | 2026-05-12
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6053459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125637795 | Ongoing | 27000 | 9000 | 2026-08-11
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6053833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124706338 | Ongoing | 27000 | 4500 | 2026-08-11
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6054150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124700721 | Ongoing | 27000 | 9600 | 2026-05-12
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6054381 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151219959 | Approved | 27000 | 0 | 2026-02-25
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6054456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125720473 | Ongoing | 27000 | 9600 | 2026-08-11
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6054545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151227017 | Approved | 27000 | 0 | 2026-02-23
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6054659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118087569 | Ongoing | 27000 | 4500 | 2026-08-11
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6054716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124451812 | Ongoing | 27000 | 9000 | 2026-08-11
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6054724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150904258 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6054748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118087667 | Approved | 27000 | 0 | 2026-02-26
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6054794 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124679126 | Ongoing | 27000 | 9000 | 2026-08-11
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6054976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124704281 | Ongoing | 27000 | 0 | 2026-08-11
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6055046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125600012 | Approved | 27000 | 0 | 2026-02-27
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6055139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105979427 | Approved | 27000 | 0 | 2026-02-25
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6055382 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125729579 | Ongoing | 27000 | 0 | 2026-04-09
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6055474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124695684 | Ongoing | 27000 | 0 | 2026-04-09
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6055475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124684013 | Ongoing | 27000 | 0 | 2026-04-09
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6055519 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140889771 | Ongoing | 27000 | 0 | 2026-04-09
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6055520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127043790 | Approved | 27000 | 0 | 2026-02-03
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6055553 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124702261 | Approved | 27000 | 0 | 2026-02-26
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6055564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151308169 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6055646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124701858 | Approved | 27000 | 0 | 2026-02-03
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6055930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127418772 | Approved | 27000 | 0 | 2026-02-13
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6056285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124684516 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6056418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124673377 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6056431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150814537 | Approved | 27000 | 0 | 2026-02-03
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6056481 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125704545 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6056527 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125707291 | Approved | 27000 | 0 | 2026-02-25
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6056807 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124694993 | Approved | 27000 | 0 | 2026-01-31
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6056896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124708096 | Approved | 27000 | 0 | 2026-02-23
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6056908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151237011 | Approved | 27000 | 0 | 2026-02-24
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6056938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140877342 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125727229 | Approved | 27000 | 0 | 2026-01-28
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124709481 | Approved | 27000 | 0 | 2026-02-18
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124713121 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124699993 | Approved | 27000 | 0 | 2026-02-20
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125730704 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150597745 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057215 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127017047 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150600450 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151250838 | Approved | 27000 | 0 | 2026-02-27
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124699217 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151278185 | Approved | 27000 | 0 | 2026-02-18
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057467 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140566859 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057468 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118087245 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124695351 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127805414 | Approved | 27000 | 0 | 2026-01-31
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057641 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125679175 | Approved | 27000 | 0 | 2026-01-31
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057645 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116557583 | Approved | 27000 | 0 | 2026-02-26
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125696371 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127039524 | Approved | 27000 | 0 | 2026-01-31
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124696352 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124696705 | Approved | 27000 | 0 | 2026-02-25
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124710435 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057914 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127016203 | Approved | 27000 | 0 | 2026-02-03
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126654784 | Approved | 27000 | 0 | 2026-02-04
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6057921 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151444962 | Approved | 27000 | 0 | 2026-02-03
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6058048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150728272 | Approved | 27000 | 0 | 2026-03-02
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6058049 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127806537 | Approved | 27000 | 0 | 2026-03-02
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6058052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148150075 | Ongoing | 27000 | 0 | 2026-05-05
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6058054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125724351 | Approved | 27000 | 0 | 2026-02-23
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6058055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127032066 | Ongoing | 27000 | 0 | 2026-05-12
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6058142 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124698842 | Ongoing | 27000 | 0 | 2026-05-13
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6058233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150883900 | Approved | 27000 | 0 | 2026-02-23
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6058323 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140936156 | Approved | 27000 | 0 | 2026-02-23
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6058456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125685745 | Approved | 27000 | 0 | 2026-03-02
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6058457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125640176 | Approved | 27000 | 0 | 2026-02-03
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6058459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125699609 | Approved | 27000 | 0 | 2026-02-04
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6058460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125717211 | Approved | 27000 | 0 | 2026-03-02
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6058478 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125690712 | Approved | 27000 | 0 | 2026-01-28
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6058544 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127037754 | Approved | 27000 | 0 | 2026-02-20
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6058545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151312156 | Approved | 27000 | 0 | 2026-02-25
CHANCHODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6228697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124714623 | Approved | 27000 | 0 | 2026-03-25
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6233915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118715370 | Approved | 23490 | 0 | 2026-05-14
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6234056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124707194 | Approved | 23490 | 0 | 2026-04-09
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6234197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124712588 | Approved | 23490 | 0 | 2026-04-09
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6234626 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125739214 | Approved | 23490 | 0 | 2026-04-09
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6234736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125622617 | Approved | 23490 | 0 | 2026-04-09
CHANCHODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1706008114/IF/IAY/6234969 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127040788 | Approved | 23490 | 0 | 2026-04-09
CHANCHODA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1706008114/WC/22012035285385 — JGSA 2025 Recharge structure sarvajanik koop jatav mohalla Tundakapura | Approved | 0 | 0 | 2025-04-14
CHANCHODA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1706008114/WC/22012035295314 — JGSA 2025 RECHARGE STRUCTURE niji koop ramchandra meena | New | 0 | 0 | 2025-04-14
CHANCHODA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1706008114/WC/22012035312339 — JGSA 2025 RECHARGE STRUCTURE niji koop gulab bai meena | New | 0 | 0 | 2025-04-14