## Work List
Exported on: 2026-10-20 19:49:08
Filters applied:
Data source: VBGRAMG
District: GUNA
Block: All
Panchayat: JHITIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ARON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1706009048/IC/22012034887296 — सार्वजनिक कूप निर्माण कार्य आमखेडाराय | Ongoing | 588165.42 | 0 | 2025-06-30
ARON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1706009048/IF/22012034429085 — व़क्षारोपण कार्य खेत की मेढ पर छोगीलाल/पदमसिंह आमखेडाराय | Ongoing | 187600 | 0 | 2018-10-04
ARON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1706009048/IF/22012034429086 — व़क्षारोपण कार्य खेत की मेढ पर जितेन्द्र/ब्रजेन्द्रसिंह आमखेडाराय | Ongoing | 187600 | 0 | 2018-10-04
ARON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1706009048/IF/22012034448624 — व़क्षारोपण कार्य निजी खेत मे हिम्मत सिंह /सुजानसिंह कुशवाह | Ongoing | 117250 | 0 | 2019-01-05
ARON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1706009048/IF/22012035284066 — कपिल धारा कूप निर्माण कार्य सनमासिंह/ग्‍यारसा कुशवाह झितिया | Ongoing | 351011.02 | 9000 | 2025-06-01
ARON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1706009048/IF/22012035284068 — कपिलधारा कूप निर्माण कार्य गुडडीवाई वेवा/खुमान कुशवाह झितिया | Ongoing | 351011.02 | 7200 | 2025-06-01
ARON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1706009048/IF/22012035359032 — JGSA 2025-26 Recharge Structure Kapildhara Foolbai 1706009048/IF/22012034393705 | New | 0 | 0 | 2025-04-17
ARON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1706009048/IF/22012035359180 — JGSA 2025-26 Recharge Structure Kapildhara Laxman1706009048/IF/22012034440937 | Approved | 0 | 0 | 2025-04-17
ARON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1706009048/IF/22012035556750 — कपिलधारा कूप निर्माण कार्य दीपक/रामकिशन | New | 0 | 0 | 2025-05-28
ARON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706009048/IF/IAY/2993755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5380569 | Completed | 23490 | 0 | 2021-04-01 | 2026-10-08
ARON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706009048/IF/IAY/3355683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2879566 | Ongoing | 27000 | 0 | 2026-01-24
ARON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706009048/IF/IAY/3855960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131375111 | Ongoing | 27000 | 0 | 2026-01-16
ARON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706009048/IF/IAY/3963617 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106507351 | Ongoing | 27000 | 0 | 2022-07-06
ARON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706009048/IF/IAY/3966359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106250925 | Ongoing | 27000 | 21000 | 2026-01-16
ARON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706009048/IF/IAY/3968954 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113648546 | Completed | 23490 | 0 | 2022-07-06 | 2026-10-08
ARON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706009048/IF/IAY/3971608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114956020 | Ongoing | 27000 | 0 | 2022-07-06
ARON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706009048/IF/IAY/3982003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121724860 | Ongoing | 27000 | 0 | 2022-07-06
ARON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1706009048/IF/IAY/4383474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122740876 | Ongoing | 27000 | 14700 | 2026-01-16