## Work List
Exported on: 2026-09-15 07:37:44
Filters applied:
Data source: VBGRAMG
District: TIKAMGARH
Block: All
Panchayat: BARANA KHAS
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JATARA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1707003036/AV/22012034537016 — बाउण्‍डी बाल निर्माण मा0 शाला बरानाताल | Ongoing | 273000 | 0 | 2020-10-07
JATARA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1707003036/AV/22012034667769 — Mukti dham nirman kary harijan vasty barana | Approved | 347299.31 | 0 | 2025-04-01
JATARA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1707003036/DP/22012034408618 — brackchharopan panchayatbhavan ke pass | Ongoing | 335000 | 0 | 2018-07-24
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1707003036/IC/22012034890215 — सार्वजनिक कूप निर्माण दिनेश पाण्‍डे के बेडा के पास | Approved | 605674.76 | 0 | 2025-04-01
JATARA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707003036/IF/22012034473507 — कपिल धारा कूप निर्माण श्री राम बाबु /ओमप्रकाश दुबे | Ongoing | 230000 | 0 | 2019-07-19
JATARA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1707003036/IF/22012034589722 — नंदनफलोधान मातादीन दांगी की भूमि पर | Ongoing | 134013.19 | 0 | 2020-08-06
JATARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Masonry/CC Anicut for Individuals / Construction of Masonry/CC Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1707003036/IF/22012035231748 — jal ganga abhiyan stapdam marramat kary surendra ke khet ke as | New | 0 | 0 | 2024-06-08
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707003036/IF/22012035347033 — खेत तालाब निर्माण कुण्‍जबिहारी पाण्‍डे की भूमि पर | Ongoing | 147621.16 | 0 | 2025-06-17
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707003036/IF/22012035414064 — khet talab nirman pajna kewat ki bhumi par barana khas | Approved | 0 | 0 | 2025-04-14
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1707003036/IF/22012035577190 — Khet talab nirman manish ke khet ke pass | Ongoing | 147621.16 | 0 | 2025-06-26
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1707003036/IF/22012035577199 — Khet talab nirman devki ke khet ke pass | Ongoing | 147621.16 | 0 | 2025-06-26
JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/4398443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115218545 | Approved | 27000 | 0 | 2022-10-09
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6011356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116454652 | Ongoing | 27000 | 0 | 2026-06-06
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6011925 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118088191 | Physically Completed | 27000 | 0 | 2026-04-14 | 2026-09-10
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6015186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115250752 | Ongoing | 27000 | 18000 | 2026-06-06
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6020182 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117011937 | Approved | 27000 | 0 | 2026-01-29
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6025333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115219013 | Ongoing | 27000 | 9000 | 2026-04-14
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6026172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121489786 | Approved | 27000 | 0 | 2026-01-22
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6026309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117008983 | Approved | 27000 | 0 | 2026-01-22
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6027362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116453075 | Ongoing | 27000 | 11400 | 2026-04-30
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6027364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116454413 | Ongoing | 27000 | 5400 | 2026-06-06
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6027489 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116453963 | Ongoing | 27000 | 5400 | 2026-07-11
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6027595 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116149539 | Approved | 27000 | 0 | 2026-01-29
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6027699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117628583 | Ongoing | 27000 | 21600 | 2026-07-10
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6027707 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118388904 | Approved | 27000 | 0 | 2026-01-29
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6027864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115908365 | Ongoing | 27000 | 12600 | 2026-05-18
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6027880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115218323 | Ongoing | 27000 | 9000 | 2026-08-05
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6027970 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115408684 | Ongoing | 27000 | 4500 | 2026-04-04
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6027971 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115408939 | Ongoing | 27000 | 10800 | 2026-04-30
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6027973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115419277 | Ongoing | 27000 | 3600 | 2026-04-30
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6028143 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119643166 | Ongoing | 27000 | 16200 | 2026-04-14
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6028219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126459158 | Ongoing | 27000 | 12600 | 2026-07-03
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6028374 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118307487 | Ongoing | 27000 | 10800 | 2026-04-14
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6028633 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116451772 | Approved | 27000 | 0 | 2026-02-03
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6028662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122627297 | Ongoing | 27000 | 3000 | 2026-04-14
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6028726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116453553 | Ongoing | 27000 | 7200 | 2026-04-14
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6028728 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115251022 | Physically Completed | 27000 | 0 | 2026-04-14 | 2026-09-10
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6028745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115377944 | Ongoing | 27000 | 16200 | 2026-06-06
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6028792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115250601 | Ongoing | 27000 | 10800 | 2026-04-30
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6028797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116536141 | Approved | 27000 | 0 | 2026-02-26
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6028899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117241632 | Ongoing | 27000 | 7200 | 2026-07-10
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6028926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116449158 | Ongoing | 27000 | 18000 | 2026-08-05
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/6062525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126528423 | Approved | 27000 | 0 | 2026-01-29
JATARA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/659806 — Construction of IAY House -IAY REG. NO. MP1276392 | Approved | 27000 | 0 | 2017-03-12
JATARA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003036/IF/IAY/678769 — Construction of IAY House -IAY REG. NO. MP3219891 | Approved | 27000 | 0 | 2017-03-12
JATARA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Dev of Silvipasture Grassslands for Community / Development of Silvipasture Grassslands for Community | Grass Land Development | 1707003036/LD/22012034528278 — CHARAGAH VIKAS KARY BARANA KHAS | Ongoing | 792213.45 | 0 | 2021-02-27
JATARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1707003036/LD/22012034943109 — bracksharopan kary mandir se pahadi tak | Ongoing | 453563.17 | 113100 | 2024-08-17
JATARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1707003036/LD/22012034943204 — brackksharopan kary varchhi mandir pahadi ke pass | Ongoing | 453563.17 | 97200 | 2024-08-17
JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1707003036/LD/22012034952402 — Mukti dham nirman kary harijan vasty barana | Approved | 347299.82 | 0 | 2025-04-02
JATARA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707003036/RC/22012034819696 — c c road nirman kary sankarji mandir ke pass | Approved | 0 | 0 | 2024-06-08
JATARA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707003036/RC/22012034819697 — cc road nirman kary gupla kewat ke makan se kishori kewat ke makan tak | Approved | 0 | 0 | 2024-06-08
JATARA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707003036/RC/22012034819707 — nali nirman kary narayan das kushvaha ke makan se nahar tak | Approved | 0 | 0 | 2024-06-08
JATARA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707003036/RC/22012034819710 — nali nirman kary jasua ke makan se nahar tak | Approved | 0 | 0 | 2024-06-08
JATARA | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707003036/RC/22012034853434 — सीसी रोड़ निर्माण कार्य मेन रोड से कुशवाहा मुहल्ला की ओर वरानाखास | Ongoing | 35399 | 0 | 2026-05-01
JATARA | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1707003036/RC/22012034853435 — सीसी रोड़ निर्माण कार्य आरोग्य केन्द्र के पास वरानाखास | Ongoing | 69266 | 17400 | 2026-05-01
JATARA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1707003036/RS/22012035139484 — नाली निर्माण कार्य शिव्वन के मकान से मैन रोड़ तक बरानाखास | Approved | 23868 | 0 | 2025-04-01
JATARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1707003036/WC/22012035063864 — dog out pond nirman kary peer babba ke niche barana khas | Ongoing | 490176.62 | 0 | 2024-03-16
JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707003036/WC/22012035264751 — नवीन तालाब निर्माण कार्य रामकली पुष्‍पकार के खेत के पास | Approved | 0 | 0 | 2025-04-01
JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707003036/WC/22012035264786 — नवीन तालाब निर्माण पन्‍ना केवट के खेत के पास | Approved | 0 | 0 | 2025-04-01
JATARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003036/WH/22012034940896 — stap dam nirman marramat kary surendra dangi ke khet ke pass | Approved | 0 | 0 | 2024-06-08
JATARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003036/WH/22012034940897 — stap dam nirman marramat kary sukhdas ahirwar ke khet ke pass | Approved | 0 | 0 | 2024-06-08
JATARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003036/WH/22012034941099 — marramat talab nirman kary napit ke khet ke pass | Approved | 0 | 0 | 2024-06-08
JATARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003036/WH/22012034941101 — marramat talab nirman kary gau shala ke pass | Approved | 0 | 0 | 2024-06-08
JATARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003036/WH/22012034941102 — marramat talab nirman kary poocha har | Approved | 0 | 0 | 2024-06-08
JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003036/WH/22012034943952 — तालाब जीर्णोद्धार कार्य भरोसा कुशवाहा के खेत के पास | Approved | 0 | 0 | 2025-04-01
JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003036/WH/22012034944390 — स्टॉपडैम मरम्मत सुखदास अहिरवार के खेत के पास | Ongoing | 601235.35 | 0 | 2025-06-16
JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003036/WH/22012034944391 — स्टॉपडेम मरम्मत सुरेंद दांगी के खेत के पास | Ongoing | 601904.04 | 17700 | 2025-06-17
JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003036/WH/22012034945542 — नहर मरम्मत कार्य स्लूस से पुलिया तक बराना खास | Approved | 0 | 0 | 2025-08-01
JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003036/WH/22012034945543 — नहर मरम्मत कार्य पुलिया से शिवजी मंदिर तक बराना खास | Approved | 0 | 0 | 2025-08-01
JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003036/WH/22012034945544 — नहर मरम्मत कार्य कैलाश सागर फीडर से कल्लू पाडे के खेत तक बराना खास | Approved | 0 | 0 | 2025-08-01
JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003036/WH/22012034945545 — नहर मरम्मत कार्य कैलाश सागर फीडर से दिलीप शर्मा के खेत तक बराना खास | Approved | 0 | 0 | 2025-08-01
JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003036/WH/22012034945546 — बांध/बंड मरम्मत बंधान घाट से बऊहार तक बरानाखास | Approved | 0 | 0 | 2025-08-01
JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003036/WH/22012034945547 — बांध/बंड मरम्मत बऊहार से लुहार के आम तक भाग 2 बरानाखास | Approved | 0 | 0 | 2025-08-01
JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003036/WH/22012034945548 — बांध/बंड मरम्मत शंकर जी मंदिर से वरगद मोड तक बरानाखास | Approved | 0 | 0 | 2025-08-01