## Work List
Exported on: 2026-10-24 04:39:47
Filters applied:
Data source: VBGRAMG
District: TIKAMGARH
Block: All
Panchayat: KITKHERA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Groups / Construction of Irrigation Well for Groups | Construction of Well | 1707003050/IC/22012034893041 — कपिलधारा कूप निर्माण अंकित /लालाराम यादव की भूमि पर किटाखेरा | Ongoing | 322434.45 | 21600 | 2026-04-10
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Groups / Construction of Irrigation Well for Groups | Construction of Well | 1707003050/IC/22012034893042 — कपिलधारा कूप निर्माण साहब सिंह /बाबूलाल दांगी की भूमि पर किटाखेरा | Ongoing | 322434.45 | 29700 | 2026-06-03
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Groups / Construction of Irrigation Well for Groups | Construction of Well | 1707003050/IC/22012034893043 — कपिलधारा कूप निर्माण वीरेन्‍द्र/भगवानदास यादव की भूमि पर किटाखेरा | Ongoing | 322434.45 | 12300 | 2026-05-15
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Groups / Construction of Irrigation Well for Groups | Construction of Well | 1707003050/IC/22012034893044 — कपिलधारा कूप निर्माण मोहन/धोकल यादव की भूमि पर किटाखेरा | Ongoing | 322434.45 | 900 | 2026-06-02
JATARA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1707003050/IF/22012034351891 — Brakchha ropan mhanvidyalay pranghra men | Physically Completed | 535000 | 0 | 2017-07-04 | 2026-09-15
JATARA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1707003050/IF/22012034474574 — Kapil dhara koop nirman chanda gotam / hagvat gotam | Ongoing | 230000 | 0 | 2021-12-03
JATARA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1707003050/IF/22012035108328 — कपिलधारा कूप निर्माण कार्य प्रेमबाईं रेकवार की भूमी पर | Ongoing | 295624.16 | 0 | 2024-03-14
JATARA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Line Plantation of Forestry Trees for Individual | Plantation | 1707003050/IF/22012035113587 — खकरी निर्माण कार्य साहब सिन्ह दांगी की भूमी पर | Ongoing | 187025.28 | 0 | 2023-12-22
JATARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Stone boulder Gully Plugs for Individual / Construction of Stone Boulder Gully Plug for Individual | Boulder Check/Gully Plug | 1707003050/IF/22012035125783 — खकरी निर्माण कार्य रहीश यादव की भूमी पर किटाखेरा | Ongoing | 192947.73 | 0 | 2024-03-14
JATARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Stone graded Bund for Individuals / Construction of Stone graded Bund for Individuals | Construction of Bund | 1707003050/IF/22012035125787 — १।२खकरी निर्माण कार्य सूरज सिंह की भूमी पर किटाखेरा | Ongoing | 170887.57 | 0 | 2024-03-14
JATARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individual | Construction of Check Dam/Stop Dam | 1707003050/IF/22012035126281 — खकरी निर्माण कार्य सम्‍पत यादव की भूमि पर किटाखेरा | Ongoing | 164762.31 | 0 | 2024-02-21
JATARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Line Plantation of Forestry Trees for Individual | Plantation | 1707003050/IF/22012035129105 — Nandan falodyan nirman karya mahanti Yadav ke khet par | Ongoing | 188340.57 | 0 | 2023-09-14
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1707003050/IF/22012035232461 — खकरी निर्माण कार्य राहुल यादव की भुमी पर किटाखेरा | Ongoing | 174095.72 | 38697.84 | 2025-05-12
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1707003050/IF/22012035232464 — खकरी निर्माण कार्य स्वामी यादव की भुमी पर किटाखेरा | Ongoing | 179160.94 | 0 | 2025-05-03
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1707003050/IF/22012035361105 — kapildhra koop nirman kunji peyare lal s/o munna adiwasi ki bhumi par | Approved | 0 | 0 | 2025-04-14
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1707003050/IF/22012035361109 — kapildhara koop nirman tulai s/o sunua sour ki bhumi par | Approved | 0 | 0 | 2025-04-14
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1707003050/IF/22012035361113 — kapildhara koop nirman sahabsingh s/o babu dangi ki bhumi par | Approved | 0 | 0 | 2025-04-14
JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1707003050/IF/22012035406711 — dag well Recharge prembai s/o ramdas raikwar ke koop ke pas kithakera | Ongoing | 25899.46 | 0 | 2025-04-27
JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1707003050/IF/22012035406804 — dag well Recharge janki s/o gyasi yadav ke koop ke pas kithakera | Ongoing | 25899.46 | 0 | 2025-04-27
JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1707003050/IF/22012035406847 — dag well Recharge ravindra s/o mahanti yadav ke koop ke pas kithakera | Ongoing | 25899.46 | 0 | 2025-04-27
JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1707003050/IF/22012035406899 — dag well Recharge swami s/o ramcharan yadav ke koop ke pas kithakera | Ongoing | 25899.46 | 0 | 2025-04-27
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1707003050/IF/22012035414636 — khet talab nirman kary swami s/o ramcharan yadav ki bhumi par | Ongoing | 147621.16 | 0 | 2025-04-30
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1707003050/IF/22012035414667 — khet talabv nirman kary ravindra s/o mahanti yadav ki bhumi par | Ongoing | 147621.16 | 0 | 2025-04-30
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1707003050/IF/22012035656124 — Kapil dhara koop Nirman Kary ankit s/o lalaram yadav | New | 0 | 0 | 2026-01-07
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1707003050/IF/22012035656131 — Kapil dhara koop Nirman Kary ankit s/o lalaram yadav | New | 0 | 0 | 2026-01-07
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1707003050/IF/22012035656160 — कपिलधारा कूप निर्माण अंकित /लालाराम यादव की भूमि पर किटाखेरा | New | 0 | 0 | 2025-08-15
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1707003050/IF/22012035656163 — कपिलधारा कूप निर्माण अंकित /लालाराम यादव की भूमि पर किटाखेरा | New | 0 | 0 | 2025-08-15
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/1169435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1340022 | Ongoing | 27000 | 0 | 2025-02-13
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/1169443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1345570 | Ongoing | 27000 | 0 | 2025-02-09
JATARA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/127864 — Construction of IAY House -IAY REG. NO. MP-07-003-050-001/46 | Approved | 27000 | 0 | 2016-02-03
JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4041461 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118602933 | Approved | 27000 | 0 | 2022-05-10
JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4042851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116895249 | Approved | 27000 | 0 | 2022-05-10
JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4042854 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116895539 | Approved | 27000 | 0 | 2022-05-10
JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4142403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117345057 | Approved | 27000 | 0 | 2022-05-23
JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4143732 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117173490 | Approved | 27000 | 0 | 2022-05-23
JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4143734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117176899 | Approved | 27000 | 0 | 2022-05-23
JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4143736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117177786 | Approved | 27000 | 0 | 2022-05-24
JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4143738 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117180211 | Approved | 27000 | 0 | 2022-05-24
JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4143954 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118303287 | Approved | 27000 | 0 | 2022-05-23
JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4143955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118304557 | Approved | 27000 | 0 | 2022-05-23
JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4143968 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118326064 | Approved | 27000 | 0 | 2022-05-23
JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4143971 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118329236 | Approved | 27000 | 0 | 2022-05-23
JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4144613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119584720 | Approved | 27000 | 0 | 2022-05-23
JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4145005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116896399 | Physically Completed | 23490 | 0 | 2022-05-23 | 2026-08-16
JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4147143 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128902519 | Approved | 27000 | 0 | 2022-05-24
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4384231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117293321 | Completed | 23490 | 0 | 2025-09-05 | 2026-09-15
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4750115 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117142596 | Ongoing | 27000 | 0 | 2025-01-29
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4750751 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116894845 | Ongoing | 27000 | 0 | 2025-02-24
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4750753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116895718 | Ongoing | 27000 | 0 | 2025-02-09
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4750756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116896232 | Ongoing | 27000 | 0 | 2025-02-09
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4750757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116896308 | Ongoing | 27000 | 0 | 2025-02-09
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4751289 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117295512 | Approved | 27000 | 0 | 2024-10-04
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4754775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118303972 | Ongoing | 27000 | 0 | 2025-02-09
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4754815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118313605 | Completed | 27000 | 0 | 2025-02-09 | 2026-09-22
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4848829 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117293929 | Ongoing | 27000 | 4200 | 2025-01-30
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4863964 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117295781 | Completed | 27000 | 0 | 2025-02-24 | 2026-09-22
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4871942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129558488 | Ongoing | 27000 | 0 | 2025-01-27
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4926650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117121841 | Completed | 27000 | 0 | 2025-05-16 | 2026-09-22
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4926656 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117124060 | Completed | 27000 | 0 | 2025-05-01 | 2026-09-22
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4926659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117140946 | Completed | 27000 | 0 | 2025-08-04 | 2026-09-22
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4927381 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117293611 | Completed | 27000 | 0 | 2025-04-22 | 2026-09-22
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4927383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117295416 | Completed | 27000 | 0 | 2025-05-01 | 2026-09-15
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/4927662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116894911 | Completed | 23490 | 0 | 2026-06-05 | 2026-09-15
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5121918 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117294245 | Ongoing | 27000 | 0 | 2025-09-10
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5133990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116896637 | Completed | 23490 | 0 | 2025-08-19 | 2026-09-15
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5172193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117141028 | Completed | 27000 | 0 | 2025-08-04 | 2026-09-15
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5188404 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118305678 | Completed | 27000 | 0 | 2025-04-22 | 2026-09-22
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5193019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117122565 | Ongoing | 27000 | 0 | 2025-05-16
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5200780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117292887 | Ongoing | 27000 | 0 | 2025-05-01
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5223047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117126182 | Completed | 27000 | 0 | 2025-08-19 | 2026-09-22
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5248065 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117295840 | Completed | 27000 | 0 | 2025-04-22 | 2026-09-15
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5295031 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117121897 | Completed | 27000 | 0 | 2025-05-01 | 2026-09-15
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5575919 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117292935 | Approved | 27000 | 0 | 2025-04-25
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5659952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116895785 | Ongoing | 27000 | 0 | 2025-09-10
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5660443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117140349 | Ongoing | 27000 | 8400 | 2026-09-07
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5703941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117293788 | Completed | 23490 | 0 | 2026-06-05 | 2026-09-15
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5779451 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117293373 | Ongoing | 27000 | 0 | 2025-09-29
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5779452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117293452 | Approved | 27000 | 0 | 2024-11-20
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5779475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117295625 | Completed | 23490 | 0 | 2025-09-05 | 2026-09-15
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5779782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117140455 | Approved | 27000 | 0 | 2025-03-18
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5779783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117140987 | Ongoing | 27000 | 0 | 2025-09-05
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5779874 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128904926 | Approved | 27000 | 0 | 2025-03-13
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5780190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118604735 | Physically Completed | 23490 | 0 | 2025-02-17 | 2026-08-09
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5780639 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119584890 | Physically Completed | 27000 | 0 | 2025-03-26 | 2026-09-27
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5780960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118610252 | Approved | 27000 | 0 | 2025-03-18
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5781423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117343388 | Approved | 27000 | 0 | 2025-02-17
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5781632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117296711 | Completed | 23490 | 0 | 2025-09-05 | 2026-09-15
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5781660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117139638 | Completed | 23490 | 0 | 2025-09-29 | 2026-09-15
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5781937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117140293 | Approved | 27000 | 0 | 2025-02-17
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5782591 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116895911 | Approved | 27000 | 0 | 2025-03-17
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5782748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127238254 | Approved | 27000 | 0 | 2024-11-20
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5885928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117141971 | Physically Completed | 23490 | 0 | 2025-02-17 | 2026-08-02
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/5886097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117296096 | Approved | 27000 | 0 | 2025-03-18
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/6034146 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117294016 | Approved | 27000 | 0 | 2025-03-26
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/6380730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117295739 | Approved | 27000 | 0 | 2026-07-15
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/6380926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128905432 | Approved | 27000 | 0 | 2025-02-13
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/6380961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117140228 | Approved | 27000 | 0 | 2025-02-13
JATARA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1707003050/IF/IAY/650840 — Construction of IAY House -IAY REG. NO. MP3393419 | Approved | 27000 | 0 | 2017-02-13
JATARA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1707003050/RC/22012034819855 — सी0सी0 रोड़ निर्माण कार्य मुन्ना सूत्रकार के मकान से कल्लू नापित के घर तक | Ongoing | 22238 | 0 | 2025-11-25
JATARA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1707003050/RC/22012034838299 — सीसी रोड निर्माण ममता अहिरवार के मकान से मुख्‍य मार्ग तक गांधीग्राम | Approved | 60000 | 0 | 2024-10-02
JATARA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1707003050/RC/22012034838301 — सीसी रोड निर्माण देवेन्‍द्र यादव के घर से शंकर यादव के घर तक | Approved | 71000 | 0 | 2024-10-02
JATARA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1707003050/RC/22012034838303 — सीसी रोड निर्माण डाक्‍टर शर्मा के मकान से मैन रोड तक | Approved | 32000 | 0 | 2024-10-02
JATARA | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1707003050/RC/22012034840377 — सी0सी0 रोड़ निर्माण कार्य मुख्य सड़क से डाक्टर शर्मा जी के मकान तक किटाखेरा | Ongoing | 32234 | 27600 | 2026-07-24
JATARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1707003050/WC/22012035075703 — डग आउट पोण्ड दीवान साब की पहाडी पर | Ongoing | 490064.64 | 0 | 2023-10-09
JATARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1707003050/WC/22012035075705 — डग आउट पोण्ड निर्माण रूप सिन्ह यादव के खेत के पास | Ongoing | 490064.64 | 0 | 2023-10-09
JATARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1707003050/WC/22012035203810 — चेकडेम मरम्मद कार्य मंटू आदिवासी के खेत के पास गाधीग्राम | Approved | 0 | 0 | 2024-04-01
JATARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dyke for Community | Underground Dyke for Ground Water Recharge | 1707003050/WC/22012035203812 — चेकडेम मरम्मद कार्य नब्बू आदिवासी के खेत के पास गाधीग्राम | Approved | 0 | 0 | 2024-04-01
JATARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1707003050/WC/22012035205516 — तालाब मरम्म्द कार्य छुट्टी की पहाडी पर गांधीग्राम | Approved | 0 | 0 | 2024-06-05
JATARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1707003050/WC/22012035205519 — तालाब मरम्म्द कार्य मोरी की पहाडी के पास गांधीग्राम | Approved | 0 | 0 | 2024-06-05