## Work List
Exported on: 2026-09-07 03:01:55
Filters applied:
Data source: VBGRAMG
District: TIKAMGARH
Block: All
Panchayat: MOHANGARH
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
JATARA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1707003066/AV/22012034541987 — Charagah nirman karya mohangarh | Ongoing | 792213.45 | 0 | 2023-10-04
JATARA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1707003066/AV/22012034617532 — आंगनवाड़ी भवन निर्माण बनारसी मोहनगढ़ | Ongoing | 500000 | 0 | 2023-05-22
JATARA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707003066/IF/22012034632342 — kapildhara koop nirman uattam/ ganpat sour ki bhumi par mohangarh | Ongoing | 263855.24 | 0 | 2021-01-07
JATARA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707003066/IF/22012034632345 — kapildhara koop nirman janki / balu sor ki bhumi par mohangarh par | Ongoing | 263855.24 | 0 | 2021-01-08
JATARA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707003066/IF/22012034663635 — Kapildhara Koop Nirman Nathu/ramu kumhar | Ongoing | 263855.24 | 0 | 2021-03-25
JATARA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707003066/IF/22012034663649 — Kapildhara Koop Nirman Nirpat/Tuti Pal | Ongoing | 263855.24 | 0 | 2021-04-09
JATARA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707003066/IF/22012034667440 — Kapil dhara koop Abhishek/Om prakash awasthi Mohangarh | Ongoing | 263855.24 | 0 | 2023-06-19
JATARA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707003066/IF/22012034751053 — CTR कपिलधारा कूप निर्माण शहजाद /हबीब शेख | Ongoing | 265707.25 | 0 | 2023-06-06
JATARA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707003066/IF/22012035011986 — Kapil dhara koop Pancham/ Gangu kumhar Mohangarh | Ongoing | 290168.7 | 0 | 2023-11-28
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1707003066/IF/22012035256161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126548349 | Ongoing | 21870 | 0 | 2025-09-05
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707003066/IF/22012035389508 — कपिलधारा कूप निर्माण मनमोहन /हीरालाल चौबे की भूमि पर | Ongoing | 322434.5 | 0 | 2025-06-13
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707003066/IF/22012035389554 — कपिलधारा कूप निर्माण मंगल /सूका अहिरवार की भूमि पर | Ongoing | 322434.5 | 32400 | 2026-02-24
JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1707003066/IF/22012035406077 — डगवेल रिचार्ज लटकन /मौजी के कूप के पास मोहनगढ | New | 0 | 0 | 2025-04-01
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707003066/IF/22012035406842 — खेत तालाब निर्माण पुष्‍पा /रामचरन केवट की भूमि पर मोहनगढ | Ongoing | 147621.16 | 0 | 2025-05-01
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707003066/IF/22012035407841 — खेत तालाब निर्माण स्‍वामी यादव की भूमि पर मोहनगढ | Ongoing | 147621.16 | 0 | 2025-05-01
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707003066/IF/22012035407868 — खेत तालाब निर्माण पुरषोत्तम/गनपत केवट की भूमि पर मोहनगढ | Ongoing | 147621.16 | 0 | 2025-05-01
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707003066/IF/22012035432691 — कपिलधारा कूप निर्माण कुलदीप /रामस्‍वरूप पुरोहित की भूमि पर मोहनगढ | Approved | 0 | 0 | 2025-04-01
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707003066/IF/22012035432728 — कपिलधारा कूप निर्माण मौजी, अमनिया, रामेश्‍वर की भूमि पर मोहनगढ | Approved | 0 | 0 | 2025-04-01
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707003066/IF/22012035432753 — कपिलधारा कूप निर्माण मंगल /सूका अहिरवार की भूमि पर मोहनगढ | New | 0 | 0 | 2025-04-01
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707003066/IF/22012035432802 — कपिलधारा कूप निर्माण सगुनिया /टुडूवा अहिरवार की भूमि पर मोहनगढ | Approved | 0 | 0 | 2025-04-01
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707003066/IF/22012035432831 — खेत तालाब निर्माण स्‍वामी यादव की भूमि पर मोहनगढ | New | 0 | 0 | 2025-04-01
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1707003066/IF/22012035432878 — खेत तालाब निर्माण सुन्‍ना खान की भूमि पर मोहनगढ | Approved | 0 | 0 | 2025-04-01
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1707003066/IF/22012035602334 — एक बगिया मॉ के नाम रेखा जोगी की भूमि पर मोहनगढ़ | Approved | 0 | 0 | 2025-04-01
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1707003066/IF/22012035638128 — एक बगिया माॅ के नाम रामरती विश्वकर्मा की भूमि पर मोहनगढ़ | Ongoing | 266578.64 | 0 | 2026-01-19
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1707003066/IF/22012035638256 — एक बगिया माॅ के नाम तीजा केवट की भूमि पर मोहनगढ़ | Ongoing | 266578.64 | 0 | 2025-11-05
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1707003066/IF/22012035638494 — एक बगिया माॅ के नाम कस्तूरी परिहार की भूमि पर मोहनगढ़ | Ongoing | 266578.64 | 0 | 2026-01-19
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1707003066/IF/22012035638504 — एक बगिया माॅ के नाम गिरजाबाई केवट की भूमि पर मोहनगढ़ | Ongoing | 266578.64 | 0 | 2025-11-05
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1707003066/IF/22012035648219 — एक बगिया माॅ के नाम उषा विश्वकर्मा के खेत पर मोहनगढ़ | Ongoing | 193542.75 | 0 | 2026-02-15
JATARA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/1395339 — Construction of IAY House -IAY REG. NO. MP2130562 | Ongoing | 27000 | 0 | 2018-06-07
JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/2244810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2082061 | Ongoing | 27000 | 0 | 2023-01-13
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/2246481 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3229394 | Ongoing | 27000 | 0 | 2025-05-26
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/2263457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2153675 | Ongoing | 27000 | 0 | 2025-05-30
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/2263587 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2385171 | Ongoing | 27000 | 0 | 2026-02-24
JATARA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/2597256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1761478 | Ongoing | 27000 | 0 | 2020-07-02
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/3054822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1492424 | Ongoing | 27000 | 0 | 2025-09-05
JATARA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/3055301 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2585627 | Ongoing | 27000 | 0 | 2021-05-07
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/3055354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4457992 | Ongoing | 27000 | 0 | 2025-02-04
JATARA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/3055362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4828948 | Ongoing | 27000 | 0 | 2022-02-03
JATARA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/3055465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5073768 | Approved | 27000 | 0 | 2021-01-11
JATARA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/3055697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4247363 | Approved | 27000 | 0 | 2021-01-11
JATARA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/3056846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4264009 | Ongoing | 27000 | 0 | 2021-04-22
JATARA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/3191106 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4727786 | Approved | 27000 | 0 | 2021-06-16
JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/3191126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4792150 | Ongoing | 27000 | 0 | 2022-05-28
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/3197826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4939067 | Ongoing | 27000 | 0 | 2025-01-30
JATARA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/3207104 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4720637 | Approved | 27000 | 0 | 2021-06-29
JATARA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/3271557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5073974 | Approved | 27000 | 0 | 2021-01-27
JATARA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/3648006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2555752 | Approved | 27000 | 0 | 2022-02-28
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/3648183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4484843 | Ongoing | 27000 | 0 | 2024-06-29
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/3648226 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4834929 | Ongoing | 27000 | 0 | 2025-08-26
JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4048755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125619478 | Ongoing | 27000 | 0 | 2022-08-04
JATARA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4136068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127518939 | Ongoing | 27000 | 0 | 2023-06-06
JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4136334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125723026 | Approved | 27000 | 0 | 2022-05-22
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4190623 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115111249 | Ongoing | 27000 | 0 | 2025-01-30
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4318879 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125338139 | Physically Completed | 23490 | 0 | 2025-08-07 | 2026-08-16
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4321961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124564218 | Ongoing | 27000 | 0 | 2024-08-30
JATARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4364292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125402930 | Ongoing | 27000 | 0 | 2022-10-05
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4610859 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125418118 | Ongoing | 27000 | 0 | 2025-02-04
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4616937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126361131 | Ongoing | 27000 | 0 | 2025-09-05
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4619517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126434185 | Ongoing | 27000 | 0 | 2025-05-15
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4629226 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128753903 | Ongoing | 27000 | 0 | 2025-01-31
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4632572 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129486171 | Ongoing | 27000 | 0 | 2025-01-08
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4632631 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129510075 | Approved | 27000 | 0 | 2024-09-11
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4634500 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129256774 | Ongoing | 27000 | 0 | 2025-01-31
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4714365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127721877 | Ongoing | 27000 | 0 | 2025-01-30
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4714885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128288762 | Ongoing | 27000 | 0 | 2025-01-30
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4775554 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125419013 | Approved | 27000 | 0 | 2024-10-04
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4781580 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128352762 | Approved | 27000 | 0 | 2024-09-10
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4782473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128455699 | Ongoing | 27000 | 0 | 2025-01-30
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4784275 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129553951 | Ongoing | 27000 | 0 | 2025-01-30
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4784903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129621701 | Ongoing | 27000 | 0 | 2025-09-03
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4866435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127587242 | Approved | 27000 | 0 | 2024-10-29
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4866443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129620976 | Ongoing | 27000 | 0 | 2025-01-31
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/4880172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124903580 | Physically Completed | 23490 | 0 | 2025-05-27 | 2026-08-16
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/5115462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125393715 | Ongoing | 27000 | 0 | 2025-08-26
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/5125186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125629421 | Ongoing | 27000 | 0 | 2026-09-05
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/5195166 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128574440 | Physically Completed | 23490 | 0 | 2025-10-30 | 2026-08-16
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/5200458 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129510439 | Ongoing | 27000 | 0 | 2025-09-05
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/5204805 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127695571 | Ongoing | 27000 | 0 | 2025-05-27
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/5225888 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128394529 | Approved | 27000 | 0 | 2025-02-20
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/5235598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125757286 | Ongoing | 27000 | 0 | 2026-09-05
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/5621660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129395585 | Ongoing | 27000 | 4200 | 2025-05-27
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/5622710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128279134 | Ongoing | 27000 | 0 | 2025-05-27
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/5624442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127507124 | Ongoing | 27000 | 0 | 2026-02-24
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/5659995 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128430096 | Approved | 27000 | 0 | 2025-05-23
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/5703872 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130293637 | Ongoing | 27000 | 0 | 2025-10-30
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/5725776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129662677 | Approved | 27000 | 0 | 2025-06-14
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/5780133 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129382294 | Physically Completed | 23490 | 0 | 2025-08-30 | 2026-08-16
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/5780147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129612298 | Ongoing | 27000 | 0 | 2026-03-02
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/5780298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129662280 | Approved | 27000 | 0 | 2025-03-11
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/5780534 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128587651 | Approved | 27000 | 0 | 2025-03-24
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/5782050 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126660538 | Ongoing | 27000 | 0 | 2025-09-03
JATARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/5885911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128602588 | Approved | 27000 | 0 | 2025-02-20
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6017890 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125723558 | Approved | 27000 | 0 | 2026-03-01
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6019274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125722525 | Approved | 27000 | 0 | 2026-03-01
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6022302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128291043 | Approved | 27000 | 0 | 2026-03-01
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6023091 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129450994 | Approved | 27000 | 0 | 2026-03-01
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6025236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125019821 | Approved | 27000 | 0 | 2026-03-01
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6025398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127695903 | Approved | 27000 | 0 | 2026-03-01
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6026124 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125396638 | Approved | 27000 | 0 | 2026-03-01
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6027852 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128754327 | Approved | 27000 | 0 | 2026-03-06
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6028614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129395217 | Ongoing | 27000 | 0 | 2026-06-03
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6028931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126454507 | Approved | 27000 | 0 | 2026-03-01
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6029015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128386340 | Approved | 27000 | 0 | 2026-03-01
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6060997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129229535 | Approved | 27000 | 0 | 2026-03-06
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6061170 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129371922 | Approved | 27000 | 0 | 2026-03-06
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6062821 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129411890 | Approved | 27000 | 0 | 2026-03-06
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6065081 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128424149 | Approved | 27000 | 0 | 2026-03-06
JATARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6065086 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125645013 | Approved | 27000 | 0 | 2026-03-06
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6358578 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129612597 | Approved | 27000 | 0 | 2026-07-27
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6358638 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129423111 | Approved | 27000 | 0 | 2026-07-23
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6358860 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127524349 | Approved | 27000 | 0 | 2026-07-23
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6359092 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125010316 | Approved | 27000 | 0 | 2026-07-23
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6359252 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128575002 | Approved | 27000 | 0 | 2026-07-26
JATARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/6380613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115216351 | Approved | 27000 | 0 | 2026-07-26
JATARA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707003066/IF/IAY/644942 — Construction of IAY House -IAY REG. NO. MP1367089 | Approved | 27000 | 0 | 2020-04-01
JATARA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707003066/RC/22012034637614 — सुदूर सडक निर्माण मंडी रोड से मजार तरफ मोहनगढ | Ongoing | 2481667.42 | 0 | 2024-09-21
JATARA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707003066/WC/22012034598969 — Shri bihari ji mandir bhoomi par sarvajanik koop nirman Mohangarh | Ongoing | 470874.11 | 56100 | 2021-01-08
JATARA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707003066/WC/22012034598973 — Sarvajanik koop nirman shri thakur chaturbhuj mandir ki bhoomi par mohangarh | Ongoing | 470874.11 | 0 | 2021-01-08
JATARA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1707003066/WC/22012034598974 — Sarvajanik koop nirman shri marwadi mandir ki bhoomi par mohangarh | Ongoing | 470874.11 | 0 | 2021-05-10
JATARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707003066/WC/22012035251025 — Naveen talab nirman ber ke har me mohangarh | Approved | 0 | 0 | 2025-01-26
JATARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1707003066/WC/22012035251026 — Naveen talab nirman ber Kudbaee ke pas mohangarh | Approved | 0 | 0 | 2025-01-26
JATARA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003066/WH/22012034944110 — Talab jirnoddhar karya Jhadi wale baba ke pas mohangarh | Ongoing | 945308.04 | 0 | 2026-04-10
JATARA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003066/WH/22012034944112 — Talab jirnoddhar karya kushwaha ke har me mohangarh | Ongoing | 940861.1 | 0 | 2026-04-10
JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003066/WH/22012034944113 — Check dam marammat karya Uttam sounr ki bhoomi par Mohangarh | Approved | 0 | 0 | 2025-04-07
JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003066/WH/22012034944329 — Check dam marammat karya patpariya nale par Mohangarh | Approved | 0 | 0 | 2025-04-07
JATARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1707003066/WH/22012034944331 — Check dam marammat karya donda ghat nale par Mohangarh | Approved | 0 | 0 | 2025-04-07