## Work List
Exported on: 2026-10-23 11:59:16
Filters applied:
Data source: VBGRAMG
District: TIKAMGARH
Block: All
Panchayat: KANJNA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PALERA | 2026-2027 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1707004018/AV/VB/22012034669406 — मुक्तिधाम निर्माण ग्राम पंचायत कंजना | New | 0 | 0 | 2026-04-14
PALERA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1707004018/DP/22012034408521 — व़क्षारोपण कार्य कब्रिस्‍तान के पास ग्राम पंचायत कंजना | Ongoing | 342000 | 0 | 2018-07-13
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1707004018/IC/22012034892939 — सार्वजनिक कूप निर्माण गढी की माता के पास ग्राम पंचायत कंजना | New | 0 | 0 | 2025-10-02
PALERA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1707004018/IF/22012034326758 — कपिल धारा कूप निर्माण हरगोविन्‍द्र यादव/बन्‍दे यादव ग्राम पंचायत कंजना | Ongoing | 230000 | 0 | 2017-03-16
PALERA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1707004018/IF/22012034657959 — Mumtaj Khan/ Halke Khan Koop Nirmad Gram Panchayat Kanjna | Ongoing | 246126.86 | 0 | 2021-12-04
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1707004018/IF/22012035216477 — कपिल धारा कूप निर्माण खित्ते अहिरवार /करी ग्राम पंचायत कंजना | Ongoing | 256101.86 | 0 | 2025-01-12
PALERA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1707004018/IF/22012035216764 — कपिल धारा कूप निर्माण दुलीचंद पटेल /बरसाई ग्राम पंचायत कंजना | Ongoing | 256101.86 | 0 | 2024-03-16
PALERA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1707004018/IF/22012035216765 — कपिल धारा कूप निर्माण अब्दुल खान /रज्जब ग्राम पंचायत कंजना | Physically Completed | 256101.86 | 0 | 2024-03-16 | 2026-09-12
PALERA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1707004018/IF/22012035219198 — कपिल धारा कूप निर्माण मुलायम यादव /हरचरन ग्राम पंचायत कंजना | Ongoing | 256101.86 | 0 | 2024-03-16
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1707004018/IF/22012035512743 — JGSA 2025 Khet Talab Nirmad Munnu Yadav Gram Panchayat Kanjna | Approved | 147621.16 | 0 | 2025-04-14
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4607987 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123851500 | Physically Completed | 27000 | 0 | 2025-01-20 | 2026-09-11
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4609935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125522869 | Physically Completed | 27000 | 0 | 2025-01-31 | 2026-09-11
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4612468 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124619046 | Ongoing | 27000 | 0 | 2025-01-31
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4613066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125854621 | Physically Completed | 27000 | 0 | 2025-01-20 | 2026-09-11
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4614382 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125860684 | Physically Completed | 27000 | 0 | 2025-01-20 | 2026-09-11
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4616135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125783823 | Ongoing | 27000 | 3600 | 2025-01-20
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4619027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125841308 | Physically Completed | 27000 | 0 | 2025-01-20 | 2026-09-11
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4620944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126515326 | Physically Completed | 27000 | 0 | 2025-01-20 | 2026-09-11
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4623669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127321747 | Physically Completed | 23490 | 0 | 2025-03-16 | 2026-07-19
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4623674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127323091 | Ongoing | 27000 | 0 | 2025-01-31
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4624306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127187985 | Physically Completed | 27000 | 0 | 2025-01-20 | 2026-09-12
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4627752 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128348165 | Physically Completed | 27000 | 0 | 2025-01-31 | 2026-09-12
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4627756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128348667 | Ongoing | 27000 | 0 | 2025-01-31
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4630651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128857213 | Physically Completed | 27000 | 0 | 2025-03-16 | 2026-09-12
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4630652 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128857608 | Physically Completed | 27000 | 0 | 2025-03-16 | 2026-09-12
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4630659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128858786 | Physically Completed | 27000 | 0 | 2025-01-20 | 2026-09-12
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4630660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128859167 | Physically Completed | 27000 | 6000 | 2025-01-31 | 2026-09-12
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4632226 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129660982 | Physically Completed | 27000 | 0 | 2025-01-20 | 2026-09-12
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4632526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128996137 | Physically Completed | 27000 | 0 | 2025-01-31 | 2026-09-12
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4632860 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129991039 | Physically Completed | 27000 | 0 | 2025-02-08 | 2026-09-12
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4633790 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129772805 | Physically Completed | 27000 | 0 | 2025-03-16 | 2026-09-12
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4636659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130212567 | Physically Completed | 27000 | 0 | 2025-03-16 | 2026-09-12
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4636660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130212600 | Physically Completed | 27000 | 0 | 2025-02-08 | 2026-09-12
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4638480 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131169804 | Physically Completed | 27000 | 0 | 2025-02-08 | 2026-09-12
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4638481 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131169827 | Physically Completed | 27000 | 0 | 2025-02-08 | 2026-09-12
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4639280 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130866200 | Physically Completed | 27000 | 0 | 2025-02-08 | 2026-09-12
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4642917 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134541538 | Ongoing | 27000 | 0 | 2025-02-08
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4710201 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125855788 | Physically Completed | 27000 | 0 | 2025-01-20 | 2026-09-12
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4710827 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125784632 | Physically Completed | 27000 | 0 | 2025-01-31 | 2026-09-12
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4718150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130674949 | Ongoing | 27000 | 14100 | 2025-02-08
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4723319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126957360 | Physically Completed | 27000 | 0 | 2025-01-31 | 2026-09-12
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4776402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125867802 | Physically Completed | 27000 | 2100 | 2025-01-31 | 2026-09-12
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4784599 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130212546 | Physically Completed | 27000 | 0 | 2025-03-16 | 2026-09-12
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4847715 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122555313 | Physically Completed | 27000 | 0 | 2025-02-08 | 2026-09-12
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4866296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125524588 | Ongoing | 27000 | 0 | 2025-03-16
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4960946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125392923 | Ongoing | 27000 | 12600 | 2025-06-27
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4969477 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130306834 | Physically Completed | 27000 | 0 | 2025-06-27 | 2026-09-01
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4971218 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130866240 | Ongoing | 27000 | 12600 | 2025-06-27
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/4972187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130576465 | Physically Completed | 27000 | 0 | 2025-05-08 | 2026-09-12
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5251652 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130576472 | Physically Completed | 27000 | 0 | 2025-05-16 | 2026-09-12
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5265230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124536156 | Ongoing | 27000 | 0 | 2025-06-27
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5270689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125784253 | Physically Completed | 27000 | 0 | 2025-06-27 | 2026-09-12
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5276569 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125526669 | Physically Completed | 27000 | 0 | 2025-05-16 | 2026-09-12
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5293808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126956449 | Physically Completed | 27000 | 0 | 2025-06-27 | 2026-09-12
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5296172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127173464 | Physically Completed | 27000 | 0 | 2025-06-27 | 2026-09-12
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5303052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131340877 | Physically Completed | 23490 | 0 | 2025-06-27 | 2026-07-19
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5326384 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125849343 | Physically Completed | 27000 | 0 | 2025-05-16 | 2026-09-01
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5334046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127175900 | Physically Completed | 27000 | 0 | 2025-05-16 | 2026-09-12
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5473897 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125785008 | Ongoing | 27000 | 0 | 2025-06-27
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5476417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131340854 | Physically Completed | 27000 | 0 | 2025-07-04 | 2026-09-12
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5553700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130128777 | Ongoing | 27000 | 0 | 2025-07-04
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5555058 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131340798 | Physically Completed | 27000 | 5100 | 2025-07-04 | 2026-08-30
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5558844 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130576439 | Physically Completed | 27000 | 0 | 2025-07-04 | 2026-09-12
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5567185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131169848 | Ongoing | 27000 | 12600 | 2025-07-04
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5619594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124618257 | Physically Completed | 23490 | 0 | 2025-07-04 | 2026-07-19
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5624185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131340771 | Ongoing | 27000 | 16200 | 2025-07-04
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5624186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131340778 | Physically Completed | 27000 | 0 | 2025-07-04 | 2026-09-12
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5653605 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127176668 | Physically Completed | 27000 | 1500 | 2025-07-11 | 2026-09-12
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5654616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130866218 | Physically Completed | 27000 | 3300 | 2025-07-11 | 2026-09-12
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5654807 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131169815 | Physically Completed | 27000 | 6900 | 2025-07-11 | 2026-08-30
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5709160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131340829 | Ongoing | 27000 | 12600 | 2025-07-18
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5809103 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124618645 | Ongoing | 27000 | 0 | 2025-09-23
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5809437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134922004 | Ongoing | 27000 | 0 | 2025-09-23
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5809489 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129181170 | Ongoing | 27000 | 0 | 2025-09-23
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5809552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130576462 | Ongoing | 27000 | 0 | 2025-09-30
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5809556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127177382 | Ongoing | 27000 | 0 | 2025-09-30
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5809652 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130866214 | Physically Completed | 27000 | 0 | 2025-09-23 | 2026-09-12
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5809653 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130866224 | Ongoing | 27000 | 0 | 2025-09-23
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5809689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131340707 | Ongoing | 27000 | 0 | 2025-09-23
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5809690 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131340781 | Physically Completed | 27000 | 0 | 2025-09-30 | 2026-09-12
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5809691 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131340786 | Ongoing | 27000 | 0 | 2025-09-30
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5809862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129991762 | Ongoing | 27000 | 0 | 2025-09-30
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5809887 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129180945 | Ongoing | 27000 | 0 | 2025-09-30
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5809963 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130128632 | Physically Completed | 27000 | 0 | 2025-09-30 | 2026-09-12
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5810003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131169719 | Physically Completed | 27000 | 0 | 2025-09-30 | 2026-09-11
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5810125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131169781 | Ongoing | 27000 | 0 | 2025-09-30
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5810317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128996231 | Ongoing | 27000 | 8400 | 2025-10-08
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5810490 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131109522 | Ongoing | 27000 | 0 | 2025-10-08
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5810929 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130128950 | Ongoing | 27000 | 0 | 2025-10-08
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5838228 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131109536 | Ongoing | 27000 | 0 | 2025-10-08
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/5838268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126504894 | Ongoing | 27000 | 0 | 2025-10-08
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/6369232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125933335 | Approved | 27000 | 0 | 2025-03-08
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004018/IF/IAY/6369569 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125939306 | Approved | 27000 | 0 | 2025-03-08
PALERA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1707004018/RC/22012034680521 — सुदूर सड़क निर्माण गड़ा घाट से कंजना की और ग्राम पंचायत कंजना | Ongoing | 936019.67 | 0 | 2024-12-05
PALERA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1707004018/RC/22012034841993 — खेत सडक निर्माण अनंतपुरा मार्ग से धनीराम रजक के कुआ तक ग्राम पंचायत कंजना | Approved | 0 | 0 | 2025-04-14
PALERA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1707004018/RC/22012034849990 — सीसी रोड निर्माण मैन राेड से छिदामी लुहार के मकान तक ग्राम पंचायत कंजना कनवर्जेन्‍स | Approved | 31700 | 0 | 2025-04-15
PALERA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovation of Fisheries Ponds for Community / Repair & Maintenance of Fishery Pond for Community | Repair & maint of Pond/ Tank | 1707004018/WC/22012035078544 — Dagout pond nirmad chotaiyan ghat ke bagal me gram panchayat kanjna | Ongoing | 402176.36 | 0 | 2023-06-18
PALERA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1707004018/WC/22012035078547 — Dagout pond nirmad ber har gram panchayat kanjna | Ongoing | 405445.15 | 0 | 2023-06-18
PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1707004018/WH/22012034944250 — स्‍टापडेम मरम्‍मत कार्य खांगरे घाट ग्राम पंचायत कंजना | Ongoing | 588448.24 | 0 | 2025-06-12
PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1707004018/WH/22012034944253 — स्टापडेम मरम्मत कार्य चमरा घाट ग्राम पंचायत कंजना | New | 0 | 0 | 2025-04-14
PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1707004018/WH/22012034944257 — स्टापडेम मरम्मत कार्य चमरा घाट ग्राम पंचायत कंजना | Approved | 0 | 0 | 2025-04-14