## Work List
Exported on: 2026-10-09 02:15:52
Filters applied:
Data source: VBGRAMG
District: TIKAMGARH
Block: All
Panchayat: KHERA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PALERA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1707004062/AV/22012034371412 — आंगनवाडी भवन बांउडीबाल सहित निर्माण ग्राम विजयपुर ग्राम पंचायत खेरा | Ongoing | 180000 | 0 | 2019-01-03
PALERA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1707004062/AV/22012034508550 — चारागाह निर्माण लालइया हार ग्राम विजयपुर ग्राम पंचायत खेरा | Ongoing | 1496132.95 | 0 | 2020-06-04
PALERA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1707004062/DP/22012034408460 — व़क्षारोपण कार्य माध्‍यमिक शाला के सामने ग्राम विजयपुर ग्राम पंचायत खेरा | Ongoing | 342000 | 0 | 2018-07-19
PALERA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1707004062/DP/22012034524094 — पेयजल कूप निर्माण गौशाला के पास ग्राम विवजयपुर पंचायत खेरा | Ongoing | 567610.07 | 0 | 2021-03-12
PALERA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1707004062/DP/22012034531360 — बृक्षा रोपण गौशाला के पास ललिया हार में ग्राम विजयपुर ग्राम पंचायत खेरा | Ongoing | 394489.84 | 0 | 2021-09-14
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1707004062/IF/22012035405936 — JGSA खेत तालाब निर्माण रामप्रसाद कुशवाहा तनय अच्छे ग्राम विजयपुर | Ongoing | 147621.16 | 0 | 2025-05-08
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1707004062/IF/22012035406476 — JGSA खेत तालाब निर्माण ब्रजलाल कुशवाहा तनय घनश्याम ग्राम विजयपुर | Ongoing | 147621.16 | 0 | 2025-05-08
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1707004062/IF/22012035459545 — JGSA खेत तालाब निर्माण रामदयाल पाल तनय गनपत ग्राम विजयपुर | Ongoing | 147621.16 | 0 | 2025-05-16
PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1707004062/IF/22012035502497 — JGSA रिचार्ज स्ट्रक्चर 2025 कपिल धारा कूप काशीराम कुशवाहा छेवला | Approved | 0 | 0 | 2025-04-14
PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1707004062/IF/22012035502592 — JGSA रिचार्ज स्ट्रक्चर 2025 कपिल धारा कूप मातादीन कुशवाहा /पंचम खेरा | Approved | 0 | 0 | 2025-04-14
PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1707004062/IF/22012035516350 — JGSA रिचार्ज स्ट्रक्चर 2025 Pramod Banshkar kapil dhara koop ke paas vijaypur | Approved | 0 | 0 | 2025-04-14
PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1707004062/IF/22012035531458 — JGSA DUGWELL RECHARGE PIT KASHIRAM KUSHWAHA KE KOOP KE PAAS SAJJANPUR CHHEVLA | New | 0 | 0 | 2025-04-14
PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1707004062/IF/22012035555673 — JGSA DUGWELL RECHARGE PIT PRAMOD BANSHKAR KE KOOP KE PAAS GRAM VIJAYPUR | Ongoing | 25899.46 | 0 | 2025-06-03
PALERA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/1257937 — Construction of IAY House -IAY REG. NO. MP4340129 | Physically Completed | 27000 | 0 | 2018-06-09 | 2026-09-11
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/4675871 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122746648 | Ongoing | 27000 | 0 | 2025-05-26
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/4675872 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122748281 | Physically Completed | 27000 | 1200 | 2025-04-23 | 2026-09-11
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/4675873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122749058 | Approved | 27000 | 0 | 2024-09-13
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/4675899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124168801 | Ongoing | 27000 | 0 | 2025-03-02
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/4675921 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124194466 | Physically Completed | 27000 | 900 | 2025-03-02 | 2026-09-11
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/4676662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124776737 | Physically Completed | 27000 | 0 | 2024-12-08 | 2026-09-11
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/4676663 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124777372 | Physically Completed | 27000 | 0 | 2024-12-08 | 2026-09-11
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/4676745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125503197 | Physically Completed | 27000 | 0 | 2025-03-02 | 2026-09-11
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/4678627 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127133050 | Approved | 27000 | 0 | 2024-09-13
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/4679427 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130821986 | Physically Completed | 27000 | 0 | 2024-12-08 | 2026-09-11
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/4679669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132294991 | Physically Completed | 27000 | 0 | 2025-03-02 | 2026-09-11
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/4679672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132316167 | Ongoing | 27000 | 0 | 2025-01-07
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/4680871 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127942893 | Physically Completed | 27000 | 0 | 2025-03-02 | 2026-09-11
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/4681958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150785727 | Approved | 27000 | 0 | 2024-09-13
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/4681961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150791094 | Physically Completed | 27000 | 0 | 2025-03-02 | 2026-09-11
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/4682114 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148995720 | Physically Completed | 27000 | 1800 | 2024-12-08 | 2026-09-11
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/4799883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148958188 | Ongoing | 27000 | 0 | 2025-01-07
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/5319075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119618118 | Ongoing | 27000 | 14400 | 2025-04-23
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/5365784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132293498 | Ongoing | 27000 | 12600 | 2025-07-18
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/5377974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148926511 | Physically Completed | 27000 | 0 | 2025-04-23 | 2026-09-11
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/5379698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119618180 | Ongoing | 27000 | 9000 | 2025-05-26
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/5383864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124775477 | Physically Completed | 27000 | 0 | 2025-04-23 | 2026-09-11
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/5383905 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148995058 | Physically Completed | 27000 | 12600 | 2025-04-23 | 2026-09-11
PALERA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/5475135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124172462 | Approved | 27000 | 0 | 2024-09-27
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/5619563 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150783040 | Physically Completed | 27000 | 16200 | 2025-05-26 | 2026-09-11
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/5623819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148927573 | Physically Completed | 27000 | 0 | 2025-05-26 | 2026-09-11
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/5623946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148995986 | Ongoing | 27000 | 12600 | 2025-05-26
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/5624613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132294631 | Physically Completed | 27000 | 0 | 2025-07-18 | 2026-09-11
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/5654900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148150065 | Physically Completed | 23490 | 0 | 2025-09-03 | 2026-07-19
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6331434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122740432 | Approved | 27000 | 0 | 2026-03-06
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6332309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128150572 | Approved | 27000 | 0 | 2026-03-06
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6332446 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130818645 | Approved | 27000 | 0 | 2026-04-16
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6332793 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148958060 | Ongoing | 27000 | 0 | 2026-10-08
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6333146 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148927726 | Approved | 27000 | 0 | 2026-04-16
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6351479 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148995341 | Approved | 27000 | 0 | 2026-03-06
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6351482 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148996548 | Ongoing | 27000 | 0 | 2026-10-08
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6351496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148989679 | Ongoing | 27000 | 0 | 2026-10-08
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6351582 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126470289 | Approved | 27000 | 0 | 2026-04-16
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6351621 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148996389 | Approved | 27000 | 0 | 2026-06-26
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6351634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148988829 | Approved | 27000 | 0 | 2026-04-16
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6351680 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148991326 | Approved | 27000 | 0 | 2026-04-16
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6351752 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148663042 | Ongoing | 27000 | 0 | 2026-10-08
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6351954 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148992598 | Approved | 27000 | 0 | 2026-03-06
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6352072 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148664892 | Approved | 27000 | 0 | 2026-04-16
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6352230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149136752 | Ongoing | 27000 | 0 | 2026-10-08
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6352303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148990864 | Approved | 27000 | 0 | 2026-06-01
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6352733 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130822849 | Approved | 27000 | 0 | 2026-04-16
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6352741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148666753 | Approved | 27000 | 0 | 2026-04-16
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6353152 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148993150 | Approved | 27000 | 0 | 2026-04-16
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6353460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148957800 | Ongoing | 27000 | 0 | 2026-10-08
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6353467 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127113683 | Approved | 27000 | 0 | 2026-03-06
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6353469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132294831 | Approved | 27000 | 0 | 2026-03-06
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6353545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148927333 | Ongoing | 27000 | 0 | 2026-10-08
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6353636 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148752570 | Ongoing | 27000 | 0 | 2026-10-08
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6353739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149576167 | Ongoing | 27000 | 0 | 2026-10-08
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6353753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127918053 | Approved | 27000 | 0 | 2026-04-16
PALERA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6353952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148990054 | Approved | 27000 | 0 | 2026-04-16
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6354053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127916938 | Approved | 27000 | 0 | 2026-03-06
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6354126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148665131 | Approved | 27000 | 0 | 2026-03-06
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6354225 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132296246 | Approved | 27000 | 0 | 2026-03-06
PALERA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1707004062/IF/IAY/6354562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130821921 | Approved | 27000 | 0 | 2026-03-06
PALERA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1707004062/RC/22012034580705 — सी सी रोड निर्माण दीवान बाबा से जमुना कुशवाहा के माकन की और ग्राम खेरा ग्राम पंचायत खेरा | Ongoing | 55750 | 0 | 2021-11-13
PALERA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1707004062/RC/22012034586347 — सी सी रोड निर्माण जमना कुशवाहा के मकान से प्रजापति मुहल्ला जियो टावर की ओर ग्राम खेरा | Ongoing | 57364 | 0 | 2021-11-13
PALERA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1707004062/RC/22012034640252 — नवीन खेत सडक़ विजयपुर से मोटे के हार तक ग्राम विजयपुर ग्राम पंचायत खेत | Ongoing | 1976676.2 | 0 | 2024-06-14
PALERA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1707004062/WC/22012034446615 — तालाब निर्माण फार्म के पास ग्राम पंचायत खेरा | Ongoing | 896000 | 0 | 2019-03-10
PALERA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1707004062/WC/22012035012639 — परकोलेशन टेंक निर्माण ऊदल कुशवाहा के खेत के पास ग्राम खेरा पंचायत खेरा | Ongoing | 494548.3 | 0 | 2024-06-14
PALERA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1707004062/WC/22012035186897 — परकोलेशन टेंक निर्माण चारोखर हार ग्राम खेरा ग्राम पंचायत खेरा | Ongoing | 492390.06 | 0 | 2024-06-15
PALERA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1707004062/WC/22012035186926 — परकोलेशन टेंक निर्माण टगरा हार ग्राम खेरा ग्राम पंचायत खेरा | Ongoing | 486015.19 | 0 | 2024-03-16
PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1707004062/WC/22012035259991 — पर्कोलेसन टैंक बेकोला हार गोचर में ग्राम छेवला ग्राम पंचायत खेरा | Approved | 0 | 0 | 2025-04-05
PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1707004062/WC/22012035283093 — JGSA रिचार्ज स्ट्रक्चर 2025 सार्वजनिक पेयजल कूप गणेशपुरा विजयपुर | Ongoing | 25899.46 | 0 | 2025-04-27
PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1707004062/WC/22012035283133 — JGSA रिचार्ज स्ट्रक्चर 2025 सार्वजनिक पेयजल कूप ग्राम खेरा | Ongoing | 25899.46 | 0 | 2025-04-27
PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1707004062/WC/22012035293983 — अमृत सरोवर निर्माण कार्य चारोखर नाला ग्राम खेरा पंचायत खेरा | Approved | 0 | 0 | 2025-04-14
PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1707004062/WC/22012035301831 — Amrat sarovar Charokhar Nala1st gram khera | Ongoing | 2481899.93 | 0 | 2025-06-04
PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1707004062/WC/22012035312126 — JGSA DUGWELL RECHARGE PIT GAUSHALA KE KOOP KE PASS GRAM VIJAYPUR | Ongoing | 25899.46 | 0 | 2025-06-10
PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1707004062/WC/22012035312127 — JGSA DUGWELL RECHARGE PIT DHANEE MAHARAJ KE KOOP KE PAAS VIJAYPUR | Approved | 25899.46 | 0 | 2025-04-14
PALERA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1707004062/WC/22012035312130 — JGSA DUGWELL RECHARGE PIT AADIWASI MUHALLA KE KOOP KE PAS VIJAPUR | Ongoing | 25899.46 | 0 | 2025-06-03