## Work List
Exported on: 2026-09-05 13:16:28
Filters applied:
Data source: VBGRAMG
District: TIKAMGARH
Block: All
Panchayat: DHARAMPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BALDEOGARH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1707005023/DP/22012034445482 — सार्वजनिक पेयजल कूप निर्माण हरिजन बस्‍ती ग्राम पंचायत धरमपुरा | Ongoing | 445000 | 0 | 2019-03-12
BALDEOGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1707005023/DP/22012034530497 — वृक्षारोपण निर्माण कार्य हनुमत पुरा की पहाड़ी पर ग्राम पंचायत धर्मपुरा | Ongoing | 685575.78 | 0 | 2021-08-12
BALDEOGARH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707005023/IF/22012034475239 — कपिलधारा कूप निर्माण राजाराम लोधी/कलुआ लोधी धर्मपुरा | Ongoing | 230000 | 0 | 2019-03-10
BALDEOGARH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1707005023/IF/22012034593473 — बकरी शेड निर्माण कार्य हरिबाई/मातादीन सौंर | Ongoing | 46636.05 | 0 | 2020-08-20
BALDEOGARH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1707005023/IF/22012034603721 — बकरी पालन शेड निर्माण उमा बरार/अशोक | Ongoing | 46636.05 | 0 | 2020-09-27
BALDEOGARH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Poultry Shelter for Individuals / Construction of Poultry Livestock_Shelter for Individuals | Poultry Shelter | 1707005023/IF/22012034603724 — कुक्‍कुट शेड निर्माण हरबूबाई/कन्‍दू | Ongoing | 51554.19 | 0 | 2020-09-27
BALDEOGARH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707005023/IF/22012034654807 — कपिलधारा कूप निर्माण चूरामन/खुमान लोधी | Ongoing | 247659.26 | 0 | 2021-02-02
BALDEOGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1707005023/IF/22012035137510 — नंदन फलोद्यान कार्य भगवानदास/हरचरन लोधी बछौडा धरमपुरा | Ongoing | 133212.69 | 0 | 2023-10-06
BALDEOGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1707005023/IF/22012035138098 — नंदन फलोद्यान कार्य आशाराम/धतुआ अहिरवार ग्राम पंचायत धरमपुरा | Ongoing | 133212.69 | 0 | 2023-09-17
BALDEOGARH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coast Line plntation of Forestry Trees-Individuals / Along the coast Line Plantation of Forestry Trees for Individuals | Plantation | 1707005023/IF/22012035142040 — नन्दन फल उद्यान बाल्चन्द्र / रामचरन लोधी ग्राम धरमपुरा ग्रा.पं. धरमपुरा | Ongoing | 133212.69 | 0 | 2024-01-03
BALDEOGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1707005023/IF/22012035143510 — नंदनफल उद्यान प्रेमचंद्र /रामद्याल लोधी ग्राम बछोडा ग्राम पं. धरमपुरा | Ongoing | 145050.83 | 0 | 2024-11-09
BALDEOGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1707005023/IF/22012035252506 — नन्दन फल उद्यान मनप्यारे / भग्गू साहू ग्राम धरमपुरा ग्रा.पं.धरमपुरा | Approved | 145050.83 | 0 | 2024-04-14
BALDEOGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1707005023/IF/22012035252513 — नन्दन फल उद्यान गोविन्द्र / मकुन्दी साहू ग्राम धरमपुरा ग्रा.पं.धरमपुरा | Approved | 145050.83 | 0 | 2024-04-14
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707005023/IF/22012035339805 — kapil dhara koop nirmad karya mannulal lodhi/manak lal bachhoda | Approved | 0 | 0 | 2025-04-10
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707005023/IF/22012035341434 — kapil dhara koop nirmad karya devendr lodhi/asharam lodhi dharampura | Approved | 0 | 0 | 2025-04-10
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707005023/IF/22012035341567 — kapil dhara koop nirmad karya matadeen sahu/makundi sahu dharampura | Approved | 0 | 0 | 2025-04-10
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707005023/IF/22012035341870 — Kapil dhara koop nirmad karya ghanshyam/kaloo Lodhi Dharampura | Approved | 0 | 0 | 2025-04-10
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707005023/IF/22012035341927 — Kapil dhara koop nirmad karya paravat/surre Lodhi | Approved | 0 | 0 | 2025-04-10
BALDEOGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1707005023/IF/22012035344256 — Khet talab nirmad karya tulsi/nandu Ahirwar Dharampura | Ongoing | 199692.75 | 0 | 2025-04-22
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707005023/IF/22012035344324 — Kapil dhara koop nirmad karya Ramju/Nandu Ahirwar Dharampura | New | 0 | 0 | 2025-04-10
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707005023/IF/22012035344497 — Kapil dhara koop nirmad karya kashiram/Dharamdas Lodhi | Approved | 0 | 0 | 2025-04-10
BALDEOGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707005023/IF/22012035354195 — kapil dhara koop nirmad karya khadi urf gajadhar lodhi gram bachhoda gram panchayat dharampura | Ongoing | 327831.8 | 61050 | 2026-04-30
BALDEOGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1707005023/IF/22012035559717 — Khet talab nirman karya kishan Lal Yadav s/o Halke yadav GP Dharampura | Ongoing | 174488.23 | 0 | 2025-06-19
BALDEOGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1707005023/IF/22012035566386 — khet talab nirmad karya geeta/manoj goswami gram panchyat dharampura | Ongoing | 147621.16 | 0 | 2025-06-25
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707005023/IF/22012035570211 — कपिलधारा कूप निर्माण कार्य रमजू/नंदू अहिरवार ग्राम पंचायत धर्मपुरा | Ongoing | 327831.8 | 0 | 2025-06-27
BALDEOGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1707005023/IF/22012035616614 — Dugwell Recharge structure surajnarayan kurmi/achchhelal kurmi gram panchyat dharampura | Approved | 0 | 0 | 2025-08-15
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1707005023/IF/22012035631520 — एक बगिया मॉ के नाम शीलावाई/रिख्‍खू लोधी बछौडा (MP643424) ग्राम पंचायत धरमपुरा | Ongoing | 266578.64 | 0 | 2025-11-01
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1707005023/IF/22012035631940 — एक बगिया मॉ के नाम सखीवाई/राकेश लोधी बछौडा (MP5878345) ग्राम पंचायत धरमपुरा | Ongoing | 214269.77 | 0 | 2025-11-01
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1707005023/IF/22012035648792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150669946 | Ongoing | 23500 | 4950 | 2025-12-10
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1707005023/IF/22012035655687 — एक बगिया मॉ के नाम दीपा/मन्‍नू लोधी बछौडा (MP2357066) ग्राम पंचायत धरमपुरा | Approved | 0 | 0 | 2025-10-02
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1707005023/IF/22012035655692 — एक बगिया मॉ के नाम ममता/पूरन लोधी बछौडा (MP2362470) ग्राम पंचायत धरमपुरा | Approved | 164051.56 | 0 | 2025-10-02
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1707005023/IF/22012035655698 — एक बगिया मॉ के नाम जमनावाई/भजनलाल लोधी बछौडा (MP4804008) ग्राम पंचायत धरमपुरा | Approved | 164051.56 | 0 | 2025-10-02
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1707005023/IF/22012035655768 — एक बगिया मॉ के नाम रम्‍बूवाई ऊर्फ रामबाई /रामेश्‍वर लोधी बछौडा (MP643421) ग्राम पंचायत धरमपुरा | Approved | 0 | 0 | 2025-10-02
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1707005023/IF/22012035658032 — एक बगिया मॉ के नाम पार्वती/धनीराम लोधी बछौडा (MP1979678) ग्राम पंचायत धरमपुरा | Approved | 0 | 0 | 2025-10-06
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1707005023/IF/22012035660152 — एक बगिया मॉ के नाम बेटीवाई/मनीराम लोधी बछौडा (MP4803456) ग्राम पंचायत धरमपुरा | Approved | 164051.56 | 0 | 2025-10-02
BALDEOGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707005023/IF/IAY/4753617 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117440004 | Approved | 27000 | 0 | 2024-10-03
BALDEOGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707005023/IF/IAY/4798653 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149246027 | Ongoing | 27000 | 0 | 2026-08-28
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707005023/IF/IAY/4801483 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150669946 | Ongoing | 27000 | 0 | 2025-06-02
BALDEOGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707005023/IF/IAY/5117818 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150685216 | Approved | 27000 | 0 | 2025-03-06
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707005023/IF/IAY/5304468 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150675300 | Physically Completed | 27000 | 1500 | 2025-07-27 | 2026-08-31
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707005023/IF/IAY/5766980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150675536 | Ongoing | 27000 | 8400 | 2025-12-08
BALDEOGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707005023/IF/IAY/5767745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150139991 | Approved | 27000 | 0 | 2025-03-06
BALDEOGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707005023/IF/IAY/5768113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148519116 | Ongoing | 27000 | 0 | 2026-08-28
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707005023/IF/IAY/5768205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150017328 | Ongoing | 27000 | 0 | 2025-12-07
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707005023/IF/IAY/5768285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150663934 | Approved | 27000 | 0 | 2025-05-19
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707005023/IF/IAY/5768594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150664497 | Approved | 27000 | 0 | 2025-05-24
BALDEOGARH | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1707005023/RC/22012034841791 — सुदूर सड़क निर्माण कार्य देवेन्द्र लोधी के खेत से मुख्य मार्ग तक ग्राम धर्मपुरा ग्राम पंचायत धर्मपुर | Approved | 0 | 0 | 2025-04-05
BALDEOGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1707005023/WC/VB/22012035329902 — Roof watar harvesting nirmad karya swasth kendra Dharampura | Approved | 0 | 0 | 2026-07-14