## Work List
Exported on: 2026-09-04 05:59:58
Filters applied:
Data source: VBGRAMG
District: TIKAMGARH
Block: All
Panchayat: MAJGUWAN
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BALDEOGARH | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1707005070/AV/22012034570365 — डायनिंग हॉल निर्माण शासकीय माध्यमिक शाला भितरवार | Ongoing | 16093.2 | 0 | 2021-07-03
BALDEOGARH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1707005070/DP/22012034408634 — बृक्षारोपण कार्य शांतिधाम परिसर भितरवार, मझगुवां | Ongoing | 342000 | 0 | 2018-07-25
BALDEOGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wastelands Block Plantation-Farm Forestry -Comm / Wasteland Block Plantation of Farm Forestry Trees for Community | Plantation | 1707005070/DP/22012034530703 — CTR नंदफलोदयान कार्य तुलसिया/बंदू पाल ग्राम पंचायत मझगुवॉं | Ongoing | 117912.51 | 1500 | 2021-07-03
BALDEOGARH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wastelands Block Plantation-Farm Forestry -Comm / Wasteland Block Plantation of Farm Forestry Trees for Community | Plantation | 1707005070/DP/22012034530704 — CTR नंदनफलोदयान कार्य हरिराम/धर्मदास पाल ग्राम पंचायत मझगुवॉं | Ongoing | 117912.51 | 0 | 2021-07-03
BALDEOGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1707005070/IF/22012035280609 — कपिलधारा कूप निर्माण रविन्‍द्र प्रताप सिंह/प्रेटी राजा ग्राम पंचायत मझगुवां | Approved | 0 | 0 | 2024-12-10
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1707005070/IF/22012035631416 — एक बगिया मॉ के नाम कौशल्‍या/मकुंद सिंह ठाकुर भितरवार (MP4583091) ग्राम पंचायत मझगुवां | Ongoing | 266578.64 | 0 | 2025-10-30
BALDEOGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707005070/IF/IAY/4753925 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117717084 | Physically Completed | 23490 | 0 | 2025-12-11 | 2026-08-09
BALDEOGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707005070/IF/IAY/663043 — Construction of IAY House -IAY REG. NO. MP1747881 | Approved | 27000 | 0 | 2020-01-12
BALDEOGARH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1707005070/IF/IAY/670114 — Construction of IAY House -IAY REG. NO. MP2324544 | Approved | 27000 | 0 | 2020-01-12
BALDEOGARH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1707005070/WC/22012034931457 — नवीन तालाब निर्माण बुनकर के हार के पास ग्राम पंचायत मझगुवां | Ongoing | 1184414.3 | 0 | 2022-04-18
BALDEOGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707005070/WC/22012035122331 — परकुलेशन टेक निर्माण लारघाट के नाले पर ग्रा0पं0 मझगुवॉं | Ongoing | 603211.4 | 0 | 2023-10-07
BALDEOGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707005070/WC/22012035122333 — परकुलेशन टेक निर्माण महेन्‍द्र सिंह के हार के नाले पर भितरवार ग्रा0पं0 मझगुवॉं | Ongoing | 611172.2 | 0 | 2023-10-07
BALDEOGARH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707005070/WC/22012035122335 — परकुलेशन टेक निर्माण भीकम सिंह के हार के नाले पर भितरवार ग्रा0पं0 मझगुवॉं | Ongoing | 586354.65 | 0 | 2023-10-07
BALDEOGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707005070/WC/22012035238622 — परकोलेशन टैंक निर्माण कार्य बगेचा के पास मझगुवां | New | 0 | 0 | 2024-08-15
BALDEOGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707005070/WC/22012035240034 — परकोलेशन टैंक निर्माण कार्य धूमगढ़ के पास मझगुवां | New | 0 | 0 | 2024-08-15
BALDEOGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707005070/WC/22012035261439 — परकुलेसन टेंक निर्माण कमतू रैकवार के हार के पास भितरवार | New | 0 | 0 | 2025-04-01
BALDEOGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707005070/WC/22012035261446 — परकुलेसन टेंक निर्माण दशरथ रैकवार के हार के पास भितरवार | New | 0 | 0 | 2025-04-01
BALDEOGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707005070/WC/22012035261452 — परकुलेसन टेंक निर्माण सिकेट्री के हार के पास मझ्गुवा | New | 0 | 0 | 2025-04-01
BALDEOGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707005070/WC/22012035261456 — परकुलेसन टेंक निर्माण दिकोल्याऊ के हार के पास मझ्गुवा | New | 0 | 0 | 2025-04-01
BALDEOGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707005070/WC/22012035261459 — परकुलेसन टेंक निर्माण दिस्सू के हार के पास मझ्गुवा | New | 0 | 0 | 2025-04-01
BALDEOGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707005070/WC/22012035261462 — परकुलेसन टेंक निर्माण मंगलयादव के हार के पास मझ्गुवा | New | 0 | 0 | 2025-04-01
BALDEOGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707005070/WC/22012035261463 — परकुलेसन टेंक निर्माण भाईसाब यादव के हार के पास मझ्गुवा | New | 0 | 0 | 2025-04-01
BALDEOGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707005070/WC/22012035261464 — परकुलेसन टेंक निर्माण रघुनाथ यदाव के हार के पास मझ्गुवा | New | 0 | 0 | 2025-04-01
BALDEOGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707005070/WC/22012035261466 — परकुलेसन टेंक निर्माण मुलुवा के हार के पास मझ्गुवा | New | 0 | 0 | 2025-04-01
BALDEOGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1707005070/WC/22012035261470 — परकुलेसन टेंक निर्माण बारे के हार के पास भितरवार | New | 0 | 0 | 2025-04-01
BALDEOGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1707005070/WC/VB/22012035330025 — निर्माण कार्य कंटू ट्रेंच हरदौल बाबा की पहाड़ी ग्राम पंचायत मझगुवां | Approved | 0 | 0 | 2026-07-30
BALDEOGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1707005070/WC/VB/22012035330032 — निर्माण कार्य कंटू ट्रेंच ग्वाल बाबा की पहाड़ी भितरवार ग्राम पंचायत मझगुवां | Approved | 0 | 0 | 2026-07-30
BALDEOGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1707005070/WC/VB/22012035330036 — रुफ वाटर हार्वेस्टिंग प्राथमिक शाला ग्राम पंचायत मझगुवां | Approved | 0 | 0 | 2026-07-30
BALDEOGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1707005070/WC/VB/22012035330040 — रूफ वाटर हार्वेस्टिंग आंगनबाड़ी केंद्र ग्राम पंचायत मझगुवां | Approved | 0 | 0 | 2026-07-30
BALDEOGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1707005070/WC/VB/22012035330042 — रूप वाटर हार्वेस्टिंग आंगनबाड़ी केंद्र भितरवार ग्राम पंचायत मझगुवां | Approved | 0 | 0 | 2026-07-30
BALDEOGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1707005070/WC/VB/22012035330043 — रुफ वाटर हार्वेस्टिंग प्राथमिक शाला ग्राम पंचायत मझगुवां | Approved | 0 | 0 | 2026-07-30
BALDEOGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1707005070/WC/VB/22012035330044 — निर्माण कार्य बोल्डर चैक फार्म नाला ग्राम पंचायत मझगुवां 01 | Approved | 0 | 0 | 2026-07-30
BALDEOGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1707005070/WC/VB/22012035330047 — निर्माण कार्य बोल्डर चैक फार्म नाला ग्राम पंचायत मझगुवां 02 | Approved | 0 | 0 | 2026-07-30
BALDEOGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1707005070/WC/VB/22012035330048 — निर्माण कार्य ग्रेवियन वैसपुरिया नाला ग्राम पंचायत मझगुवां 01 | Approved | 0 | 0 | 2026-07-30
BALDEOGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1707005070/WC/VB/22012035330051 — निर्माण कार्य ग्रेवियन वैसपुरिया नाला ग्राम पंचायत मझगुवां 02 | Approved | 0 | 0 | 2026-07-30