## Work List
Exported on: 2026-10-18 16:26:55
Filters applied:
Data source: VBGRAMG
District: CHHATARPUR
Block: All
Panchayat: MUDEHRA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
GAURIHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1708001002/AV/22012034662547 — गोठान निर्माण कार्य निर्माण मुड़हरा | Ongoing | 56000 | 0 | 2024-12-25
GAURIHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1708001002/DP/22012034579435 — ब्रक्षारोपड़ निर्माण कार्य मुड़ेहरा से चंदवारा मार्ग में | Ongoing | 789594.33 | 0 | 2023-04-14
GAURIHAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1708001002/IF/22012034440543 — हितैसी कपिल धारा कूप निर्माण चुनवाद यादव / लल्लू यादव | Ongoing | 200000 | 0 | 2019-03-13
GAURIHAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708001002/IF/22012034467630 — RFR_kail_ khet talab_ vijay singh/kalideen khangar | Ongoing | 288000 | 0 | 2019-03-13
GAURIHAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001002/IF/22012035063949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123369641 | Ongoing | 18500 | 0 | 2023-04-05
GAURIHAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708001002/IF/22012035126456 — खेत तालाब निर्माण कार्य गोविन्द प्रसाद तिवारी | Ongoing | 385261.22 | 0 | 2023-10-03
GAURIHAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708001002/IF/22012035162039 — खेत तालाब निर्माण गरीबा / बल्‍दू प्रजापति | Ongoing | 385261.22 | 0 | 2023-10-08
GAURIHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1708001002/IF/22012035254476 — pashu shed nirman lakhan kushwaha | Approved | 0 | 0 | 2024-06-08
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708001002/IF/22012035347514 — खेत तालाब निर्माण कार्य मंगल सिंह / मूरत सिंह | New | 0 | 0 | 2025-04-14
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708001002/IF/22012035347516 — खेत तालाब निर्माण कार्य मंगल सिंह / मूरत सिंह | Ongoing | 395663.21 | 0 | 2025-04-25
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708001002/IF/22012035347540 — खेत तालाब निर्माण कार्य पोला / गंगवा अहिरवार | Approved | 395663.21 | 0 | 2025-04-14
GAURIHAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1708001002/IF/22012035371015 — JGSA 2025 Recharge Structure Rajendra Kumar Byohariya | Approved | 0 | 0 | 2025-04-20
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708001002/IF/22012035611163 — एक बगिया मां के नाम जानकी / रामदीन कुशवाहा | Ongoing | 270108.4 | 0 | 2025-09-21
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708001002/IF/22012035622629 — एक बगिया मां के नाम सविता / शैलेन्‍द्र तिवारी | Ongoing | 270108.4 | 7500 | 2025-09-21
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708001002/IF/22012035622647 — एक बगिया मां के नाम आशा / गणेश अहिरवार | Ongoing | 277747.2 | 9300 | 2025-09-21
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708001002/IF/22012035622655 — एक बगिया मां के नाम पूजा / प्रमोद तिवारी | Ongoing | 277747.2 | 9300 | 2025-09-21
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708001002/IF/22012035632816 — एक बगिया मां के नाम कार्य सुमित्रा / विनोद कुशवाहा | Approved | 271842.58 | 0 | 2025-08-16
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708001002/IF/22012035632863 — एक बगिया मां के नाम कार्य रेखा / हल्‍के विश्‍वकर्मा | Ongoing | 142295.13 | 0 | 2025-12-18
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708001002/IF/22012035640055 — KHET TAALAB VIMLA SAHU/HALKE SAHU | Ongoing | 167012.44 | 0 | 2026-02-12
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708001002/IF/22012035652539 — Khet talab nirman kary pappu sahu | Ongoing | 189150.31 | 0 | 2026-02-05
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001002/IF/IAY/5285220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122324005 | Physically Completed | 27000 | 0 | 2025-07-28 | 2026-09-20
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001002/IF/IAY/5848509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127184843 | Ongoing | 27000 | 0 | 2025-11-26
GAURIHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001002/IF/IAY/5848531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126629828 | Approved | 27000 | 0 | 2025-02-19
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001002/IF/IAY/5848545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121938270 | Ongoing | 27000 | 0 | 2025-11-04
GAURIHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001002/IF/IAY/5848576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126619995 | Ongoing | 27000 | 0 | 2026-05-26
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001002/IF/IAY/5848583 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117270473 | Ongoing | 27000 | 0 | 2025-11-26
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001002/IF/IAY/5848586 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123794559 | Ongoing | 27000 | 0 | 2025-12-16
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001002/IF/IAY/5848614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121938135 | Ongoing | 27000 | 0 | 2025-11-04
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001002/IF/IAY/5848625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123794887 | Ongoing | 27000 | 0 | 2025-12-16
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001002/IF/IAY/5876693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123441495 | Ongoing | 27000 | 0 | 2026-02-27
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001002/IF/IAY/5876802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118578339 | Ongoing | 27000 | 0 | 2026-02-05
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001002/IF/IAY/5886559 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123454779 | Ongoing | 27000 | 0 | 2026-02-27
GAURIHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001002/IF/IAY/6219530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123372288 | Ongoing | 27000 | 0 | 2026-06-13
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001002/IF/IAY/6219555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123445726 | Approved | 27000 | 0 | 2025-05-17
GAURIHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001002/IF/IAY/6219583 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122323758 | Ongoing | 27000 | 0 | 2026-06-13
GAURIHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001002/IF/IAY/6219603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123457024 | Ongoing | 27000 | 0 | 2026-06-13
GAURIHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001002/IF/IAY/6219616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121936403 | Ongoing | 27000 | 0 | 2026-08-27
GAURIHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001002/IF/IAY/6219652 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117941162 | Ongoing | 27000 | 0 | 2026-06-13
GAURIHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708001002/IF/IAY/6219719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121939344 | Approved | 27000 | 0 | 2025-08-03
GAURIHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708001002/RC/22012034472858 — सी सी रोड एवम नाली निर्माण हरिमोहन साहू के माकांन से लक्ष्मी अहिरवार के मकान की ओर | Ongoing | 31950 | 0 | 2019-10-03
GAURIHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708001002/RC/22012034473529 — सी सी रोड एम नाली निर्माण गंगा कुशवाहा के मकान से बाब जी की ओर | Ongoing | 66450 | 0 | 2019-09-23
GAURIHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708001002/RC/22012034824206 — सी.सी. रोड सह नाली निर्माण मेन रोड से रामहित कुशवाहा के मकान की ओर | Ongoing | 146000 | 0 | 2024-09-14
GAURIHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708001002/RC/22012034849011 — सी सी रोड सह नाली निर्माण कार्य भूरी वेडिया के मकान से सुखनंदन विश्‍वकर्मा के मकान की ओर | Ongoing | 89000 | 0 | 2025-12-15
GAURIHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1708001002/RS/22012035117032 — नाली निर्माण कार्य संजय सिंह के मकान से अंजना नाला की ओर | Ongoing | 25000 | 0 | 2023-10-07
GAURIHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1708001002/RS/22012035131283 — नाली निर्माण कार्य प्राथमिक शाला से अशोक गुप्ता के मकान की ओर | Approved | 67000 | 0 | 2024-06-08
GAURIHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1708001002/RS/22012035136383 — नाली निर्माण कार्य हनुमान जी के मंदिर से अंजन नाला की ओर | New | 0 | 0 | 2025-01-25
GAURIHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1708001002/RS/22012035136448 — नाली निर्माण कार्य हनुमान जी के मंदिर से अंजन नाला की ओर | Approved | 78000 | 0 | 2025-01-23
GAURIHAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1708001002/WC/22012035303231 — koop recharge pit nirman kary prajapati muhal koop | Approved | 16000 | 0 | 2025-04-14