## Work List
Exported on: 2026-10-21 15:03:32
Filters applied:
Data source: VBGRAMG
District: CHHATARPUR
Block: All
Panchayat: BADAGAON
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NOWGOAN | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1708003019/AV/22012034664540 — पुलिया निर्माण कार्य धुवयाऊ तलैया के पास ग्राम पंचायत बड़ागांव | Ongoing | 61000 | 0 | 2025-03-06
NOWGOAN | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1708003019/AV/22012034664688 — आंगनबाड़ी भवन निर्माण कार्य केन्द्र 03 ग्राम पंचायत बड़ागांव | Approved | 98800 | 0 | 2024-10-25
NOWGOAN | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1708003019/AV/22012034669059 — नाली निर्माण कार्य फूला विश्वकर्मा के घर से नाला तक | Ongoing | 58000 | 0 | 2026-02-18
NOWGOAN | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1708003019/IF/22012034597004 — मेड़बंधान निर्माण कार्य, महेन्द्र सिंह पिता नत्थू सिंह जाॅबकार्ड नं0 333-A ग्राम पंचायत बड़ागांव | Ongoing | 64780.1 | 0 | 2021-04-22
NOWGOAN | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1708003019/IF/22012034597007 — मेड़बंधान निर्माण कार्य, श्री रामसिंह तनय ओमकार सिंह ठाकुर जाॅबकार्ड नं0 332-A ग्राम पंचायत बड़ागांव | Ongoing | 64780.1 | 0 | 2020-12-28
NOWGOAN | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1708003019/IF/22012034597010 — मेड़बंधान निर्माण कार्य, श्री राघुनाथ सिंह तनय ओमकार सिंह ठाकुर जाॅबकार्ड नं0 410 A ग्राम पंचायत बड़ाग | Ongoing | 64780.1 | 0 | 2021-06-28
NOWGOAN | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1708003019/IF/22012034597340 — मेड़बंधान निर्माण कार्य, श्री जाहर सिंह तनय तोडन सिंह सेंगर जाॅबकार्ड नं0 253-A ग्राम पंचायत बड़ागांव | Ongoing | 97170.14 | 0 | 2020-12-21
NOWGOAN | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1708003019/IF/22012034908557 — हितग्राही मूलक नाडिप टांका निर्माण किशोरी,काशीराम,ओमकार,रघुनाथ,रामजी,गिरजा,विन्‍द्रावन,अमान,रोशनी,अम | Ongoing | 23160 | 0 | 2021-12-18
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1708003019/IF/22012035445615 — कपिलधारा कूप निर्माण कार्य, श्री रमेश पिता रमला आदिवासी जॉबकार्ड नं0 39 ग्राम पंचायत बड़ागाँव | Approved | 502139.2 | 0 | 2025-04-14
NOWGOAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1708003019/IF/22012035518844 — डगवेल कूप रिचार्ज निर्माण कार्य कालीचरन तनय नंदकिशोर यादव ग्राम पंचायत बड़ागाँव | Approved | 15000 | 0 | 2025-04-04
NOWGOAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1708003019/IF/22012035518897 — डगवेल कूप रिचार्ज निर्माण कार्य श्रीमती फूला तनय संतोष विश्वकर्मा ग्राम पंचायत बड़ागांव | Approved | 15000 | 0 | 2025-04-04
NOWGOAN | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003019/IF/IAY/3834748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124535878 | Ongoing | 27000 | 0 | 2022-08-20
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003019/IF/IAY/4931002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141978551 | Ongoing | 27000 | 0 | 2025-04-28
NOWGOAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003019/IF/IAY/4952634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118845340 | Physically Completed | 27000 | 0 | 2025-03-21 | 2026-09-22
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003019/IF/IAY/5786847 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124739920 | Physically Completed | 27000 | 15300 | 2026-01-29 | 2026-09-13
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003019/IF/IAY/5788031 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126441908 | Ongoing | 27000 | 0 | 2026-01-29
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003019/IF/IAY/5788139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141977852 | Ongoing | 27000 | 16800 | 2026-02-09
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003019/IF/IAY/5788140 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141978008 | Physically Completed | 27000 | 4200 | 2025-09-02 | 2026-09-22
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003019/IF/IAY/5860591 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141978721 | Physically Completed | 23490 | 4200 | 2025-11-30 | 2026-07-26
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708003019/IF/IAY/5894056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141977834 | Approved | 27000 | 0 | 2025-06-17
NOWGOAN | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708003019/RC/22012034839193 — सी0सी0रोड एवं नाली निर्माण कार्य, मातन के मंदिर से बृजकिशोर नाई के घर तक ग्राम पंचायत बड़ागाँव | Approved | 17000 | 0 | 2024-10-25
NOWGOAN | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708003019/RC/22012034839196 — सी0सी0रोड एवं पुलिया निर्माण कार्य हरिजनबस्ती से पुलिया तक ग्राम पंचायत बड़ागाँव | Approved | 105000 | 0 | 2024-10-25
NOWGOAN | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1708003019/RS/22012034533372 — SLWM सामुदायिक नाडिप टांका निर्माण कार्य 12 नग ग्राम पंचायत बड़ागाँव | Ongoing | 297909.27 | 0 | 2021-09-18
NOWGOAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1708003019/WC/22012035295427 — सोखत गड्डा निर्माा कार्य बड़ी यादव के घर के पास हैण्डपम्प पर ग्राम पंचायत बड़ागांव | Approved | 4000 | 0 | 2025-04-04
NOWGOAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1708003019/WC/22012035295433 — सोखत गड्डा निर्माण कार्य मातन के पास हैण्डपम्प के पास ग्राम पंचायत बड़गाँव | Approved | 4000 | 0 | 2025-04-25
NOWGOAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1708003019/WC/22012035295441 — डगवेल निर्माण कार्य आंगनबाड़ी केन्द्र क्रमांक 01 के पास सार्वजनिक कूप ग्राम पंचायत बड़ागाँव | Approved | 15000 | 0 | 2025-04-04
NOWGOAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1708003019/WC/22012035305903 — डगवेल कूप रिचार्ज निर्माण कार्य श्री बद्री प्रसाद तनय बालकिशुन यादव ग्राम पंचायत बड़गाँव | Approved | 15000 | 0 | 2025-04-04