## Work List
Exported on: 2026-09-05 08:43:16
Filters applied:
Data source: VBGRAMG
District: CHHATARPUR
Block: All
Panchayat: NAYAGOWN
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NOWGOAN | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1708003033/AV/22012034512828 — गौशाला निर्माण कार्य खकरी वीरपुरा नयागाव | Ongoing | 3784582.21 | 0 | 2020-10-02
NOWGOAN | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1708003033/IF/22012034507516 — खेत तालाब निर्माण कार्य, श्री बसंत यादव बगैरह खुटिया ग्राम पंचायत नयागाँव | Ongoing | 101996.79 | 0 | 2019-12-13
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708003033/IF/22012035610431 — fgdggdffgfgffggfgfd | New | 0 | 0 | 2025-04-04
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708003033/IF/22012035620873 — एक बगिया माँ के नाम श्रीमती फूला पति भू0 स्वामी सम्बंध पति ग्राम पंचायत नयागांव | New | 0 | 0 | 2025-04-04
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708003033/IF/22012035620891 — एक बगिया माँ के नाम श्रीमती हरीश कुमारी अरजरिया पति भानुप्रतापभू0 स्वामी सम्बंध पति ग्रापंचा नयागांव | Ongoing | 284702.77 | 0 | 2025-09-23
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708003033/IF/22012035621358 — sgg | New | 0 | 0 | 2025-04-04
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708003033/IF/22012035621364 — एक बगिया माँ के नाम श्रीमती फूला पति पर्वत राजपूत भू स्वामी सम्बंध पति ग्राम पंचायत नयागांव | Approved | 0 | 0 | 2025-04-14
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708003033/IF/22012035621808 — एक बगिया माँ के नाम श्रीमती कमलेश यादव पति प्रीतम भू0 स्वामी सम्बंध पति ग्रा0 नयागाँव | Approved | 0 | 0 | 2025-08-25
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708003033/IF/22012035621818 — hgdfd | New | 0 | 0 | 2025-05-15
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708003033/IF/22012035621995 — एक बगिया माँ के नाम श्रीमती फूला राजूपत पति राजू राजपूत भू0 स्वामी सम्बंध पति ग्रा0 नयागाँव | New | 0 | 0 | 2025-04-04
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708003033/IF/22012035622049 — एक बगिया माँ के नाम श्रीमती फूला राजूपत पति राजू राजपूत भू0 स्वामी सम्बंध पति ग्रा0 नयागाँव | Ongoing | 284702.77 | 0 | 2025-09-30
NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1708003033/IF/22012035663130 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142216047 | Ongoing | 23490 | 0 | 2026-07-01
NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1708003033/IF/22012035663132 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142216125 | Ongoing | 23490 | 0 | 2026-07-01
NOWGOAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003033/IF/IAY/4614976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125967689 | Ongoing | 27000 | 0 | 2025-01-29
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003033/IF/IAY/5861994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151047601 | Ongoing | 27000 | 4500 | 2026-01-30
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003033/IF/IAY/5862199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123035982 | Ongoing | 27000 | 0 | 2026-02-16
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003033/IF/IAY/5862246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125947669 | Ongoing | 27000 | 0 | 2026-02-16
NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003033/IF/IAY/6020899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122820410 | Physically Completed | 23490 | 0 | 2026-04-12 | 2026-08-09
NOWGOAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1708003033/WC/22012035289326 — रूफ वाटर हारवेस्टिंग निर्माण कार्य आंगनबाड़ी केन्द्र 415 ग्राम पंचायत नयागांव | New | 0 | 0 | 2025-04-04
NOWGOAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1708003033/WC/22012035289335 — रूफ वाटर हारवेस्टिंग निर्माण कार्य हरिजन कन्या छात्रावास ग्राम पंचायत नयागांव | Approved | 18000 | 0 | 2025-04-04
NOWGOAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1708003033/WC/22012035289345 — रूफ वाटर हारवेस्टिंग निर्माण कार्य सामुदायिक स्वच्छता परिसर पंचायत भवन के पास ग्राम पंचायत नयागांव | Approved | 18000 | 0 | 2025-04-04
NOWGOAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1708003033/WC/22012035302043 — रूफवाटर हार्वेस्टिंग निर्माण कार्य शा0मा0शाला भवन ग्राम पंचायत नयागांव | Approved | 18000 | 0 | 2025-04-04
NOWGOAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1708003033/WC/22012035302046 — रूफवाटर हार्वेस्टिंग निर्माण कार्य शासकीय कन्या छात्रावास ग्राम पंचायत नयागांव | Approved | 18000 | 0 | 2025-04-04