## Work List
Exported on: 2026-09-10 03:30:39
Filters applied:
Data source: VBGRAMG
District: CHHATARPUR
Block: All
Panchayat: BAROHI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NOWGOAN | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1708003063/AV/22012034596462 — बाउण्ड्रीवॉल निर्माण कार्य, समाज भवन की ग्राम पंचायत बर्रोही | Ongoing | 79000 | 0 | 2021-11-17
NOWGOAN | 2026-2027 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1708003063/AV/22012034668033 — शान्तिधाम निर्माण कार्य ग्राम मड़ापुरवा ग्राम पंचायत बर्रोही | Ongoing | 41000 | 0 | 2026-05-08
NOWGOAN | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1708003063/AV/22012034668034 — शान्तिधाम निर्माण कार्य ग्राम बर्रोही ग्राम पंचायत बर्रोही खसरा नं0 416 | Ongoing | 41000 | 0 | 2026-03-12
NOWGOAN | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Grass Land Development and Silvi-pasture / Development of Silvipasture Grassslands for Community | Grass Land Development | 1708003063/DP/22012034628730 — चारागाह निर्माण कार्य खसरा नं0 214 ग्राम पंचायत बर्रोही | Approved | 0 | 0 | 2024-08-15
NOWGOAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Grass Land Development and Silvi-pasture / Development of Silvipasture Grassslands for Community | Grass Land Development | 1708003063/DP/22012034629513 — चारागाह निर्माण कार्य खसरा नं0 214 ग्राम पंचायत बर्रोही | Ongoing | 999307.02 | 0 | 2025-05-29
NOWGOAN | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1708003063/IF/22012034510129 — खेत तालाब निर्माण कार्य हरजू/जोराबल अहिरवार | Ongoing | 310386.65 | 0 | 2020-01-03
NOWGOAN | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1708003063/IF/22012034510887 — खेत तालाब निर्माण कार्य, श्री कालका प्रसाद/जोराबल अहिरवार जाॅबकार्ड नं0 26 सी | Ongoing | 101997.1 | 0 | 2020-01-03
NOWGOAN | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1708003063/IF/22012034542102 — हितैषी कपिल धारा कूप निर्माण कार्य नरेन्‍द्र , हर्ष / देवेन्‍द्र सिंह | Ongoing | 243792.43 | 0 | 2020-09-29
NOWGOAN | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1708003063/IF/22012034551377 — हितैशी कपिलधारा कूप निर्माण कार्य, लखनलाल/हल्के सेन जाॅबकार्ड नं0 58-B ग्राम फुलारी | Ongoing | 243792.43 | 0 | 2021-12-05
NOWGOAN | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1708003063/IF/22012034569129 — मेड़बंधान निर्माण कार्य, श्री लखन सेन/हल्के सेन जाॅबकार्ड नं0 58-B ग्राम फुुलारी | Ongoing | 64780.1 | 0 | 2020-09-29
NOWGOAN | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1708003063/IF/22012034598544 — मेड़बंधान निर्माण कार्य धनीराम/हल्के सेन ग्राम फुलारी ग्राम पंचायत बर्रोही जाॅबकार्ड नं0 58 | Ongoing | 83069.12 | 0 | 2020-09-29
NOWGOAN | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1708003063/IF/22012034803251 — वृक्षारोपण निर्माण कार्य भानपाल/चिरोंजी पाल ग्राम मडापुरवा ग्राम पंचायत बर्रोही | Ongoing | 117912.51 | 0 | 2021-10-22
NOWGOAN | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1708003063/IF/22012034899343 — SLWM व्यक्तिगत नाडिप टांका निर्माण कार्य, जगदीश, रामदीन, हरिचरन, महेश, परमानंद, परमलाल, प्रकाशचन्द्र | Ongoing | 178953.03 | 0 | 2021-12-05
NOWGOAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1708003063/IF/22012035295871 — खेत तालाब निर्माण कार्य श्री रमेश कुशवाहा तनय बुुल्ला कुशवाहा जॉबकार्ड नं0 75-A ग्राम पंचायत बर्रोही | Approved | 0 | 0 | 2024-10-25
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1708003063/IF/22012035519473 — कपिलधारा कूप निर्माण कार्य श्री मिहीलाल तनय खिलैया प्रजापति जॉबकार्ड नं0 40 -A ग्राम पंचायत बर्रोही | Approved | 494375.93 | 0 | 2025-04-04
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1708003063/IF/22012035519493 — कपिलधारा कूप निर्माण कार्य श्री बल्लू तनय किलकोटा अहिरवार जॉबकार्ड नं0 143 -A ग्राम पंचायत बर्रोही | Approved | 0 | 0 | 2025-04-04
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708003063/IF/22012035619889 — gfdgf | New | 0 | 0 | 2025-04-04
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708003063/IF/22012035620037 — एक बगिया माँ के नाम श्रीमती गंशी प्रजापति पति श्री चूरामन प्रजापति भू0 स्वामी सम्बंध पति ग्रा0बर्रोह | Ongoing | 284702.77 | 5400 | 2025-09-19
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708003063/IF/22012035620151 — एक बगिया माँ के नाम श्रीमती रामरती अहिरवार पति दयाराम अहिरवार भू0 स्वामी सम्बंध पति ग्रा0बर्रोही | New | 0 | 0 | 2025-04-04
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Block Plantation of Biodrainage Trees in Fields for Individuals | Plantation | 1708003063/IF/22012035620157 — एक बगिया माँ के नाम श्रीमती रामरती अहिरवार पति दयाराम अहिरवार भू0 स्वामी सम्बंध पति ग्रा0बर्रोही | Approved | 0 | 0 | 2025-04-04
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708003063/IF/22012035620301 — एक बगिया माँ के नाम श्रीमती रामदेवी पति मंगू प्रजापति भू0 स्वामी सम्बंध पति ग्रा0बर्रोही | New | 0 | 0 | 2025-04-04
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708003063/IF/22012035621303 — dfg | New | 0 | 0 | 2025-04-04
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708003063/IF/22012035641627 — एक बगिया माँ के नाम श्रीमती रामदेवी प्रजापति पति मंगू प्रजापति ग्राम पंचायत बर्रोही | Ongoing | 284704.22 | 5400 | 2025-11-26
NOWGOAN | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/3686643 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114660828 | Ongoing | 27000 | 0 | 2022-08-19
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/4929059 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123025474 | Physically Completed | 23490 | 0 | 2025-04-30 | 2026-08-09
NOWGOAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/4929063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123035262 | Physically Completed | 23490 | 1800 | 2025-03-12 | 2026-07-19
NOWGOAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5143822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123033455 | Ongoing | 27000 | 0 | 2025-03-26
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5210231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119332329 | Ongoing | 27000 | 0 | 2025-04-23
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5231072 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150522521 | Ongoing | 27000 | 0 | 2025-04-02
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5275102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119596642 | Ongoing | 27000 | 3600 | 2025-04-16
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5300964 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119897968 | Physically Completed | 23490 | 0 | 2025-04-27 | 2026-07-15
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5392247 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126938693 | Ongoing | 27000 | 0 | 2025-04-16
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5401943 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119520682 | Ongoing | 27000 | 0 | 2025-04-16
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5644669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126964398 | Physically Completed | 27000 | 0 | 2025-09-13 | 2026-08-30
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5727237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148310670 | Ongoing | 27000 | 0 | 2026-02-05
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5781861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119303092 | Physically Completed | 23490 | 0 | 2025-09-12 | 2026-08-09
NOWGOAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5860711 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127048950 | Physically Completed | 23490 | 1800 | 2026-02-07 | 2026-08-16
NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5970147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127050327 | Ongoing | 27000 | 1500 | 2026-08-26
NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5970219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119333773 | Ongoing | 27000 | 3600 | 2026-07-17
NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5970338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126937456 | Ongoing | 27000 | 1800 | 2026-08-06
NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5970802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119542441 | Ongoing | 27000 | 7200 | 2026-07-17
NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5971103 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119850486 | Ongoing | 27000 | 7200 | 2026-07-17
NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5971175 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123033996 | Ongoing | 27000 | 1800 | 2026-08-25
NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5971314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151496224 | Ongoing | 27000 | 7200 | 2026-07-17
NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5971369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123788887 | Ongoing | 27000 | 3600 | 2026-07-17
NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5971565 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119597666 | Ongoing | 27000 | 1800 | 2026-08-06
NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5971884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126959962 | Ongoing | 27000 | 5400 | 2026-08-06
NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/5971947 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119733606 | Ongoing | 27000 | 3600 | 2026-08-06
NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/6234970 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127049844 | Ongoing | 23490 | 7200 | 2026-08-11
NOWGOAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708003063/IF/IAY/6234997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126936417 | Ongoing | 23490 | 1800 | 2026-08-25
NOWGOAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1708003063/LD/22012034954067 — चारागाह निर्माण कार्य खसरा नं0 294 ग्राम पंचायत बर्रोही | Approved | 0 | 0 | 2025-04-04
NOWGOAN | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708003063/RC/22012034849849 — सी0सी0रोड निर्माण कार्य मैन रोड हनुमतयाऊ तक ग्राम पंचायत बर्रोही | Ongoing | 87000 | 0 | 2026-05-01
NOWGOAN | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708003063/RC/22012034849850 — सी0सी0रोड निर्माण कार्य मैन रोड से काली माता मंदिर की ओर ग्राम पंचायत बर्रोही | Ongoing | 72000 | 0 | 2026-02-04
NOWGOAN | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1708003063/WC/22012034554734 — सामु दायिक खेत तालाब(कम्युनिटी) निर्माणकार्य खसरा न. 393 ग्राम फुलारी ग्राम पंचायत बरोही | Ongoing | 332572.21 | 0 | 2020-07-25
NOWGOAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1708003063/WC/22012035134662 — एनीकट निर्माण कार्य, कनवारा नाला पर जगप्रसाद पटेल के खेत के पास ग्रा0फुलारी ग्रा0पंचा0 बर्रोही | Ongoing | 421028.69 | 0 | 2023-10-06
NOWGOAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1708003063/WC/22012035142748 — लूज बोल्डर निर्माण कार्य, सिमराई नाला पर मनीराम पटेल के खेत के पास ग्राम फुलारी ग्रा0पंचायत बर्रोही | Ongoing | 295389.08 | 0 | 2023-10-08
NOWGOAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1708003063/WC/22012035142749 — लूज बोल्डर निर्माण कार्य, सिमराई नाला पर जगदीश पटेल के खेत के पास ग्राम फुलारी ग्रा0पंचायत बर्रोही | Ongoing | 295389.08 | 0 | 2023-10-08
NOWGOAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1708003063/WC/22012035142750 — लूज बोल्डर निर्माण कार्य, सिमराई नाला पर परममानंद पटेल के खेत के पास ग्राम फुलारी ग्रा0पंचायत बर्रोह | Ongoing | 295389.08 | 0 | 2023-10-08
NOWGOAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1708003063/WC/22012035142751 — लूज बोल्डर निर्माण कार्य, सिमराई नाला पर कुसुम पटेल के खेत के पास ग्राम फुलारी ग्रा0पंचायत बर्रोही | Ongoing | 295389.08 | 0 | 2023-10-08
NOWGOAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1708003063/WC/22012035176217 — एनीकट निर्माण कार्य सिमराई नाला पर रामस्वरूप पटेल के खेत के पास ग्राम फुलारी ग्रा0पंचायत बर्रोही | New | 0 | 0 | 2023-10-02