## Work List
Exported on: 2026-08-31 07:00:45
Filters applied:
Data source: VBGRAMG
District: CHHATARPUR
Block: All
Panchayat: PANOUTHA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1708004036/FR/22012034325317 — sarjanik khet talab bihariju mandir ke pass | New | 0 | 0 | 2025-05-25
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1708004036/IF/22012035080231 — kapil dhara koop nirmarn kary phula patel | Ongoing | 398499.7 | 0 | 2025-05-11
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708004036/IF/22012035246347 — Nandan fal udhyan Manoj patel | Approved | 0 | 0 | 2024-04-14
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1708004036/IF/22012035282979 — khet talab nirmarn kary mukul rai | Approved | 0 | 0 | 2024-04-14
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1708004036/IF/22012035563828 — khet talab nirmarn kary mulua rajak | Approved | 186735.92 | 0 | 2025-05-25
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1708004036/IF/22012035566028 — Khet talab nirman kary kunwar lal patel | Approved | 182810.67 | 0 | 2025-05-25
CHHATARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/3353357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5661633 | Approved | 27000 | 0 | 2021-11-12
CHHATARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/3955703 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147042174 | Approved | 27000 | 0 | 2022-05-05
CHHATARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/4365267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127060560 | Approved | 27000 | 0 | 2022-07-20
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/4927724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122767763 | Ongoing | 27000 | 0 | 2025-03-15
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/4929869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127797458 | Ongoing | 27000 | 0 | 2025-03-15
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/4929873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127804020 | Ongoing | 27000 | 0 | 2025-05-07
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/4930690 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127001309 | Ongoing | 27000 | 0 | 2025-03-10
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/4930693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127004146 | Ongoing | 27000 | 0 | 2025-05-05
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5190062 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127805975 | Physically Completed | 23490 | 0 | 2025-04-05 | 2026-08-02
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5736731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145626085 | Approved | 27000 | 0 | 2025-02-15
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5739469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147041542 | Ongoing | 27000 | 0 | 2025-11-08
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5740684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126697965 | Ongoing | 27000 | 0 | 2026-07-27
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5936146 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127799491 | Ongoing | 27000 | 0 | 2026-07-27
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5936472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127327891 | Ongoing | 27000 | 0 | 2026-07-27
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5936856 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127793493 | Physically Completed | 27000 | 0 | 2026-05-24 | 2026-08-30
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5936858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127796676 | Ongoing | 27000 | 0 | 2026-07-27
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5937457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123594828 | Approved | 27000 | 0 | 2026-02-23
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5937538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122770479 | Approved | 27000 | 0 | 2026-02-23
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5937876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127030990 | Ongoing | 27000 | 0 | 2026-05-24
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5937989 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127037459 | Ongoing | 27000 | 0 | 2026-05-24
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5937991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127039182 | Ongoing | 27000 | 0 | 2026-05-24
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5937992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127052098 | Ongoing | 27000 | 0 | 2026-07-27
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5937995 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127064187 | Ongoing | 27000 | 0 | 2026-05-24
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5938170 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124302186 | Ongoing | 27000 | 4200 | 2026-05-24
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5939047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122768708 | Approved | 27000 | 0 | 2026-02-23
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5939052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127028010 | Approved | 27000 | 0 | 2026-02-23
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5939829 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123654964 | Ongoing | 27000 | 0 | 2026-05-24
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5940084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124739742 | Ongoing | 27000 | 0 | 2026-07-27
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5940133 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127802073 | Ongoing | 27000 | 0 | 2026-05-24
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5940405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122767483 | Ongoing | 27000 | 0 | 2026-07-27
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5940515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123656404 | Ongoing | 27000 | 0 | 2026-07-27
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5941608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127796942 | Physically Completed | 23490 | 0 | 2026-05-24 | 2026-08-23
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5941618 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122770098 | Ongoing | 27000 | 0 | 2026-07-20
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5941723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122766173 | Ongoing | 27000 | 2100 | 2026-05-24
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5941930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123663161 | Ongoing | 27000 | 0 | 2026-08-18
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5942273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126980947 | Ongoing | 27000 | 4200 | 2026-05-24
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5942342 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127110306 | Approved | 27000 | 0 | 2026-02-23
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5943027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127794080 | Ongoing | 27000 | 0 | 2026-05-24
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5943347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130413284 | Physically Completed | 23490 | 0 | 2026-05-24 | 2026-08-09
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/5979043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127032807 | Ongoing | 27000 | 0 | 2026-07-27
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/6014261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127791978 | Ongoing | 27000 | 0 | 2026-07-27
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/6015344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123655394 | Ongoing | 27000 | 4200 | 2026-07-27
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/6018825 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147041779 | Approved | 27000 | 0 | 2026-03-02
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/6019501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127061621 | Ongoing | 27000 | 0 | 2026-05-24
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/6019586 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127029273 | Ongoing | 27000 | 0 | 2026-07-27
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/6022880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127044578 | Ongoing | 27000 | 0 | 2026-05-24
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/6023271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122769073 | Ongoing | 27000 | 0 | 2026-07-20
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/6040341 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122766766 | Ongoing | 27000 | 1500 | 2026-05-24
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/6040498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127059860 | Approved | 27000 | 0 | 2026-03-10
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/6061234 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127046420 | Approved | 27000 | 0 | 2026-02-28
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/6083799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123602335 | Ongoing | 27000 | 0 | 2026-07-27
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/6085241 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124742081 | Approved | 27000 | 0 | 2026-03-19
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/6087483 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126251278 | Ongoing | 27000 | 0 | 2026-05-24
CHHATARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004036/IF/IAY/6089340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127036196 | Ongoing | 27000 | 0 | 2026-05-24
CHHATARPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1708004036/RS/22012035129591 — Nali nirman kary renj se kherai ki puliya ki or dhimar mohalla sahit | Ongoing | 62000 | 0 | 2024-08-28
CHHATARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1708004036/WC/22012035142047 — Sarvjanik koop nirman basor mohlla | Ongoing | 546464.26 | 0 | 2025-02-02
CHHATARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1708004036/WC/22012035173129 — मिनी परकोलेशन टैंक का निर्माण पनौठा | New | 0 | 0 | 2024-01-26
CHHATARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1708004036/WC/22012035237783 — sarjanik khet talab nirmarn kary power house ke pass | Approved | 0 | 0 | 2024-12-24
CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1708004036/WC/22012035271753 — recharge pit nirmarn kary sarvjanik koop kumhar mohlaa | Approved | 0 | 0 | 2025-04-14
CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1708004036/WC/22012035301176 — sarjanik khet talab nirmarn kary joran ke pass | Approved | 0 | 0 | 2025-05-05
CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1708004036/WC/22012035314017 — Khet talab nirman kary bihari ju mandir ke khet ke pasd | Approved | 316850.06 | 0 | 2025-05-25