## Work List
Exported on: 2026-09-02 18:03:05
Filters applied:
Data source: MGNREGA + VBGRAMG
District: CHHATARPUR
Block: All
Panchayat: BRAJPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
CHHATARPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1708004077/AV/22012034370813 — anganwadi bhavan | Closed | 0 | 0 | 2017-10-02
CHHATARPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1708004077/AV/22012034392395 — SHANTI DHAM NIRMAN KARY BRAJPURA NO. 02 | Closed | 245000 | 0 | 2018-08-15
CHHATARPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1708004077/AV/22012034546914 — FOOD GRAIN STORAGR STRUCTURE NIRMAN KARY BRAJPURA | Closed | 307550.88 | 0 | 2020-08-17
CHHATARPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1708004077/AV/22012034593512 — school dining bench prathmik shala brajpura | Completed | 6000 | 5796 | 2021-10-19 | 2023-07-08
CHHATARPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1708004077/AV/22012034640174 — मुक्तिधाम निर्माण कार्य जबारन की पुलिया के पास | Closed | 329108.4 | 0 | 2023-04-14
CHHATARPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1708004077/AV/22012034643119 — BOUNDARYWALL NIRMAN KARY HIGER SECONDARY SCHOOL BRAJPURA | Completed | 159000 | 158828 | 2023-10-05 | 2024-11-09
CHHATARPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1708004077/AV/22012034655209 — खेल मैदान निर्माण कार्य शासकीय हायर सेकेंडरी स्कूल बृजपुरा | Closed | 0 | 0 | 2024-01-24
CHHATARPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1708004077/AV/22012034660298 — Khel medan nirmad H.S.School brajpura | Approved | 261110.41 | 0 | 2024-08-16
CHHATARPUR | 2026-2027 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1708004077/AV/22012034664788 — ANGANWADI BHAWAN NIRMAN KARY KINDRA NO 2 BRAJPURA | Ongoing | 99000 | 1800 | 2024-04-14
CHHATARPUR | 2026-2027 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1708004077/AV/VB/YD/22012034669470 — Constr of CmpOnd wall for gov schools madhyamik shala | New | 0 | 0 | 2026-05-05
CHHATARPUR | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1708004077/DP/1 — ब़क्षारोपण ब़जपुरा से सिमररिया मार्ग पर | Completed | 496000 | 87600 | 2007-07-05 | 2008-12-11
CHHATARPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1708004077/DP/22012034535463 — BRAKSHAROPAN KARY BABBAJO MANDIR PAHADI | Completed | 394489.84 | 271356 | 2021-09-02 | 2024-11-28
CHHATARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1708004077/DP/22012034580002 — वृक्षारोपण कार्य बब्बाजू मंदिर भाग - 2 | Closed | 0 | 0 | 2023-04-14
CHHATARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1708004077/DP/22012034580003 — वृक्षारोपण कार्य बब्बाजू मंदिर भाग - 2 | Closed | 0 | 0 | 2023-04-14
CHHATARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1708004077/DP/22012034580004 — वृक्षारोपण कार्य बब्बाजू मंदिर भाग - 2 | Closed | 0 | 0 | 2023-04-14
CHHATARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1708004077/DP/22012034580005 — वृक्षारोपण कार्य बब्बाजू मंदिर भाग - 2 | Closed | 0 | 0 | 2023-04-14
CHHATARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1708004077/DP/22012034580006 — वृक्षारोपण कार्य बब्बाजू मंदिर भाग - 2 | Closed | 0 | 0 | 2023-04-14
CHHATARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1708004077/DP/22012034580007 — वृक्षारोपण कार्य बब्बाजू मंदिर भाग - 2 | Closed | 0 | 0 | 2023-04-14
CHHATARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1708004077/DP/22012034580008 — वृक्षारोपण कार्य बब्बाजू मंदिर भाग - 2 | Completed | 699360.07 | 299194 | 2023-10-05 | 2025-08-24
CHHATARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1708004077/DP/22012034605203 — MERI MATI MERA DESH VASUDHA VANDHAN VRIKSHAROPAN KARY HIGHER SECONDARY SCHOOL BRAJPURA | Completed | 67510.87 | 21216 | 2023-10-05 | 2024-09-27
CHHATARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1708004077/DP/22012034621876 — बृक्षारोपण कार्य शासकीय हायर सेकेंडरी स्कूल बृजपुरा | Deleted | 0 | 0 | 2024-06-08
CHHATARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1708004077/DP/22012034624736 — बृक्षारोपण कार्य शासकीय हायर सेकेंडरी स्कूल परि‍सर बृजपुरा | Completed | 169891.64 | 68871.96 | 2024-11-16 | 2025-08-24
CHHATARPUR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1708004077/DP/VB/22012034630832 — braksharopan karya pragteswar balaji dham parisar grampanchayat Brajpura | Approved | 0 | 0 | 2026-06-05
CHHATARPUR | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1708004077/IF/178 — kapil dhara koop nirmad ramswaroop yadav | Completed | 213000 | 202606 | 2011-02-28 | 2012-06-01
CHHATARPUR | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1708004077/IF/211 — सिचाई कुप ramkerpal पटेल व्रजपुरा | Completed | 213000 | 211263.5 | 2011-03-15 | 2012-05-27
CHHATARPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1708004077/IF/22012034340976 — vrakchharopan kary simariya marg | Completed | 335000 | 22028 | 2017-05-19 | 2018-11-15
CHHATARPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1708004077/IF/22012034440959 — KAPIL DHARA KOOP NIRMAN KARY RAM KISHOR PATAL | Completed | 210000 | 63461 | 2019-01-08 | 2025-02-06
CHHATARPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1708004077/IF/22012034460586 — KAPILDHARA KOOP | Closed | 0 | 0 | 2019-01-26
CHHATARPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1708004077/IF/22012034469884 — HITESHI KAPIL DHARA KOOP NIRMAN KARY RATI BAI W/O BALKISHUN YADAV | Completed | 210000 | 209206 | 2019-03-07 | 2023-07-08
CHHATARPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1708004077/IF/22012034530019 — HITESHI KAPIL DHARA KOOP NIRMAN KARY LADDU YADAV W/O ARJUN YADAV | Completed | 235670.78 | 105315 | 2020-09-06 | 2024-12-02
CHHATARPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1708004077/IF/22012034530025 — HITESHI KAPIL DHARA KOOP NIRMAN KARY HEERA LAL PATEL S/O BALADEEN PATEL | Completed | 235670.78 | 206852 | 2020-04-22 | 2023-06-09
CHHATARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1708004077/IF/22012034645583 — PASHU SHED NIRMAN KARY HARISHCHANDRA PATEL | Completed | 101804.91 | 98245.18 | 2021-04-05 | 2023-06-08
CHHATARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1708004077/IF/22012034645584 — PASHU SHED NIRMAN KARY GHANSHYAM PATEL | Completed | 101804.91 | 99792.35 | 2021-04-05 | 2023-06-08
CHHATARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1708004077/IF/22012034645742 — PASHU SHED NIRMAN KARY RAJENDRA YADAV | Completed | 101804.91 | 98134.64 | 2021-04-05 | 2022-09-08
CHHATARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Raising of Nursery for Individuals / Raising of Nursery for Individuals | Nursery Development | 1708004077/IF/22012034853220 — NANDAN PHALODHYAN KARYA GORELAL/LALARAM YADAV | Closed | 127912.51 | 0 | 2021-08-15
CHHATARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Raising of Nursery for Individuals / Raising of Nursery for Individuals | Nursery Development | 1708004077/IF/22012034853223 — NANDAN PHALODHYAN KARYA BAHORA/SUKKA PAAL | Completed | 127912.51 | 55962 | 2021-10-19 | 2025-03-12
CHHATARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Raising of Nursery for Individuals / Raising of Nursery for Individuals | Nursery Development | 1708004077/IF/22012034853236 — NANDAN PHALODHYAN KARYA SMT. AARTI/SUKHNANDAN SAHU | Closed | 127912.51 | 0 | 2021-08-15
CHHATARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Raising of Nursery for Individuals / Raising of Nursery for Individuals | Nursery Development | 1708004077/IF/22012034853243 — NANDAN PHALODHYAN KARYA AASHARAM/RAMDEEN SAHU | Closed | 127912.51 | 0 | 2021-08-15
CHHATARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Raising of Nursery for Individuals / Raising of Nursery for Individuals | Nursery Development | 1708004077/IF/22012034853248 — NANDAN PHALODHYAN KARYA RAVISHANKAR/LALARAM YADAV | Closed | 127912.51 | 0 | 2021-08-15
CHHATARPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1708004077/IF/22012035196932 — कपिलधारा कूप निर्माण कार्य मोहन पाल S/O कसिया पाल | Closed | 0 | 0 | 2024-01-24
CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1708004077/IF/22012035475180 — JGSA dugwell recharge pit nirmad hitesi koop ratibai yadav ke khet ke pas grampanchayat brajpura | Completed | 22007.92 | 21804.72 | 2025-05-06 | 2025-12-31
CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1708004077/IF/22012035490321 — JGSA dugwell recharge pit nirmad hitesi koop jeevan/chhimma ahirwar ke pas grampanchayat brajpura | Completed | 22007.92 | 21405.36 | 2025-05-09 | 2025-12-31
CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1708004077/IF/22012035490339 — JGSA dugwell recharge pit nirmad hitesi koop paradise ahirwar ke pas grampanchayat brajpura | Approved | 22007.92 | 0 | 2025-04-14
CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1708004077/IF/22012035528929 — JGSA dugwell recharge pit nirmad hitesi koop bhagunta pal ke khet ke pas grampanchayat brajpura | Completed | 21863.49 | 21019.36 | 2025-05-20 | 2026-02-21
CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1708004077/IF/22012035528952 — JGSA dugwell recharge pit nirmad hitesi koop anurag patel ke khet ke pas grampanchayat brajpura | Completed | 21863.49 | 21499.42 | 2025-05-20 | 2025-12-31
CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1708004077/IF/22012035528962 — JGSA dugwell recharge pit nirmad hitesi koop prembai patel ke khet ke pas grampanchayat brajpura | Completed | 21863.49 | 21493.72 | 2025-05-20 | 2025-12-31
CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1708004077/IF/22012035528988 — JGSA dugwell recharge pit nirmad hitesi koop bhagwat patel ke koop ke pas grampanchayat brajpura | Completed | 21791.28 | 21574.48 | 2025-05-20 | 2025-12-31
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708004077/IF/22012035594212 — एक बगिया माँ के नाम श्रीमती रति पटेल पत्नी लखन पटेल (भूस्वामी श्री लखन पटेल पति) | Ongoing | 284038.6 | 850 | 2025-08-27
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708004077/IF/22012035594213 — एक बगिया माँ के नाम दीप कुमारी पटेल पत्नी श्री कैलाश पटेल (भूस्वामी श्री हरगोविन्द पटेल ससुर) | Ongoing | 284038.6 | 850 | 2025-08-27
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1708004077/IF/22012035594218 — एक बगिया माँ के नाम रामकुमार पटेल पति भगवत पटेल (भूस्वामी श्री रामकृपाल पटेल ससुर) | Deleted | 0 | 0 | 2025-08-01
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708004077/IF/22012035596621 — एक बगिया मॉं के नाम श्रीमती रामकुंवर पटेल पति भगवत पटेल (भूस्वामी श्री रामकृपाल पटेल ससुर) | Ongoing | 283820.78 | 350.02 | 2025-09-03
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1708004077/IF/22012035648769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126611604 | Completed | 24000 | 23490 | 2025-12-07 | 2026-01-26
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1708004077/IF/22012035648773 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126439793 | Completed | 24000 | 23475 | 2025-12-07 | 2026-03-13
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1708004077/IF/22012035648780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124939727 | Completed | 24000 | 23490 | 2025-12-07 | 2026-01-26
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1708004077/IF/22012035648786 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125781868 | Completed | 24000 | 23490 | 2025-12-07 | 2026-01-26
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1708004077/IF/22012035648788 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124939209 | Completed | 24000 | 23490 | 2025-12-07 | 2026-01-26
CHHATARPUR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1708004077/IF/561 — सिचाई कुप भगुन्त पाल व्रजपुरा | Completed | 319000 | 315268 | 2012-05-03 | 2013-09-30
CHHATARPUR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1708004077/IF/562 — सिचाई कुप छिम्मा/मुलुवा अहिरवार व्रजपुरा | Completed | 387000 | 377124 | 2012-05-12 | 2015-05-15
CHHATARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/9993692215 — IAY BHUMANIDEEN RAIKWAR | Completed | 14310 | 13953 | 2015-12-05 | 2017-02-28
CHHATARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/9993692216 — IAY PATTU BASAOR | Completed | 14310 | 14310 | 2015-12-05 | 2017-02-28
CHHATARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1708004077/IF/9993693071 — KAPIL DHARA KOOP HARBIPAL W/O BANDI | Completed | 373000 | 94239 | 2015-12-26 | 2020-11-03
CHHATARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1708004077/IF/9993701191 — KAPIL DHARA KOOP LALTA BAI PATEL | Completed | 375000 | 364694 | 2016-03-19 | 2019-09-07
CHHATARPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Drainage in Water Logged Areas / Drainage of chaur or waterlogged areas Land for Individuals | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1708004077/IF/9993713040 — ramswarup patel kapidara kuap | Deleted | 0 | 0 | 2016-01-26
CHHATARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1708004077/IF/9993713062 — kapil dhara kuap ntthu yadav | Deleted | 0 | 0 | 2016-01-26
CHHATARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1708004077/IF/9993713148 — kapil dhara koop mukesh ravat | Deleted | 0 | 0 | 2016-01-26
CHHATARPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/2396623 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4262095 | Completed | 17100 | 15960 | 2020-05-28 | 2021-10-26
CHHATARPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/2397873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4233992 | Completed | 17100 | 17100 | 2020-05-04 | 2021-09-21
CHHATARPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/2405066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4540886 | Completed | 17100 | 16340 | 2020-05-04 | 2021-02-24
CHHATARPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/285393 — Construction of IAY House -IAY REG. NO. MP2784225 | Completed | 15030 | 14480 | 2017-01-27 | 2018-08-29
CHHATARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/3083125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4648500 | Completed | 17370 | 17213 | 2021-07-13 | 2023-06-14
CHHATARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/3083126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4648498 | Completed | 17370 | 17314 | 2021-07-13 | 2023-06-07
CHHATARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/3834051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123775170 | Completed | 18360 | 18360 | 2022-07-07 | 2022-11-12
CHHATARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/3834130 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123790965 | Completed | 18360 | 18173 | 2022-05-25 | 2023-05-20
CHHATARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/3838512 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125063152 | Completed | 18360 | 18360 | 2022-05-27 | 2022-11-02
CHHATARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/3843816 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123028171 | Completed | 18360 | 17748 | 2022-05-27 | 2023-04-25
CHHATARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4213737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123034831 | Completed | 18360 | 18360 | 2022-08-05 | 2022-10-23
CHHATARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/44783 — Construction of IAY House -IAY REG. NO. MP-08-004-077-001/13696 | Approved | 27000 | 0 | 2015-11-30
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4597889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123049084 | Completed | 21870 | 18711 | 2024-09-28 | 2024-12-02
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4605357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124466414 | Completed | 21870 | 21870 | 2024-09-28 | 2025-02-19
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4610498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125063901 | Completed | 21870 | 18711 | 2024-09-28 | 2024-12-02
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4926741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122882375 | Completed | 23490 | 22842 | 2025-03-14 | 2025-05-15
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4928277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126610563 | Completed | 23490 | 22986 | 2025-03-18 | 2025-05-15
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4928472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126463520 | Completed | 23490 | 23040 | 2025-03-12 | 2025-05-15
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4928474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126464817 | Completed | 23490 | 22842 | 2025-03-14 | 2025-05-15
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4928545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123490587 | Completed | 23490 | 23040 | 2025-03-12 | 2025-06-10
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4928608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125064803 | Completed | 23490 | 22842 | 2025-03-14 | 2025-06-13
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4928610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125066432 | Completed | 23490 | 23202 | 2025-03-15 | 2025-05-26
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4928679 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126234779 | Completed | 23490 | 23040 | 2025-03-12 | 2025-06-13
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4928683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126238853 | Completed | 23490 | 22770 | 2025-03-12 | 2025-05-19
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4928693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126246824 | Completed | 23490 | 23292 | 2025-03-21 | 2025-06-20
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4929061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123032692 | Completed | 23490 | 23094 | 2025-03-21 | 2025-06-13
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4929370 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123195693 | Completed | 23490 | 23058 | 2025-03-11 | 2025-05-15
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4929450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125586356 | Completed | 23490 | 23094 | 2025-03-21 | 2025-05-15
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4929542 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129937181 | Completed | 23490 | 23130 | 2025-03-12 | 2025-06-13
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4929846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126416069 | Completed | 23490 | 23166 | 2025-03-14 | 2025-07-15
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4929849 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126419412 | Completed | 23490 | 23166 | 2025-03-14 | 2025-06-13
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4930380 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125780461 | Completed | 23490 | 23166 | 2025-03-14 | 2025-06-13
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4932596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126519128 | Completed | 23490 | 23130 | 2025-03-12 | 2025-05-19
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/4932659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127987839 | Completed | 23490 | 23490 | 2025-04-01 | 2025-06-13
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/5013137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123184430 | Completed | 23490 | 23310 | 2025-03-22 | 2025-05-16
CHHATARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/5013618 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123035574 | Completed | 23490 | 23310 | 2025-03-22 | 2025-06-20
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/5154010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125781110 | Completed | 23490 | 23490 | 2025-04-01 | 2025-07-01
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/5384361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123837851 | Completed | 23490 | 23490 | 2025-04-16 | 2025-07-15
CHHATARPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/558308 — Construction of IAY House -IAY REG. NO. MP3601450 | Completed | 15030 | 14607 | 2017-01-27 | 2018-11-15
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/5737798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126422053 | Completed | 23490 | 23490 | 2025-08-20 | 2025-10-06
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/5741862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124467917 | Completed | 23490 | 23490 | 2025-08-20 | 2025-10-06
CHHATARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/5741937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125529467 | Completed | 23490 | 23490 | 2025-08-20 | 2025-10-06
CHHATARPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/938757 — Construction of IAY House -IAY REG. NO. MP2802385 | Completed | 15480 | 15480 | 2017-06-02 | 2018-02-18
CHHATARPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1708004077/IF/IAY/971000 — Construction of IAY House -IAY REG. NO. MP3578101 | Completed | 15480 | 15308 | 2017-05-27 | 2018-06-07
CHHATARPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1708004077/LD/22012034234938 — MED BANDHAN KARY DEVKIYA PAL | Deleted | 50000 | 0 | 2015-10-24
CHHATARPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1708004077/LD/22012034234943 — MED BANDHAN RAMKRIPAL PATEL | Deleted | 50000 | 0 | 2015-10-31
CHHATARPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1708004077/LD/22012034234945 — MED BANDHAN KARY BHAGUNTA PAL | Completed | 50000 | 3498 | 2015-11-01 | 2018-08-21
CHHATARPUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1708004077/LD/22012034255682 — medh bdhan natthu yadav | Deleted | 0 | 0 | 2016-01-26
CHHATARPUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1708004077/LD/22012034255727 — medbdhan harbi pal | Deleted | 0 | 0 | 2016-01-26
CHHATARPUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1708004077/LD/22012034255729 — med bdhan lalita bai patel | Deleted | 0 | 0 | 2016-01-26
CHHATARPUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1708004077/LD/22012034255733 — med bdhan vishvnath patel | Deleted | 0 | 0 | 2016-01-26
CHHATARPUR | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1708004077/LD/22012034296832 — SHANTI DHAAM NIRMAN BRIJPURA KRAMAANK 01 | Completed | 245000 | 231160 | 2016-12-30 | 2018-11-15
CHHATARPUR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1708004077/LD/22012034360431 — santidham | Closed | 0 | 0 | 2017-10-02
CHHATARPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1708004077/LD/22012034523215 — medbadhan nirman kar nathu yadav | Completed | 76587.49 | 13062 | 2021-04-05 | 2026-05-21
CHHATARPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1708004077/LD/22012034523216 — mdbadhan nirmankar munna yadav | Closed | 76587.49 | 0 | 2020-08-15
CHHATARPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1708004077/LD/22012034586238 — muktidham nirman karya jabaran ki puliya ke pass brajpura | Closed | 0 | 0 | 2022-10-02
CHHATARPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1708004077/LD/22012034588165 — muktidham nirman karya jabaran ki puliya ke pass brajpura | Closed | 0 | 0 | 2022-08-16
CHHATARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1708004077/LD/22012034588714 — muktidham nirman karya jabaran ki puliya ke pass | Ongoing | 329608.4 | 27846 | 2023-06-15
CHHATARPUR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1708004077/RC/1 — पुलिया निर्माण कार्य व़जपुरा से सिमरिया मार्ग पर | Completed | 499000 | 389442.59 | 2006-09-12 | 2006-10-30
CHHATARPUR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1708004077/RC/14 — पुलिया निर्माण कार्य व्रजपुरा | Completed | 499000 | 463900 | 2006-12-01 | 2007-01-01
CHHATARPUR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal First coat / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1708004077/RC/15 — पुलिया निर्माण कार्य व्रजपुरा | Deleted | 492000 | 0 | 2006-09-12
CHHATARPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/22012034190343 — सी सी रोड नाली निर्माण मा0 शा0 गेट से नवीन अतिरिक् | Completed | 103281 | 77316 | 2013-10-19 | 2014-09-30
CHHATARPUR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/22012034230380 — C.C. road nali nirman Main road se Janki patel k | Completed | 152000 | 132634.24 | 2014-09-27 | 2016-08-11
CHHATARPUR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/22012034230383 — C.C. road nali nirman Harijan mohall bariya se M | Completed | 32000 | 23811.24 | 2014-09-27 | 2015-05-14
CHHATARPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1708004077/RC/22012034299582 — SUDUR SADHK ataniya marg se simariya marg tak | Deleted | 0 | 0 | 2016-01-26
CHHATARPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/22012034299584 — cc road ramprasad mishra ke ghar se panchyat bhavan tak | Deleted | 0 | 0 | 2016-01-26
CHHATARPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/22012034336543 — C.C. Road Nali sahit nirman kary ramprasad patel ke makan se D.P. wale khet tak | Completed | 80000 | 63984 | 2017-04-28 | 2018-11-15
CHHATARPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/22012034350657 — C.C. ROAD NIRMAN NALI SAHIT SHYAMLAL KORI SE PANNA KORI TAK | Completed | 36112 | 30960 | 2017-08-25 | 2018-11-15
CHHATARPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/22012034350660 — C.C. ROAD NIRMAN GANPAT PATEL SE SANTU KE GHAR TAK | Completed | 36000 | 34452 | 2018-12-29 | 2025-01-31
CHHATARPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/22012034398404 — CC ROAD EVAM NALI NIRMAAN LALLU RAJA KE MAKAAN SE RAMMU SEN SE MAKAAN TAK | Completed | 69750 | 67860 | 2019-02-21 | 2025-01-31
CHHATARPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/22012034443427 — CC ROAD NALI SASHIT NIRMAN KARYA | Closed | 0 | 0 | 2019-01-26
CHHATARPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/22012034542979 — CC ROAD & NALI NIRMAN KARY GULKHIYA RAJAK SE RAMKRIPAL KE MAKAN TAK | Completed | 50000 | 44460 | 2020-09-29 | 2025-01-31
CHHATARPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/22012034543058 — CC ROAD & NALI NIRMAN KARY CHINGA RAJAK SE MATHURA AHIRWAR KE GHAR TAK | Completed | 25000 | 31020 | 2020-09-29 | 2021-10-06
CHHATARPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/22012034549107 — CC ROAD & NALI NIRMAN KARY HAJJU SHIVHRE KE GHAR SE PANCHYAT BHAWAN KO AUR | Completed | 145000 | 99270 | 2020-12-05 | 2025-01-31
CHHATARPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/22012034555769 — CC ROAD & NALI NIRMAN KARY MATHURA AHIRWAR SE TANKI KI AOR | Completed | 36000 | 21048 | 2021-02-18 | 2022-04-20
CHHATARPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/22012034555912 — CC ROAD & NALI NIRMAN KARY MUNNI SHAU SE DARUWA PAL KE GHAR TAK | Completed | 13000 | 10095 | 2021-02-12 | 2021-07-22
CHHATARPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/22012034563600 — CC ROAD & NALI NIRMAN RAMADHEEN PATEL SE VISHWNATH KE GHAR KI OR | Closed | 36000 | 0 | 2021-01-26
CHHATARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/22012034592783 — CC ROAD NALI NIRMAN ATANIYA MARG SE RATIRAM PRAJAPATI KE OOR G.P. BRIJPURA | Completed | 42000 | 1 | 2022-04-20 | 2022-04-27
CHHATARPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/22012034646086 — CC ROAD NALI NIRMAN SAHIT MAIN ROAD SE RATIRAM PATEL KE GHAR KE OOR BRIJPURA | Completed | 23000 | 22950 | 2023-08-04 | 2023-09-25
CHHATARPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/22012034646089 — CC ROAD NALI NIRMAN SAHIT MANSUKH PATEL KE GHAR SE RAMGOPAL SHIVHARE KE OOR BRIJPURA | Completed | 36000 | 35971 | 2023-10-05 | 2024-09-27
CHHATARPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/22012034824092 — सीसी रोड निर्माण कार्य काशीराम पटेल के घर से संतोष पटेल के घर की ओर ब्रजपुरा | Completed | 56000 | 54918 | 2024-08-24 | 2024-10-08
CHHATARPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/22012034845138 — CC ROAD NIRMAN KARY HANUMAN JI MINDER SE MAIN ROAD TAK | Completed | 114000 | 113199.5 | 2025-11-08 | 2026-01-17
CHHATARPUR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1708004077/RC/362 — मुरमी करण कार्य kuryana se channu ke khet tsk ब्रज | Completed | 280000 | 13191 | 2011-06-06 | 2011-06-23
CHHATARPUR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1708004077/RC/363 — ब्रजपुरा सेअतनियां रोड मुरमी करण कार्य ब्रजपुरा | Completed | 129000 | 124481 | 2011-05-19 | 2013-03-28
CHHATARPUR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1708004077/RC/5 — ब्रजपुरा से सिमरिया रोड मुरमी करण कार्य | Completed | 452000 | 164505 | 2006-06-10 | 2006-11-03
CHHATARPUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/528 — सीसी रोड नाली सहित रामक्रपाल के मकान से मगलदीन पटे | Completed | 84000 | 79900 | 2012-08-30 | 2013-03-07
CHHATARPUR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/6 — सी सी रोड निर्माण , ब्रजपुरा | Completed | 460000 | 532630 | 2006-09-09 | 2007-12-12
CHHATARPUR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1708004077/RC/8 — सी सी रोड निर्माण कार्य , ब्रजपुरा | Completed | 495000 | 618640 | 2006-05-17 | 2007-12-12
CHHATARPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1708004077/RS/22012034190619 — NBA Group Dhaniya Raikwar | Completed | 4400 | 4328 | 2014-01-04 | 2014-02-18
CHHATARPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1708004077/RS/22012034190621 — NBA Group Bhagwandas Ahirwar | Completed | 4400 | 4328 | 2014-01-04 | 2014-02-18
CHHATARPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1708004077/RS/22012034190623 — NBA Group Harbi pal | Completed | 4400 | 4328 | 2014-01-04 | 2014-02-18
CHHATARPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1708004077/RS/22012034190626 — NBA Group Pappu Ahirwar | Completed | 4400 | 4328 | 2014-01-04 | 2014-02-18
CHHATARPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1708004077/RS/22012034190787 — NBA Group No Babbu pal | Completed | 4400 | 4328 | 2014-01-18 | 2014-02-18
CHHATARPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1708004077/RS/22012034190790 — NBA Group No Bhumanibai pal | Completed | 4400 | 4328 | 2014-01-04 | 2014-02-18
CHHATARPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1708004077/RS/22012034190828 — NBA Group No 1 Geeta Ahirwar | Completed | 4400 | 4328 | 2014-01-04 | 2014-02-18
CHHATARPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1708004077/RS/22012034190834 — NBA Group No Tulsharani | Completed | 4400 | 4328 | 2014-01-04 | 2014-02-18
CHHATARPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1708004077/RS/22012034190838 — NBA Group No Lalla bai Pal | Completed | 4400 | 4328 | 2014-01-04 | 2014-02-18
CHHATARPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1708004077/RS/22012034190840 — NBA Group No Shimmu Raikwar | Completed | 4400 | 4328 | 2014-01-04 | 2014-02-18
CHHATARPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1708004077/RS/22012034190843 — NBA Group No Mahadev Raikwar | Completed | 4400 | 4328 | 2014-01-04 | 2014-02-18
CHHATARPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1708004077/RS/22012034190845 — NBA Group No Geeta Shivhare | Completed | 4400 | 4328 | 2014-01-04 | 2014-02-18
CHHATARPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1708004077/RS/22012034190847 — NBA Group No Raghubeer Sen | Completed | 4400 | 4328 | 2014-01-04 | 2014-02-18
CHHATARPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1708004077/RS/22012034190849 — NBA Group No Bhagbal Patel | Completed | 4400 | 4328 | 2014-01-04 | 2014-02-18
CHHATARPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1708004077/RS/22012034194601 — NBA Group no Nathua Sour | Completed | 4400 | 4328 | 2014-01-18 | 2014-02-18
CHHATARPUR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1708004077/RS/22012034237375 — NBA नंदी अहिरवार ब्रजपुरा | Completed | 5400 | 4728 | 2014-05-31 | 2016-08-11
CHHATARPUR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1708004077/RS/22012034237376 — NBA हरदयाल पटेल ब्रजपुरा | Completed | 5400 | 4728 | 2014-05-31 | 2016-08-11
CHHATARPUR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1708004077/RS/22012034237378 — NBA पुन्‍ना कोरी ब्रजपुरा | Completed | 5400 | 2628 | 2014-05-31 | 2016-08-11
CHHATARPUR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1708004077/RS/22012034237380 — NBA पुन्‍ना रैकवार ब्रजपुरा | Completed | 5400 | 4728 | 2014-05-31 | 2016-08-13
CHHATARPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1708004077/RS/22012034492685 — nadhiv tenk nirmard karay munna yadav | Closed | 0 | 0 | 2020-01-26
CHHATARPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1708004077/RS/22012034492689 — nadap tenk nirman kar Dashrath patel | Closed | 0 | 0 | 2020-01-26
CHHATARPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1708004077/RS/22012034492702 — nadep tenk nirmankarya Indra pal patel | Closed | 0 | 0 | 2020-01-26
CHHATARPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1708004077/RS/22012034604925 — samudayik swachhata parisar nirman prathmik sala ke pass | Completed | 44000 | 41786 | 2021-12-04 | 2023-07-08
CHHATARPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1708004077/RS/22012034604926 — samudayik swachhata parisar nirman prathmik sala ke pass | Closed | 0 | 0 | 2021-08-18
CHHATARPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1708004077/RS/22012034604927 — samudayik swachhata parisar nirman prathmik sala ke pass | Closed | 44000 | 0 | 2021-08-18
CHHATARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1708004077/RS/22012034667712 — NALI NIRMAN KARYA RAMDIN PATEL KE GHAR SE SHANKAR JI MANDIR TAK G.P. BRIJPURA | Completed | 36070 | 23256 | 2022-10-05 | 2023-07-08
CHHATARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1708004077/RS/22012034679314 — nadep nirman karya m.s.ke pass | Closed | 49267.21 | 0 | 2022-10-02
CHHATARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1708004077/RS/22012034679315 — nadep nirman karya high school ke pass buda badh road brajpura | Closed | 49267.21 | 0 | 2022-10-02
CHHATARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1708004077/RS/22012034679316 — nadep niram karya baba ji mandir ke pass bali basti brajpura | Closed | 49267.21 | 0 | 2022-10-02
CHHATARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1708004077/RS/22012034679317 — nadep niram karya simiriya road patel basti brajpura | Closed | 0 | 0 | 2022-10-02
CHHATARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1708004077/RS/22012034679319 — nadep nirman karya koriyana muhalla brajpura | Closed | 0 | 0 | 2022-10-02
CHHATARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Anganwadi Multi Unit Toilets for Comm / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1708004077/RS/22012034680073 — NALI NIRMAN KARY SHYAM LAL KE GHAR SE RAMKRIPAL KE GHAR KE OOR G.P. BRIJPURA | Closed | 0 | 0 | 2022-08-16
CHHATARPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Anganwadi Multi Unit Toilets for Comm / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1708004077/RS/22012034680074 — NALI NIRMAN KARY SHYAM LAL KE GHAR SE RAMKRIPAL KE GHAR KE OOR G.P. BRIJPURA | Completed | 35637 | 34937.98 | 2023-10-12 | 2025-03-04
CHHATARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1708004077/RS/22012034683850 — nadep nirman karya kashiram patel | Closed | 0 | 0 | 2022-10-02
CHHATARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1708004077/RS/22012034683851 — nadep nirman karya baijnath patel | Closed | 0 | 0 | 2022-10-02
CHHATARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1708004077/RS/22012034685369 — nadep nirman karya kishori patel brajpura | Closed | 0 | 0 | 2022-10-02
CHHATARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1708004077/RS/22012034685370 — NADEP NIRMAN KARYA GAJADHAR PATEL | Closed | 0 | 0 | 2022-10-02
CHHATARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1708004077/RS/22012034685371 — NADEP NIRMAN KARYA HALKE PATEL | Closed | 0 | 0 | 2022-10-02
CHHATARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1708004077/RS/22012034693675 — nadep nirman karya gajadhar patel | Closed | 0 | 0 | 2023-01-26
CHHATARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1708004077/RS/22012034693677 — nadep nirman karya harsevak patel | Closed | 0 | 0 | 2023-01-25
CHHATARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1708004077/RS/22012034693679 — nadep nirman karya baijnath patel | Closed | 0 | 0 | 2023-01-25
CHHATARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1708004077/RS/22012034693680 — nadep nirman ratiram patel | Closed | 0 | 0 | 2023-01-25
CHHATARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1708004077/RS/22012034693681 — nadep nirman karya halke patel | Closed | 0 | 0 | 2023-01-25
CHHATARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1708004077/RS/22012034693682 — nadep nirman karya govandi patel | Closed | 0 | 0 | 2023-01-25
CHHATARPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1708004077/RS/22012034699819 — ABY RICHARGE PIT NAL JAL YOJANA KE BOR KE PASS BRIJPURA | Completed | 16000 | 15912 | 2023-08-04 | 2023-09-25
CHHATARPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1708004077/RS/22012034702649 — NALI NIRMAN KARYA MUNNA YADAV SE RAILWAY BRIDGE KI OR | Completed | 30000 | 29614 | 2023-10-07 | 2023-12-14
CHHATARPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1708004077/RS/22012034702652 — NALI NIRMAN KARYA ACHHE LAL RAJAK SE NANDI AHIRWAR KE GHAR KI OR | Completed | 20298 | 20162 | 2023-10-07 | 2023-12-14
CHHATARPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Anganwadi Multi Unit Toilets for Comm / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1708004077/RS/22012035129970 — नाली निर्माण कार्य घनश्याkम पटेल के घर से संतोष्‍ पटेल के घर की ओर बृजपुरा | Completed | 25000 | 24300 | 2024-08-17 | 2024-09-12
CHHATARPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Anganwadi Multi Unit Toilets for Comm / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1708004077/RS/22012035136699 — सामुदायिक स्वkच्छ-ता परिसर बृजपुरा अतनिया मार्ग के पास राष्ट़ी-य राजमार्ग के बगल में बृजपुरा | Completed | 56000 | 53129.77 | 2025-07-30 | 2026-04-04
CHHATARPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1708004077/SK/9993647809 — Bharat Nirman Rajeev Gandhi Sewa Kendra,BRAJPURA | Completed | 1485000 | 999431.8 | 2015-08-22 | 2016-12-30
CHHATARPUR | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1708004077/WC/001 — कूप निर्माण कार्य परसददी अहिरवार ब़जपुरा | Completed | 99600 | 94978.68 | 2007-06-13 | 2007-05-09
CHHATARPUR | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sub Surface Dam / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1708004077/WC/011 — नवीन तालाब निर्माण बुजपुरा से अतीनिया मार्ग, ब्रजप | Completed | 490000 | 379538 | 2008-02-05 | 2023-12-18
CHHATARPUR | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1708004077/WC/10 — देशु के खेत मे तालाब निर्माण ब्रजपुरा | Completed | 13080 | 13400 | 2006-07-17 | 2008-01-25
CHHATARPUR | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1708004077/WC/11 — नवीन तालाब निर्माण व्रजपुरा (N.F.F.W.) | Completed | 443000 | 130267 | 2006-04-01 | 2006-06-02
CHHATARPUR | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1708004077/WC/12 — वियर नवीन तालाब निर्माण कार्य ब़जपुरा | Completed | 497000 | 365089 | 2007-04-12 | 2007-06-15
CHHATARPUR | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1708004077/WC/13 — सिद़दु तालाब घाट एवं पडच टेंक निर्माण ब़जपुरा | Completed | 463000 | 386357 | 2007-06-08 | 2007-09-15
CHHATARPUR | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1708004077/WC/1754 — सिचाई कुप प्रेम बाई / किशोरी पटेल व्रजपुरा | Completed | 180000 | 157686 | 2009-12-20 | 2009-10-14
CHHATARPUR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1708004077/WC/2133 — नवीन तालाब निर्माण ब्रजपुरा | Completed | 496000 | 90072 | 2011-05-20 | 2011-06-30
CHHATARPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1708004077/WC/22012034522807 — KHET TALAB NIRMAN KARY LADDU YADAV W/O ARJUN YADAV | Completed | 101997.1 | 41276 | 2020-04-22 | 2024-12-17
CHHATARPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1708004077/WC/22012034624478 — GABION SANRACHNA NIRMAN KARY NATHU YADAV KE KHET KE PASS | Closed | 0 | 0 | 2021-01-26
CHHATARPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1708004077/WC/22012034624479 — GAVION SANRACHNA NIRMAN KARY KISHORI PATEL KE KHET KE PASS | Closed | 0 | 0 | 2021-01-26
CHHATARPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1708004077/WC/22012034642273 — GABION SANRACHNA NIRMAN KARY RIKSHA NALA PAR KISHORI KE PASS | Closed | 100496.69 | 0 | 2021-04-03
CHHATARPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1708004077/WC/22012034642281 — GABION SANRACHNA NIRMAN RIKSHA NALA PAR NATHU KE PASS | Closed | 0 | 0 | 2021-04-03
CHHATARPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1708004077/WC/22012035033728 — khet talab nirman karya prembai patel/kishori patel | Closed | 0 | 0 | 2022-10-02
CHHATARPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Earthen Spur for Community / Construction of Earthen Spur for Community | Construction of Spur | 1708004077/WC/22012035057090 — khet talab nirman karya prembai patel | Closed | 0 | 0 | 2023-01-25
CHHATARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1708004077/WC/22012035091786 — ABY ROOF WATER HARVESTING HIGHER SECONDARY BRAJPURA | Completed | 16000 | 15470 | 2023-07-26 | 2023-09-25
CHHATARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1708004077/WC/22012035114667 — खेत तालाब निर्माण कार्य दरबारी अहिरवार बृजपुरा | Closed | 0 | 0 | 2023-04-14
CHHATARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1708004077/WC/22012035114698 — सार्वजनिक कूप निर्माण कार्य हरि सिद्ध देव स्थान बृजपुरा | Physically Completed | 561315.97 | 438058.11 | 2023-10-05 | 2026-04-27
CHHATARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1708004077/WC/22012035173004 — MINI PARCOLATION TANK BRAJPURA | Deleted | 0 | 0 | 2023-08-02
CHHATARPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1708004077/WC/22012035189347 — गेबियन संरचना निर्माण कार्य किशोरी पटेल के खेत के पास | Closed | 122356.65 | 0 | 2024-01-24
CHHATARPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1708004077/WC/22012035189362 — गेबियन संरचना निर्माण कार्य जबारन का नाला बड़ी पोर के पास | Completed | 122356.65 | 62482.98 | 2024-03-16 | 2025-08-25
CHHATARPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1708004077/WC/22012035189371 — गेबियन संरचना निर्माण कार्य रिक्शा नाला मुक्तिधाम के पास | Completed | 122356.65 | 50056.06 | 2024-03-16 | 2025-08-24
CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1708004077/WC/22012035265865 — मिनी पर्कोलेशन टैंक निर्माण जवाहर नाला पर ग्राम पंचायत बृजपुरा | Approved | 199464.32 | 0 | 2025-04-14
CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1708004077/WC/22012035266356 — mini percolation tank baramdev ke pas grampanchayat brajpura | Completed | 199138.8 | 166327.41 | 2025-05-07 | 2025-08-25
CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1708004077/WC/22012035288744 — ROOF WATER HARVESTING PANCHYAT BHAWAN | Completed | 11000 | 9016 | 2025-05-01 | 2025-08-25
CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1708004077/WC/22012035288761 — ROOF WATER HARVESTING ANGANWADI BHAWAN | Approved | 11000 | 0 | 2025-04-04
CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1708004077/WC/22012035289139 — ROOF WATER HARVESTING SAMAZ BHAWAN | Completed | 11000 | 10215.96 | 2025-05-01 | 2025-08-25
CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1708004077/WC/22012035298046 — JGSA dugwell recharge pit nirmad sarvjanik koop patel mahalla ke pas grampanchayat brajpura | Completed | 22007.92 | 21712.62 | 2025-05-13 | 2025-12-31
CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1708004077/WC/22012035301015 — JGSA dugwell recharge pit nirmad brajveti behar ke pas grampanchayat brajpura | Completed | 22007.92 | 21065.44 | 2025-05-13 | 2026-01-26
CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1708004077/WC/22012035307846 — JGSA dugwell recharge pit nirmad sarvjanik koop amit sharma ke makan k pas grampanchayat brajpura | Completed | 21791.28 | 20280.54 | 2025-05-21 | 2025-12-31
CHHATARPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1708004077/WC/3 — siddh तालाब खुदाई कार्य ब्रजपुरा | Completed | 212000 | 175756 | 2008-04-04 | 2008-07-30
CHHATARPUR | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1708004077/WC/4 — कपिल धारा कूप निर्माण श्री मती देवकिया/पारीक्षित ब्रजपुरा | Completed | 140000 | 242944 | 2008-03-31 | 2008-05-05
CHHATARPUR | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1708004077/WC/8 — सिध्‍द तालाब निर्माण एवं सुन्‍दरीकरण घाट निर्माण ब़जपुरा | Completed | 468000 | 532517 | 2007-12-04 | 2008-02-25
CHHATARPUR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1708004077/WH/19961419 — doliy taliya marammat brajpura | Completed | 246000 | 208736 | 2017-05-27 | 2018-11-15
CHHATARPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1708004077/WH/22012034932429 — TALAB JEERODDHAR KARY DOLY TALIYA | Completed | 96824.55 | 83140 | 2022-09-01 | 2024-07-05
CHHATARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1708004077/WH/22012034939462 — ABY BRAJBETI BEHAR JINODHHAR KARY BRAJPURA | Completed | 124000 | 123725 | 2024-03-16 | 2025-03-04
CHHATARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1708004077/WH/22012034945145 — TALAB MARAMAT KARY BRAJPURA | Completed | 607000 | 600211.16 | 2025-06-16 | 2026-05-29