## Work List
Exported on: 2026-10-10 18:36:57
Filters applied:
Data source: VBGRAMG
District: CHHATARPUR
Block: All
Panchayat: SIMARIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BADA MALEHARA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Village/Rural Haat for community / Construction of Rural Haat Building for Community | Construction of Village Haats | 1708006017/AV/22012034664457 — सार्वजनिक चबूतरा निर्माण कार्य पुरानी पंचायत भवन के पास ग्राम पंचायत सिमरिया | Approved | 3500 | 0 | 2025-01-24
BADA MALEHARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1708006017/IC/22012034888886 — कूप निर्माण कार्य सिंचाई हेतु समुदाय की लिए नत्वान साहू के खेत के पास ग्राम पंचायत सिमरिया | New | 0 | 0 | 2025-01-26
BADA MALEHARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1708006017/IC/22012034888887 — कूप निर्माण कार्य सिंचाई हेतु समुदाय की लिए ब्रजलाल के खेत के पास ग्राम पंचायत सिमरिया | New | 0 | 0 | 2025-01-26
BADA MALEHARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1708006017/IC/22012034889329 — सामुदायिक कूप निर्माण कार्य सामुदायिक सिंचाई हेतु नतथन साहू के खेत के पास ग्राम पंचायत सिमरिया | New | 0 | 0 | 2025-01-26
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1708006017/IC/22012034892803 — कूप निर्माण कार्य सिंचाई हेतु समुदाय के लिये ग्बाल बाबा के पास ग्राम पंचायत सिमरिया | New | 0 | 0 | 2025-08-15
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1708006017/IC/22012034892804 — कूप निर्माण कार्य सिंचाई हेतु समुदाय के लिये ब्रजलाल कुशवाहा के खेत के पास ग्राम पंचायत सिमरिया | New | 0 | 0 | 2025-08-15
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708006017/IF/22012035591091 — एक बगिया माँ के नाम गनेशी बाई/ बाबूलाल पटेल भू स्वामी (सम्बन्ध पति) ग्राम पंचायत सिमरिया | Approved | 0 | 0 | 2025-08-14
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708006017/IF/22012035619767 — एक बगिया माँ के नाम लक्ष्मी / मुन्नालाल प्रजापति भू स्वामी (सम्बन्ध पति) ग्राम पंचायत सिमरिया | Ongoing | 275925.18 | 0 | 2026-02-24
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708006017/IF/22012035633230 — एक बगिया माँ के नाम ब्रजेश राजा परमार/मदनपाल सिंह भू स्वामी (सम्बन्ध पति) ग्राम पंचायत सिमरिया | Ongoing | 275925.18 | 0 | 2025-11-29
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708006017/IF/22012035633232 — एक बगिया माँ के नाम कल्लो कुशवाहा/लछुवा कुशवाहा भू स्वामी (सम्बन्ध पति) ग्राम पंचायत सिमरिया | Ongoing | 275925.18 | 0 | 2025-11-29
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708006017/IF/22012035633237 — एक बगिया माँ के नाम पुनिया कुशवाहा/ भैयालाल कुशवाहा भू स्वामी (सम्बन्ध पति) ग्राम पंचायत सिमरिया | Ongoing | 275925.18 | 0 | 2025-11-29
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708006017/IF/22012035650659 — हितेषी खेत तालाब निर्माण कार्य श्यामलाल/हिकले यादव पात्रता लघु सीेमांत कृषक | Approved | 0 | 0 | 2025-08-15
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708006017/IF/22012035656655 — हितेशी खेत तालाब निर्माण कार्य बारेलाल/मनका अहिरवार पात्रता एस0सी0 | Approved | 147620.89 | 0 | 2025-12-26
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1708006017/IF/22012035656657 — हितेशी खेत तालाब निर्माण कार्य हरजुवा/दुर्जना अहिरवार पात्रता एस0सी0 | Approved | 147620.89 | 0 | 2025-12-26
BADA MALEHARA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1708006017/IF/9993714000 — Kapildhara Koop - Damarua/Nanga Ahirwar | Physically Completed | 395000 | 0 | 2016-03-02 | 2026-09-11
BADA MALEHARA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1708006017/IF/9993714001 — Kapildhara- Jugga/Malkhan Sour | Physically Completed | 395000 | 0 | 2016-03-02 | 2026-09-11
BADA MALEHARA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006017/IF/IAY/3654436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100068044 | Ongoing | 27000 | 0 | 2023-07-19
BADA MALEHARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006017/IF/IAY/3920207 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100067585 | Ongoing | 27000 | 0 | 2022-08-02
BADA MALEHARA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006017/IF/IAY/3947093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125883442 | Ongoing | 27000 | 0 | 2022-06-08
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006017/IF/IAY/4547105 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106531565 | Ongoing | 27000 | 0 | 2026-02-13
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006017/IF/IAY/4586979 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120765257 | Ongoing | 27000 | 0 | 2026-02-13
BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006017/IF/IAY/5569000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121613271 | Ongoing | 27000 | 0 | 2026-06-17
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006017/IF/IAY/5765461 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125312369 | Physically Completed | 27000 | 0 | 2026-02-21 | 2026-09-28
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006017/IF/IAY/5765843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106484173 | Ongoing | 27000 | 0 | 2026-02-13
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006017/IF/IAY/5766105 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124102649 | Physically Completed | 27000 | 0 | 2026-02-14 | 2026-09-28
BADA MALEHARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006017/IF/IAY/5766108 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124123831 | Approved | 27000 | 0 | 2025-02-17
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006017/IF/IAY/5768344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118166916 | Ongoing | 27000 | 0 | 2026-02-21
BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006017/IF/IAY/5768500 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124124641 | Ongoing | 27000 | 0 | 2026-06-17
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006017/IF/IAY/5768510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123784901 | Ongoing | 27000 | 0 | 2026-02-14
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006017/IF/IAY/5975912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122116505 | Approved | 27000 | 0 | 2026-02-10
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006017/IF/IAY/5975913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122123416 | Approved | 27000 | 0 | 2026-02-10
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006017/IF/IAY/5975914 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122125796 | Approved | 27000 | 0 | 2026-02-26
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006017/IF/IAY/5981084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126220608 | Approved | 27000 | 0 | 2026-02-26
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006017/IF/IAY/5982879 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122124613 | Approved | 27000 | 0 | 2026-02-10
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006017/IF/IAY/5984957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126349485 | Approved | 27000 | 0 | 2026-02-11
BADA MALEHARA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708006017/RC/22012034551726 — सी सी रोड एवं नाली निर्माण कार्य रामस्वरूप पाठक के मकान से मचखेरा रोड तक ग्राम पंचायत सिमरिया | Ongoing | 42000 | 0 | 2021-03-22
BADA MALEHARA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708006017/RC/22012034553252 — सी सी रोड एवं नाली निर्माण कार्य सुकरत वर्मा के घर से मुन्नालाल जैन के घर तक ग्राम पंचायत सिमरिया | Ongoing | 28000 | 0 | 2021-01-25
BADA MALEHARA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708006017/RC/22012034823321 — सी सी रोड निर्माण कार्य मंगल भवन से अजुद्दी अहिरवार के घर तक ग्राम पंचायत सिमरिया | New | 0 | 0 | 2024-06-08
BADA MALEHARA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708006017/RC/22012034823322 — सी सी रोड निर्माण कार्य मंगल भवन से अजुद्दी अहिरवार के घर तक ग्राम पंचायत सिमरिया | New | 0 | 0 | 2024-06-08
BADA MALEHARA | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708006017/RC/22012034837569 — सी सी रोड निर्माण कार्य मेंन रोड से हाई स्कूल तक ग्राम पंचायत सिमरिया | Ongoing | 28000 | 0 | 2026-04-24
BADA MALEHARA | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708006017/RC/22012034847030 — सी सी रोड निर्माण कार्य बारेलाल आदिवासी के मकान से जू-जू वंशकार के घर के पास तक ग्राम पंचायत सिमरिया | Ongoing | 54000 | 0 | 2026-04-24
BADA MALEHARA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708006017/RC/22012034847031 — सी सी रोड निर्माण कार्य राजाराम यादव के मकान से स्कूल की ओर समरेठा ग्राम पंचायत सिमरिया | Approved | 93000 | 0 | 2025-06-08
BADA MALEHARA | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1708006017/RC/22012034849152 — सी सी रोड निर्माण कार्य सामुदायिक मंदिर परिसर ग्राम पंचायत सिमरिया | Ongoing | 34000 | 0 | 2026-05-31
BADA MALEHARA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1708006017/RS/22012035129718 — नाली निर्माण कार्य स्कूल से देवी मंदिर की ओर ग्राम पंचायत सिमरिया | Approved | 19000 | 0 | 2024-06-08
BADA MALEHARA | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1708006017/RS/22012035138438 — नाली निर्माण कार्य ब्रिजनंदन रैकवार के मकान से बल्दुवा साहू के मकान तक ग्राम पंचायत सिमरिया | Ongoing | 56000 | 0 | 2026-05-31
BADA MALEHARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708006017/WC/22012035252192 — सार्वजानिक खेत तालाब निर्माण कार्य सिमरिया हार के पास ग्राम पंचायत सिमरिया | Approved | 0 | 0 | 2025-01-26
BADA MALEHARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708006017/WC/22012035252193 — सार्वजानिक खेत तालाब निर्माण कार्य कल्लू अहिरवार के खेत के पास ग्राम पंचायत सिमरिया | Approved | 0 | 0 | 2025-01-26
BADA MALEHARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708006017/WC/22012035255017 — सार्वजनिक खेत तालाब निर्माण कार्य चरवाहार ग्राम पंचायत सिमरिया | Approved | 0 | 0 | 2025-01-25
BADA MALEHARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708006017/WC/22012035255035 — सार्वजनिक खेत तालाब निर्माण का हथनी टूर के पास ग्राम पंचायत सिमरिया | Approved | 0 | 0 | 2025-01-26
BADA MALEHARA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1708006017/WC/VB/22012035331426 — स्टेगर्ड कंटूर ट्रेंच निर्माण कार्य सोराई पहाड़ी पर ग्राम सिमरिया | Approved | 0 | 0 | 2026-06-08