## Work List
Exported on: 2026-10-13 12:36:55
Filters applied:
Data source: VBGRAMG
District: CHHATARPUR
Block: All
Panchayat: BANDHA CHANDOLI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BADA MALEHARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Avenue Plantation for Community | Plantation | 1708006019/DP/22012034606039 — सामुदायिक वृक्षारोपण निर्माण कार्य शासकीय हाई स्कूल परिसर बंधा चंदौली | Ongoing | 290437.93 | 0 | 2023-08-28
BADA MALEHARA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1708006019/IF/22012035268607 — हितेषी खेत तालाब निर्माण कार्य जगन्नाथ/भैयालाल लोधी पात्रता लघु सीमांत कृषक | Ongoing | 299977.13 | 0 | 2025-03-08
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1708006019/IF/22012035618482 — एक बगिया माँ के नाम लल्लाबाई लोधी /पूरन लोधी भू स्वामी (सम्बन्ध पति) ग्रा पंचा बंधाचंदोली | Ongoing | 275923.76 | 0 | 2025-12-27
BADA MALEHARA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006019/IF/IAY/5235933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130587357 | Physically Completed | 27000 | 0 | 2026-02-17 | 2026-09-28
BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006019/IF/IAY/5899870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130586365 | Physically Completed | 27000 | 0 | 2026-04-25 | 2026-09-28
BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006019/IF/IAY/5899871 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130586378 | Physically Completed | 27000 | 0 | 2026-06-03 | 2026-09-28
BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006019/IF/IAY/5900150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130587154 | Physically Completed | 27000 | 0 | 2026-04-25 | 2026-09-28
BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1708006019/IF/IAY/5900271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144149556 | Ongoing | 27000 | 0 | 2026-06-10
BADA MALEHARA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1708006019/IF/IAY/637935 — Construction of IAY House -IAY REG. NO. MP2223241 | Ongoing | 27000 | 0 | 2026-06-15
BADA MALEHARA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1708006019/LD/22012034594032 — स्टोन बंड निर्माण कार्य शांति धाम कंचना की पुलिया के पास | Ongoing | 575444.21 | 0 | 2024-03-16
BADA MALEHARA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1708006019/RS/22012035137535 — नाली निर्माण कार्य जय सिंह घोषी के घर से भागूइन खेरा की और ग्राम पंचायत बंधाचंदौली | Approved | 65000 | 0 | 2025-04-14
BADA MALEHARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1708006019/WC/22012035226619 — सार्वजनिक खेत तालाब निर्माण कार्य पठापुर रोड के पास | Approved | 0 | 0 | 2024-10-02
BADA MALEHARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708006019/WC/22012035253527 — सार्वजनिक खेत तालाब निर्माण कार्य ओरिया के खेत के पास | Approved | 0 | 0 | 2025-01-24
BADA MALEHARA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1708006019/WC/22012035253530 — सार्वजनिक खेत तालाब निर्माण कार्य बंधा सिमरिया मार्ग के पास | Approved | 0 | 0 | 2025-01-24
BADA MALEHARA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1708006019/WC/22012035315220 — JGSA 2025 डग वेल निर्माण कार्य रामचरण लोधी के कूप पर ग्राम पंचायत बंधाचंदौली | Approved | 15000 | 0 | 2025-04-14